## README
Multi-state Cox proportional-hazards model — results
Cause-specific model for successful phase transitions (clock-reset, semi-Markov)
Model specification
Surv(Duration, event) ~ strata(from, Inv_Environment) + from:covariate + cluster(Inv_index)
Ties: Efron. Standard errors: robust, clustered on Inv_index.
Baseline stratified by phase of origin (from) and environment (onshore/offshore).
All covariates interacted with phase of origin -> phase-specific hazard ratios.
Sample
n = 1082 transition spells ¦ 462 successes ¦ 377 cancellations ¦ 243 censored.
Main model: concordance = 0.716 (se 0.016). Global Schoenfeld chi2 = 29.41, df = 28, p = 0.39.
Robustness model: concordance = 0.717 (se 0.016). Global Schoenfeld chi2 = 40.68, df = 30, p = 0.09.
Reference levels
Region: Extra-EU ¦ Jurisdiction: Internal ¦ Infrastructure: New ¦ Element: Cable/Line ¦
Technology: AC ¦ COVID-19: 0 (no overlap) ¦ New Directive: 0 (pre-2018) ¦
Capacity: High ¦ Length: Long.
Sheets
Main model - full cause-specific success model (Table 1).
Robustness - physical-scale controls added (capacity, length; 'Missing' level).
Stability - main vs robustness HRs, with log-scale and percentage changes.
Diagnostics - Schoenfeld PH tests, model fit, joint tests of physical-scale terms.
Reading the tables
HR > 1 accelerates the transition; HR < 1 delays it. Significance: *** p<0.001, ** p<0.01, * p<0.05, . p<0.1.
Caveat on the robustness specification
The robustness model differs from the main model in TWO respects: it adds Capacity_Cat and
Length_Cat, and it drops Inv_Element_Category (collinear with Length = Zero). Differences
between the two columns in 'Stability' therefore cannot be attributed to physical scale alone.
See the note at the foot of the Stability sheet.
Source
All figures transcribed from the R console output supplied by the user (survival 3.8-3,
R 4.5.2). No quantity in this workbook is re-estimated here; the Stability sheet's derived
columns are live formulas over the Main model and Robustness sheets.

## Main model
Table 1 — Structural and temporal drivers (cause-specific: successful transition)
Phase | Variable | HR | 95% CI low | 95% CI high | coef | robust SE | z | p-value | sig.
1 Consideration | Region: EU Member (vs Extra-EU) | 2.5811 | 1.6607 | 4.0116 | 0.94821 | 0.225 | 4.214 | <0.001 | ***
2 Planning | Region: EU Member (vs Extra-EU) | 0.99238 | 0.5727 | 1.7196 | -0.007652 | 0.28048 | -0.027 | 0.978
3 Design & Permitting | Region: EU Member (vs Extra-EU) | 1.9596 | 1.1762 | 3.2648 | 0.67275 | 0.26043 | 2.583 | 0.010 | **
4 Construction | Region: EU Member (vs Extra-EU) | 2.0229 | 1.2626 | 3.2408 | 0.70452 | 0.24047 | 2.93 | 0.003 | **
1 Consideration | Jurisdiction: Cross-border (vs Internal) | 1.7971 | 1.1537 | 2.7995 | 0.5862 | 0.22614 | 2.592 | 0.010 | **
2 Planning | Jurisdiction: Cross-border (vs Internal) | 1.0953 | 0.67998 | 1.7641 | 0.090985 | 0.2432 | 0.374 | 0.708
3 Design & Permitting | Jurisdiction: Cross-border (vs Internal) | 1.2381 | 0.84347 | 1.8173 | 0.21357 | 0.19582 | 1.091 | 0.275
4 Construction | Jurisdiction: Cross-border (vs Internal) | 1.1338 | 0.78155 | 1.6447 | 0.12554 | 0.18981 | 0.661 | 0.508
1 Consideration | Infrastructure: Upgrade (vs New) | 0.64648 | 0.38 | 1.0998 | -0.43621 | 0.27112 | -1.609 | 0.108
2 Planning | Infrastructure: Upgrade (vs New) | 1.1325 | 0.66201 | 1.9375 | 0.12446 | 0.27395 | 0.454 | 0.650
3 Design & Permitting | Infrastructure: Upgrade (vs New) | 1.9457 | 1.1603 | 3.2627 | 0.66562 | 0.26375 | 2.524 | 0.012 | *
4 Construction | Infrastructure: Upgrade (vs New) | 0.9916 | 0.64378 | 1.5274 | -0.008436 | 0.2204 | -0.038 | 0.969
1 Consideration | Element: Nodal (vs Cable/Line) | 0.70629 | 0.4041 | 1.2345 | -0.34772 | 0.28488 | -1.221 | 0.222
2 Planning | Element: Nodal (vs Cable/Line) | 1.3592 | 0.79202 | 2.3325 | 0.30689 | 0.27555 | 1.114 | 0.265
3 Design & Permitting | Element: Nodal (vs Cable/Line) | 1.652 | 0.99937 | 2.731 | 0.50201 | 0.25646 | 1.957 | 0.050 | .
4 Construction | Element: Nodal (vs Cable/Line) | 0.80088 | 0.46855 | 1.3689 | -0.22205 | 0.27351 | -0.812 | 0.417
1 Consideration | Technology: DC (vs AC) | 0.36304 | 0.20943 | 0.6293 | -1.0132 | 0.28069 | -3.61 | <0.001 | ***
2 Planning | Technology: DC (vs AC) | 1.4326 | 0.85884 | 2.3896 | 0.35949 | 0.26105 | 1.377 | 0.168
3 Design & Permitting | Technology: DC (vs AC) | 0.94258 | 0.44032 | 2.0178 | -0.059134 | 0.38834 | -0.152 | 0.879
4 Construction | Technology: DC (vs AC) | 1.1543 | 0.63207 | 2.1082 | 0.14354 | 0.30729 | 0.467 | 0.640
1 Consideration | COVID-19 shock | 0.18057 | 0.10665 | 0.3057 | -1.7116 | 0.26866 | -6.371 | <0.001 | ***
2 Planning | COVID-19 shock | 0.15206 | 0.07955 | 0.2907 | -1.8835 | 0.33059 | -5.697 | <0.001 | ***
3 Design & Permitting | COVID-19 shock | 0.10101 | 0.05971 | 0.1709 | -2.2925 | 0.26823 | -8.547 | <0.001 | ***
4 Construction | COVID-19 shock | 0.34026 | 0.19515 | 0.5933 | -1.078 | 0.28364 | -3.801 | <0.001 | ***
1 Consideration | New Directive (post-2018) | 3.4518 | 2.0034 | 5.9477 | 1.2389 | 0.2776 | 4.463 | <0.001 | ***
2 Planning | New Directive (post-2018) | 1.9134 | 1.1036 | 3.3173 | 0.64886 | 0.28077 | 2.311 | 0.021 | *
3 Design & Permitting | New Directive (post-2018) | 5.4507 | 3.0965 | 9.5946 | 1.6957 | 0.28851 | 5.878 | <0.001 | ***
4 Construction | New Directive (post-2018) | 2.2914 | 1.2158 | 4.3187 | 0.82917 | 0.32336 | 2.564 | 0.010 | *

## Robustness
Robustness — primary drivers with physical-scale controls (capacity & length)
Capacity/length entered as categories with an explicit 'Missing' level (no listwise deletion); element category omitted (collinear with zero length). n = 1082.
Phase | Variable | HR | 95% CI low | 95% CI high | coef | robust SE | z | p-value | sig.
1 Consideration | Region: EU Member (vs Extra-EU) | 2.6961 | 1.7415 | 4.174 | 0.99182 | 0.22299 | 4.448 | <0.001 | ***
2 Planning | Region: EU Member (vs Extra-EU) | 0.83079 | 0.48443 | 1.4248 | -0.18538 | 0.27521 | -0.674 | 0.501
3 Design & Permitting | Region: EU Member (vs Extra-EU) | 1.997 | 1.186 | 3.3628 | 0.69166 | 0.26588 | 2.601 | 0.009 | **
4 Construction | Region: EU Member (vs Extra-EU) | 1.8841 | 1.1607 | 3.0584 | 0.63347 | 0.24716 | 2.563 | 0.010 | *
1 Consideration | Jurisdiction: Cross-border (vs Internal) | 1.9434 | 1.2721 | 2.969 | 0.66445 | 0.21621 | 3.073 | 0.002 | **
2 Planning | Jurisdiction: Cross-border (vs Internal) | 1.0053 | 0.62233 | 1.624 | 0.005304 | 0.24469 | 0.022 | 0.983
3 Design & Permitting | Jurisdiction: Cross-border (vs Internal) | 1.0918 | 0.74657 | 1.5968 | 0.087859 | 0.19395 | 0.453 | 0.651
4 Construction | Jurisdiction: Cross-border (vs Internal) | 1.078 | 0.73173 | 1.5882 | 0.075143 | 0.1977 | 0.38 | 0.704
1 Consideration | Infrastructure: Upgrade (vs New) | 0.59915 | 0.36841 | 0.9744 | -0.51224 | 0.24813 | -2.064 | 0.039 | *
2 Planning | Infrastructure: Upgrade (vs New) | 1.1159 | 0.66072 | 1.8845 | 0.10962 | 0.26737 | 0.41 | 0.682
3 Design & Permitting | Infrastructure: Upgrade (vs New) | 2.1012 | 1.2554 | 3.5171 | 0.74253 | 0.26282 | 2.825 | 0.005 | **
4 Construction | Infrastructure: Upgrade (vs New) | 0.99328 | 0.61683 | 1.5995 | -0.006738 | 0.24307 | -0.028 | 0.978
1 Consideration | Technology: DC (vs AC) | 0.57533 | 0.32993 | 1.0033 | -0.55281 | 0.28371 | -1.949 | 0.051 | .
2 Planning | Technology: DC (vs AC) | 1.9432 | 1.1232 | 3.3619 | 0.66436 | 0.27968 | 2.375 | 0.018 | *
3 Design & Permitting | Technology: DC (vs AC) | 1.1462 | 0.48082 | 2.7323 | 0.13645 | 0.44322 | 0.308 | 0.758
4 Construction | Technology: DC (vs AC) | 1.2578 | 0.62258 | 2.541 | 0.22933 | 0.35879 | 0.639 | 0.523
1 Consideration | COVID-19 shock | 0.12479 | 0.08232 | 0.1892 | -2.0811 | 0.21223 | -9.806 | <0.001 | ***
2 Planning | COVID-19 shock | 0.12221 | 0.0666 | 0.2243 | -2.102 | 0.30974 | -6.786 | <0.001 | ***
3 Design & Permitting | COVID-19 shock | 0.07507 | 0.04525 | 0.1246 | -2.5893 | 0.25833 | -10.023 | <0.001 | ***
4 Construction | COVID-19 shock | 0.17273 | 0.09237 | 0.323 | -1.756 | 0.31937 | -5.499 | <0.001 | ***
1 Consideration | New Directive (post-2018) | 3.26 | 2.0628 | 5.1521 | 1.1817 | 0.23351 | 5.061 | <0.001 | ***
2 Planning | New Directive (post-2018) | 1.7597 | 1.0203 | 3.0349 | 0.56512 | 0.2781 | 2.032 | 0.042 | *
3 Design & Permitting | New Directive (post-2018) | 5.9174 | 3.4139 | 10.2569 | 1.7779 | 0.28064 | 6.335 | <0.001 | ***
4 Construction | New Directive (post-2018) | 2.7875 | 1.3626 | 5.7022 | 1.0251 | 0.36517 | 2.807 | 0.005 | **
Physical-scale controls (main effects — not interacted with phase)
Variable |  | HR | 95% CI low | 95% CI high | coef | robust SE | z | p-value | sig.
Capacity: Low (vs High) |  | 1.2302 | 0.9244 | 1.6371 | 0.20715 | 0.1458 | 1.421 | 0.155
Capacity: Missing (vs High) |  | 1.5245 | 0.85694 | 2.7123 | 0.4217 | 0.29393 | 1.435 | 0.151
Capacity: Zero (vs High) |  | 1.9253 | 1.3838 | 2.6787 | 0.65509 | 0.16849 | 3.888 | <0.001 | ***
Length: Missing (vs Long) |  | 0.32482 | 0.16304 | 0.6472 | -1.1245 | 0.35169 | -3.197 | 0.001 | **
Length: Short (vs Long) |  | 0.93678 | 0.73431 | 1.1951 | -0.065312 | 0.12424 | -0.526 | 0.599
Length: Zero (vs Long) |  | 0.90451 | 0.63697 | 1.2844 | -0.10036 | 0.17892 | -0.561 | 0.575
Note: the physical-scale signal concentrates in the zero-capacity and missing-length levels, which proxy nodal (substation) assets captured by element category in the main model.

## Stability
Coefficient stability — main vs robustness model (primary drivers)
Geographic and temporal drivers keep sign, order of magnitude and significance. Technology (DC) does not: see the flagged rows and the note below.
Phase | Variable | HR (main) | HR (robustness) | Δ log-HR | % change | Significance at p<0.05
1 Consideration | Region: EU Member (vs Extra-EU) | 2.5811 | 2.6961 | 0.043611 | 4.458% | unchanged
2 Planning | Region: EU Member (vs Extra-EU) | 0.99238 | 0.83079 | -0.17773 | -16.28% | unchanged
3 Design & Permitting | Region: EU Member (vs Extra-EU) | 1.9596 | 1.997 | 0.018915 | 1.91% | unchanged
4 Construction | Region: EU Member (vs Extra-EU) | 2.0229 | 1.8841 | -0.071052 | -6.859% | unchanged
1 Consideration | Jurisdiction: Cross-border (vs Internal) | 1.7971 | 1.9434 | 0.078251 | 8.139% | unchanged
2 Planning | Jurisdiction: Cross-border (vs Internal) | 1.0953 | 1.0053 | -0.085681 | -8.211% | unchanged
3 Design & Permitting | Jurisdiction: Cross-border (vs Internal) | 1.2381 | 1.0918 | -0.12571 | -11.81% | unchanged
4 Construction | Jurisdiction: Cross-border (vs Internal) | 1.1338 | 1.078 | -0.050401 | -4.915% | unchanged
1 Consideration | Infrastructure: Upgrade (vs New) | 0.64648 | 0.59915 | -0.07603 | -7.321% | CHANGES
2 Planning | Infrastructure: Upgrade (vs New) | 1.1325 | 1.1159 | -0.014838 | -1.473% | unchanged
3 Design & Permitting | Infrastructure: Upgrade (vs New) | 1.9457 | 2.1012 | 0.076912 | 7.995% | unchanged
4 Construction | Infrastructure: Upgrade (vs New) | 0.9916 | 0.99328 | 0.0016978 | 0.1699% | unchanged
1 Consideration | Technology: DC (vs AC) | 0.36304 | 0.57533 | 0.46042 | 58.47% | CHANGES
2 Planning | Technology: DC (vs AC) | 1.4326 | 1.9432 | 0.30487 | 35.65% | CHANGES
3 Design & Permitting | Technology: DC (vs AC) | 0.94258 | 1.1462 | 0.19558 | 21.6% | unchanged
4 Construction | Technology: DC (vs AC) | 1.1543 | 1.2578 | 0.085796 | 8.958% | unchanged
1 Consideration | COVID-19 shock | 0.18057 | 0.12479 | -0.36952 | -30.89% | unchanged
2 Planning | COVID-19 shock | 0.15206 | 0.12221 | -0.21849 | -19.63% | unchanged
3 Design & Permitting | COVID-19 shock | 0.10101 | 0.07507 | -0.29684 | -25.68% | unchanged
4 Construction | COVID-19 shock | 0.34026 | 0.17273 | -0.67798 | -49.24% | unchanged
1 Consideration | New Directive (post-2018) | 3.4518 | 3.26 | -0.057177 | -5.557% | unchanged
2 Planning | New Directive (post-2018) | 1.9134 | 1.7597 | -0.083744 | -8.033% | unchanged
3 Design & Permitting | New Directive (post-2018) | 5.4507 | 5.9174 | 0.082158 | 8.563% | unchanged
4 Construction | New Directive (post-2018) | 2.2914 | 2.7875 | 0.19595 | 21.65% | unchanged
How to read this sheet
Δ log-HR is the change on the estimation scale and is the quantity to report; a difference in raw HR understates
movement for hazard ratios below 1 (COVID-19, phase 4: HR 0.340 -> 0.173 is only -0.167 in levels but -68% in logs).
'CHANGES' flags a covariate that crosses the 5% threshold between the two specifications.
Caveat: the robustness model both ADDS capacity/length and DROPS element category, so a flagged row cannot be
attributed to physical scale alone. To separate the two, estimate an intermediate model that drops element
category only. The attenuation of the DC coefficient is expected on substantive grounds — HVDC assets are
systematically longer and higher-capacity, so the scale controls absorb part of the technology effect.

## Diagnostics
Model diagnostics
Schoenfeld proportional-hazards test — main model
Term | chi2 | df | p
from:is_EU | 4.25 | 4 | 0.37
from:Project_Jurisdiction | 3.5 | 4 | 0.48
from:Infr_Type | 5.25 | 4 | 0.26
from:Inv_Element_Category | 1.93 | 4 | 0.75
from:Inv_Technology | 2.42 | 4 | 0.66
from:Covid19 | 3.74 | 4 | 0.44
from:NewDirective | 3.77 | 4 | 0.44
GLOBAL | 29.41 | 28 | 0.39
Schoenfeld proportional-hazards test — robustness model
Term | chi2 | df | p
Capacity_Cat | 6.7 | 3 | 0.082
Length_Cat | 4.65 | 3 | 0.199
from:is_EU | 4.92 | 4 | 0.296
from:Project_Jurisdiction | 4.25 | 4 | 0.373
from:Infr_Type | 5.81 | 4 | 0.214
from:Inv_Technology | 3.22 | 4 | 0.522
from:Covid19 | 5.82 | 4 | 0.213
from:NewDirective | 4.57 | 4 | 0.334
GLOBAL | 40.68 | 30 | 0.092
Joint tests of physical-scale terms (capacity + length)
Test | chi2 | df | p | Interpretation
Likelihood-ratio (nested, unclustered) | 37.805 | 6 | 1.226e-06 | physical scale improves fit
Robust Wald (clustered SE) | 29.207 | 6 | 5.558e-05 | confirmed with robust variance
The LRT is computed on the unclustered fits: the likelihood does not depend on the robust variance estimator.
Model fit
Statistic | Main | Robustness
Number of spells (n) | 1082 | 1082
Events (successes) | 462 | 462
Concordance | 0.716 | 0.717 |  | se = 0.016 in both
Likelihood ratio test (chi2) | 219.7 | 251 |  | df = 28 and 30, p < 2e-16
Wald test (chi2) | 271.3 | 398 |  | df = 28 and 30, p < 2e-16
Score (logrank) test (chi2) | 208.1 | 238.4 |  | robust: 143.3 and 152.4, p < 2e-16
Note: PH assumption is not rejected in either specification (global p = 0.39 and 0.09). Capacity_Cat is the closest to the threshold (p = 0.08).