## Sheet1
Year | meta |  |  |  |  | 2010 | [7 empty] | 2012 | [9 empty] | 2013 | [9 empty] | 2014 | [11 empty] | 2015 | [9 empty] | 2016 | [20 empty] | 2018 | [15 empty] | 2020 | [20 empty] | 2022 | [22 empty] | 2024 | [22 empty] | 2026 | [14 empty] | meta
Column | Inv_First_year_present | Inv_Last_year_present | Inv_Years_present | Inv_index | Investment Conclusion | Project_ID | Inv_Description | Inv_Status | Inv_Commissioning_Year | Inv_Commissioning_Year_Standardized | Inv_Is_Present | Inv_Substation From | Inv_Substation To | Project_ID | Inv_index | Inv_Description | Inv_Status | Inv_Progress | Inv_Commissioning_Year | Inv_Commissioning_Year_Standardized | Inv_Is_Present | Inv_Substation From | Inv_Substation To | Project_ID | Inv_index | Inv_Description | Inv_Status | Inv_Progress Driver | Inv_Commissioning_Year | Inv_Commissioning_Year_Standardized | Inv_Is_Present | Inv_Substation From | Inv_Substation To | Project_ID | Inv_index | Project_Name | Inv_Description | Inv_Status | Inv_Progress | Inv_Progress Driver | Inv_Commissioning_Year | Inv_Commissioning_Year_Standardized | Inv_Is_Present | Inv_Substation From | Inv_Substation To | Inv_index | Inv_Description | Inv_Status | Inv_Progress | Inv_Progress Driver | Inv_Commissioning_Year | Inv_Commissioning_Year_Standardized | Inv_Is_Present | Inv_Substation From | Inv_Substation To | Project_ID | Inv_index | Project_Name | Inv_Name | Inv_Description | Inv_Status | Inv_Progress | Inv_Progress Driver | Inv_Commissioning_Year | Inv_Commissioning_Year_Standardized | Inv_Is_Present | Project_Promoter | Project_Is_cross_border | Inv_Substation From | Inv_Substation To | Inv_Element type | Inv_Technology[AC/DC] | Inv_Capacity [MW] | Inv_Voltage [kV] | Inv_Line length [km] | Inv_type [New-Upgrade] | Project_ID | Inv_index | Project_Name | Inv_Name | Inv_Status | Inv_Progress | Inv_Progress Driver | Inv_Commissioning_Year | Inv_Commissioning_Year_Standardized | Inv_Is_Present | Project_Promoter | Inv_Substation From | Inv_Substation To | Inv_Element type | Inv_Technology[AC/DC] | Inv_Voltage [kV] | Project_ID | Inv_index | Project_Name | Inv_Name | Inv_Description | Inv_Status | Inv_Progress | Inv_Progress Driver | Inv_Commissioning_Year | Inv_Commissioning_Year_Standardized | Inv_Is_Present | Project_Promoter | Project_PCI_number | Inv_Is_main_investment | Project_Is_cross_border | Inv_Substation From | Inv_Substation To | Inv_Element type | Inv_Technology[AC/DC] | Inv_Line length [km] | Project_type [New-Upgrade] | Project_ID | Inv_index | Project_Name | Inv_Name | Inv_Description | Inv_Status | Inv_Progress | Inv_Progress Driver | Inv_Commissioning_Year | Inv_Commissioning_Year_Standardized | Inv_Is_Present | Project_Promoter | Project_PCI_number | Inv_Is_main_investment | Project_Is_cross_border | Inv_Substation From | Inv_Substation To | Inv_Element type | Inv_Technology[AC/DC] | Inv_Capacity [MW] | Inv_Voltage [kV] | Inv_Line length [km] | Project_type [New-Upgrade] | Project_ID | Inv_index | Project_Name | Inv_Name | Inv_Description | Inv_Status | Inv_Progress | Inv_Progress Driver | Inv_Commissioning_Year | Inv_Commissioning_Year_Standardized | Inv_Is_Present | Project_Promoter | Project_PCI_number | Inv_Is_main_investment | Project_Is_cross_border | Inv_Substation From | Inv_Substation To | Inv_Element type | Inv_Technology[AC/DC] | Inv_Capacity [MW] | Inv_Voltage [kV] | Inv_Line length [km] | Project_type [New-Upgrade] | Project_ID | Inv_index | Project_Name | Inv_Name | Inv_Description | Inv_Status | Inv_Progress | Inv_Commissioning_Year | Inv_Commissioning_Year_Standardized | Inv_Is_Present | Project_Promoter | Project_Is_cross_border | Inv_Substation From | Inv_Substation To | Project_type [New-Upgrade] | Inv_first_reported_commissioning_year | Inv_last_reported_commissioning_year | delay | duration | Project_Country_ISO3 | Inv_Substation_From_Final | Inv_Substation_To_Final | Inv_From_Lat | Inv_From_Lon | Inv_To_Lat | Inv_To_Lon
0 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 1 | Commissioned | 1 | Creation of a new 400kV station in Frades B connected to Pedralva by means of two new 400kV, 40km lines. The realisation of this two connections can take advantage of some already existing 150kV single lines, which will be reconstructed as double circuit lines 400+150kV line and partially sharing towers with those 400kV circuits. | 3 | 2015 | 2015 | 1 | Frades B (PT) | Pedralva 1&2 (PT) | 1 | 1. 1 | Creation of a new 400kV station in Frades B connected to Pedralva by means of two new 400kV, 40km lines. The realization of this two connections can take advantage of some already existing 150kV single lines, which will be reconstructed as double circuit lines 400+150kV line and partially sharing towers with those 400kV circuits. | 3 | Adjustment resulting from the new date of the hydro power plant. | 2014 | 2014 | 1 | Frades B (PT) | Pedralva 1&2 (PT) | 1. 1 | 1. 1 | Connection of the new 400kV substation V.Minho to Pedralva substation by means of two new 400kV lines(2x43)km. The realization of this two connections can take advantage of some already existing 150kV single lines, which will be reconstructed as double circuit lines 400+150kV line and partially sharing towers with those 400kV circuits. | 4 | Although the investment is already under construction some constraints regarding environmental issues led the commissioning date to be postponed. | 2015 | 2015 | 1 | V.Minho (PT) | Pedralva (PT) | 1 | 1 | RES in north of Portugal | Connection of the new 400kV substation V.Minho to Pedralva substation by means of two new 400kV lines(2x43)km. The realization of this two connections can take advantage of some already existing 150kV single lines, which will be reconstructed as double circuit lines 400+150kV line and partially sharing towers with those 400kV circuits. | 4 | Delayed | Although the investment is already under construction some constraints regarding environmental issues led the commissioning date to delay | 2015 | 2015 | 1 | V.Minho (PT) | Pedralva (PT) | 1 | Connection of the new 400kV substation V.Minho to Pedralva substation by means of two new 400kV lines(2x43)km. The realization of this two connections can take advantage of some already existing 150kV single lines, which will be reconstructed as double circuit lines 400+150kV line and partially sharing towers with those 400kV circuits. | 4 | Investment on time | The first circuit was commissioned in 2014, the second is under construction. Progressed as planned. | 2015 | 2015 | 1 | V.Minho (PT) | Pedralva (PT) | 1 | 1 | RES in north of Portugal | V.Minho-Pedralva 1&2 | Connection of the new 400kV substation V.Minho to Pedralva substation by means of two new 400kV lines(33.5+33)km. The realization of this two connections can take advantage of some already existing 150kV single lines, which will be reconstructed as double circuit lines 400+150kV line and partially sharing towers with those 400kV circuits. | 5 | Commissioned | The first circuit was commissioned in 2014, the second in 2015. | 29/ 12/ 2015 | 2015 | 1 |  | 0 | V.Minho (PT) | Pedralva (PT) | Overhead Line | AC | 1650 | 400 | 66.5 | Upgrade | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 5 | PRT | V.Minho | Pedralva |  |  | 41.5599 | -8.3209
1 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 1000 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 175 | 1000 | Great Belt II | 600 MW HVDC subsea link between both DK systems (2 synchr. areas, 2 market areas) | 1 | New Investment | in case of n expanded DKE-SE connection this link could be beneficial. | 2030 | 2030 | 1 | Malling (DKW) | Kyndby (DKE) | 1000 | 600 MW HVDC subsea link between both DK systems (2 synchr. areas, 2 market areas) | 1 | Investment on time | This project was identified in the first phase of TYNDP14 project and then assessed. It fits to the new category ‘Future project candidates’: projects under consideration or with expected commissioning date beyond 2030. This means, status is unchanged sin | 2030 | 2030 | 1 | Malling (DKW) | Kyndby (DKE) | 175 | 1000 | Great Belt II | Great Belt II | 600 MW HVDC subsea link between both DK systems (2 synchr. areas, 2 market areas) | 1 | Investment on time | optional candidate project from TYNDP14 | 1/ 1/ 2030 | 2030 | 1 |  | 0 | Malling (DKW) | Kyndby (DKE) | Subsea Cable | DC | 600 | 450 | 200 | New | 175 | 1000 | Great Belt II | Great Belt II | 1 | Investment on time |  | 2030 | 2030 | 1 | Energinet.dk | Malling (DKW) | Kyndby (DKE) | Subsea Cable | DC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | DNK | Malling | Kyndby | 56.0377 | 10.1912 | 55.7949 | 11.9191
2 | 2014 | 2014 | [2014] | 1001 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 220 | 1001 | Southern Aegean Interconnector | New DC link (2 converter SS + 250 km DC subm. cable) to Crete | 3 | New Investment | Project application to TYNDP 2014. commissioning date: 2018-2020 | 2020 | 2020 | 1 | LEVITHA island | KORAKIA (new s/s in Crete) |  |  | 6 | Cancelled |  |  |  | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 6 | GRC | Levitha Island | Korakia | 37.0079 | 26.4676 | 37.3603 | 23.0641
3 | 2016 | 2016 | [2016] | 1002 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 147 | 1002 | South Balkan (CSE9) | Tirana 3 (AL) - Prizren (RS) | New 400 kV OHL between SS Tirana 3 – SS Skavica with around 100 km length. New 400 kV OHL between SS Skavica (Albania) and SS Prizren (Kosovo) with around 45 km (30 km Albanian Part). SS Skavica is a new SS and all this investment is dependent of construction of 300 MW HPP Skavica which is plant to be connected in SS Skavica. | 2 | New Investment | New investment | 1/ 1/ 2028 | 2028 | 1 |  | 1 | SS Skavica | SS Prizren | Overhead Line | AC | 0 | 400 | 45 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2028 | 2028 | 0 | 12 | ALB;SRB;BGR;GRC;MKD | Skavica | Prizren | 41.9145 | 20.3608 | 41.31 | 19.4855
4 | 2014 | 2020 | [2014, 2015, 2016, 2018, 2020] | 1004 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 163 | 1004 | BalticCorridor | Reinforcement of existing 330 kV OHL between Paide and Sindi 330 kV substations in Estonia. Old line will be replaced with new towers and wires of 3x400 mm2 in phase. The thermal capacity of the line is planned 1143 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 2 | New Investment | - | 2030 | 2030 | 1 | Sindi | Paide | 1004 | Reinforcement of existing 330 kV OHL between Paide and Sindi 330 kV substations in Estonia. Old line will be replaced with new towers and wires of 3x400 mm2 in phase. The thermal capacity of the line is planned 1143 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 1 | Investment on time | Progressed as planned. | 2030 | 2030 | 1 | Sindi | Paide | 170 | 1004 | Baltic synchronization | 330kV OHL Paide-Sindi (L346) | Reinforcement of existing 330 kV OHL between Paide and Sindi 330 kV substations in Estonia. Old line will be replaced with new towers and wires of 3x400 mm2 in phase. The thermal capacity of the line is planned 1143 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 6 | Cancelled | we have developed an operational procedure to overcome the overloading issues, therefore the investment can be postponed | 01/01/2025 | 2025 | 1 |  | 0 | Sindi | Paide | Overhead Line | AC | 200 | 330 | 76 | New | 170 | 1004 | Baltics synchro with CE | 330kV OHL Paide-Sindi (L346) | 1 | Investment on time |  | 01/01/2025 | 2025 | 1 |  | Sindi | Paide | Overhead Line | AC | 330 | 170 | 1004 | Baltic States Synchronization with Continental Europe | 330kV OHL Paide-Sindi (L346) | Reinforcement of existing 330 kV OHL between Paide and Sindi 330 kV substations in Estonia. Old line will be replaced with new towers and wires of 3x400 mm2 in phase. The thermal capacity of the line is planned 1143 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 1 | Cancelled |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Sindi | Paide | ACTransmissionLine | AC | 76 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2025 | -5 | 11 | EST;LTU;LVA;POL | Sindi | Paide | 58.4075 | 24.6583 | 58.8869 | 25.5699
5 | 2014 | 2015 | [2014, 2015] | 1005 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 172 | 1005 | ElecLink | Eleclink is a new FR – UK interconnection cable thought the channel Tunnel between Selindge (UK) and Mandarins (FR). Converter stations will be located on Eurotunnel concession at Folkestone and Coquelles. This HVDC interconnection is a PCI project (Project of common interest). It will increase by 1GW the interconnection capacity between UK and FR by 2016. | 3 | New Investment |  | 2016 | 2016 | 1 | Sellindge (UK) | Le Mandarins (FR) | 1005 | Eleclink is a new FR – UK interconnection cable thought the channel Tunnel between Selindge (UK) and Mandarins (FR). Converter stations will be located on Eurotunnel concession at Folkestone and Coquelles. This HVDC interconnection is a PCI project (Project of common interest). It will increase by 1GW the interconnection capacity between UK and FR by 2016. | 3 | Delayed | Progressed as planned | 2018 | 2018 | 1 | Sellindge (UK) | Le Mandarins (FR) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2018 | 2 | 4 | FRA;GBR | Sellindge | Le Mandarins | 51.1086 | 0.98837
6 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 1008 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 173 | 1008 | FR-BE phase 2 | The following (combination of) options are envisioned and will be further studied: - Lonny-Achène-Gramme (Reconductoring with High Temperature Low Sag conductors or HVDC) - Capelle-Courcelles (HVDC) - Warande-Zeebrugge/Alfa (HVDC) | 1 | New Investment | Preliminary analyses show the need for an additional reinforcement in visions 3 & 4 (2030) between France & Belgium , complementary to project # 23. | 2030 | 2030 | 1 | tbd(FR) | tbd(BE) | 1008 | The option that will be evaluated envisions the replacement of the current conductors on the axis Lonny-Achène- Gramme with high performance conductors. The integration of complementary flux control measures is subject to further studies depicting the interaction with the 225kV axis Aubange-Moulaine, hereby not excluding that these studies could lead to alternative solutions (new HVDC corridor, upgrade 225kV to 380kV,...). | 1 | Investment on time | Related to the long-term perspective of the energy transition. Subject to further studies given uncertainties around its practical implementation. | 2030 | 2030 | 1 | tbd(FR) | tbd(BE) | 280 | 1008 | FR-BE Phase 3 (study) | Lonny-Achène-Gramme: HTLS upgrade (under study) | The option that will be evaluated envisions the replacement of the current conductors on the axis Lonny-Achène-Gramme with high performance conductors. Hereby not excluding that the bilateral study could lead to complementary / alternative solutions such as a new HVDC corridor (onshore or offshore) or installation of a PST. | 1 | Investment on time | Related to the long-term perspective of the energy transition. Subject to further studies to determine techno-economic most optimum solution taking into account the feasability of different solutions. | 01/01/2025 | 2025 | 1 |  | 1 | Lonny (FR) | Gramme (BE) | Overhead Line | AC | 1000 | 400 | 75 | Upgrade | 280 | 1008 | FR-BE III: study Lonny-Achene-Gramme | Study Lonny-Achene-Gramme | 1 | Investment on time |  | 2025-2030 | 2030 | 1 | ELIA; RTE | Lonny (FR) | Gramme (BE) | Phase Shift Transformer | AC | 400 | 280 | 1008 | FR-BE: study Lonny-Achene-Gramme | Study Lonny-Achene-Gramme | Installation of PST(s) and/or line capacity upgrade of Lonny-Achene-Gramme. On this axis multiple needs are required : by 2025, installation of a PST at Achêne (planned in the Belgium NDP) to secure the current transfer capacity with the Nuclear shutdown in Belgium that could affect directly axis "Lonny-Achêne-Gramme" with closing of power plant of Tihange. By 2030, to increase the transfer capacity between France and Belgium, Project 280 (HTLS reinforcement + use of PST set in 2025 + additionnal PST) is under consideration in TYNDP 2020. As the two set of reinforcement are on the same axis, for sure they will interact together but the goal is not exactly the same | 1 | Investment on time |  | 2030 | 2030 | 1 | ELIA RTE |  | 1 | 1 | Lonny (FR) | Gramme (BE) | ACTransmissionLine | AC | 0 | MostlyUpgrade | 280 | 1008 | FR-BE: study Lonny-Achene-Gramme | Study Lonny-Achene-Gramme | Installation of PST(s) and/or line capacity upgrade of Lonny-Achene-Gramme | 1 | Investment on time |  | 12-2030 | 2030 | 1 | Elia, Rte | 2.32 | 1 | 1 | Lonny (FR) | Gramme (BE) | ACTransmissionLine | AC | 0 | 400 | 100 | MostlyUpgrade | 280 | 1008 | FR-BE: Lonny-Achene-Gramme | Lonny-Achene-Gramme | Installation of PST and line capacity upgrade of Lonny-Achene-Gramme | 2 | Investment on time |  | 12-2030 | 2030 | 1 | Elia, Rte | 1.8 | 1 | 1 | Lonny (FR) | Gramme (BE) | ACTransmissionLine | AC | 0 | 400 | 100 | MostlyUpgrade | 280 | 1008 | FR-BE: Lonny-Achene-Gramme | Lonny-Achene-Gramme | Installation of PST and line capacity upgrade of Lonny-Achene-Gramme | 2 |  | 12-2030 | 2030 | 1 | Elia, Rte | 1 | XX | XX | Mostly upgrade | 2030 | 2030 | 0 | 16 | BEL;FRA | Lonny | Gramme | 49.8156 | 4.5876 | 50.4163 | 4.447
7 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 1010 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 163 | 1010 | BalticCorridor | Reinforcement of existing 330 kV OHL with new towers and wires of 3x300 mm2 in phase. The thermal capacity of the line is planned 1000 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 1 | New Investment | - | 2030 | 2030 | 1 | Tartu | Valmiera | 1010 | Reinforcement of existing 330 kV OHL with new towers and wires of 3x300 mm2 in phase. The thermal capacity of the line is planned 1000 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 2 | Rescheduled | The project have been moved forward because of prioritisation of the Synchronization project to which all those investments are related to | 2024 | 2024 | 1 | Tartu | Valmiera | 170 | 1010 | Baltic synchronization | 330 kV OHL Tartu-Valmiera | Reinforcement of existing 330 kV OHL with new towers and wires of 3x300 mm2 in phase. The thermal capacity of the line is planned 1000 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 1 | Rescheduled | Baltic States desinchronisation | 1/ 1/ 2025 | 2025 | 1 |  | 1 | Tartu | Valmiera | Overhead Line | AC | 500 | 330 | 133 | Upgrade | 170 | 1010 | Baltics synchro with CE | 330 kV OHL Tartu-Valmiera | 2 | Investment on time | Final decision for certain construction time will be made in May 2018. | 1/ 1/ 2025 | 2025 | 1 |  | Tartu | Valmiera | Overhead Line | AC | 330 | 170 | 1010 | Baltic States Synchronization with Continental Europe | 330 kV OHL Tartu-Valmiera | Reinforcement of existing 330 kV OHL. The investment is also a backbone for Baltics Synchronization with CESA. | 3 | Investment on time |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Tartu | Valmiera | ACTransmissionLine | AC | 133 | New | 170 | 1010 | Baltic States Synchronization with Continental Europe | 330 kV OHL Tartu-Valmiera | Reinforcement of existing 330 kV OHL. The investment is also a backbone for Baltics Synchronization with CESA. On Estonian territory parallel 110 kV lines will be installed on the common tower (approx. 51 km) to reduce social and environmental impact. | 4 | Ahead of time |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Tartu (EE) | Valmiera (LV) | ACTransmissionLine | AC | 0 | 330 | 133 | MostlyNew | 170 | 1010 | Baltic States Synchronization with Continental Europe | 330 kV OHL Tartu-Valmiera | Reinforcement of existing 330 kV OHL. The investment is also a backbone for Baltics Synchronization with CESA. On Estonian territory parallel 110 kV lines will be installed on the common tower (approx. 51 km) to reduce social and environmental impact. | 5 | Ahead of time |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Tartu (EE) | Valmiera (LV) | ACTransmissionLine | AC | 0 | 330 | 133 | MostlyNew | 170 | 1010 | Baltic States Synchronization with Continental Europe | 330 kV OHL Tartu-Valmiera | Reinforcement of existing 330 kV OHL. The investment is also a backbone for Baltics Synchronization with CESA. On Estonian territory parallel 110 kV lines will be installed on the common tower (approx. 51 km) to reduce social and environmental impact. | 5 | Commissioned | 11-2023 | 2023 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2030 | 2023 | -7 | 9 | EST;LTU;LVA;POL | Tartu | Valmiera | 58.378 | 26.729 | 57.5389 | 25.4262
8 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 1011 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 163 | 1011 | BalticCorridor | Reinforcement of existing 330 kV OHL with new towers and wires of 3x300 mm2 in phase. The thermal capacity of the line is planned 1000 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 1 | New Investment | - | 2030 | 2030 | 1 | Tsirguliina | Valmiera | 1011 | Reinforcement of existing 330 kV OHL with new towers and wires of 3x300 mm2 in phase. The thermal capacity of the line is planned 1000 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 2 | Rescheduled | The project have been moved forward because of prioritisation of the Synchronization project to which all those investments are related to | 2025 | 2025 | 1 | Tsirguliina | Valmiera | 170 | 1011 | Baltic synchronization | Valmiera -Tsirguliina 330 kV | Reinforcement of existing 330 kV OHL with new towers and wires of 3x300 mm2 in phase. The thermal capacity of the line is planned 1000 MVA.The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 1 | Rescheduled | - | 1/ 1/ 2025 | 2025 | 1 |  | 1 | Tsirguliina | Valmiera | Overhead Line | AC | 500 | 330 | 60 | Upgrade | 170 | 1011 | Baltics synchro with CE | Valmiera -Tsirguliina 330 kV | 2 | Investment on time | Final decision for certain construction time will be made in May 2018. | 1/ 1/ 2025 | 2025 | 1 |  | Tsirguliina | Valmiera | Overhead Line | AC | 330 | 170 | 1011 | Baltic States Synchronization with Continental Europe | Valmiera -Tsirguliina 330 kV | Reinforcement of existing 330 kV OHL. The investment is also a backbone for Baltics Synchronization with CESA | 3 | Investment on time |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Tsirguliina | Valmiera | ACTransmissionLine | AC | 60 | New | 170 | 1011 | Baltic States Synchronization with Continental Europe | Valmiera -Tsirguliina 330 kV | Reinforcement of existing 330 kV OHL. The investment is also a backbone for Baltics Synchronization with CESA | 3 | Investment on time |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Tsirguliina (EE) | Valmiera (LV) | ACTransmissionLine | AC | 0 | 330 | 60 | MostlyNew | 170 | 1011 | Baltic States Synchronization with Continental Europe | Valmiera -Tsirguliina 330 kV | Reinforcement of existing 330 kV OHL. The investment is also a backbone for Baltics Synchronization with CESA | 4 | Investment on time |  | 12-2024 | 2024 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Tsirguliina (EE) | Valmiera (LV) | ACTransmissionLine | AC | 0 | 330 | 60 | MostlyNew | 170 | 1011 | Baltic States Synchronization with Continental Europe | Valmiera -Tsirguliina 330 kV | Reinforcement of existing 330 kV OHL. The investment is also a backbone for Baltics Synchronization with CESA | 5 | Commissioned | 11-2024 | 2024 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2030 | 2024 | -6 | 10 | EST;LTU;LVA;POL | Tsirguliina | Valmiera | 57.8651 | 26.1965 | 57.5389 | 25.4262
9 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 1012 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 163 | 1012 | BalticCorridor | Reinforcement of existing 330 kV OHL between Balti and Tartu 330 kV substations in Estonia. Old line will be replaced with new towers and wires of 3x400 mm2 in phase. The thermal capacity of the line is planned 1143 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 1 | New Investment | - | 2030 | 2030 | 1 | Balti | Tartu | 1012 | Reinforcement of existing 330 kV OHL between Balti and Tartu 330 kV substations in Estonia. Old line will be replaced with new towers and wires of 3x400 mm2 in phase. The thermal capacity of the line is planned 1143 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 2 | Rescheduled | The project have been moved forward because of prioritisation of the Synchronization project to which all those investments are related to | 2024 | 2024 | 1 | Balti | Tartu | 170 | 1012 | Baltic synchronization | 330 kV OHL Tartu-Balti (L300) | Reinforcement of existing 330 kV OHL between Balti and Tartu 330 kV substations in Estonia. Old line will be replaced with new towers and wires of 3x400 mm2 in phase. The thermal capacity of the line is planned 1143 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 2 | Rescheduled | - | 1/ 1/ 2024 | 2024 | 1 |  | 0 | Balti | Tartu | Overhead Line | AC | 500 | 330 | 168 | Upgrade | 170 | 1012 | Baltics synchro with CE | 330 kV OHL Tartu-Balti (L300) | 2 | Investment on time | Final decision for certain construction time will be made in May 2018. | 1/ 1/ 2024 | 2024 | 1 |  | Balti | Tartu | Overhead Line | AC | 330 | 170 | 1012 | Baltic States Synchronization with Continental Europe | 330 kV OHL Tartu-Balti (L300) | Reinforcement of existing 330 kV OHL between Balti and Tartu 330 kV substations in Estonia. Old line will be replaced with new towers and wires of 3x400 mm2 in phase. The thermal capacity of the line is planned 1143 MVA. The investment is also a backbone for Baltics Synchronization with CESA (project nr 170). | 3 | Investment on time |  | 2023 | 2023 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Balti | Tartu | ACTransmissionLine | AC | 168 | New | 170 | 1012 | Baltic States Synchronization with Continental Europe | 330 kV OHL Tartu-Balti (L300) | Reinforcement of existing 330 kV OHL between Balti and Tartu 330 kV substations in Estonia. Old 330 kV line will be replaced with new one with a conductor 3x400 mm2 in phase. The thermal capacity of the line is planned 2400A @ wire max operating temperature 80 degrees celsius. The investment is also a backbone for Baltics Synchronization with CESA (project nr 170). Parallel 110 kV lines will be installed on the common towers along the whole length of the line corridor (approx. 132 km) to reduce social and environmental impact. | 3 | Ahead of time |  | 12-2023 | 2023 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Balti | Tartu | ACTransmissionLine | AC | 0 | 330 | 132 | MostlyNew | 170 | 1012 | Baltic States Synchronization with Continental Europe | 330 kV OHL Tartu-Balti (L300) | Reinforcement of existing 330 kV OHL between Balti and Tartu 330 kV substations in Estonia. Old 330 kV line will be replaced with new one with a conductor 3x400 mm2 in phase. The thermal capacity of the line is planned 2400A @ wire max operating temperature 80 degrees celsius. The investment is also a backbone for Baltics Synchronization with CESA (project nr 170). Parallel 110 kV lines will be installed on the common towers along the whole length of the line corridor (approx. 132 km) to reduce social and environmental impact. | 5 | Ahead of time |  | 05-2023 | 2023 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Balti | Tartu | ACTransmissionLine | AC | 0 | 330 | 132 | MostlyNew | 170 | 1012 | Baltic States Synchronization with Continental Europe | 330 kV OHL Tartu-Balti (L300) | Reinforcement of existing 330 kV OHL between Balti and Tartu 330 kV substations in Estonia. Old 330 kV line will be replaced with new one with a conductor 3x400 mm2 in phase. The thermal capacity of the line is planned 2400A @ wire max operating temperature 80 degrees celsius. The investment is also a backbone for Baltics Synchronization with CESA (project nr 170). Parallel 110 kV lines will be installed on the common towers along the whole length of the line corridor (approx. 132 km) to reduce social and environmental impact. | 5 | Commissioned | 05-2023 | 2023 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2030 | 2023 | -7 | 9 | EST;LTU;LVA;POL | Balti | Tartu |  |  | 58.378 | 26.729
10 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 1013 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 163 | 1013 | BalticCorridor | Reinforcement of existing 330 kV OHL between Eesti and Tsirguliina 330 kV substations in Estonia. Old line will be replaced with new towers and wires of 3x400 mm2 in phase. The thermal capacity of the line is planned 1143 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 1 | New Investment | - | 2030 | 2030 | 1 | Eesti | Tsirguliina | 1013 | Reinforcement of existing 330 kV OHL between Eesti and Tsirguliina 330 kV substations in Estonia. Old line will be replaced with new towers and wires of 3x400 mm2 in phase. The thermal capacity of the line is planned 1143 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 2 | Rescheduled | The project have been moved forward because of prioritisation of the Synchronization project to which all those investments are related to | 2018 | 2018 | 1 | Eesti | Tsirguliina | 170 | 1013 | Baltic synchronization | Eesti-Tsirguliina 330kV OHL | Reinforcement of existing 330 kV OHL between Eesti and Tsirguliina 330 kV substations in Estonia. Old line will be replaced with new towers and wires of 3x400 mm2 in phase. The thermal capacity of the line is planned 1143 MVA. The investment is also a backbone for Baltics Synchronization with CE (project nr 170). | 2 | Rescheduled | - | 1/ 1/ 2025 | 2025 | 1 |  | 0 | Eesti | Tsirguliina | Overhead Line | AC | 500 | 330 | 243 | New | 170 | 1013 | Baltics synchro with CE | Viru-Tsirguliina 330kV OHL | 2 | Investment on time | Final decision for certain construction time will be made in May 2018. | 1/ 1/ 2025 | 2025 | 1 |  | Viru | Tsirguliina | Overhead Line | AC | 330 | 170 | 1013 | Baltic States Synchronization with Continental Europe | Viru-Tsirguliina 330kV OHL | Reinforcement of existing 330 kV OHL between Viru and Tsirguliina 330 kV substations in Estonia. Old line will be replaced with new towers and wires of 3x400 mm2 in phase. The thermal capacity of the line is planned 1143 MVA. The investment is also a backbone for Baltics Synchronization with CESA (project nr 170). | 3 | Investment on time |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Viru | Tsirguliina | ACTransmissionLine | AC | 243 | New | 170 | 1013 | Baltic States Synchronization with Continental Europe | Viru-Tsirguliina 330kV OHL | Reinforcement of existing 330 kV OHL between Viru and Tsirguliina 330 kV substations in Estonia. Old 330 kV line will be replaced with new one with a conductor 3x400 mm2 in phase. The thermal capacity of the line is planned 2400A @ wire max operating temperature 80 degrees celsius. The investment is also a backbone for Baltics Synchronization with CESA (project nr 170). Parallel 110 kV lines will be installed on the common tower (approx. 14 km) to reduce social and environmental impact. To optimize line lenght and reactive power compensation a new 330 kV substation (named Mustvee) will be constructed in the middle of the power line. | 3 | Rescheduled | During the planning and design process since last TYNDP 2020 the exact construction and outage schedule was specified and coordinated and therefore the line reconstruction schedule was also changed. Planned commissioning in October-November 2025. Planned construction starts June 2023. | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Viru | Tsirguliina | ACTransmissionLine | AC | 0 | 330 | 244 | MostlyNew | 170 | 1013 | Baltic States Synchronization with Continental Europe | Viru-Tsirguliina 330kV OHL | Reinforcement of existing 330 kV OHL between Viru and Tsirguliina 330 kV substations in Estonia. Old 330 kV line will be replaced with new one with a conductor 3x400 mm2 in phase. The thermal capacity of the line is planned 2400A @ wire max operating temperature 80 degrees celsius. The investment is also a backbone for Baltics Synchronization with CESA (project nr 170). Parallel 110 kV lines will be installed on the common tower (approx. 14 km) to reduce social and environmental impact. To optimize line lenght and reactive power compensation a new 330 kV substation (named Mustvee) will be constructed in the middle of the power line. | 4 | Ahead of time | Due to accelerated synchronization of the Baltic States, the construction on Viru-Tsirguliina was accelerated. The construction on the line started in June 2023, the line will be energized in December 2024 and officially commissioned in February 2025. | 02-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Viru | Tsirguliina | ACTransmissionLine | AC | 0 | 330 | 244 | MostlyNew | 170 | 1013 | Baltic States Synchronization with Continental Europe | Viru-Tsirguliina 330kV OHL | Reinforcement of existing 330 kV OHL between Viru and Tsirguliina 330 kV substations in Estonia. Old 330 kV line will be replaced with new one with a conductor 3x400 mm2 in phase. The thermal capacity of the line is planned 2400A @ wire max operating temperature 80 degrees celsius. The investment is also a backbone for Baltics Synchronization with CESA (project nr 170). Parallel 110 kV lines will be installed on the common tower (approx. 14 km) to reduce social and environmental impact. To optimize line lenght and reactive power compensation a new 330 kV substation (named Mustvee) will be constructed in the middle of the power line. | 4 |  | 06-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2030 | 2025 | -5 | 11 | EST;LTU;LVA;POL | Viru | Tsirguliina | 57.7365 | 26.7433 | 57.8651 | 26.1965
11 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 1014 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 174 | 1014 | Greenconnector | New +/- 400 kV DC cable and subsea link between Switzerland and Italy. Very short AC cable (380 kV) between the site of the converter station and the substation of Sils i.D. | 3 | New Investment | Project application to TYNDP 2014. | 2018 | 2018 | 1 | Verderio (I) | Sils (CH) | 1014 | New +/- 400 kV DC cable and subsea link between Switzerland and Italy. Very short AC cable (380 kV) between the site of the converter station and the substation of Sils i.D. | 3 | Delayed | Progressed as planned | 2021 | 2021 | 1 | Verderio (I) | Sils (CH) | 174 | 1014 | Greenconnector | Greenconnector | ​Greenconnector is an HVDC interconnector project between Italy and Switzerland for power transport using DC cables rather than overhead lines. The route length is about 150 km. The design power is 1000 MW (1200 MW in overload condition), while the DC voltage is +/- 400 kV DC. Two cables will be installed, working with a bipolar scheme. Great part of the cables route will exploit a section of an existing oil pipeline, no longer in service since January 1997. This pipeline crosses the Italian and Switzerland border at Splügenpass and is running close by the two end stations of the Greenconnector project (Sils in Graubunden Canton and Verderio Inferiore, Lecco). The cables will be pulled inside the pipeline itself, reducing the amount of civil works required before and after cable laying and therefore limiting even temporary environmental impact. For about 47 km the cables will run across the Como lake.​ |  |  |  | 2021 | 2021 | 1 |  | 0 | Verderio | Sils i.D. |  | DC |  | 400 | 150 |  | 174 | 1014 | Greenconnector | Greenconnector | 3 | Delayed | A different location of the Converter Station in Switzerland is under evaluation due to local opposition. A rerouting of the final part of the Interconnector is under evaluation as well. | 2022 | 2022 | 1 | Worldenergy SA | Verderio | Sils i.D. | Underground Cable | DC | 400 | 174 | 1014 | Greenconnector | Greenconnector | Greenconnector is an HVDC interconnector project between Italy and Switzerland for power transport using DC cables rather than overhead lines. The route length is about 165 km. The design power is 1000 MW (1200 MW in overload condition), while the DC voltage is +/- 400 kV DC. Two cables will be installed, working with a bipolar scheme. Great part of the cables route will exploit a section of an existing oil pipeline, no longer in service since January 1997. This pipeline crosses the Italian and Switzerland border at Splgenpass and is running close by the two end stations of the Greenconnector project (Bonaduz in Graubunden Canton and Verderio Inferiore, Lecco). The cables will be pulled inside the pipeline itself, reducing the amount of civil works required before and after cable laying and therefore limiting even temporary environmental impact. For about 47 km the cables will run across the Como lake. | 3 | Delayed | A different location of the Converter Station in Switzerland has been evaluated due to local opposition. A rerouting of the final part of the Interconnector has been evaluated as well. | 2024 | 2024 | 1 | Worldenergy SA | 2.14 | 1 | 1 | Verderio | Bonaduz | DCTransmissionLine | DC | 165 | New | 174 | 1014 | Greenconnector | Greenconnector | Greenconnector is an HVDC interconnector project between Italy and Switzerland for power transport using DC cables rather than overhead lines. The route length is about 165 km. The design power is 1000 MW (1200 MW in overload condition), while the DC voltage is +/- 400 kV DC. Two cables will be installed, working with a bipolar scheme. Great part of the cables route will exploit a section of an existing oil pipeline, no longer in service since January 1997. This pipeline crosses the Italian and Switzerland border at Splgenpass and is running close by the two end stations of the Greenconnector project (Bonaduz in Graubunden Canton and Verderio Inferiore, Lecco). The cables will be pulled inside the pipeline itself, reducing the amount of civil works required before and after cable laying and therefore limiting even temporary environmental impact. For about 47 km the cables will run across the Como lake. | 3 | Delayed | Negotiations with the Swiss authorities are in progress and advancing | 12-2026 | 2026 | 1 | Worldenergy SA | 2.14 | 1 | 1 | Verderio | Bonaduz | DCTransmissionLine | DC | 1000 | 400 | 165 | New | 174 | 1014 | Greenconnector | Greenconnector | Greenconnector is an HVDC interconnector project between Italy and Switzerland for power transport using DC cables rather than overhead lines. The route length is about 165 km. The design power is 1000 MW (1200 MW in overload condition), while the DC voltage is +/- 400 kV DC. Two cables will be installed, working with a bipolar scheme. Great part of the cables route will exploit a section of an existing oil pipeline, no longer in service since January 1997. This pipeline crosses the Italian and Switzerland border at Splgenpass and is running close by the two end stations of the Greenconnector project (Bonaduz in Graubunden Canton and Verderio Inferiore, Lecco). The cables will be pulled inside the pipeline itself, reducing the amount of civil works required before and after cable laying and therefore limiting even temporary environmental impact. For about 47 km the cables will run across the Como lake. | 3 | Delayed | Negotiations with the Swiss authorities are in progress and advancing | 02-0296 | 2029 | 1 | Worldenergy SA | 2.14 | 1 | 1 | Verderio | Bonaduz | DCTransmissionLine | DC | 1000 | 400 | 165 | New | 174 | 1014 | Greenconnector | Greenconnector | Greenconnector is an HVDC interconnector project between Italy and Switzerland for power transport using DC cables rather than overhead lines. The route length is about 165 km. The design power is 1000 MW (1200 MW in overload condition), while the DC voltage is +/- 400 kV DC. Two cables will be installed, working with a bipolar scheme. Great part of the cables route will exploit a section of an existing oil pipeline, no longer in service since January 1997. This pipeline crosses the Italian and Switzerland border at Splgenpass and is running close by the two end stations of the Greenconnector project (Bonaduz in Graubunden Canton and Verderio Inferiore, Lecco). The cables will be pulled inside the pipeline itself, reducing the amount of civil works required before and after cable laying and therefore limiting even temporary environmental impact. For about 47 km the cables will run across the Como lake. |  |  | 03-2033 | 2033 | 1 | Greenconnector AG | 1 | XX | XX | New | 2018 | 2033 | 15 | 19 | CHE;ITA | Verderio | Bonaduz | 45.6657 | 9.4376 | 46.8113 | 9.3984
12 | 2014 | 2020 | [2014, 2015, 2016, 2018, 2020] | 1016 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 179 | 1016 | DKE - DE | new 600 MW HVDC subsea cable connecting DK2 and DE | 1 | New Investment | RGBS common investigations for TYNDP14 | 2030 | 2030 | 1 | Bjæverskov (DK2) | Bentwisch (DE) | 1016 | new 600 MW HVDC subsea cable connecting DK2 and DE | 1 | Investment on time | optional candidate project from TYNDP14 | 2030 | 2030 | 1 | Bjæverskov (DK2) | Bentwisch (DE) | 179 | 1016 | DKE - DE | Kontek 2 | new 600 MW HVDC subsea cable connecting DK2 and DE | 1 | Investment on time | optional candidate project from TYNDP14 | 1/ 1/ 2030 | 2030 | 1 |  | 1 | Bjæverskov (DK2) | Bentwisch (DE) | Subsea Cable | DC | 600 | 400 | 170 | New | 179 | 1016 | DKE - DE (Kontek2) | DKE-DE (Kontek 2) | 1 | Investment on time |  | > 2030 | 2030 | 1 | 50Hertz Transmission, Energinet.dk | Bjæverskov (DK2) | Bentwisch (DE) | Subsea Cable | DC | 400 | 179 | 1016 | DKE - DE (Kontek2) | DKE-DE (Kontek 2) | New 600 MW HVDC subsea cable connecting DK2 and DE. Also called Kontek 2 | 1 | Investment on time |  | 2030 | 2030 | 1 | Energinet.dk 50HERTZ |  | 1 | 1 | Ørslevvester (DKE) | Bentwisch (DE) | OffshoreDCTransmissionCable | DC | 170 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | DEU;DNK | Ørslevvester | Bentwisch | 55.4681 | 11.688 | 54.1162 | 12.2022
13 | 2014 | 2022 | [2014, 2015, 2016, 2018, 2020, 2022] | 1018 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 183 | 1018 | DKW-DE, Westcoast | new 380 kV cross border line DK1-DE for integration of RES and increase of NTC | 2 | Investment on time | in TYNDP12 this investment was part of 43.A90 | 2022 | 2022 | 1 | Niebüll (DE) | Endrup (DKW) | 1018 | new 380 kV cross border line DK1-DE for integration of RES and increase of NTC | 2 | Investment on time | investigated together with project 39 | 2022 | 2022 | 1 | Niebüll (DE) | Endrup (DKW) | 183 | 1018 | DKW-DE, Westcoast | WestCoast Line, North v2 | new 380 kV Overhead line DK1-DE for integration of RES and increase of NTC | 2 | Investment on time | project planning and technical design is progressing | 31/ 12/ 2022 | 2022 | 1 |  | 1 | Niebüll (DE) | Endrup (DKW) | Underground Cable | AC | 500 | 380 | 92 | New | 183 | 1018 | "DKW-DE, Westcoast" | DKW-DE, Westcoast, TYNDP ID 183.1018 | 3 | Investment on time |  | 31/ 12/ 2022 | 2022 | 1 | Energinet.dk,TENNET-DE | Klixbüll (DE) | Endrup (DKW) | Overhead Line | AC | 380 | 183 | 1018 | DKW-DE, Westcoast | DKW-DE, Westcoast, TYNDP ID 183.1018 | New 380 kV line DKW-DE between Klixbuell (DE) and Endrup (DKW) as part of connection Endrup-Brunsbüttel | 3 | Investment on time |  | 2023 | 2023 | 1 | Energinet.dk TenneT DE | 1.3.1 | 1 | 1 | Klixbüll (DE) | Endrup (DKW) | ACTransmissionLine | AC | 92 | New | 183 | 1018 | DKW-DE, Westcoast | DKW-DE, Westcoast, TYNDP ID 183.1018 | New 380 kV line DKW-DE between Klixbuell (DE) and Endrup (DKW) as part of connection Endrup-Brunsbüttel | 3 | Investment on time |  | 12-2023 | 2023 | 1 | Energinet, TenneT DE |  | 1 | 1 | Klixbüll (DE) | Endrup (DKW) | ACTransmissionLine | AC | 0 | 380 | 92 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2023 | 1 | 9 | DEU;DNK | Klixbüll | Endrup | 54.8021 | 8.89 | 55.5235 | 8.7183
14 | 2014 | 2015 | [2014, 2015] | 1020 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 185 | 1020 | Greenwire IE-GB | Greenwire Interconnector spur 1, enables additional 500MW of interconnection between UK and Irish market | 2 | New Investment | Opportunity to connect Irish RES to GB market | 2018 | 2018 | 1 | Dunstown | Pembroke | 1020 | Greenwire Interconnetor spur 1, enables additional 500MW of interconnection between UK and Irish market | 2 | Delayed | Progressed as planned | 2021 | 2021 | 1 | Dunstown | Pembroke | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2021 | 3 | 7 | GBR;IRL | Dunstown | Pembroke |  |  | 51.674 | -4.9087
15 | 2014 | 2015 | [2014, 2015] | 1021 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 185 | 1021 | Greenwire IE-GB | Greenwire Interconnector spur 2, enables additional 1000MW of interconnection between UK and Irish market | 2 | New Investment | Project application to TYNDP 2014. | 2017 | 2017 | 1 | Woodland | Pentir | 1021 | Greenwire Interconnetor spur 2, enables additional 1000MW of interconnection between UK and Irish market | 2 | Delayed | Progressed as planned | 2021 | 2021 | 1 | Woodland | Pentir | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2021 | 4 | 7 | GBR;IRL | Woodland | Pentir | 53.293 | -6.1987 | 53.1959 | -4.1608
16 | 2014 | 2015 | [2014, 2015] | 1024 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1024 | Irish-Scottish Isles | HVCD link between Cruachan (onshore) to Argyll offshore hub | 1 | New Investment | Project application to TYNDP 2014. | 2030 | 2030 | 1 | Cruachan | Argyll hub | 1024 | HVDC link between Cruachan (onshore) to Argyll offshore hub | 1 | Investment on time | Progressed as planned | 2030 | 2030 | 1 | Cruachan | Argyll hub | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | IRL;GBR | Cruachan | Argyll | 53.9841 | -10.1965
17 | 2014 | 2015 | [2014, 2015] | 1025 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1025 | Irish-Scottish Isles | A new dedicated offshore HVDC hub platform to allow connection of offshore renewable generation and interconnection capacity. | 1 | New Investment | The ISLES project will serve multiple offshore resources off the coasts of Scotland and Northern Ireland, and also facilitate a connection between GB and NI | 2030 | 2030 | 1 | Argyll hub |  | 1025 | A new dedicated offshore HVDC hub platform to allow connection of offshore renewable generation and interconnection capacity. | 1 | Investment on time | Progressed as planned | 2030 | 2030 | 1 | Argyll hub | [6 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | IRL;GBR | Argyll
18 | 2014 | 2015 | [2014, 2015] | 1026 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1026 | Irish-Scottish Isles | A new dedicated offshore HVDC hub platform to allow connection of offshore renewable generation and interconnection capacity. | 1 | New Investment | Project application to TYNDP 2014. | 2030 | 2030 | 1 | Coleraine hub |  | 1026 | A new dedicated offshore HVDC hub platform to allow connection of offshore renewable generation and interconnection capacity. | 1 | Investment on time | Progressed as planned | 2030 | 2030 | 1 | Coleraine hub | [6 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | IRL;GBR | Coleraine
19 | 2014 | 2015 | [2014, 2015] | 1027 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1027 | Irish-Scottish Isles | A new dedicated offshore HVDC hub platform to allow connection of offshore renewable generation and interconnection capacity. | 1 | New Investment | The ISLES project will serve multiple offshore resources off the coasts of Scotland and Northern Ireland, and also facilitate a connection between GB and NI | 2030 | 2030 | 1 | Coolkeeragh hub |  | 1027 | A new dedicated offshore HVDC hub platform to allow connection of offshore renewable generation and interconnection capacity. | 1 | Investment on time | Progressed as planned | 2030 | 2030 | 1 | Coolkeeragh hub | [6 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | IRL;GBR | Coolkeeragh |  | 55.0377 | -7.2514
20 | 2014 | 2015 | [2014, 2015] | 1028 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1028 | Irish-Scottish Isles | HVCD link between Argyll offshore hub and Coleraine offshore hub | 1 | New Investment | The ISLES project will serve multiple offshore resources off the coasts of Scotland and Northern Ireland, and also facilitate a connection between GB and NI | 2030 | 2030 | 1 | Argyll | Coleraine | 1028 | HVDC link between Argyll offshore hub and Coleraine offshore hub | 1 | Investment on time | Progressed as planned | 2030 | 2030 | 1 | Argyll | Coleraine | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | IRL;GBR | Argyll | Coleraine
21 | 2014 | 2015 | [2014, 2015] | 1029 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1029 | Irish-Scottish Isles | HVCD link between Coolkeeragh onshore and Coolkeeragh offshore hub | 1 | New Investment | The ISLES project will serve multiple offshore resources off the coasts of Scotland and Northern Ireland, and also facilitate a connection between GB and NI | 2030 | 2030 | 1 | Coolkeeragh | Coolkeeragh hub | 1029 | HVDC link between Coolkeeragh onshore and Coolkeeragh offshore hub | 1 | Investment on time | Progressed as planned | 2030 | 2030 | 1 | Coolkeeragh | Coolkeeragh hub | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | IRL;GBR | Coolkeeragh | Coolkeeragh | 55.0377 | -7.2514 | 55.0377 | -7.2514
22 | 2014 | 2015 | [2014, 2015] | 1030 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1030 | Irish-Scottish Isles | HVCD link between Colerain onshore and Coleraine offshore hub | 1 | New Investment | The ISLES project will serve multiple offshore resources off the coasts of Scotland and Northern Ireland, and also facilitate a connection between GB and NI | 2030 | 2030 | 1 | Coleraine | Coleraine hub | 1030 | HVDC link between Colerain onshore and Coleraine offshore hub | 1 | Investment on time | Progressed as planned | 2030 | 2030 | 1 | Coleraine | Coleraine hub | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | IRL;GBR | Coleraine | Coleraine
23 | 2014 | 2015 | [2014, 2015] | 1031 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1031 | Irish-Scottish Isles | HVCD link between Coleraine offshore hub and Coolkeeragh offshore hub | 1 | New Investment | The ISLES project will serve multiple offshore resources off the coasts of Scotland and Northern Ireland, and also facilitate a connection between GB and NI | 2030 | 2030 | 1 | Coleraine hub | Coolkeeragh hub | 1031 | HVDC link between Coleraine offshore hub and Coolkeeragh offshore hub | 1 | Investment on time | Progressed as planned | 2030 | 2030 | 1 | Coleraine hub | Coolkeeragh hub | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | IRL;GBR | Coleraine | Coolkeeragh |  |  | 55.0377 | -7.2514
24 | 2014 | 2015 | [2014, 2015] | 1032 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1032 | Irish-Scottish Isles | HVCD link between Hunterston (onshore) to Argyll offshore hub | 1 | New Investment | The ISLES project will serve multiple offshore resources off the coasts of Scotland and Northern Ireland, and also facilitate a connection between GB and NI | 2030 | 2030 | 1 | Hunterston | Coleraine hub | 1032 | HVDC link between Hunterston (onshore) to Argyll offshore hub | 1 | Investment on time | Progressed as planned | 2030 | 2030 | 1 | Hunterston | Coleraine hub | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | IRL;GBR | Hunterston | Coleraine
25 | 2014 | 2015 | [2014, 2015] | 1033 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 190 | 1033 | Norway-Great Britain | A 650 km long 500 kV 1400 MW HVDC subsea interconnector between western Norway and eastern Scotland. | 3 | New Investment | Project application to TYNDP 2014. | 2020 | 2020 | 1 | Sima | Peterhead | 1033 | A 650 km long 500 kV 1400 MW HVDC subsea interconnector between western Norway and eastern Scotland. | 3 | Delayed | Progressed as planned | 2022 | 2022 | 1 | Sima | Peterhead | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2022 | 2 | 8 | NOR | Sima | Peterhead |  |  | 57.5053 | -1.7813
26 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 1034 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 170 | 1034 | Baltics synchro with CE | 400 kV interconnection line for synchronous interconnection of Baltics | 1 | New Investment | - | 2023 | 2023 | 1 | Substation in Lithuania | State border | 1034 | 400 kV interconnection line for synchronous interconnection of Baltics | 1 | Investment on time | Progressed as planned | 2023 | 2023 | 1 | Substation in Lithuania | State border | 170 | 1034 | Baltic synchronization | New 400 kV interconnection line | New 400 kV interconnection line necessary for synchronous interconnection of Baltics with CE. | 1 | New Investment | New line routing and implementation time depends from decisions for project 170. “Baltic synchronization”. | 01/01/2031 | 2031 | 1 |  | 0 | New planned 400 kV Marijampole substation or exicting 400 kV Aytus substation. | State border | Overhead Line | AC | 600 | 400 | 60 | New | 170 | 1034 | Baltics synchro with CE | New 400 kV interconnection line from Lithuania to state border | 2 | New Investment | depends from ongoing studies | 2024 | 2024 | 1 |  | Marijampole | State border | Overhead Line | AC | 400 | 170 | 1034 | Baltic States Synchronization with Continental Europe | New HVDC interconnector "Harmony Link" | New HVDC subsea cable connection between Lithuania and Poland. The project includes HVDC submarine and land cable system and converter stations at each end | 3 | Investment on time |  | 2026 | 2026 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 1 | 1 | Darbenai | Zarnowiec | OffshoreDCTransmissionCable | DC | 400 | New | 170 | 1034 | Baltic States Synchronization with Continental Europe | New HVDC interconnector "Harmony Link" | New HVDC subsea cable connection between Lithuania and Poland. The project includes HVDC submarine and land cable system and converter stations at each end. | 3 | Investment on time |  | 01-2026 | 2026 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 1 | 1 | Darbenai | Zarnowiec | OffshoreDCTransmissionCable | DC | 700 | 300 | 330 | MostlyNew | 170 | 1034 | Baltic States Synchronization with Continental Europe | New HVAC interconnector "Harmony Link" | New HVAC double-circuit three-phase 220 kV land cable connection between Gižai 110/10 kV substation in Lithuania and existing Elk Bis 400/110 kV substation in Poland. The scope of works of Elk Bis substation focuses in particular on the extension by 220 kV switchgear together with autotransformers and shunt reactors, modernization of primary and secondary equipment, together with control and protection systems and measurement equipment. The scope of works at Gižai substation is design and construction of the 330/220/110 kV substation together with autotransformers and shunt reactors, modernisation of primary and secondary equipment, together with control and protection systems and measurement. Two new 220/110 kV substations in Norki and Wigry will be constructed, together with autotransformers and shunt reactors. The existing Ostroleka-Elk 220 kV overhead line of will be modernized. The overall length of the interconnector is about 240 km. | 2 | Delayed | The main reason of delay is due to unsuccessful converter stations and HDVC cable tenders as in both cases the prices offered significantly exceeded the contracting authorities’ budgets. As a result of it the replanning of the project activities has been started. | 12-2030 | 2030 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 1 | 1 | Gižai | Elk Bis | OnshoreACTransmissionCable | AC | 700 | 220 | 330 | MostlyNew | 170 | 1034 | Baltic States Synchronization with Continental Europe | New HVAC interconnector "Harmony Link" | New HVAC double-circuit three-phase 220 kV land cable connection between Gižai 110/10 kV substation in Lithuania and existing Elk Bis 400/110 kV substation in Poland. The scope of works of Elk Bis substation focuses in particular on the extension by 220 kV switchgear together with autotransformers and shunt reactors, modernization of primary and secondary equipment, together with control and protection systems and measurement equipment. The scope of works at Gižai substation is design and construction of the 330/220/110 kV substation together with autotransformers and shunt reactors, modernisation of primary and secondary equipment, together with control and protection systems and measurement. Two new 220/110 kV substations in Norki and Wigry will be constructed, together with autotransformers and shunt reactors. The existing Ostroleka-Elk 220 kV overhead line of will be modernized. The overall length of the interconnector is about 240 km. |  |  | 12-2030 | 2030 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2023 | 2030 | 7 | 16 | EST;LTU;LVA;POL | Giai | Elk Bis
27 | 2014 | 2022 | [2014, 2015, 2016, 2018, 2020, 2022] | 1035 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 58 | 1035 | GerPol Power Bridge | Construction of new 400/220 kV Substation Baczyna to connect the new line Krajnik-Baczyna. | 2 | Investment on time | The investment was part of n°58.353 in TYNDP 2012 and is now presented stand alone. It is in the tendering procedure (design and build scheme). | 2018 | 2018 | 1 | Baczyna |  | 1035 | Construction of new 400/220 kV Substation Baczyna to connect the new line Krajnik-Baczyna. | 2 | Delayed | The investment is in the tendering procedure (design and build scheme). The investment is planned to be completed in Q1 2019. | 2019 | 2019 | 1 | Baczyna |  | 230 | 1035 | GerPol Power Bridge I | Baczyna | Construction of new 400/110 kV Substation Baczyna to connect the new line Krajnik-Baczyna. | 3 | Delayed | The investment is in the tendering procedure (design and build scheme). The investment is planned to be completed in 2020. Change of commissioning date compared to previous reprting due to realization schedule of other investements (line Krajnik-Baczyna and Baczyna-Plewiska). | 12/06/2020 | 2020 | 1 |  | 0 | Baczyna |  | Substation |  | 750 | 400 |  | New | 230 | 1035 | GerPol Power Bridge I | Baczyna | 3 | Rescheduled |  | 2020 | 2020 | 1 |  | Baczyna | n.a. | Substation | AC | 400 | 230 | 1035 | GerPol Power Bridge I | Baczyna | Construction of new 400/110 kV Substation Baczyna to connect the new line Krajnik-Baczyna. | 3 | Investment on time |  | 2021 | 2021 | 1 | Polskie Sieci Elektroenergetyczne S.A. | 3.14 (including 3.14.2, 3.14.3, 3.14.4) | 0 | 0 | Baczyna | n.a. | OnshoreSubstation | AC | 0 | New | 230 | 1035 | GerPol Power Bridge I | Baczyna | Construction of new 400/110 kV Substation Baczyna to connect the new line Krajnik-Baczyna-Plewiska. | 4 | Delayed | The contract with the contractor was terminated in February 2020. The tender for a new contractor has already been concluded. | 12-2024 | 2024 | 1 | Polskie Sieci Elektroenergetyczne S.A. | 3.14 Internal reinforcements in Poland (including 3.14.2, 3.14.3, 3.14.4) | 0 | 0 | Baczyna | Baczyna | OnshoreSubstation | AC | 0 | 400 | 0 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2024 | 6 | 10 | POL | Baczyna | Baczyna
28 | 2014 | 2015 | [2014, 2015] | 1036 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 59 | 1036 | LitPol Link Stage 1 | New Substation Siedlce Ujrzanów will be connected by new line Miłosna-Siedlce Ujrzanów and later by new line Kozienice-Siedlce Ujrzanów | 4 | Investment on time | The investment was previously included in the investment no. 369 as "new 400 kV switchgear in existing Substation Siedlce". The concept has changed and there is a new substation in a different location. | 2015 | 2015 | 1 | Siedlce Ujrzanów |  | 1036 | New Substation Siedlce Ujrzanów will be connected by new line Miłosna-Siedlce Ujrzanów and later by new line Kozienice-Siedlce Ujrzanów | 4 | Investment on time | Under construction. | 2015 | 2015 | 1 | Siedlce Ujrzanów | [6 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 1 | BEL | Siedlce Ujrzanów |  | 52.1339 | 22.3146
29 | 2014 | 2015 | [2014, 2015] | 1037 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 59 | 1037 | LitPol Link Stage 1 | New 400/110 kV Substation Ełk Bis connected by two double 400 kV lines Łomża-Ełk and Ełk-Alytus creating an interconnector Poland-Lithuania. | 4 | Investment on time | The inv. was part of inv. no 370 in TYNDP2012 as "new 400kV switchgear in existing Substation Ełk". The concept has changed, it is not possible to extend the existing substation and there is a new substation in a different location, expected in 2015. | 2015 | 2015 | 1 | Elk Bis |  | 1037 | New 400/110 kV Substation Ełk Bis connected by two double 400 kV lines Łomża-Ełk and Ełk-Alytus creating an interconnector Poland-Lithuania. | 4 | Investment on time | Investment under construction. | 2015 | 2015 | 1 | Ełk Bis | [6 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 1 | LTU;POL | Ek Bis
30 | 2014 | 2016 | [2014, 2015, 2016] | 1038 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 123 | 1038 | LitPol Link Stage 2 | Construction of the second 500 MW back-to-Back converter station in Alytus | 2 | New Investment | This investment was missing not explicitly mentioned in TYNDP 2012,but was already foreseen. | 2020 | 2020 | 1 | Alytus |  | 1038 | Construction of the second 500 MW back-to-Back converter station in Alytus | 2 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Alytus |  | 123 | 1038 | LitPol Link Stage 2 | Back-to-back in Alytus | Construction of the second 500 MW Back-to-Back converter station in Alytus (LT). | 2 | Investment on time | No change of status. | 31/12/2020 | 2020 | 1 |  | 0 | Alytus |  | LCC converter station |  | 500 | 400 |  | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 6 | LTU | Alytus
31 | 2014 | 2016 | [2014, 2015, 2016] | 1039 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 26 | 1039 | Austria - Italy | New 380/220/132 kV substation with related connections to 380 kV Sandrigo Cordignano and 220 KV Soverzene Scorzè where removing limitations are planned | 2 | Delayed | The Volpago Substation was included in the TYNDP 2012 as part of the item 26.83 which had as commissioning date 2015. Permitting process delayed due to territorial constraint | 2020 | 2020 | 1 | Volpago (IT) |  | 1039 | New 380/220/132 kV substation with related connections to 380 kV Sandrigo Cordignano and 220 KV Soverzene Scorzè where removing limitations are planned | 2 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Volpago (IT) |  | 26 | 1039 | Austria - Italy | Volpago substation | New 380/220/132 kV substation with related connections to 380 kV Sandrigo Cordignano and 220 KV Soverzene Scorzè where removing limitations are planned | 2 | Investment on time | - | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Volpago (IT) |  | Substation |  | 800 | 380 |  | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2022 | 2 | 8 | ITA | Volpago |  | 45.7781 | 12.1198
32 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 1041 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 33 | 1041 | 33 | Removing limitations on existing 220 kV grid between Villanova e S.Barbara | 2 | New Investment | The item 1041 has a significant effect on the grid transfer capacity | 2020 | 2020 | 1 | Villanova (IT) | S. Barbara (IT) | 1041 | Removing limitations on existing 220 kV grid between Villanova e S.Barbara | 2 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Villanova (IT) | S. Barbara (IT) | 33 | 1041 | Central Northern Italy | Rem. lim. in Central Italy | Removing limitations on existing 220 kV grid between Villanova e S.Barbara | 2 | Delayed | Additional technical studies on-going. | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Villanova (IT) | S. Barbara (IT) | Overhead Line | AC | 600 | 220 | 350 | Upgrade | 33 | 1041 | Central Northern Italy | Rem. lim. in Central Italy | 2 | Investment on time |  | 2022 | 2022 | 1 |  | Villanova (IT) | S. Barbara (IT) | Overhead Line | AC | 220 | 33 | 1041 | Central Northern Italy | Rem. lim. in Central Italy | Removing limitations on existing 220 kV grid between Villanova e S.Barbara | 2 | Investment on time |  | 2026 | 2026 | 1 | TERNA |  | 0 | 0 | Villanova (IT) | S. Barbara (IT) | ACTransmissionLine | AC | 350 | Upgrade | 33 | 1041 | Central Northern Italy | Rem. lim. in Central Italy | Removing limitations on existing 220 kV grid between Villanova e S.Barbara | 4 | Ahead of time |  | 12-2023 | 2023 | 1 | Terna SpA |  | 0 | 0 | Villanova (IT) | S. Barbara (IT) | ACTransmissionLine | AC | 0 | 220 | 350 | Upgrade | 33 | 1041 | Central Northern Italy | Removing limitations in Central Italy | Removing limitations on existing 220 kV grid between Villanova e S.Barbara | 4 | Investment on time |  | 12-2023 | 2023 | 1 | Terna SpA |  | 0 | 0 | Villanova (IT) | S. Barbara (IT) | ACTransmissionLine | AC | 0 | 220 | 350 | Upgrade | 33 | 1041 | Central Northern Italy | Removing limitations in Central Italy | Removing limitations on existing 220 kV grid between Villanova and S.Barbara | 4 |  | 12-2026 | 2026 | 1 | Terna SpA | 0 | XX | XX | Upgrade | 2020 | 2026 | 6 | 12 | ITA | Villanova | S. Barbara | 43.0071 | 12.3278 | 40.1806 | 15.2567
33 | 2014 | 2014 | [2014] | 1042 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 220 | 1042 | Southern Aegean Interconnector | New DC link (2 converter SS + 270 km DC subm. cable) to connect 537MW of offshore WF generation to the mainland (Area of Athens) | 3 | New Investment | Project application to TYNDP 2014. commissioning date expected: 2018-2020 | 2020 | 2020 | 1 | LAVRION 400kV S/S | LEVITHA island |  |  | 6 | Cancelled |  |  |  | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 6 | GRC | Lavrion Ss | Levitha Island | 37.7143 | 24.0548 | 37.0079 | 26.4676
34 | 2014 | 2015 | [2014, 2015] | 1043 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 198 | 1043 | Area of Lake Constance | Point Neuravensburg – Point Austrian National border (AT) Between switching point Neuravensburg and Austrian National border (AT) a new line with a significantly higher transmission capacity will be constructed in an existing corridor (grid enhancement). | 2 | Investment on time | This project is a concretion of TYNDP 2012 project 44.A77. This investment is caused by the investment 136 "Bodensee Studie". Due to the ongoing planning stage, this section was developed and an own investment item was created. | 2023 | 2023 | 1 | Neuravensburg | border area (AT) | 1043 | Point Neuravensburg – Point Austrian National border (AT) Between switching point Neuravensburg and Austrian National border (AT) a new line with a significantly higher transmission capacity will be constructed in an existing corridor (grid enhancement). | 2 | Investment on time | Progressed as planned | 2023 | 2023 | 1 | Neuravensbu rg | border area (AT) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 9 | AUT | Neuravensbu Rg | Border Area
35 | 2014 | 2016 | [2014, 2015, 2016] | 1045 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 92 | 1045 | ALEGrO | AC BE Reinforcements Internal reinforcements in AC network in Belgium have started in the context of securing infeed from the 380kV network into the Limburg & Liège area. These reinforcements are also needed to facilitate the integration of ALEGrO into the Belgian grid. The reinforcements consist of - extension of an existing single 380 kV connection between Lixhe and Herderen by adding an additional circuit with high performance conductors (HTLS) - creation of 380kV substation in Lixhe, including a 380/150 transformator - creation of 380kV substation in Genk (André Dumont), including a 380/150 kV transformator | 3 | Investment on time | This investment item is split off from the generic Alegro investment item which up to now included also the internal reinforcements | 2017 | 2017 | 1 | Lixhe | Herderen | 1045 | Internal reinforcements in AC network in BE are needed to integrate Alegro, whilst at the same time contributing to security of supply of Liege and Limburg area by securing infeed from 380kV network The reinforcements consist of - extension of existing single 380 kV connection between Lixhe and Herderen by adding an additional circuit in high temperature low sag conductors (HTLS) - construction of 380kV substation in Lixhe with 380/150 transfo - creation of 380kV substation in Genk (André Dumont) with 380/150 kV trafo | 3 | Investment on time | Progressed as planned. | 2017 | 2017 | 1 | Lixhe | Herderen | 92 | 1045 | ALEGrO | ALEGrO - AC reinforcements in Belgium | Internal reinforcements in AC network in BE are needed to integrate Alegro, whilst at the same time contributing to security of supply of Liege and Limburg area by securing infeed from 380kV network. The reinforcements consist of i) installation of a second 380 kV circuit on the existing 380 kV overhead line Lixhe-Herderen (2017). This second circuit will be realized with high performance conductors (HTLS) ii) construction of a 380 kV substation in Lixhe including two 380/220 kV transformers (2017) and one 380/150 kV transformer (2019) | 4 | Investment on time | Progressed as planned. | 01/01/2017 | 2017 | 1 |  | 0 | Lixhe | Herderen | Overhead Line | AC | 1000 | 380 | 10 | Upgrade |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2017 | 0 | 3 | AUT;BEL | Lixhe | Herderen | 50.7551 | 5.6801 | 50.807 | 5.5742
36 | 2014 | 2015 | [2014, 2015] | 1048 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 92 | 1048 | ALEGrO | Potentially additional AC BE Reinforcements Envisions the installation of a second 380 kV overhead line between Herderen to Lixhe. And the installation of a 2nd 380/150 transformator in Limburg area (probably substation André Dumont). These reinforcements are conditional to the evolution of production in the Limburg-Liège area and to the evolution of the physical (transit) flux towards 2020-2025. | 1 | New Investment | Evolution of generation in the Limburg-Liège must be accounted for in the perimeter of the Alegro project. This conditional project has a commissioning date set to 2020 as indication for further monitoring of the need. | 2020 | 2020 | 1 | Lixhe | Herderen | 1048 | There is a potential project to connect central production at Lixhe substation on top of Alegro (+- 900 MW). Should this scenario happen, then additional internal BE grid reinforcements are needed - second 380 kV overhead line connection between Herderen to Lixhe - installation of a 2nd 380/150 transfo in Limburg area (probably substation André Dumont) | 1 | Investment on time | No decision to date about the potential new production units. This conditional project has a commissioning date set to 2020 to indicate the ~5 year timespan from decision to realization of the investment. | 2020 | 2020 | 1 | Lixhe | Herderen | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 6 | AUT;BEL;ISL | Lixhe | Herderen | 50.7551 | 5.6801 | 50.807 | 5.5742
37 | 2014 | 2015 | [2014, 2015] | 1049 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 26 | 1049 | Austria - Italy | interconnector IT-AT (phase 2) | 1 | New Investment | project progress | 2023 | 2023 | 1 | tbd (IT) | tbd (AT) | 1049 | interconnector IT-AT (phase 2) | 6 | Cancelled | feasibility reasons led to cancel the investment |  |  | 1 | tbd (IT) | tbd (AT) | [10 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 |  |  |  | AUT;ITA
38 | 2014 | 2022 | [2014, 2015, 2016, 2018, 2020, 2022] | 1050 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 24 | 1050 | Belgian North Border | Conditional: Gramme-Van Eyck + Massenhoven-Meerhout-Van Eyck Envisions to double the transport capacity by upgrading the Gramme-Van Eyck axis to high-performance conductors, and by putting a second 380kV circuit on the Massenhoven-Meerhout-Van Eyck axis. The need to upgrade is conditional to the evolution of production in the LImburg-Liège area and to the evolution of the physical (transit)flux towards 2020-2025. This need will be further monitored. | 2 | Investment on time | This investment is a split off from invest item 445a from in TYNDP 2012, and complemented with the Massenhoven-Meerhout-Van Eyck section. This investment is subject to further monitoring towards 2020-2025 given its dependency on production in the area in combination with evolution of the (transit)flux. | 2020 | 2020 | 1 | Gramme (BE) | Massenhoven (BE) | 1050 | Installation of a second circuit on the axis Massenhoven- Meerhout-Van Eyck. Combined with second phase of reinforcement on the axis Gramme-Van Eyck aiming at doubling the capacity over the whole axis by upgrading remaining line sections to high- performance conductors a) 55km double circuit between Gramme-Zutendaal b) 30 km single circuit (Zutendaal - Van Eyck) c) 10 km single circuit (Herderen-Lixhe) | 1 | Investment on time | The need for this project towards 2020-2025 horizon is to be further monitored in accordance with the evolution of the transitflux and the potential of new production units that could be deployed within the area. | 2020 | 2020 | 1 | Gramme | Van Eyck | 252 | 1050 | Internal Belgian Backbone East | Van Eyck - Gramme | Further reinforcement of the 380 kV overhead line Gramme-Van Eyck by upgrading the following line sections to high-performance conductors i) 55km double circuit between Gramme-Zutendaal ii) 30 km single circuit Zutendaal Van Eyck iii) 10 km single circuit Lixhe-Herderen | 1 | Investment on time | The need for this investment towards 2020-2025 horizon is to be further monitored in accordance with the evolution of transitflux/interconnection capacity on the surrounding borders, and with the evolution in the production park i.e. planned nuclear phase out and potential of new production units that could be deployed within the area. | 01/01/2025 | 2025 | 1 |  | 0 | Van Eyck | Gramme | Overhead Line | AC | 1400 | 380 | 90 | Upgrade | 252 | 1050 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | HTLS upgrade VanEyck-Gramme | 1 | Rescheduled |  | 31/12/2029 | 2029 | 1 | ELIA | Van Eyck | Gramme | Overhead Line | AC | 380 | 252 | 1050 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | Van Eyck - Gramme: HTLS upgrade | Upgrade of this double-circuit axis to HTLS conductors. Note that recently installed conductors along this axis anticipated the future HTLS upgrade, they don't have to be further upgraded. | 2 | Investment on time |  | 2029 | 2029 | 1 | ELIA |  | 0 | 0 | Van Eyck | Gramme | ACTransmissionLine | AC | 90 | Upgrade | 252 | 1050 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | Van Eyck - Gramme: HTLS upgrade | Upgrade of this double-circuit axis to HTLS conductors. Note that recently installed conductors along this axis anticipated the future HTLS upgrade, they don't have to be further upgraded. | 2 | Investment on time |  | 12-2029 | 2029 | 1 | Elia |  | 0 | 0 | Van Eyck | Gramme | ACTransmissionLine | AC | 0 | 380 | 90 | Upgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2029 | 9 | 15 | BEL | Van Eyck | Gramme | 51.2108 | 4.4116 | 50.4163 | 4.447
39 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 1051 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 199 | 1051 | Lake Geneva South | Upgrade of the double circuit 225 kV line between Cornier (France) and Riddes and Saint Triphon (Switzerland) to a single circuit 400 kV line between Cornier and Chavalon (Switzerland). In order to take most benefit from this, the existing 400 kV Genissiat substation will be connected in/out to the existing line Cornier-Montagny. | 1 | New Investment | grid studies conducted after TYNDP2012 release allowed to define the investment | 2025 | 2025 | 1 | CORNIER (FR) | CHAVALON (CH) | 1051 | Upgrade of the double circuit 225 kV line between Cornier (France) and Riddes and Saint Triphon (Switzerland) to a single circuit 400 kV line between Cornier and Chavalon (Switzerland). In order to take most benefit from this, the existing 400 kV Genissiat substation will be connected in/out to the existing line Cornier-Montagny. | 1 | Investment on time | In-depth feasibility studies are needed to find the most suitable solution taking into accou socio-environmental conditions. | 2025 | 2025 | 1 | CORNIER (FR) | CHAVALON (CH) | 199 | 1051 | Lake Geneva South | Cornier - Chavalon 400 kV | Upgrade of the double circuit 225 kV line between Cornier (France) and Riddes and Saint Triphon (Switzerland) to a single circuit 400 kV line between Cornier and Chavalon (Switzerland). This investment will complement PST solutions around Lake Geneva. | 1 | Rescheduled | In-depth feasibility studies are needed to find the most suitable solution taking into account socio-environmental conditions. The commissioning date is being reassessed accordingly. | 1/ 1/ 2026 | 2026 | 1 |  | 1 | CORNIER (FR) | CHAVALON (CH) | Overhead Line | AC | 400 | 400 | 65 | Upgrade | 199 | 1051 | Lake Geneva South | Cornier - La Bâtiaz | 1 |  |  | 2035 | 2035 | 1 | RTE,SWISSGRID | Cornier (FR) | La Bâtiaz (CH) | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2035 | 10 | 21 | CHE;FRA | Cornier | La Bâtiaz | 46.6669 | 6.7686 | 46.1032 | 7.0649
40 | 2014 | 2016 | [2014, 2015, 2016] | 1053 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 120 | 1053 | 2nd Offshore-Onshore Corridor | 1 GW connection to inland: phase 1 Preliminary analysis shows the need to reinforce the 380kV network with a second offshore-onshore corridor in order to evacuate up to 4 GW of offshore wind. The solutions under study consist of multiple investment items. This investment item envisions the possibility of a 1 GW DC solution between an offshore hub towards an inland location (substation Doel or further inland could be a possible location). Subject to further studies. The cost estimate does not take into account the construction of an eventual offshore hub. | 1 | New Investment | Additional offshore-onshore corridor needed in order to evacuate full potential of up to 4GW (compared to current target of 2,3 GW) of offshore wind in the Belgian part of the North Sea in visions 3 & 4. | 2030 | 2030 | 1 | Offshore Hub - TBD | Doel - TBD | 1053 | To evacuate up to 3.3 GW wind, thus 1 GW more than currenlty planned, preliminary studies indicated that this corridor could consists of a 1 GW DC connection from an offshore platform or nearby Stevin substation in Zeebrugge towards the Antwerp Area (substation Doel could be a possible location) Subject to further studies. | 1 | Investment on time | Long-term potential of energy transition: additional offshore-onshore corridor needed in order to evacuate up to 4GW of offshore wind in the Belgian part of the North Sea. | 2030 | 2030 | 1 | Offshore OR Stevin - TBD | Doel (BE) - TBD | 120 | 1053 | 2nd Offshore-Onshore Corridor (Belgium) | 1 GW to Antwerp area | To evacuate up to 3.3 GW wind, thus 1 GW more than currenlty planned, preliminary studies indicated that this corridor could consists of a 1 GW DC connection from an offshore platform or nearby Stevin substation in Zeebrugge towards the Antwerp Area (substation Doel could be a possible location). Subject to further studies. | 1 | Investment on time | Long-term potential of energy transition&#58; additional offshore-onshore corridor needed in order to evacuate up to 4GW of offshore wind in the Belgian part of the North Sea. | 1/ 1/ 2025 | 2025 | 1 |  | 0 | Offshore Hub OR Stevin - TBD | Doel (BE) - TBD | Underground Cable | DC | 1000 | 320 | 100 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2025 | -5 | 11 | BEL | Or Stevin - | Doel |  |  | 51.3111 | 4.2643
41 | 2014 | 2014 | [2014] | 1054 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 219 | 1054 | EUROASIA interconnector | New HVDC interconnection between Israel and Cyprus | 2 | New Investment | Project application to TYNDP 2014. | 2018 | 2018 | 1 | Hadera site (ISRAEL) | Vasilikos site (CYPRUS) |  |  | 6 | Cancelled |  |  |  | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2018 | 0 | 4 | CYP;ISR | Hadera Site | Vasilikos Site
42 | 2014 | 2020 | [2014, 2015, 2016, 2018, 2020] | 1062 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 163 | 1062 | BalticCorridor | Internal reinforcement for Baltic Corridor 600 MW | 1 | New Investment | - | 2030 | 2030 | 1 | TEC2 | Salaspils | 1062 | Internal reinforcement for Baltic Corridor 600 MW | 1 | Rescheduled | In the previous TYNDP 2014 the investment was selected under the project Baltic corridor ID 163 and initially it was planed as 330 kV OHL between substations Salaspils RigasCHP2. During the CPS for TYNDP 2016 in the RGBS we explored that whole project B | 2020 | 2020 | 1 | RigaCHP2 | RigaHPP | 62 | 1062 | Estonia-Latvia 3rd IC | RigaCHP2-RigaHPP | Internal reinforcement for 3rd EE-LV interconnectors and significant investment for Baltic Synchronization projetc (ID 170) | 1 | New Investment | -Security of Supply, Capacity increase through Baltic States by 600 MW | 1/ 1/ 2020 | 2020 | 1 |  | 0 | RigaCHP2 | RigaHPP | Underground Cable | AC | 600 | 330 | 10 | New | 62 | 1062 | Estonia-Latvia 3rd IC | Riga CHP2 - Riga HPP | 3 |  |  | 1/ 1/ 2020 | 2020 | 1 |  | Riga CHP2 | Riga HPP | Overhead Line | AC | 330 | 62 | 1062 | Estonia-Latvia 3rd IC | Riga CHP2 - Riga HPP | The internal reinforcement for 3rd EE-LV interconnector and significant investment for Baltic Synchronization project | 4 | Investment on time |  | 2020 | 2020 | 1 | AST ELERING | 4.2 | 0 | 1 | Riga CHP2 (LV) | Riga HPP (LV) | ACTransmissionLine | AC | 15 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2020 | -10 | 6 | EST;LVA | Riga Chp | Riga Hpp
43 | 2014 | 2016 | [2014, 2015, 2016] | 1063 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 163 | 1063 | BalticCorridor | Investment is necessary to strenghtening internal grid in Latvia due to get transmission capacity of 600 MW via Latvia | 1 | New Investment | - | 2030 | 2030 | 1 | TEC1 | TEC2 | 1063 | Investment is necessary to strenghtening internal grid in Latvia due to get transmission capacity of 600 MW via Latvia | 1 | Investment on time | Progressed as planned | 2030 | 2030 | 1 | TEC1 | TEC2 | 170 | 1063 | Baltic synchronization | TEC1-TEC2 | Investment is necessary to strenghtening internal grid in Latvia due to get transmission capacity of 600 MW via Latvia | 1 | Rescheduled | - | 1/ 1/ 2025 | 2025 | 1 |  | 0 | TEC1 | TEC2 | Overhead Line | AC | 600 | 330 | 12 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2025 | -5 | 11 | EST;LVA;LTU;POL | Tec | Tec | 59.9617 | 30.317 | 59.9617 | 30.317
44 | 2014 | 2016 | [2014, 2015, 2016] | 1064 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 163 | 1064 | BalticCorridor | To get 600 MW of capacity via Baltic States additionally. | 1 | New Investment | - | 2030 | 2030 | 1 | Viskali (LV) | Musa (LT) | 1064 | To get 600 MW of capacity via Baltic States additionally. | 1 | Investment on time | Progressed as planned | 2030 | 2030 | 1 | Viskali (LV) | Musa (LT) | 170 | 1064 | Baltic synchronization | Viskali (LV) - Musa (LT) | To increase transmission capacity by 600 MW via Baltic States. | 1 | Rescheduled | Comissioning date changed from 2030 to 2025, to avoid splitting project 170."Baltic synchronisation" in two stages. | 1/ 1/ 2025 | 2025 | 1 |  | 1 | Viskali (LV) | Musa (LT) | Overhead Line | AC | 600 | 330 | 88 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2025 | -5 | 11 | LTU;LVA | Viskali | Musa | 56.6229 | 23.7111 | 54.9365 | 24.9126
45 | 2014 | 2016 | [2014, 2015, 2016] | 1065 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 163 | 1065 | BalticCorridor | To increase transmission capacity by 600 MW via Baltic States | 1 | New Investment | - | 2030 | 2030 | 1 | Aizkraukle (LV) | Panevežys (LT) | 1065 | To increase transmission capacity by 600 MW via Baltic States | 1 | Investment on time | Progressed as planned | 2030 | 2030 | 1 | Aizkraukle (LV) | Panevežys (LT) | 170 | 1065 | Baltic synchronization | Aizkraukle(LV)-Panevėžys(LT) | To increase transmission capacity by 600 MW via Baltic States. | 1 | Rescheduled | Comissioning date changed from 2030 to 2025, to avoid splitting project 170."Baltic synchronisation" in two stages. | 1/ 1/ 2025 | 2025 | 1 |  | 1 | Aizkraukle (LV) | Panevežys (LT) | Overhead Line | AC | 600 | 330 | 127 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2025 | -5 | 11 | LTU;LVA | Aizkraukle | Paneveys | 56.6011 | 25.2543
46 | 2014 | 2015 | [2014, 2015] | 1068 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 213 | 1068 | Santa Llogaia - Bescano | New OHL 400kV AC double circuit Bescano-Santa Llogaia, required to connect the new HVDC interconnection to the existing network and secure the supply in the area of Gerona | 4 | Investment on time | Progress as planned | 2014 | 2014 | 1 | Bescanó | Santa Llogaia | 1068 | New OHL 400kV AC double circuit Bescano-Santa Llogaia, required to connect the new HVDC interconnection to the existing network and secure the supply in the area of Gerona | 5 | Commissioned | Progressed as planned | 2014 | 2014 | 1 | Bescanó | Santa Llogaia | [10 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2014 | 2014 | 0 | 0 | ESP | Bescanó | Santa Llogaia | 41.967 | 2.739 | 42.5767 | 1.0887
47 | 2014 | 2016 | [2014, 2015, 2016] | 1069 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 203 | 1069 | Aragón-Castellón | Mezquita-Morella 400 kV line | 3 | Delayed | Delayed because National law RDL 13/2012 has frozen the permitting process until publication of the next NDP | 2017 | 2017 | 1 | Mezquita | Morella | 1069 | Mezquita-Morella 400 kV line | 3 | Investment on time | Final phase of permitting. Construction will start soon. | 2017 | 2017 | 1 | Mezquita | Morella | 203 | 1069 | Aragón-Castellón | Mezquita-Morella | Mezquita-Morella 400 kV line | 3 | Investment on time | Final phase of permitting. Construction will start soon. | 1/ 1/ 2017 | 2017 | 1 |  | 0 | Mezquita | Morella | Overhead Line | AC | 1420 | 400 | 68 | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2017 | 0 | 3 | ESP | Mezquita | Morella |  |  | 40.6188 | -0.099803
48 | 2014 | 2016 | [2014, 2015, 2016] | 1070 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 203 | 1070 | Aragón-Castellón | OHL 400kV AC Mudejar-Morella | 3 | Delayed | Delayed because National law RDL 13/2012 has frozen the permitting process until publication of the next NDP | 2017 | 2017 | 1 | Mudejar | Morella | 1070 | OHL 400kV AC Mudejar-Morella | 4 | Investment on time | The investment progressed as previously planned | 2017 | 2017 | 1 | Mudejar | Morella | 203 | 1070 | Aragón-Castellón | Mudejar-Morella | OHL 400kV AC Mudejar-Morella | 5 | Commissioned |  |  |  | 1 |  | 0 | Mudejar | Morella | Overhead Line | AC | 1420 | 400 | 34 | New | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 |  |  |  | ESP | Mudejar | Morella | 39.9111 | -0.57183 | 40.6188 | -0.099803
49 | 2014 | 2015 | [2014, 2015] | 1071 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 210 | 1071 | E15 | Würmlach - Somplago | 3 | New Investment | Project application to TYNDP 2014. | 2017 | 2017 | 1 | Würmlach (AT) | Somplago (IT) | 1071 | Würmlach - Somplago | 3 | Delayed | Progressed as planned | 2018 | 2018 | 1 | Würmlach (AT) | Somplago (IT) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2018 | 1 | 4 | AUT;ITA | Würmlach | Somplago | 46.6575 | 13.0154 | 46.3485 | 13.0679
50 | 2014 | 2016 | [2014, 2015, 2016] | 1075 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 146 | 1075 | CSE8 Transbalkan Corridor | New internal 400 kV OHL will connect existing SS Kragujevac with SS Kraljevo which is planned for upgrade to 400 kV voltage level. This investment will enhance the possibility of energy transits in direction north-east to south-west and east to west. | 3 | Delayed | New axis for transits from East to the West, typically from Bulgaria to Bosnia and Montenegro, and further to the west. | 2018 | 2018 | 1 | Kragujevac | Kraljevo | 1075 | New internal 400 kV OHL will connect existing SS Kragujevac with SS Kraljevo which is planned for upgrade to 400 kV voltage level. This investment will enhance the possibility of energy transits in direction north-east to south-west and east to west. | 3 | Investment on time | New axis for transits from East to the West, typically from Bulgaria to Bosnia and Montenegro, and further to the west. | 2018 | 2018 | 1 | Kragujevac | Kraljevo | 146 | 1075 | CSE8 Transbalkan Corridor | 400 kV OHL Kragujevac-Kraljevo | New internal 400 kV OHL will connect existing SS Kragujevac with SS Kraljevo which is planned for upgrade to 400 kV voltage level. This investment will enhance the possibility of energy transits in direction north-east to south-west and east to west. | 4 | Delayed | Due to insufficient financial support from EU this project is postponed. | 2019 | 2019 | 1 |  | 0 | Kragujevac | Kraljevo | Overhead Line | AC | 1095 | 400 | 55 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2019 | 1 | 5 | SRB;MNE;BIH | Kragujevac | Kraljevo | 43.9072 | 19.262 | 44.1021 | 18.9788
51 | 2014 | 2016 | [2014, 2015, 2016] | 1076 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 146 | 1076 | CSE8 Transbalkan Corridor | Upgrade of the existing 220/110kV substation Kraljevo 3 by constructing the 400 kV level. | 3 | Delayed | This upgrade is required for the construction of new 400 kV OHL Kragujevac - Kraljevo which will increase local security of supply and power transfer from Eastern to Western part of region. | 2017 | 2017 | 1 | Kraljevo |  | 1076 | Upgrade of the existing 220/110kV substation Kraljevo 3 by constructing the 400 kV level. | 3 | Delayed | “Realization of this project is delayed for one year because of problems with obtaining necessary permits on local level. Now, the problem is resolved and we are in the phase of closing financial structure for its realization.” | 2018 | 2018 | 1 | Kraljevo |  | 146 | 1076 | CSE8 Transbalkan Corridor | Upgrade of SS Kraljevo | Upgrade of the existing 220/110kV substation Kraljevo 3 by constructing the 400 kV level. | 4 | Delayed | Due to insufficient financial support from EU this project is postponed. | 2019 | 2019 | 1 |  | 0 | Kraljevo |  | Substation |  | 1095 | 400 |  | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2019 | 2 | 5 | SRB;MNE;BIH | Kraljevo |  | 44.1021 | 18.9788
52 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 1082 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 214 | 1082 | Interco Iceland-UK | Interco Iceland-UK | 1 | New Investment |  | 2030 | 2030 | 1 | tbd | tbd | 1082 | Interco Iceland-UK | 1 | Investment on time | Increased RES integration and market coupling | 2030 | 2030 | 1 | tbd | tbd | 214 | 1082 | Interco Iceland-UK | Interco Iceland-UK | Interco Iceland-UK | 1 | New Investment | Increased RES integration and market coupling<br><br> | 1/ 1/ 2030 | 2030 | 1 |  | 0 | tbd | tbd | Subsea Cable | DC | 0 | 500 | 1000 | New | 214 | 1082 | Interco Iceland-UK | Interco Iceland-UK | 1 |  |  | 2030 | 2030 | 1 | LANDSNET;NGIHL | tbd | tbd | Subsea Cable | DC | 500 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | GBR;ISL
53 | 2014 | 2015 | [2014, 2015] | 1099 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 90 | 1099 | Swiss Roof | Rüthi - Grynau 2 x 380 kV Rüthi - Bonaduz 1 x 380 kV | 2 | Investment on time | Investment 136 now comprises the cross-border part of former investment 136, and investment 1099 is the Swiss part of former investment 136. | 2022 | 2022 | 1 | Rüthi | Bonaduz - Grynau | 1099 | Rüthi - Grynau 2 x 380 kV Rüthi - Bonaduz 1 x 380 kV | 1 | Investment on time | Progressed as planned | 2022 | 2022 | 1 | Rüthi | Bonaduz - Grynau | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2022 | 0 | 8 | CHE | Rüthi | Bonaduz - Grynau | 47.2558 | 9.7003
54 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 1107 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 225 | 1107 | ALEGRO 2 | This investment item envisions the possibility of a second 1 GW interconnection between Belgium and Germany. Subject to further studies. | 1 | New Investment | Preliminary studies on high RES scenario's have indicated potential for further regional welfare & RES integration increase by further increasing the interconnection capacity between Belgium & Germany towards time horizon 2025-2030. | 2030 | 2030 | 1 | BE (TBD) | DE (TBD) | 1107 | This investment item envisions the possibility of a second 1 GW HVDC interconnection between Belgium and Germany. Subject to further studies. | 1 | Investment on time | Preliminary studies on high RES scenarios have indicated potential for further regional welfare & RES integration increase by further increasing the interconnection capacity between Belgium & Germany. | 2030 | 2030 | 1 | BE (TBD) | DE (TBD) | 225 | 1107 | 2nd interconnector Belgium - Germany | 2nd interconnecter between Belgium and Germany | This investment item envisions the possibility of a second 1 GW HVDC interconnection between Belgium and Germany. Subject to further studies. | 2 | Rescheduled | The project has been rescheduled with an indicative date of 2025 related to its potential to security-of-supply (adequacy) contribution within a context of planned nuclear phase out. The evaluation of this potential as well as interaction with reinforcements on neighboring borders are subject of further studies. | 01/01/2025 | 2025 | 1 |  | 1 | to be defined (BE) | to be defined (DE) | Underground Cable | DC | 1000 | 320 | 100 | New | 225 | 1107 | 2nd interconnector Belgium - Germany | 2nd interconnecter between Belgium and Germany | 1 | Investment on time |  | 2028 | 2028 | 1 | AMPRION;ELIA | to be defined (BE) | to be defined (DE) | Underground Cable | DC | 0 | 225 | 1107 | 2nd interconnector Belgium - Germany | 2nd interconnecter between Belgium and Germany | This investment item envisions the possibility of a second 1 GW HVDC interconnection between Belgium and Germany. Subject to further studies. | 1 | Delayed | The recently adopted Clean Energy Package will have a significant impact on the future market design. These developments are likely to have a major impact on the project of a second interconnector between Belgium and Germany. However, as a lot of these regulatory changes are still about to enter into force, the exact impact on this project cannot be established today. | 2035 | 2035 | 1 | AMPRION ELIA |  | 1 | 1 | Gramme (BE) | Dahlem (DE) | DCTransmissionLine | DC | 150 | New | 225 | 1107 | 2nd interconnector Belgium - Germany | 2nd interconnecter between Belgium and Germany | This investment item envisions the possibility of a second 1 GW HVDC interconnection between Belgium and Germany. Subject to further studies. | 1 | Rescheduled |  | 12-2038 | 2038 | 1 | Amprion, Elia |  | 1 | 1 | Gramme (BE) | Dahlem (DE) | DCTransmissionLine | DC | 1000 | 660 | 150 | New | 225 | 1107 | 2nd interconnector Belgium - Germany | 2nd interconnecter between Belgium and Germany | This investment item envisions the possibility of a second 2 GW HVDC interconnection between Belgium and Germany. Subject to further studies. | 1 | Investment on time |  | 12-2037 | 2037 | 1 | Amprion, Elia |  | 1 | 1 | Gramme (BE) | Dahlem (DE) | DCTransmissionLine | DC | 2000 | 525 | 110 | New | 225 | 1107 | 2nd interconnector Belgium - Germany | 2nd interconnecter between Belgium and Germany | This investment item envisions the possibility of a second HVDC interconnection between Belgium and Germany. The capacity of the 2nd interconnector is foreseen in 2 GW but is still subject to further studies. | 1 |  | 12-2038 | 2038 | 1 | Amprion, Elia | 1 | XX | XX | New | 2030 | 2038 | 8 | 24 | BEL;DEU | Gramme | Dahlem | 50.4163 | 4.447 | 52.4574 | 13.2811
55 | 2014 | 2015 | [2014, 2015] | 1111 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 182 | 1111 | BRITIB (GB-FR-ES) | Interconnection project between Indian Queens (Great Britain), Cordemais (France) and Gatica (Spain) in a multiterminal HVDC configuration with 3 sections of 1000 MW each, and a submarine route from Spain to Great Britain along the French coast. | 1 | New Investment | Project application to TYNDP 2014. | 2018 | 2018 | 1 | Gatica | Indian Queens | 1111 | Interconnection project between Indian Queens (Great Britain), Cordemais (France) and Gatica (Spain) in a multiterminal HVDC configuration with 3 sections of 1000 MW each, and a submarine route from Spain to Great Britain along the french coast. | 1 | Delayed | Progressed as planned | 2020 | 2020 | 1 | Gatica | Indian Queens | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2020 | 2 | 6 | ESP;FRA;GBR | Gatica | Indian Queens |  |  | 50.3933 | -4.9316
56 | 2014 | 2015 | [2014, 2015] | 1112 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 138 | 1112 | Black Sea Corridor | Construction of a new 400/110kV power line breaking up the existing 400kV Saedinenie OHL and connecting 400/110kV Svoboda substation. | 2 | Delayed | Delayed due to lack of funding | 2019 | 2019 | 1 | Svoboda (BG) | splitting point | 1112 | Construction of a new 400/110kV power line breaking up the existing 400kV Saedinenie OHL and connecting 400/110kV Svoboda substation. | 6 | Cancelled | Cancelled due to lack of funding |  |  | 1 | Svoboda (BG) | splitting point | [10 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 |  |  |  | BGR | Svoboda | Splitting Point | 43.7493 | 27.8178
57 | 2014 | 2014 | [2014] | 1113 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 228 | 1113 | Marex | 1500 MW HVDC VSC cable | 2 | New Investment | Project application for TYNDP 2014. | 2018 | 2018 | 1 | Glinsk 400kV | Connah's Quay 400kV |  |  | 6 | Cancelled |  |  |  | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2018 | 0 | 4 | GBR;IRL | Glinsk | Connahs Quay | 53.6536 | -8.4374 | 53.2328 | -3.0832
58 | 2016 | 2016 | [2016] | 1117 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 170 | 1117 | Baltic synchronization | B2B at Narva | B2B construction with 500 MW capacity on existing Estonia-Russia 330 kV AC lines on Estonian side, in Narva area. | 2 | New Investment | The investment is related to Baltic synchronisation cluster. | 1/ 1/ 2024 | 2024 | 1 |  | 0 | Eesti |  | Substation |  | 500 | 330 |  | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2024 | 2024 | 0 | 8 | EST;LVA;LTU;POL | Eesti |  | 59.434 | 24.752
59 | 2016 | 2022 | [2016, 2018, 2020, 2022] | 1118 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 170 | 1118 | Baltic synchronization | SVC and control upgrades | SVC implementation in weak grid parts due to decrease of SC capacity; upgrade of PSS in power stations. AGC impementation and commissioning in SCADA systems and power plants; WAMS and WAMPAC systems | 2 | New Investment | New investment | 1/ 1/ 2024 | 2024 | 1 |  | 0 | Eesti 330 kV |  | Compensation |  | 0 | 330 |  | New | 170 | 1118 | Baltics synchro with CE | SVC and control upgrades | 2 | Investment on time |  | 1/ 1/ 2024 | 2024 | 1 |  | Eesti 330 kV | - | Compensation | AC | 330 | 170 | 1118 | Baltic States Synchronization with Continental Europe | Further infrastructure aspects related to the implementation of the synchronisation of the Baltic States’ system with the continental European network | Further infrastructure aspects ‘not-known-today’ related to the implementation of the synchronisation of the Baltic States’ system with the continental European Network arising from ongoing synchronisation studies | 1 | New Investment |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | - | - |  | AC | 0 | New | 170 | 1118 | Baltic States Synchronization with Continental Europe | Further infrastructure aspects related to the implementation of the synchronisation of the Baltic States’ system with the continental European network | Further infrastructure aspects ‘not-known-today’ related to the implementation of the synchronisation of the Baltic States’ system with the continental European Network arising from ongoing synchronisation studies. | 1 | Investment on time |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | - | - |  | AC | 0 | 330 | 0 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2024 | 2025 | 1 | 9 | EST;LTU;LVA;POL | Eesti |  | 59.434 | 24.752
60 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1205 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 259 | 1205 | HU-RO | HU-RO | ​400kV OHL between Hungary and Romania in order to reach the market based target capacity resulted from the Common Planning Studies based on V4; in Romania a new transformer 400/220kV in Rosiori substation is necessary as internal investment associated to this project | 1 | New Investment |  | >2030 | 2030 | 1 |  | 1 | Jozsa | Oradea | Overhead Line | AC |  | 400 |  | New | 259 | 1205 | HU-RO | HU-RO | 1 | Investment on time |  | >2030 | 2030 | 1 | MAVIR,Transelectrica | Józsa | Oradea | Overhead Line | AC | 400 | 259 | 1205 | HU-RO | HU-RO | New 120 km single circuit 400 kV OHL between Hungary and Romania (90 km on Hungarian and 30 km on Romanian side) in order to reach the market based target capacity resulted from the TYNDP 2016 Common Planning Studies based in V4 and TYNDP 2018 IoSN in DG2040 and GCA2040. Internal investments in Romania associated to the project are also included. | 1 | Investment on time |  | 2030 | 2030 | 1 | MAVIR TRANSELECTRICA |  | 1 | 1 | Józsa | Oradea | ACTransmissionLine | AC | 120 | MostlyNew | 259 | 1205 | HU-RO | HU-RO | New 120 km single circuit 400 kV OHL between Hungary and Romania (90 km on Hungarian and 30 km on Romanian side). Internal investments in Romania associated to the project are also included. | 2 | Investment on time |  | 12-2030 | 2030 | 1 | MAVIR, Transelectrica |  | 1 | 1 | Józsa | Oradea | ACTransmissionLine | AC | 0 | 400 | 120 | MostlyNew | 259 | 1205 | HU-RO | New 400 kV OHL Debrecen Dél (HU) - Oradea Sud (RO) | New 90 km single circuit 400 kV OHL between Hungary and Romania (60 km on Hungarian and 30 km on Romanian side). Internal investments in Romania associated to the project are also included. | 2 | Investment on time |  | 12-2030 | 2030 | 1 | MAVIR, Transelectrica | 2.5.1, 2.5.2, 2.5.3, 2.5.4, 2.5.5 | 1 | 1 | Debrecen Dél | Oradea Sud | ACTransmissionLine | AC | 0 | 400 | 90 | MostlyNew | 259 | 1205 | HU-RO | New 400 kV OHL Debrecen Dél (HU) - Oradea Sud (RO) | New 90 km single circuit 400 kV OHL between Hungary and Romania (60 km on Hungarian and 30 km on Romanian side). Internal investments in Romania associated to the project are also included. | 2 |  | 12-2030 | 2030 | 1 | MAVIR, Transelectrica | 1 | XX | XX | Mostly new | 2030 | 2030 | 0 | 14 | HUN;ROU | Debrecen Dél | Oradea Sud | 47.5012 | 21.5473 | 47.0518 | 21.918
61 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1206 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 276 | 1206 | FR-ES project -Navarra-Landes | HVDC Pamplona area -Cantegrit | HVDC Pamplona area (Spain) -Cantegrit (France)​ | 2 | New Investment |  | 01/01/2025 | 2025 | 1 |  | 1 | Pamplona area | Cantegrit | Underground Cable | DC | 1500 | 320 | 180 | New | 276 | 1206 | FR-ES project -Navarra-Landes | HVDC Pamplona area -Cantegrit | 2 | Rescheduled |  | 01/12/2026 | 2026 | 1 | REE;RTE | Pamplona area | Cantegrit | Underground Cable | DC | 320 | 276 | 1206 | FR-ES project -Navarra-Landes | HVDC Pamplona area - Cantegrit | HVDC Pamplona area(Spain) -Cantegrit (France) | 2 | Rescheduled |  | 2029 | 2029 | 1 | Red Eléctrica de España RTE | 2.27.2 | 1 | 1 | Pamplona area | Cantegrit | DCTransmissionLine | DC | 225 | New | 276 | 1206 | FR-ES project -Navarra-Landes | HVDC Pamplona area - Cantegrit | HVDC Pamplona area(Spain) -Cantegrit (France) | 2 | Investment on time |  | 12-2030 | 2030 | 1 | Red Eléctrica, Rte | 2.27.2 | 1 | 1 | Pamplona area | Cantegrit | DCTransmissionLine | DC | 2000 | 320 | 225 | New | 276 | 1206 | FR-ES project -Navarra-Landes | HVDC Pamplona area - Cantegrit | HVDC Pamplona area(Spain) -Cantegrit (France) | 1 | Investment on time |  | 12-2037 | 2037 | 1 | Red Eléctrica, Rte | 1.7.1 | 1 | 1 | Pamplona area | Cantegrit | DCTransmissionLine | DC | 2000 | 320 | 225 | New | 276 | 1206 | FR-ES project -Navarra-Landes | HVDC Pamplona area - Cantegrit | HVDC Pamplona area(Spain) -Cantegrit (France) | 1 |  | 12-2037 | 2037 | 1 | Red Eléctrica, Rte | 1 | XX | XX | New | 2025 | 2037 | 12 | 21 | ESP;FRA | Pamplona Area | Cantegrit |  |  | 44.2482 | -0.80087
62 | 2016 | 2024 | [2016, 2018, 2020, 2022, 2024] | 1207 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 276 | 1207 | FR-ES project -Navarra-Landes | Upgrade Cantegrit-Saucats | Upgrade of 2* 400 kV lines Cantegrit-Saucats​ | 2 | New Investment |  | 01/01/2025 | 2025 | 1 |  | 0 | Cantegrit | Saucats | Overhead Line | AC |  | 400 | 70 | Upgrade | 276 | 1207 | FR-ES project -Navarra-Landes | Upgrade Cantegrit-Saucats | 2 | Rescheduled |  | 2026 | 2026 | 1 |  | Cantegrit | Saucats | Overhead Line | AC | 400 | 276 | 1207 | FR-ES project -Navarra-Landes | Upgrade Cantegrit-Saucats | Upgrade of 2* 400 kV lines Cantegrit-Saucats | 2 | Rescheduled |  | 2029 | 2029 | 1 | Red Eléctrica de España RTE | 2.27.2 | 0 | 1 | Cantegrit | Saucats | ACTransmissionLine | AC | 70 | New | 276 | 1207 | FR-ES project -Navarra-Landes | Upgrade Cantegrit-Saucats | Upgrade of 2* 400 kV lines Cantegrit-Saucats | 2 | Rescheduled |  | 12-2030 | 2030 | 1 | Red Eléctrica, Rte | 2.27.2 | 0 | 1 | Cantegrit | Saucats | ACTransmissionLine | AC | 0 | 400 | 70 | New | 276 | 1207 | FR-ES project -Navarra-Landes | Upgrade Cantegrit-Saucats | Upgrade of 2* 400 kV lines Cantegrit-Saucats | 1 | Rescheduled |  | 00-0000 | 2036 | 1 | Red Eléctrica, Rte | 1.7.1 | 0 | 1 | Cantegrit | Saucats | ACTransmissionLine | AC | 0 | 400 | 70 | New | [9 empty] | 0 | [5 empty] | 2025 | 2036 | 11 | 20 | ESP;FRA | Cantegrit | Saucats | 44.2482 | -0.80087 | 44.6528 | -0.59589
63 | 2016 | 2022 | [2016, 2018, 2020, 2022] | 1208 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 276 | 1208 | FR-ES project -Navarra-Landes | Upgrade Cantegrit-Marsillon | Upgrade of existing 2*225kV line Cantegrit-Marsillon to 1* 400kV​ | 2 | New Investment |  | 01/01/2025 | 2025 | 1 |  | 0 | Cantegrit | Marsillon | Overhead Line | AC |  | 400 | 80 | Upgrade | 276 | 1208 | FR-ES project -Navarra-Landes | Upgrade Cantegrit-Marsillon | 2 | Rescheduled |  | 2026 | 2026 | 1 |  | Cantegrit | Marsillon | Overhead Line | AC | 400 | 276 | 1208 | FR-ES project -Navarra-Landes | Upgrade Cantegrit-Marsillon | Upgrade of existing 2*225kV line Cantegrit-Marsillon to 1* 400kV | 2 | Rescheduled |  | 2029 | 2029 | 1 | Red Eléctrica de España RTE | 2.27.2 | 0 | 1 | Cantegrit | Marsillon | ACTransmissionLine | AC | 80 | New | 276 | 1208 | FR-ES project -Navarra-Landes | Upgrade Cantegrit-Marsillon | Upgrade of existing 2*225kV line Cantegrit-Marsillon to 1* 400kV | 2 | Rescheduled |  | 12-2030 | 2030 | 1 | Red Eléctrica, Rte | 2.27.2 | 0 | 1 | Cantegrit | Marsillon | ACTransmissionLine | AC | 0 | 400 | 80 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2030 | 5 | 14 | ESP;FRA | Cantegrit | Marsillon | 44.2482 | -0.80087 | 43.3908 | -0.59997
64 | 2016 | 2016 | [2016] | 1209 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 273 | 1209 | Closing of 400 kV ring around Belgrade region | New SS 400/110 kV Belgrade West | "​New SS 400/110 Belgrade West will increase realiability of supplying of consumpution of Belgrade city. It is precondition for closing 400 kVloop around Belgrade region." | 1 | New Investment |  | 01/01/2035 | 2035 | 1 |  | 0 | SS 400/110 kV Belgrade |  | Substation |  |  | 400 |  | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 19 | SRB | Belgrade |  | 47.6689 | 19.0757
65 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 121 | Cancelled | 121 | Construction of different new 400kV OHL sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 250km. | 3 | 2014 | 2014 | 1 | Bickigen (CH) | Romanel (CH) | 91 | 91. 121 | Construction of different new 400kV OHL sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 250km. | 3 | Delays due to authorization process. | 2015 | 2015 | 1 | Bickigen (CH) | Romanel (CH) | 91. 121 | 91. 121 | Construction of different new 400kV OHL sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 250km. | 3 | Long permitting procedure (comprising several phases) | 2020 | 2020 | 1 | Bickigen (CH) | Romanel (CH) | 91 | 121 | Swiss Ellipse | Construction of different new 400kV OHL sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 250km. | 3 | Delayed | long permitting procedure (comprising several phases) | 2020 | 2020 | 1 | Bickigen (CH) | Romanel (CH) | 121 | Construction of different new 400kV OHL sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 250km. | 3 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Bickigen (CH) | Romanel (CH) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2014 | 2020 | 6 | 10 | CHE | Bickigen | Romanel | 47.0908 | 7.649 | 46.5564 | 6.5101
66 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1210 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 276 | 1210 | FR-ES project -Navarra-Landes | New substation Pamplona area | New substation Pamplona area 400 kV and connection to the 400 kV line Ichaso-Castejón/Muruarte​ | 2 | New Investment |  | 01/01/2025 | 2025 | 1 |  | 0 | Pamplona area |  | Substation |  |  | 400 |  | New | 276 | 1210 | FR-ES project -Navarra-Landes | New substation Pamplona area | 2 | Rescheduled |  | 01/01/2026 | 2026 | 1 |  | Pamplona area | Pamplona area | Substation | AC | 400 | 276 | 1210 | FR-ES project -Navarra-Landes | New substation Pamplona area | New substation Pamplona area 400 kV and connection to the 400 kV line Ichaso-Castejón/Muruarte? | 2 | Rescheduled |  | 2029 | 2029 | 1 | Red Eléctrica de España RTE | 2.27.2 | 0 | 1 | Pamplona area | Pamplona area | OnshoreSubstation | AC | 0 | New | 276 | 1210 | FR-ES project -Navarra-Landes | New substation Pamplona area | New substation Pamplona area 400 kV and connection to the 400 kV line Ichaso-Castejón/Muruarte? | 2 | Investment on time |  | 12-2030 | 2030 | 1 | Red Eléctrica, Rte | 2.27.2 | 0 | 1 | Pamplona area | Pamplona area | OnshoreSubstation | AC | 0 | 400 | 0 | New | 276 | 1210 | FR-ES project -Navarra-Landes | New substation Pamplona area | New substation Pamplona area 400 kV and connection to the 400 kV line Ichaso-Castejón/Muruarte? | 2 | Investment on time |  | 12-2030 | 2030 | 1 | Red Eléctrica, Rte | 1.7.1 | 0 | 1 | Pamplona area | Pamplona area | OnshoreSubstation | AC | 0 | 400 | 0 | New | 276 | 1210 | FR-ES project -Navarra-Landes | New substation Pamplona area | New substation Pamplona area 400 kV and connection to the 400 kV line Ichaso-Castejón/Muruarte? | 2 |  | 12-2035 | 2035 | 1 | Red Eléctrica, Rte | 1 | XX | XX | New | 2025 | 2035 | 10 | 19 | ESP;FRA | Pamplona Area | Pamplona Area
67 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1211 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 270 | 1211 | FR-ES project -Aragón-Atlantic Pyrenees | Aragón region -Marsillón | New axis Aragón region -Marsillon (AC or DC)​ | 2 | New Investment |  | 01/01/2025 | 2025 | 1 |  | 1 | Aragón region | Marsillon | Underground Cable | DC | 1500 | 320 |  | New | 270 | 1211 | FR-ES project -Aragón-Atlantic Pyrenees | HVDC Aragon region -Marsillon | 2 | Rescheduled |  | 01/01/2026 | 2026 | 1 | REE;RTE | Aragon region | Marsillon | Underground Cable | DC | 320 | 270 | 1211 | FR-ES project -Aragón-Atlantic Pyrenees | HVDC Aragon region -Marsillon | New axis Aragon region -Marsillon | 2 | Rescheduled |  | 2030 | 2030 | 1 | Red Eléctrica de España RTE | 2.27.1 | 1 | 1 | Aragon region | Marsillon | DCTransmissionLine | DC | 230 | New | 270 | 1211 | FR-ES project -Aragón-Atlantic Pyrenees | HVDC Aragon region -Marsillon | New axis Aragon region -Marsillon | 2 | Investment on time |  | 09-2030 | 2030 | 1 | Red Eléctrica, Rte | 2.27.1 | 1 | 1 | Aragon region | Marsillon | DCTransmissionLine | DC | 2000 | 320 | 120 | New | 270 | 1211 | FR-ES project -Aragón-Atlantic Pyrenees | HVDC Aragon region -Marsillon | New axis Aragon region -Marsillon | 1 | Investment on time |  | 12-2041 | 2041 | 1 | Red Eléctrica, Rte | 1.7.2 | 1 | 1 | Aragon region | Marsillon | DCTransmissionLine | DC | 2000 | 320 | 120 | New | 270 | 1211 | FR-ES project -Aragón-Atlantic Pyrenees | HVDC Aragon region -Marsillon | New axis Aragon region -Marsillon | 1 |  | 12-2041 | 2041 | 1 | Red Eléctrica, Rte | 1 | XX | XX | New | 2025 | 2041 | 16 | 25 | ESP;FRA | Aragon Region | Marsillon |  |  | 43.3908 | -0.59997
68 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1212 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 270 | 1212 | FR-ES project -Aragón-Atlantic Pyrenees | New axis Ejea-Aragón region 400 kV |  | 2 | New Investment |  | 01/01/2025 | 2025 | 1 |  | 0 | Ejea de los Caballeros | Aragón region | Overhead Line |  |  | 400 | 110 |  | 270 | 1212 | FR-ES project -Aragón-Atlantic Pyrenees | New axis Ejea-Aragon region 400 kV | 2 | Rescheduled |  | 01/01/2026 | 2026 | 1 |  | Ejea de los Caballeros | Aragon region | Overhead Line | AC | 400 | 270 | 1212 | FR-ES project -Aragón-Atlantic Pyrenees | New axis Ejea-Aragon region 400 kV | New AC line (double circuit 400kV) between Ejea and Aragon region where the converter station is located | 2 | Rescheduled |  | 2030 | 2030 | 1 | Red Eléctrica de España RTE | 2.27.1 | 0 | 1 | Ejea de los Caballeros | Aragon region | ACTransmissionLine | AC | 110 | New | 270 | 1212 | FR-ES project -Aragón-Atlantic Pyrenees | New axis Ejea-Aragon region 400 kV | New AC line (double circuit 400kV) between Ejea and Aragon region where the converter station is located | 2 | Investment on time |  | 09-2030 | 2030 | 1 | Red Eléctrica, Rte | 2.27.1 | 0 | 1 | Ejea de los Caballeros | Aragon region | ACTransmissionLine | AC | 0 | 400 | 110 | New | 270 | 1212 | FR-ES project -Aragón-Atlantic Pyrenees | New axis Ejea-Aragon region 400 kV | New AC line (double circuit 400kV) between Ejea and Aragon region where the converter station is located | 2 | Investment on time |  | 09-2030 | 2030 | 1 | Red Eléctrica, Rte | 1.7.2 | 0 | 1 | Ejea de los Caballeros | Aragon region | ACTransmissionLine | AC | 0 | 400 | 110 | New | 270 | 1212 | FR-ES project -Aragón-Atlantic Pyrenees | New axis Ejea-Aragon region 400 kV | New AC line (double circuit 400kV) between Ejea and Aragon region where the converter station is located | 2 |  | 09-2035 | 2035 | 1 | Red Eléctrica, Rte | 1 | XX | XX | New | 2025 | 2035 | 10 | 19 | ESP;FRA | Ejea De Los Caballeros | Aragon Region | 42.1333 | -1.1366
69 | 2016 | 2024 | [2016, 2018, 2020, 2022, 2024] | 1214 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 270 | 1214 | FR-ES project -Aragón-Atlantic Pyrenees | Ejea de los Caballeros subestation | new 400kV Ejea de los Caballeros subestation and connection to the lines La Serna-Magallón and Magallón Peñalba​ | 2 | New Investment |  | 01/01/2025 | 2025 | 1 |  | 0 | Ejea de los Caballeros |  | Substation |  |  |  | 6 | New | 270 | 1214 | FR-ES project -Aragón-Atlantic Pyrenees | Ejea de los Caballeros subestation | 2 | Rescheduled |  | 01/01/2025 | 2025 | 1 |  | Ejea de los Caballeros | Ejea de los Caballeros | Substation | AC | 400 | 270 | 1214 | FR-ES project -Aragón-Atlantic Pyrenees | Ejea de los Caballeros subestation | New 400kV Ejea de los Caballeros subestation and connection to the lines La Serna-Magallon and Magallon Peñalba | 2 | Rescheduled |  | 2030 | 2030 | 1 | Red Eléctrica de España RTE | 2.27.1 | 0 | 1 | Ejea de los Caballeros | Ejea de los Caballeros | OnshoreSubstation | AC | 0 | New | 270 | 1214 | FR-ES project -Aragón-Atlantic Pyrenees | Ejea de los Caballeros subestation | New 400kV Ejea de los Caballeros subestation and connection to the lines La Serna-Magallon and Magallon Peñalba | 2 | Investment on time |  | 09-2030 | 2030 | 1 | Red Eléctrica, Rte | 2.27.1 | 0 | 1 | Ejea de los Caballeros | Ejea de los Caballeros | OnshoreSubstation | AC | 0 | 400 | 0 | New | 270 | 1214 | FR-ES project -Aragón-Atlantic Pyrenees | Ejea de los Caballeros subestation | New 400kV Ejea de los Caballeros subestation and connection to the lines La Serna-Magallon and Magallon Peñalba | 2 | Investment on time |  | 09-2030 | 2030 | 1 | Red Eléctrica, Rte | 1.7.2 | 0 | 1 | Ejea de los Caballeros | Ejea de los Caballeros | OnshoreSubstation | AC | 0 | 400 | 0 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2025 | 2030 | 5 | 14 | ESP;FRA | Ejea De Los Caballeros | Ejea De Los Caballeros | 42.1333 | -1.1366 | 42.1333 | -1.1366
70 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1215 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 270 | 1215 | FR-ES project -Aragón-Atlantic Pyrenees | Aragón region subestation | New 400 kV Aragón region subestation and connection to existing network and future cross border project​ | 2 | New Investment |  | 01/01/2025 | 2025 | 1 |  | 0 | Aragón region |  | Substation |  |  | 400 | 5 | New | 270 | 1215 | FR-ES project -Aragón-Atlantic Pyrenees | Aragon region subestation | 2 | Rescheduled |  | 01/01/2025 | 2025 | 1 |  | Aragon region | Aragon region | Substation | AC | 400 | 270 | 1215 | FR-ES project -Aragón-Atlantic Pyrenees | Aragon region subestation | New 400 kV Aragon region subestation and connection to existing network and future cross border project | 2 | Rescheduled |  | 2030 | 2030 | 1 | Red Eléctrica de España RTE | 2.27.1 | 0 | 1 | Aragon region | Aragon region | OnshoreSubstation | AC | 0 | New | 270 | 1215 | FR-ES project -Aragón-Atlantic Pyrenees | Aragon region subestation | New 400 kV Aragon region subestation and connection to existing network and future cross border project | 2 | Investment on time |  | 09-2030 | 2030 | 1 | Red Eléctrica, Rte | 2.27.1 | 0 | 1 | Aragon region | Aragon region | OnshoreSubstation | AC | 0 | 400 | 0 | New | 270 | 1215 | FR-ES project -Aragón-Atlantic Pyrenees | Aragon region subestation | New 400 kV Aragon region subestation and connection to existing network and future cross border project | 2 | Investment on time |  | 09-2030 | 2030 | 1 | Red Eléctrica, Rte | 1.7.2 | 0 | 1 | Aragon region | Aragon region | OnshoreSubstation | AC | 0 | 400 | 0 | New | 270 | 1215 | FR-ES project -Aragón-Atlantic Pyrenees | Aragon region subestation | New 400 kV Aragon region subestation and connection to existing network and future cross border project | 2 |  | 09-2035 | 2035 | 1 | Red Eléctrica, Rte | 1 | XX | XX | New | 2025 | 2035 | 10 | 19 | ESP;FRA | Aragon Region | Aragon Region
71 | 2016 | 2016 | [2016] | 1217 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 273 | 1217 | Closing of 400 kV ring around Belgrade region | New OHL 400 kV SS Pancevo 2 - SS Belgrade West | "​This line will close 400 kV loop around Belgrade city. By closing of this loop, transmission capacity in direction East - West will be increased." | 1 | New Investment |  | 01/01/2035 | 2035 | 1 |  | 1 | SS 400/220/110 kV Pancevo 2 | SS 400/110 kV Belgrade West | Substation |  |  | 400 | 60 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 19 | SRB | Pancevo | Belgrade West | 44.8706 | 20.64 | 44.8915 | 20.0787
72 | 2016 | 2016 | [2016] | 1218 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 272 | 1218 | Network upgrade in Central Serbia from 220 kV to 400 kV voltage level | Upgrade of exsisting OHL 220 kV to 400 kV between SS Nis 2 and SS Kruševac 1 | "​This investment is a part of East - West corridor." | 1 | New Investment |  | 01/01/2034 | 2034 | 1 |  | 1 | SS 400/110 kV Nis 2 | SS 400/220/110 kV Krusevac 1 | Overhead Line | AC |  | 400 | 72 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2034 | 2034 | 0 | 18 | ISL;SRB | Nis | Krusevac | 43.3529 | 24.4123 | 43.5826 | 21.3265
73 | 2016 | 2016 | [2016] | 1219 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 249 | 1219 | Façade Atlantique | Cubnezais - Marmagne | ​New double 400 kV line in place of existing single circuit line from Cubnezais to Marmagne. | 1 | New Investment | This investment is necessary to transmit the RES generation from France and Iberian peninsula | 2030 | 2030 | 1 |  | 0 | Cubnezais | Marmagne | Overhead Line | AC | 3000 | 400 | 300 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | FRA | Cubnezais | Marmagne | 45.0738 | -0.40786
74 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 122 | Cancelled | 122 | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV. Total length: 120km. | 3 | 2014 | 2014 | 1 | Chippis (CH) | Lavorgo (CH) | 91 | 91. 122 | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV. Total length: 120km. | 3 | Delays due to authorization process. | 2017 | 2017 | 1 | Chippis (CH) | Lavorgo (CH) | 91. 122 | 91. 122 | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV. Total length: 120km. | 3 | Long permitting procedure (comprising several phases) | 2020 | 2020 | 1 | Chippis (CH) | Lavorgo (CH) | 91 | 122 | Swiss Ellipse | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV. Total length: 120km. | 3 | Delayed | long permitting procedure (comprising several phases) | 2020 | 2020 | 1 | Chippis (CH) | Lavorgo (CH) | 122 | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV. Total length: 120km. | 3 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Chippis (CH) | Lavorgo (CH) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2014 | 2020 | 6 | 10 | CHE | Chippis | Lavorgo | 46.2805 | 7.5406 | 46.4418 | 8.8404
75 | 2016 | 2016 | [2016] | 1220 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 272 | 1220 | Network upgrade in Central Serbia from 220 kV to 400 kV voltage level | Upgrading SS 220/110 kV Krusevac 1 to 400 kV voltage level | "​This investment is part on the East - West corridor." | 1 | New Investment |  | 01/01/2034 | 2034 | 1 |  | 0 | SS 220/110 kV Krusevac 1 |  | Substation |  |  | 400 |  | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2034 | 2034 | 0 | 18 | ISL;SRB | Krusevac |  | 43.5826 | 21.3265
76 | 2016 | 2016 | [2016] | 1221 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 249 | 1221 | Façade Atlantique | Marmagne - Tabarderie | ​Changing conductors on the existing lines. | 1 | New Investment | This investment is necessary to accomodate the north to south and south to north flows increased by large changes in the generation pattern. | 2030 | 2030 | 1 |  | 0 | Marmagne | Tabarderie | Overhead Line | AC | 3500 | 400 | 80 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | FRA | Marmagne | Tabarderie |  |  | 47.7465 | 2.525
77 | 2016 | 2016 | [2016] | 1222 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 272 | 1222 | Network upgrade in Central Serbia from 220 kV to 400 kV voltage level | Upgrading of exsisting OHL 220 kV to 400 kV between SS Krusevac 1 and SS Kraljevo 3 | "​This investment is a part of East - West corridor." | 1 | New Investment |  | 01/01/2034 | 2034 | 1 |  | 0 | SS 400/220/110 kV Krusevac 1 | SS 400/220/110 kV Kraljevo 3 | Overhead Line |  |  | 400 | 48 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2034 | 2034 | 0 | 18 | ISL;SRB | Krusevac | Kraljevo | 43.5826 | 21.3265 | 44.1021 | 18.9788
78 | 2016 | 2016 | [2016] | 1223 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 272 | 1223 | Network upgrade in Central Serbia from 220 kV to 400 kV voltage level | Uprading exsisting OHL 220 kV to 400 kV between SS Kraljevo 3 and SS Bajina Basta | "​This investment is a part of East - West corridor." | 1 | New Investment |  | 01/01/2030 | 2030 | 1 |  | 0 | SS 400/220/110 kV Kraljevo 3 | SS 400/220 kV Bajina Basta | Overhead Line |  |  | 400 | 80 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | ISL;SRB | Kraljevo | Bajina Basta | 44.1021 | 18.9788 | 43.9712 | 19.566
79 | 2016 | 2020 | [2016, 2018, 2020] | 1224 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 253 | 1224 | Upstream reinforcement in France to increase FR-CH capacity | Uprate of Creys-St Vulbas |  | 1 | New Investment |  | 2020 | 2020 | 1 |  | 0 | Creys(FR) | Saint Vulbas (FR) | Overhead Line | AC | 700 | 400 | 21 | Upgrade | 253 | 1224 | Upstream reinforcement in France to increase FR-CH capacity | Uprate of Creys-St Vulbas | 1 | Rescheduled |  | 2031 | 2031 | 1 | RTE | Creys(FR) | Saint Vulbas (FR) | Overhead Line | AC | 400 | 253 | 1224 | Upstream reinforcement in France to increase FR-CH capacity | Uprate of Creys-St Vulbas | Uprate of the double circuit 400-kV line Creys - Saint Vulbas with HTLS | 1 | Rescheduled |  | 2031 | 2031 | 1 | RTE |  | 0 | 1 | Creys (FR) | Saint Vulbas (FR) | ACTransmissionLine | AC | 21 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2031 | 11 | 15 | CHE;FRA | Creys | Saint Vulbas | 45.7264 | 5.4874 | 45.8306 | 5.2896
80 | 2016 | 2022 | [2016, 2018, 2020, 2022] | 1225 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 253 | 1225 | Upstream reinforcement in France to increase FR-CH capacity | PST in Cornier | ​Phase Shifter Transformer in order to attract the flows and alleviate the congestion on the France-switzerland interconnection west of Lake Geneva. | 1 | New Investment |  | 2020 | 2020 | 1 |  | 1 | Cornier (FR) |  | Phase Shift Transformer |  | 400 | 400 |  | New | 253 | 1225 | Upstream reinforcement in France to increase FR-CH capacity | PST in Cornier | 1 | Rescheduled |  | 2031 | 2031 | 1 |  | Cornier (FR) | Cornier (FR) | Phase Shift Transformer | AC | 400 | 253 | 1225 | Upstream reinforcement in France to increase FR-CH capacity | PST in Cornier | Phase Shifter Transformer in order to attract the flows and alleviate the congestion on the France-switzerland interconnection west of Lake Geneva. | 1 | Rescheduled |  | 2031 | 2031 | 1 | RTE |  | 1 | 1 | Cornier (FR) | Cornier (FR) | PhaseShiftingTransformer | AC | 0 | New | 253 | 1225 | Upstream reinforcement in France to increase FR-CH capacity | PST in Cornier | Phase Shifter Transformer in order to attract the flows and alleviate the congestion on the France-switzerland interconnection west of Lake Geneva. | 1 | Investment on time |  | 12-2031 | 2031 | 1 | Rte |  | 1 | 1 | Cornier (FR) | Cornier (FR) | PhaseShiftingTransformer | AC | 0 | 400 | 0 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2031 | 11 | 15 | CHE;FRA | Cornier | Cornier | 46.6669 | 6.7686 | 46.6669 | 6.7686
81 | 2016 | 2016 | [2016] | 1226 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 274 | 1226 | Concept project France-Switzerland 400kV AC | new 400-kV France-Switzerland interconnection | Concept investment that could allow to increase the cross-border capacity between France and Switzerland. | 1 | New Investment |  | 2030 | 2030 | 1 |  | 1 |  |  | Overhead Line | AC | 1000 | 400 | 25 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | CHE;FRA
82 | 2016 | 2016 | [2016] | 1227 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 275 | 1227 | Concept project France-Switzerland HVDC | New HVDC cross-border link between France and Switzerland | ​The project consists of a new cross-border HVDC between France and Switzerland. | 1 | New Investment |  | 2030 | 2030 | 1 |  | 1 |  |  | Underground Cable | DC | 1000 | 320 | 200 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | CHE;FRA
83 | 2016 | 2018 | [2016, 2018] | 1228 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 269 | 1228 | Uprate the western 220kV Sevilla Ring | Uprate D.Rodrigo-Aljarafe | Uprate OHL 220kV line D.Rodrigo-Aljarafe​ | 2 | New Investment |  | 2017 | 2017 | 1 |  | 0 | D.Rodrigo | Aljarafe | Overhead Line |  |  | 220 | 34 |  | 269 | 1228 | Uprate the western 220kV Sevilla Ring | Uprate D.Rodrigo-Aljarafe | 4 | Delayed | Partially constructed. Delay due to the difficulty in finding a window for a planned outage necessary for the works. | 2019 | 2019 | 1 | REE | D.Rodrigo | Aljarafe | Overhead Line | AC | 220 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2019 | 2 | 3 |  | D.Rodrigo | Aljarafe
84 | 2016 | 2018 | [2016, 2018] | 1229 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 269 | 1229 | Uprate the western 220kV Sevilla Ring | Uprate Aljarafe-Santiponce | Uprate OHL 220kV line Aljarafe-Santiponce​ | 2 | New Investment |  | 2019 | 2019 | 1 |  | 1 | Aljarafe | Santiponce | Overhead Line |  |  | 220 | 13 |  | 269 | 1229 | Uprate the western 220kV Sevilla Ring | Uprate Aljarafe-Santiponce | 3 | Investment on time |  | 2019 | 2019 | 1 |  | Aljarafe | Santiponce | Overhead Line | AC | 220 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2019 | 0 | 3 |  | Aljarafe | Santiponce
85 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 123 | Cancelled | 123 | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 90km. | 2 | 2015 | 2015 | 1 | Mettlen (CH) | Ulrichen (CH) | 91 | 91. 123 | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 90km. | 2 | Delays due to authorization process. | 2019 | 2019 | 1 | Mettlen (CH) | Ulrichen (CH) | 91. 123 | 91. 123 | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 90km. | 2 |  | 2019 | 2019 | 1 | Mettlen (CH) | Ulrichen (CH) | 91 | 123 | Swiss Ellipse | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 90km. | 2 | Investment on time | none | 2019 | 2019 | 1 | Mettlen (CH) | Ulrichen (CH) | 123 | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 90km. | 2 | Investment on time | Progressed as planned | 2019 | 2019 | 1 | Mettlen (CH) | Ulrichen (CH) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2019 | 4 | 9 | CHE | Mettlen | Ulrichen | 47.5311 | 9.1236 | 46.5066 | 8.305
86 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1231 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 228 | 1231 | Muhlbach - Eichstetten | Muhlbach Eichstetten | Operation of a second circuit at 400kV OHL Muhlbach - Eichstetten, instead of the currently operated circuit Eichstetten - Vogelgrun at 225kV and reinforcement of the existing circuit 400kV OHL Muhlbach - Eichstetten. Some restructurations on the existing grid may be necessary in the area. Reinforcement of the existing circuit at 400kV OHL Muhlbach - Eichstetten in order to increase the thermal capacity of the line. | 2 | Rescheduled | The detailed timeline of the investment is under definition but it is expected works should be completed slightly before initially thought. | 2025 | 2025 | 1 |  | 1 | Muhlbach | Eichstetten | Overhead Line | AC | 300 | 400 | 32 | Upgrade | 228 | 1231 | Muhlbach - Eichstetten | Muhlbach Eichstetten | 2 | Investment on time |  | 2025 | 2025 | 1 | RTE; TransnetBW; Amprion | Muhlbach | Eichstetten | Overhead Line | AC | 400 | 228 | 1231 | Muhlbach - Eichstetten | Muhlbach Eichstetten | Deployment of a second 400kV circuit at existing double circuit OHL Muhlbach - Eichstetten, instead of the currently operated circuit Eichstetten - Vogelgrun (currently operated with 225kV). Some topological adjustments of the existing grid in the area might prove to be necessary. This also include a transformer in Sierentz substation to balance flows between 225kV and 400kV grid in the area. | 2 | Investment on time |  | 2025 | 2025 | 1 | RTE TRANSNET-BW |  | 1 | 1 | Muhlbach | Eichstetten | ACTransmissionLine | AC | 32 | Upgrade | 228 | 1231 | Muhlbach - Eichstetten | Muhlbach Eichstetten | Reinforcement of the existing 400kV OHL and deployment of a second 400kV circuit at existing dou-ble circuit OHL Muhlbach - Eichstetten, instead of the currently operated circuit Eichstetten - Vo-gelgrun (currently operated with 225kV). The project includes also a transformer in Sierentz substation to balance flows between 225kV and 400kV grid in the area. | 2 | Rescheduled | Adjustment of commissioning date to 2026 during the project planning process. | 12-2026 | 2026 | 1 | Rte, TransnetBW |  | 1 | 1 | Muhlbach | Eichstetten | ACTransmissionLine | AC | 0 | 400 | 32 | Upgrade | 228 | 1231 | Muhlbach - Eichstetten | Muhlbach Eichstetten | Reinforcement of the existing 400kV OHL and deployment of a second 400kV circuit at existing double circuit OHL Muhlbach - Eichstetten, instead of the currently operated circuit Eichstetten - Vo-gelgrun (currently operated with 225kV). The project includes also a transformer in Sierentz substation to balance flows between 225kV and 400kV grid in the area. | 3 | Rescheduled | Adjustment of commissioning date to 2027 during the project planning process. | 12-2027 | 2027 | 1 | Rte, TransnetBW |  | 1 | 1 | Muhlbach | Eichstetten | ACTransmissionLine | AC | 0 | 400 | 32 | Upgrade | 228 | 1231 | Muhlbach - Eichstetten | Muhlbach Eichstetten | Reinforcement of the existing 400kV OHL and deployment of a second 400kV circuit at existing double circuit OHL Muhlbach - Eichstetten, instead of the currently operated circuit Eichstetten - Vo-gelgrun (currently operated with 225kV). The project includes also a transformer in Sierentz substation to balance flows between 225kV and 400kV grid in the area. |  |  | 12-2030 | 2030 | 1 | Rte, TransnetBW | 1 | XX | XX | Upgrade | 2025 | 2030 | 5 | 14 | DEU;FRA | Muhlbach | Eichstetten |  |  | 48.0938 | 7.7314
87 | 2016 | 2022 | [2016, 2018, 2020, 2022] | 1232 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 230 | 1232 | GerPol Power Bridge I | Baczyna-Plewiska | Construction of new 400 kV double circuit line Baczyna - Plewiska | 2 | New Investment |  | 31/12/2020 | 2020 | 1 |  | 0 | Baczyna | Plewiska | Overhead Line | AC | 750 | 400 | 142 | New | 230 | 1232 | GerPol Power Bridge I | Plewiska | 2 | Rescheduled |  | 2024 | 2024 | 1 |  | Baczyna | Plewiska | Overhead Line | AC | 400 | 230 | 1232 | GerPol Power Bridge I | Baczyna-Plewiska | Construction of new 400 kV double circuit line Baczyna - Plewiska | 3 | Rescheduled |  | 2022 | 2022 | 1 | Polskie Sieci Elektroenergetyczne S.A. | 3.14 (including 3.14.2, 3.14.3, 3.14.4) | 1 | 0 | Baczyna | Plewiska | ACTransmissionLine | AC | 147 | New | 230 | 1232 | GerPol Power Bridge I | Baczyna-Plewiska | Construction of new 400 kV double circuit line Baczyna - Plewiska with expansion of 400/220/110 kV Plewiska substation | 4 | Rescheduled |  | 02-2023 | 2023 | 1 | Polskie Sieci Elektroenergetyczne S.A. | 3.14 Internal reinforcements in Poland (including 3.14.2, 3.14.3, 3.14.4) | 1 | 0 | Baczyna | Plewiska | ACTransmissionLine | AC | 0 | 400 | 147 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2023 | 3 | 7 | POL | Baczyna | Plewiska |  |  | 52.3665 | 16.8098
88 | 2016 | 2016 | [2016] | 1234 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 232 | 1234 | Kontek-3 | Investments to be created | ​The third HVDC connector between Denmark-East and Germany, "Kontek-3" | 1 | New Investment |  | > 2030 | 2030 | 1 |  | 1 |  |  | Overhead Line | DC | 600 | 400 |  | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | BEL;DEU;DNK
89 | 2016 | 2020 | [2016, 2018, 2020] | 1235 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 233 | 1235 | Spanish Pumping | Conceptual project |  | 1 | New Investment |  | 2025 | 2025 | 1 |  | 0 |  |  | Overhead Line | AC |  | 400 |  |  | 233 | 1235 | Connection of Aragon Pumping hydro | Conceptual project | 1 | Delayed | National Development Plan does not contain yet a solution for the second phase of projects 1011 and 1019, which compete with each other. | 2027 | 2027 | 1 | REE | - | - | Overhead Line | AC | 400 | 233 | 1235 | Connection of Aragon Pumping hydro | Conceptual project | No details about the required network are known yet | 1 | Delayed | National Development Plan does not contain yet a solution for the second phase of projects 1011 and 1019, which compete with each other. | 2027 | 2027 | 1 | Red Eléctrica de España |  | 1 | 0 | - | - | ACTransmissionLine | AC | 0 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2027 | 2 | 11 | ESP
90 | 2016 | 2020 | [2016, 2018, 2020] | 1236 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 234 | 1236 | DKE-PL-1 | DKE-PL-1 | The first HVDC connector between Denmark-East and Poland | 1 | New Investment |  | >2030 | 2030 | 1 |  | 1 | Avedøre (DK) | Dunowo (PL) | Overhead Line | DC | 600 |  | 330 | New | 234 | 1236 | DKE - PL-1 | DKE-PL-1 | 1 | Investment on time |  | >2030 | 2030 | 1 | Energinet; PSE | Avedøre (DKE) | Dunowo (PL) | Subsea Cable | DC | 400 | 234 | 1236 | DKE - PL-1 | DKE-PL-1 | The first HVDC connector between Denmark-East and Poland. The planned transmission capacity of the new connection is 600 MW. | 1 | Investment on time |  | 2033 | 2033 | 1 | Energinet.dk Polskie Sieci Elektroenergetyczne S.A. |  | 1 | 1 | Avedøre (DKE) | Dunowo (PL) | OffshoreDCTransmissionCable | DC | 330 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2033 | 3 | 17 | DNK;POL | Avedøre | Dunowo | 55.6257 | 12.4556 | 54.1097 | 16.1078
91 | 2016 | 2016 | [2016] | 1239 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 237 | 1239 | COBRA-2 | Investments to be created | ​The second HVDC connector between Denmark-West and The Netherlands. | 1 | New Investment | potential project resulting from common planning studies analysis from ENTSO-E RGNS. | > 2030 | 2030 | 1 |  | 1 |  |  | Overhead Line | DC | 700 |  |  | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | DNK;NLD
92 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 124 | Cancelled | 124 | Upgrade of existing 225kV OHL into 400kV. Line length: 90km. | 1 | 2020 | 2020 | 1 | Mettlen (CH) | Airolo (CH) | 31 | 31. 124 | Upgrade of existing 225kV OHL into 400kV. Line length: 90km. | 1 | Progresses as planned | 2020 | 2020 | 1 | Mettlen (CH) | Airolo (CH) | 31. 124 | 31. 124 | Upgrade of existing 225kV OHL into 400kV. Line length: 90km. | 1 |  | 2020 | 2020 | 1 | Mettlen (CH) | Airolo (CH) | 31 | 124 | Italy-Switzerland | Upgrade of existing 225kV OHL into 400kV. Line length: 90km. | 1 | Investment on time | - | 2020 | 2020 | 1 | Mettlen (CH) | Airolo (CH) | 124 | Upgrade of existing 225kV OHL into 400kV. Line length: 90km. | 6 | Cancelled | not part of the national grid development plan TYNDP 2016 Project 'Swiss Ellipse I' now ensures the role of former investment 124 |  |  | 1 | Mettlen (CH) | Airolo (CH) | [10 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 |  |  |  | CHE | Mettlen | Airolo | 47.5311 | 9.1236 | 46.529 | 8.6086
93 | 2016 | 2016 | [2016] | 1240 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 238 | 1240 | Kontiskan 2 | Kontiskan 2 - Renewal | Renewal of the existing Kontiskan 2 HVDC interconnector between Denmark-West (DK1) and Sweden (SE3) to maintain capacity between Sweden and Denmark. | 1 | New Investment |  | >2030 | 2030 | 1 |  | 1 | Lindome (SE3) | Vester Hassing (DkV) | Subsea Cable | DC | 300 | 300 | 90 | Missing Data |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | DNK;SWE | Lindome | Vester Hassing | 57.5791 | 12.0877 | 57.0682 | 10.1253
94 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1241 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 239 | 1241 | Fenno-Skan 1 renewal | Fenno-Skan 1 renewal | Renewal of the existing 400 kV HVDC cable interconnection between Finland and Sweden. The projects capacity is estimated to range between 500-800 MW which could mean an updgrade compared to today. | 1 | New Investment |  | 2030+ | 2030 | 1 |  | 1 | Dannebo (SE3) | Rauma (FI) | Subsea Cable | DC | 500 | 400 | 200 | Missing Data | 239 | 1241 | Fenno-Skan 1 renewal | Fenno-Skan 1 renewal | 1 | Investment on time |  | 2029 | 2029 | 1 | Fingrid;Svenska Kraftnät | Hjalta (SE2) | Tuovila (FI) | Subsea Cable | DC | 300 | 239 | 1241 | Fenno-Skan 1 renewal | Fenno-Skan 1 renewal | Replacement of the existing 400 kV HVDC cable interconnection between Finland and Sweden. Fennoskan 1 will be decomissioned at the same time with this project being commisioned, which reduces capacity between FI and SE3 by 400 MW while increasing SE2-FI by 800 MW. | 1 | Rescheduled | The remaining lifetime of Fenno-Skan 1 will be investigated before making final decisions on its renewal. In addition, a joint study showed that the substantial benefits of this project will be realized in case of significant increase of consumption, new RES generation or the decommissioning of the remaining Swedish Nuclear plants which is expected in the 2040s. | 2035 | 2035 | 1 | FINGRID Svenska Kraftnät |  | 1 | 1 | Hjalta (SE2) | Tuovila (FI) | OffshoreDCTransmissionCable | DC | 200 | Upgrade | 239 | 1241 | Fenno-Skan 1 renewal | Fenno-Skan 1 renewal | Replacement of the existing 400 kV HVDC cable interconnection between Finland and Sweden. Fennoskan 1 will be decommissioned and a new interconnector with the capacity of 800 MW will be built between FI and SE3, resulting in a total capacity of 1600 MW between FI and SE3. | 1 | Rescheduled | According to new studies, Fenno-Skan 1 lifetime can be continued until 2040 and this project will be commissioned after that. | 12-2040 | 2040 | 1 | Fingrid, Svenska Kraftnät |  | 1 | 1 | SE3 | FI | OffshoreDCTransmissionCable | DC | 800 | 500 | 250 | Upgrade | 239 | 1241 | Fenno-Skan 3 | Fenno-Skan 3 | Replacement of the existing 400 kV HVDC cable interconnection between Finland and Sweden. Fennoskan 1 will be decommissioned and a new interconnector with the capacity of 800 MW will be built between FI and SE3, resulting in a total capacity of 1600 MW between FI and SE3. | 1 | Rescheduled | According to new studies, Fenno-Skan 1 lifetime can be continued until 2040 and this project will be commissioned after that. | 06-2038 | 2038 | 1 | Fingrid, Svenska Kraftnät |  | 1 | 1 | SE3 | FI | OffshoreDCTransmissionCable | DC | 800 | 500 | 250 | Upgrade | 239 | 1241 | Fenno-Skan 3 | Fenno-Skan 3 | Replacement of the existing 400 kV HVDC cable interconnection between Finland and Sweden. Fennoskan 1 will be decommissioned and a new interconnector with the capacity of 800 MW will be built between FI and SE3, resulting in a total capacity of 1600 MW between FI and SE3. | 1 |  | 06-2038 | 2038 | 1 | Fingrid, Svenska Kraftnät | 1 | XX | XX | Upgrade | 2030 | 2038 | 8 | 22 | FIN;SWE | Se | Fi |  |  | 60.2166 | 19.9439
95 | 2016 | 2016 | [2016] | 1242 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 240 | 1242 | 380-kV-grid enhancement between Area Güstrow/Bentwisch and Wolmirstedt | AC Upgrade Bentwisch-Güstrow | AC Upgrade (220 kV to 380 kV) of existing line between Bentwisch and Güstrow. | 1 | New Investment |  | 2025 | 2025 | 1 |  | 0 | Bentwisch (DE) | Güstrow (DE) | Overhead Line | AC |  | 380 | 36 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 9 | DEU | Bentwisch | Güstrow | 54.1162 | 12.2022 | 53.7936 | 12.1765
96 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1245 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 244 | 1245 | Vigy - Uchtelfangen area | Vigy Uchtelfangen (or beyond) | Upgrade of existing transmission OHL between Vigy and Uchtelfangen (or beyond) to increase its capacity. Dynamic Line Rating (DLR) or High Temperature Low Sag (HTLS) conductors are the two investigated options. | 2 | Investment on time |  | 2030 | 2030 | 1 |  | 1 | Vigy (FR) | Uchtelfangen (DE) | Overhead Line | AC | 1500 | 400 | 65 | Upgrade | 244 | 1245 | Vigy - Uchtelfangen area | Vigy - Uchtelfangen (or beyond) | 2 | Investment on time |  | 2027 | 2027 | 1 | Amprion;Rte | Vigy (FR) | Uchtelfangen (DE) | Overhead Line | AC | 400 | 244 | 1245 | Vigy - Uchtelfangen area | Vigy - Uchtelfangen (or beyond) | Upgrade of existing transmission OHL between Vigy and Uchtelfangen (or beyond) to increase the thermal cross-border capacity. To reach a higher capacity the options are High Temperature Low Sag (HTLS) conductors or a reconstruction of the tie-line in the existing route . | 2 | Delayed | Scope of the project changed due to technical reasons. | 2028 | 2028 | 1 | AMPRION RTE |  | 1 | 1 | Vigy (FR) | Uchtelfangen (DE) | ACTransmissionLine | AC | 65 | MostlyUpgrade | 244 | 1245 | Vigy - Uchtelfangen area | Vigy - Uchtelfangen (or beyond) | Upgrade of existing transmission OHL between Vigy and Uchtelfangen (or beyond) to increase the thermal cross-border capacity. To reach a higher capacity the options are High Temperature Low Sag (HTLS) conductors or a reconstruction of the tie-line in the existing route . | 2 | Rescheduled | additionnal works in Ensdorf to receive the PST need to be coordinated with previous works in the same substation (upgrade transformer) for internal reason | 12-2029 | 2029 | 1 | Amprion, Rte |  | 1 | 1 | Vigy (FR) | Uchtelfangen (DE) | ACTransmissionLine | AC | 0 | 400 | 65 | MostlyUpgrade | 244 | 1245 | Vigy - Uchtelfangen area | Vigy - Uchtelfangen (or beyond) | Upgrade of existing transmission OHL between Vigy and Uchtelfangen (or beyond) to increase the thermal cross-border capacity. To reach a higher capacity the options are High Temperature Low Sag (HTLS) conductors or a reconstruction of the tie-line in the existing route . | 3 | Investment on time |  | 12-2029 | 2029 | 1 | Amprion, Rte |  | 1 | 1 | Vigy (FR) | Uchtelfangen (DE) | ACTransmissionLine | AC | 0 | 400 | 65 | MostlyUpgrade | 244 | 1245 | Vigy - Uchtelfangen area | Vigy - Uchtelfangen (or beyond) | Upgrade of existing transmission OHL between Vigy and Uchtelfangen (or beyond) to increase the thermal cross-border capacity. To reach a higher capacity the options are High Temperature Low Sag (HTLS) conductors or a reconstruction of the tie-line in the existing route . |  |  | 12-2029 | 2029 | 1 | Amprion, Rte | 1 | XX | XX | Mostly upgrade | 2030 | 2029 | -1 | 13 | DEU;FRA | Vigy | Uchtelfangen | 49.2039 | 6.298 | 49.3788 | 7.0194
97 | 2016 | 2020 | [2016, 2018, 2020] | 1246 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 245 | 1246 | 201 Upgrade Meeden - Diele | Upgrade Meeden - Diele |  | 2 | Investment on time | Engineering completed, permits requested, construction planned. | 01-01-2019 | 2019 | 1 |  | 1 | Meeden [NL] | Diele [DE] | Overhead Line |  |  | 380 | 27 | Upgrade | 245 | 1246 | Upgrade Meeden - Diele | Upgrade Meeden - Diele | 4 | Investment on time |  | 2019 | 2019 | 1 | TENNET-NL;TENNET-DE | Meeden [NL] | Diele [DE] | Overhead Line | AC | 380 | 245 | 1246 | Upgrade Meeden - Diele | Upgrade Meeden - Diele | Increase of the interconnection capacity between The Netherlands and Germany by adding one new phase shifting transformer and apply dynamic line rating on the existing 380 kV double circuit tie line between Meeden and Diele. | 4 | Investment on time |  | 2021 | 2021 | 1 | TENNET-NL TenneT DE |  | 1 | 1 | Meeden [NL] | Diele [DE] | ACTransmissionLine | AC | 27 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2021 | 2 | 5 | DEU;NLD | Meeden Nl | Diele De | 53.1387 | 6.9282 | 53.1201 | 7.3117
98 | 2016 | 2018 | [2016, 2018] | 1248 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 248 | 1248 | Offshore Wind Baltic Sea (II) | Offshore Wind Baltic (II) | AC grid connections connecting Offshore Wind Farms in Cluster 1, 2 or 4 of the Baltic Sea (see German Offshore Grid Development Plan). Clusters are located north east of Rügen mainly in the German Exclusive Economic Zone. | 1 | Investment on time |  | 2026 | 2026 | 1 |  | 0 |  |  | Subsea Cable | AC | 500 | 220 |  |  | 248 | 1248 | Offshore Wind Baltic Sea (II) | AC Offshore Connection Cluster 1, 2,4 | 3 | Investment on time |  | 2022 | 2022 | 1 | 50Hertz Transmission | OWF Cluster Baltic Sea (DE) | Lubmin (DE) | Subsea Cable | AC | 220 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2026 | 2022 | -4 | 6 | DEU | Owf Cluster Baltic Sea | Lubmin |  |  | 54.1322 | 13.6138
99 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 125 | Commissioned | 125 | New 400kV double circuit (OHL and underground cable) between Schwanden and Limmern. | 3 | 2015 | 2015 | 1 | Schwanden (CH) | Limmern (CH) | 91 | 91. 125 | New 400kV double circuit (OHL and underground cable) between Schwanden and Limmern. | 3 | Progresses as planned | 2015 | 2015 | 1 | Schwanden (CH) | Limmern (CH) | 91. 125 | 91. 125 | New 400kV double circuit (OHL and underground cable) between Schwanden and Limmern. OHL part | 4 |  | 2015 | 2015 | 1 | Schwanden (CH) | Limmern (CH) | 91 | 125 | Swiss Ellipse | New 400kV double circuit (OHL and underground cable) between Schwanden and Limmern. OHL part | 4 | Investment on time | none | 2015 | 2015 | 1 | Schwanden (CH) | Limmern (CH) | 125 | New 400kV double circuit (OHL and underground cable) between Schwanden and Limmern. OHL part | 4 | Investment on time | Progressed as planned | 2015 | 2015 | 1 | Schwanden (CH) | Limmern (CH) | [5 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 5 | CHE | Schwanden | Limmern | 46.9956 | 9.0714 | 47.5293 | 7.6067
100 | 2016 | 2018 | [2016, 2018] | 1251 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 255 | 1251 | Connection Navarra-Basque Country | New line 400 kV Muruarte-Ichaso | North axis Project between Navarra and the Basque Country. New input/output in Ichaso 400 kV for RES integration. | 2 | New Investment |  | 2020 | 2020 | 1 |  | 0 | Muruarte | Ichaso | Overhead Line | AC |  | 400 | 145 | New | 255 | 1251 | Connection Navarra-Basque Country | New line 400 kV Muruarte-Ichaso | 3 | Delayed | Delay due to long permitting process | 2023 | 2023 | 1 | REE | Muruarte | Ichaso | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2023 | 3 | 7 |  | Muruarte | Ichaso |  |  | 43.0724 | -2.2579
101 | 2016 | 2018 | [2016, 2018] | 1252 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 256 | 1252 | Long-term conceptual interconnector DE-NL | Long-term inter-connector DE-NL | Upgrades of existing interconnections as well as new ones are analysed. The used technology is open – both AC and DC options are under consideration. | 1 | New Investment | Concept, under investigation | >2030 | 2030 | 1 |  | 1 | to be defined (DE) | to be defined (NL) | Overhead Line |  |  | 400 |  |  | 256 | 1252 | Study to upgrade interconnection DE-NL | Long term upgrade interconnection DE-NL | 1 | New Investment |  | 2040 | 2040 | 1 | Amprion;TENNET-NL | to be defined (DE) | to be defined (NL) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2040 | 10 | 24 | DEU;NLD | To Be Defined | To Be Defined
102 | 2016 | 2016 | [2016] | 1253 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 257 | 1253 | Douro Spanish-Portuguese reinforcement | Reinforcement in the Douro river area |  | 1 | New Investment | New investment | > 2030 | 2030 | 1 |  | 1 |  |  | Overhead Line | AC |  | 400 | [6 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | ESP;PRT
103 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1255 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 260 | 1255 | New Great Britain - Netherlands Interconnector | Interconnector GB-NL |  | 1 | Investment on time | Preliminary studies have indicated potential for further regional welfare & RES integration increase by further increasing the interconnection capacity between Netherlands & UK. | 2030 | 2030 | 1 |  | 1 |  |  | Overhead Line | [5 empty] | 260 | 1255 | New Great Britain - Netherlands interconnection | Interconnector GB-NL | 1 | Investment on time |  | 2030 | 2030 | 1 | NGIHL;TENNET-NL | TBD | TBD | Subsea Cable | DC | 0 | 260 | 1255 | Project 260 – Multi-purpose HVDC interconnection between Great Britain and The Netherlands | Interconnector GB-NL | Multi-purpose interconnector between GB and NL also connecting GB and NL windfarms. | 1 | Investment on time |  | 2030 | 2030 | 1 | National Grid TENNET-NL | 1.16 | 1 | 1 | TBD | TBD | OffshoreDCTransmissionCable | DC | 0 | New | 260 | 1255 | Project 260 – Multi-purpose HVDC interconnection between Great Britain and The Netherlands | Interconnector GB-NL | Multi-purpose interconnector between GB and NL also connecting GB and NL windfarms. | 1 | Investment on time |  | 12-2030 | 2030 | 1 | National Grid, TenneT-NL |  | 1 | 1 | TBD | TBD | OffshoreDCTransmissionCable | DC | 1800 | 525 | 0 | New | 260 | 1255 | Project 260 – Multi-purpose HVDC interconnection between Great Britain and The Netherlands | Interconnector GB-NL | Multi-purpose interconnector between GB and NL also connecting GB and NL windfarms. | 1 | Investment on time |  | 12-2030 | 2030 | 1 | National Grid, TenneT-NL | 4.6 | 1 | 1 | TBD | TBD | OffshoreDCTransmissionCable | DC | 1800 | 525 | 0 | New | 260 | 1255 | Project 260 – Multi-purpose HVDC interconnection between Great Britain and The Netherlands | Interconnector GB-NL | Multi-purpose interconnector between GB and NL also connecting GB and NL windfarms. | 2 |  | 12-2032 | 2032 | 1 | National Grid, TenneT-NL | 1 | XX | XX | New | 2030 | 2032 | 2 | 16 | GBR;NLD
104 | 2016 | 2016 | [2016] | 1256 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 261 | 1256 | Long-term conceptual "West-East corridor" in North Sea | Investments to be created |  |  | Investment on time |  |  |  | 1 |  | 1 |  |  | Overhead Line | [14 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [9 empty] | BEL
105 | 2016 | 2020 | [2016, 2018, 2020] | 1257 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 262 | 1257 | Belgium-Netherlands: further evolution | Belgium-Netherlands: further evolution | The reference solutions being further studied envisions an upgrade of the capacity of the cross-border lines by replacing the current conductors with high performance (HTLS) conductors combined with the installation of additional phase shifting transformers. | 1 | New Investment | This project is introduced in the TYNDP16 via a Common Planning Study elaborated within the Regional Group North Sea and is being studied by TenneT NL and Elia. | 01/01/2022 | 2022 | 1 |  | 1 | Van Eyck (BE) OR Zandvliet (BE) - TBC | Maasbracht (NL) OR Kreekrak (NL) - TBC | Overhead Line | AC |  | 380 | 10 | Upgrade | 262 | 1257 | Belgium-Netherlands: Zandvliet-Rilland | Belgium-Netherlands: Zandvliet-Rilland | 2 | Investment on time |  | 2022 | 2022 | 1 | ELIA; TENNET-NL | Zandvliet (BE) | Rilland (NL) | Overhead Line | AC | 380 | 262 | 1257 | Belgium-Netherlands: Zandvliet-Rilland | Belgium-Netherlands: Zandvliet-Rilland | Upgrade of the capacity of the cross-border lines by replacing the current conductors with high performance (HTLS) conductors combined with the installation of additional phase shifting transformers in Zandvliet. | 4 | Investment on time |  | 2022 | 2022 | 1 | ELIA TENNET-NL |  | 1 | 1 | Zandvliet (BE) | Rilland (NL) | PhaseShiftingTransformer | AC | 10 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2022 | 0 | 6 | BEL;NLD | Zandvliet | Rilland | 51.36 | 4.3087 | 51.4165 | 4.1812
106 | 2016 | 2022 | [2016, 2018, 2020, 2022] | 1258 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 263 | 1258 | Swiss Roof II | Rüthi - Bonaduz/Grynau | Integration of the new 380 kV tie-line Rüthi (CH) - Meiningen (AT) through optimisations between Rüthi and Grynau, Rüthi and Bonaduz and the construction of a new 380 kV substation and a new 380/220 kV transformer in Rüthi. | 1 | Investment on time |  | 01/01/2023 | 2023 | 1 |  | 0 | Rüthi | Grynau & Bonaduz | Overhead Line | AC |  | 380 |  |  | 263 | 1258 | Lake Constance East | Rüthi - Bonaduz/Mettlen | 1 | Rescheduled | under consideration, commissioning year 2035 | 2035 | 2035 | 1 | Swissgrid, VUEN | Rüthi | Mettlen & Bonaduz | Overhead Line | AC | 380 | 263 | 1258 | Lake Constance East | Rüthi - Bonaduz/Mettlen | Integration of the new 380 kV tie-line Rüthi (CH) - Meiningen (AT) through optimisations between Rüthi and Mettlen, Rüthi and Bonaduz and the construction of a new 380 kV substation and a new 380/220 kV transformer in Rüthi. | 1 | Investment on time |  | 2035 | 2035 | 1 | SWISSGRID VUEN |  | 0 | 1 | Rüthi | Mettlen & Bonaduz | ACTransmissionLine | AC | 1 | MostlyNew | 263 | 1258 | Lake Constance East | Rüthi - Bonaduz/Mettlen | Integration of the new 380 kV tie-line Rüthi (CH) - Meiningen (AT) through optimisations between Rüthi and Mettlen, Rüthi and Bonaduz and the construction of a new 380 kV substation and a new 380/220 kV transformer in Rüthi. | 1 | Investment on time |  | 12-2035 | 2035 | 1 | Swissgrid, VUEN, Amprion, Transnet-BW |  | 0 | 1 | Rüthi | Mettlen & Bonaduz | ACTransmissionLine | AC | 0 | 380 | 1 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2035 | 12 | 19 | AUT;CHE;DEU | Rüthi | Mettlen Bonaduz | 47.2558 | 9.7003
107 | 2016 | 2020 | [2016, 2018, 2020] | 1259 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 264 | 1259 | Swiss Roof I | Beznau - Mettlen | Optimization of the existing route by voltage conversion to 380 kV, partial reinforcement including a new 380/220 kV transformer in Beznau. | 3 | Investment on time |  | 01/01/2025 | 2025 | 1 |  | 0 | Beznau | Mettlen | Overhead Line | AC |  | 380 |  |  | 264 | 1259 | Swiss Roof I | Beznau - Mettlen | 3 | Investment on time |  | 2025 | 2025 | 1 | Swissgrid | Beznau | Mettlen | Overhead Line | AC | 380 | 264 | 1259 | Swiss Roof I | Beznau - Mettlen | Optimization of the existing route by voltage conversion to 380 kV, partial reinforcement. | 3 | Delayed | Permitting procedure | 2029 | 2029 | 1 | SWISSGRID |  | 0 | 0 | Beznau | Mettlen | ACTransmissionLine | AC | 64 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2029 | 4 | 13 | CHE | Beznau | Mettlen | 47.5542 | 8.2297 | 47.5311 | 9.1236
108 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 126 | Cancelled | 126 | New 2x 400kV cable connection between Golbia and the Bernina line double circuit. | 1 | 2020 | 2020 | 1 | Golbia (CH) | Robbia (CH) | 91 | 91. 126 | New 2x 400kV cable connection between Golbia and the Bernina line double circuit. | 1 | Progresses as planned | 2019 | 2019 | 1 | Golbia (CH) | Robbia (CH) | 91. 126 | 91. 126 | New 2x 400kV cable connection between Golbia and the Bernina line double circuit. | 1 |  | 2019 | 2019 | 1 | Golbia (CH) | Robbia (CH) | 91 | 126 | Swiss Ellipse | New 2x 400kV cable connection between Golbia and the Bernina line double circuit. | 1 | Investment on time | none | 2019 | 2019 | 1 | Golbia (CH) | Robbia (CH) | 126 | New 2x 400kV cable connection between Golbia and the Bernina line double circuit. | 1 | Rescheduled | Swissgrid has issued its new national strategic grid, and this investment is no longer in the (in the TYNDP 2016 jargon) mid-term category | 2025 | 2025 | 1 | Golbia (CH) | Robbia (CH) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2025 | 5 | 15 | CHE | Golbia | Robbia | 46.2712 | 10.1059 | 46.3481 | 10.0626
109 | 2016 | 2016 | [2016] | 1260 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 265 | 1260 | Swiss Ellipse II | Grimsel connection | Voltage increase to 380 kV of line Innertkirchen – Ulrichen and construction of a new 380 kV substation and a new 380/220 kV transformer in Innertkirchen in order to connect the new pump storage power plant. | 2 | Investment on time |  | 01/01/2029 | 2029 | 1 |  | 0 | Innertkirchen | Ulrichen | Overhead Line | AC |  | 380 | [6 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2029 | 2029 | 0 | 13 | CHE | Innertkirchen | Ulrichen | 46.7054 | 8.2286 | 46.5066 | 8.305
110 | 2016 | 2018 | [2016, 2018] | 1261 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 266 | 1261 | Swiss Ellipse I | Bickigen - Chippis - Chamoson | Chippis - Bickigen: Optimisation of the existing route by voltage conversion to 380 kV Chamoson - Chippis: Reinforcement by new construction of a 380 kV route New 380/220 kV transformer in Chippis | 3 | Investment on time |  | 01/01/2019 | 2019 | 1 |  | 0 | Bickigen | Chamoson | Overhead Line | AC |  | 380 |  |  | 266 | 1261 | Swiss Ellipse I | Bickigen - Chippis - Chamoson | 3 | Delayed | permitting procedure | 2021 | 2021 | 1 | Swissgrid | Bickigen | Chamoson | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2021 | 2 | 5 |  | Bickigen | Chamoson | 47.0908 | 7.649 | 46.2013 | 7.2233
111 | 2016 | 2024 | [2016, 2018, 2020, 2022, 2024] | 1262 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 267 | 1262 | Hansa PowerBridge 2 | Hansa Power Bridge 2 | Possible second HVDC cable interconnector between southern Sweden (Bidding area SE4) and Germany (50Hertz). This project candidate is driven by market based target capacities found in the Common Planning Studies by Regional Group Baltic Sea. | 1 | New Investment |  | 2030 | 2030 | 1 |  | 1 | Substation SE4 | Güstrow (DE) | Subsea Cable | DC |  |  |  | New | 267 | 1262 | Hansa PowerBridge II | Hansa PowerBridge II | 1 | Investment on time |  | 2030 | 2030 | 1 | 50Hertz Transmission, Svenska Kraftnät (SvK) | Hurva (SE4) | Guestrow (DE) | Subsea Cable | DC | 300 | 267 | 1262 | Hansa PowerBridge II | Hansa PowerBridge II | Possible second HVDC cable interconnector between southern Sweden (Bidding area SE4) and Germany (50Hertz). This project candidate is driven by market based target capacities found in the Common Planning Studies by Regional Group Baltic Sea. | 1 | Investment on time |  | 2030 | 2030 | 1 | Svenska Kraftnät 50HERTZ |  | 1 | 1 | Hurva (SE4) | Guestrow (DE) | OffshoreDCTransmissionCable | DC | 300 | New | 267 | 1262 | Hansa PowerBridge II | Hansa PowerBridge II | Possible second HVDC cable interconnector between southern Sweden (Bidding area SE4) and Germany (50Hertz). This project candidate is driven by market based target capacities found in the Common Planning Studies by Regional Group Baltic Sea. | 1 | Delayed | Postponement of commissioning, currently the full focus is on HBPI | 12-2035 | 2035 | 1 | Svenska kraftnät, 50Hertz |  | 1 | 1 | Hurva (SE4) | Sanitz/Dettmannsdorf (DE) | OffshoreDCTransmissionCable | DC | 700 | 300 | 300 | New | 267 | 1262 | Hansa PowerBridge II | Hansa PowerBridge II | Possible second HVDC cable interconnector between southern Sweden (Bidding area SE4) and Germany (50Hertz). This project candidate is driven by market based target capacities found in the Common Planning Studies by Regional Group Baltic Sea. | 1 | Delayed | Postponement of commissioning, currently the full focus is on HBPI. | 12-2040 | 2040 | 1 | Svenska kraftnät, 50Hertz |  | 1 | 1 | Hurva (SE4) | Gnewitz (DE) | OffshoreDCTransmissionCable | DC | 700 | 300 | 300 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2030 | 2040 | 10 | 24 | DEU;SWE | Hurva | Gnewitz | 55.796 | 13.4384 | 54.0788 | 12.5132
112 | 2016 | 2016 | [2016] | 1263 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 268 | 1263 | Upgrading existing single 400 kV interconnection line between Romania and Serbia to double 400 kV line | Portile de Fier (RO) - Djerdap (RS) 2nd | The project stems from the need to increase the transfer capacity between Romania and Serbia in order to accomodate connection of RES and improve market. | 1 | Investment on time |  | 01/01/2035 | 2035 | 1 |  | 1 | Portile de Fier | Djerdap | Overhead Line | AC | 500 | 400 |  | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 19 | DEU;ROU;SRB | Portile De Fier | Djerdap | 46.6075 | 23.8328 | 44.6713 | 22.5294
113 | 2016 | 2018 | [2016, 2018] | 1264 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 271 | 1264 | Long term conceptual project "Northern Seas offshore grid infrastructure" | Investments to be created |  |  | Investment on time |  |  |  | 1 |  | 1 |  |  | Overhead Line | [5 empty] | 271 | 1264 | "Northern Seas Offshore Grid infrastructure" - a Long Term Conceptual Project | Investments to be created | 1 |  |  | 0 |  | 1 | EirGrid, Elia System Operator, Energinet.dk, Creos Luxembourg, National Grid, RTE,TenneT TSO GmbH, SONI, Statnett, TenneT TSO B.V. | 0 | 0 | Overhead Line | DC | 0 | [10 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [9 empty] | BEL
114 | 2016 | 2016 | [2016] | 1266 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 277 | 1266 | New double 400 kV interconnection line between Bulgaria and Serbia | Sofia West (BG) - Nis 2 (RS) 2nd | The project stems from the need to increase the transfer capacity between Bulgaria and Serbia in order to accomodate connection of RES and improve electricity market. | 1 | Investment on time |  | 01/01/2034 | 2034 | 1 |  | 1 | Sofia West (BG) | Nis 2 (RS) | Overhead Line | AC | 800 | 400 |  | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2034 | 2034 | 0 | 18 | BGR;SRB | Sofia West | Nis | 42.4432 | 22.9853 | 43.3529 | 24.4123
115 | 2016 | 2016 | [2016] | 1267 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 278 | 1267 | Additional project France - Spain | Investments to be created |  | 1 | Investment on time |  | 2030 | 2030 | 1 |  | 1 |  |  | Overhead Line | [9 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | BEL;ESP;FRA
116 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1269 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 243 | 1269 | New 400 kV interconnection line between Serbia and Croatia | New 400 kV overhead line Sombor (RS) – Ernestinovo (HR) | The project necessity stems for the need to increase the transfer capacity between RS and HR in order to accommodate connection of RES and improve market integration, according to the results by the Common Planning Studies based on TYNDP2014 Vision 4. | 1 | New Investment | Based on the results by the Common Planning Studies based on Vision 4.Project will increase the transfer capacity between RS and HR in order to accommodate connection of RES and improve market integration. | 31/12/2030 | 2030 | 1 |  | 1 | Ernestinovo | Sombor | Overhead Line | AC | 500 | 400 | 70 | New | 243 | 1269 | New 400 kV interconnection line between Serbia and Croatia | New 400 kV overhead line Sombor (RS) - Ernestinovo (HR) | 1 | Investment on time |  | 01/01/2035 | 2035 | 1 | EMS, HOPS | Ernestinovo | Sombor | Overhead Line | AC | 400 | 243 | 1269 | New 400 kV interconnection line between Serbia and Croatia | New 400 kV overhead line Sombor (RS) - Ernestinovo (HR) | The project necessity stems for the need to increase the transfer capacity between RS and HR in order to accommodate connection of RES and improve market integration, according to the results based on TYNDP2018 CBA. | 1 | Investment on time |  | 2035 | 2035 | 1 | EMS HOPS |  | 1 | 1 | Ernestinovo | Sombor | ACTransmissionLine | AC | 70 | New | 243 | 1269 | New 400 kV interconnection line between Serbia and Croatia | New 400 kV overhead line Sombor (RS) - Ernestinovo (HR) | The project necessity stems for the need to increase the transfer capacity between RS and HR in order to accommodate connection of RES and improve market integration, according to the results based on TYNDP CBA. | 1 | Investment on time |  | 09-2035 | 2035 | 1 | EMS, HOPS |  | 1 | 1 | SS Ernestinovo | SS Sombor 3 | ACTransmissionLine | AC | 0 | 400 | 70 | New | 243 | 1269 | New 400 kV interconnection line between Serbia and Croatia | New 400 kV overhead line Sombor (RS) - Ernestinovo (HR) | The project necessity stems for the need to increase the transfer capacity between RS and HR in order to accommodate connection of RES and improve market integration, according to the results based on TYNDP CBA. | 1 | Delayed | There is a slight delay due to the new circumstances and observations regarding the project. | 09-2038 | 2038 | 1 | EMS, HOPS |  | 1 | 1 | SS Ernestinovo | SS Sombor 3 | ACTransmissionLine | AC | 0 | 400 | 70 | New | 243 | 1269 | New 400 kV interconnection line between Serbia and Croatia | New 400 kV overhead line SS Sombor 3 (RS) - SS Ernestinovo (HR) | The project necessity stems for the need to increase the transfer capacity between RS and HR in order to accommodate connection of RES and improve market integration, according to the results based on TYNDP CBA. | 1 |  | 09-2038 | 2038 | 1 | EMS, HOPS | 1 | XX | XX | New | 2030 | 2038 | 8 | 22 | HRV;SRB | Ernestinovo | Sombor | 45.4516 | 18.6589 | 45.7727 | 19.1147
117 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 127 | Cancelled | 127 | Upgrade of existing 150kV line into 220kV line. | 1 | 2020 | 2020 | 1 | Magadino (CH) | Verzasca (CH) | 91 | 91. 127 | Upgrade of existing 150kV line into 220kV line. | 1 | Progresses as planned | 2020 | 2020 | 1 | Magadino (CH) | Verzasca (CH) | 91. 127 | 91. 127 | Upgrade of existing 150kV line into 220kV line. | 1 |  | 2020 | 2020 | 1 | Magadino (CH) | Verzasca (CH) | 91 | 127 | Swiss Ellipse | Upgrade of existing 150kV line into 220kV line. | 1 | Investment on time | none | 2020 | 2020 | 1 | Magadino (CH) | Verzasca (CH) | 127 | Upgrade of existing 150kV line into 220kV line. | 1 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Magadino (CH) | Verzasca (CH) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 10 | CHE | Magadino | Verzasca | 46.1474 | 8.8559 | 46.2803 | 8.804
118 | 2016 | 2020 | [2016, 2018, 2020] | 1270 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 229 | 1270 | GerPol Power Bridge II | Baczyna-Zielona Góra | Indentation to the 2x400 kV line Baczyna - Plewiska (construction 40 km new 2x400 kV line from new substation Zielona Góra to the point of indentation). Creating new route 2x 400 kV Baczyna - Zielona Góra. | 1 | Investment on time |  | >2030 | 2030 | 1 |  | 0 | Baczyna-Plewiska Indentation | Zielona Góra | Overhead Line | AC | 750 | 400 | 40 | New | 229 | 1270 | GerPol Power Bridge II | Baczyna-Zielona Góra | 1 | Investment on time |  | >2030 | 2030 | 1 | 50Hertz Transmission, PSE | Baczyna-Plewiska indentation | Zielona Góra | Overhead Line | AC | 400 | 229 | 1270 | GerPol Power Bridge II | Baczyna-Zielona Góra | Indentation to the one circuit of 400 kV line Baczyna - Plewiska (construction 40 km new 400 kV line from new substation Zielona Góra to the point of indentation). Creating new route 400 kV Baczyna - Zielona Góra. | 1 | Investment on time |  | 2035 | 2035 | 1 | Polskie Sieci Elektroenergetyczne S.A. 50HERTZ |  | 0 | 1 | Baczyna-Plewiska indentation | Zielona Góra | ACTransmissionLine | AC | 40 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2035 | 5 | 19 | DEU;POL | Baczyna-Plewiska Indentation | Zielona Góra |  |  | 52.5114 | 13.4595
119 | 2016 | 2020 | [2016, 2018, 2020] | 1271 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 229 | 1271 | GerPol Power Bridge II | Zielona Góra - Plewiska | Indentation to the 2x400 kV line Baczyna - Plewiska (construction 40 km new 2x400 kV line from new substation Zielona Góra to the point of indentation). Creating new 2x400 kV route Zielona Góra - Plewiska. | 1 | Investment on time |  | >2030 | 2030 | 1 |  | 0 | Zielona Góra | Plewiska | Overhead Line | AC | 750 | 400 | 40 | New | 229 | 1271 | GerPol Power Bridge II | Zielona Góra - Plewiska | 1 | Investment on time |  | >2030 | 2030 | 1 |  | Zielona Góra | Baczyna-Plewiska indentation | Overhead Line | AC | 400 | 229 | 1271 | GerPol Power Bridge II | Zielona Góra - Plewiska | Indentation to the one circuit of 400 kV line Baczyna - Plewiska (construction 40 km new 400 kV line from new substation Zielona Góra to the point of indentation). Creating new 400 kV route Zielona Góra - Plewiska. | 1 | Investment on time |  | 2035 | 2035 | 1 | Polskie Sieci Elektroenergetyczne S.A. 50HERTZ |  | 0 | 1 | Zielona Góra | Baczyna-Plewiska indentation | ACTransmissionLine | AC | 40 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2035 | 5 | 19 | DEU;POL | Zielona Góra | Baczyna-Plewiska Indentation | 52.5114 | 13.4595
120 | 2016 | 2020 | [2016, 2018, 2020] | 1272 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 229 | 1272 | GerPol Power Bridge II | Zielona Góra | Construction of new substation 400/110 kV Zielona Góra to connect 400 kV lines : Baczyna - Zielona Góra, Zielona Góra - Plewiska, Zielona Góra - Gubin | 1 | Investment on time |  | >2030 | 2030 | 1 |  | 0 | Zielona Góra |  | Substation |  | 1500 | 400 |  | New | 229 | 1272 | GerPol Power Bridge II | Zielona Góra | 1 | Investment on time |  | >2030 | 2030 | 1 |  | Zielona Góra | n.a. | Substation | AC | 400 | 229 | 1272 | GerPol Power Bridge II | Zielona Góra | Construction of new substation 400/110 kV Zielona Góra to connect 400 kV lines : Baczyna - Zielona Góra, Zielona Góra - Plewiska, Zielona Góra - Eisenhuettenstadt (with installation of Phase Shifting Transformers), Zielona Góra - Polkowice | 1 | Investment on time |  | 2035 | 2035 | 1 | Polskie Sieci Elektroenergetyczne S.A. 50HERTZ |  | 0 | 1 | Zielona Góra | n.a. | OnshoreSubstation | AC | 0 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2035 | 5 | 19 | DEU;POL | Zielona Góra | N.A. | 52.5114 | 13.4595 | 51.5902 | 7.3188
121 | 2016 | 2018 | [2016, 2018] | 1273 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 229 | 1273 | GerPol Power Bridge II | Zielona Góra-Gubin | Construction of new 2x400 kV line from new substation Zielona Góra to new substation Gubin | 1 | Investment on time |  | >2030 | 2030 | 1 |  | 0 | Zielona Góra | Gubin | Overhead Line | AC | 1500 | 400 | 60 | New | 229 | 1273 | GerPol Power Bridge II | Zielona Góra-Gubin | 1 | Investment on time |  | >2030 | 2030 | 1 |  | Zielona Góra | Gubin | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 |  | Zielona Góra | Gubin | 52.5114 | 13.4595 | 51.9509 | 14.7293
122 | 2016 | 2018 | [2016, 2018] | 1274 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 229 | 1274 | GerPol Power Bridge II | Gubin | Construction of new 400 kV substation Gubin to connect new 400 kV lines: 2x400 kV Zielona Góra - Gubin and crossborder 2x400 kV line Gubin - Eisenhuettenstadt with PST installation on crossborder line Gubin - Eisenhuettenstadt | 1 | Investment on time |  | >2030 | 2030 | 1 |  | 0 | Gubin |  | Substation |  | 1500 | 400 |  | New | 229 | 1274 | GerPol Power Bridge II | Gubin | 1 | Investment on time |  | >2030 | 2030 | 1 |  | Gubin | n.a. | Substation | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 |  | Gubin | N.A. | 51.9509 | 14.7293 | 51.5902 | 7.3188
123 | 2016 | 2018 | [2016, 2018] | 1275 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 229 | 1275 | GerPol Power Bridge II | Gubin - Eisenhuettenstadt | Construction of new crossborder 2x400 kV line between new substation Gubin (PL) end existing substation Eisenhuettenstadt (DE) | 1 | Investment on time |  | >2030 | 2030 | 1 |  | 1 | Gubin | Eisenhuettenstadt | Overhead Line |  | 1500 | 400 | 20 | New | 229 | 1275 | GerPol Power Bridge II | Eisenhuettenstadt | 1 | Investment on time |  | >2030 | 2030 | 1 |  | Gubin (PL) | Eisenhuettenstadt (DE) | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | DEU;POL | Gubin | Eisenhuettenstadt | 51.9509 | 14.7293 | 52.1449 | 14.6294
124 | 2016 | 2020 | [2016, 2018, 2020] | 1276 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 241 | 1276 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | Upgrading of existing 220 kV line between SS Đakovo (HR) and SS Tuzla (BA) to 400 kV line | The project necessity stems for the need to increase the target transfer capacity between HR and BA in order to accommodate market integration and exploitation of RES, according to the results by the Common Planning Studies based on TYNDP2014 Vision 4. | 1 | New Investment | Based on the results by the Common Planning Studies based on Vision 4.Project will increase the transfer capacity between BA and HR in order to accommodate connection of RES and improve market integration. | 31/12/2030 | 2030 | 1 |  | 1 | Đakovo | Tuzla | Overhead Line | AC | 500 | 400 | 91 | Upgrade | 241 | 1276 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | Upgrading of existing 220 kV line between SS Dakovo (HR) and TPP Tuzla (BA) to 400 kV line | 1 | Rescheduled |  | 31/12/2032 | 2032 | 1 | HOPS;NOS BiH | Dakovo | Tuzla | Overhead Line | AC | 400 | 241 | 1276 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | Upgrading of existing 220 kV line between SS Dakovo (HR) and TPP Tuzla (BA) to 400 kV line | The project necessity stems for the need to increase the target transfer capacity between HR and BA in order to accommodate market integration and exploitation of RES, according to the results by the Common Planning Studies based on TYNDP2014 Vision 4. | 1 | Investment on time |  | 2033 | 2033 | 1 | HOPS NOS-BIH |  | 0 | 1 | Dakovo | Tuzla | ACTransmissionLine | AC | 91 | MostlyUpgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2033 | 3 | 17 | BIH;HRV | Dakovo | Tuzla | 45.3081 | 18.4116 | 44.5393 | 18.6749
125 | 2016 | 2020 | [2016, 2018, 2020] | 1277 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 241 | 1277 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | Upgrading of existing 220 kV line between SS Đakovo (HR) and Gradačac (BA) to 400 kV line | The project necessity stems for the need to increase the target transfer capacity between HR and BA in order to accommodate market integration and exploitation of RES, according to the results by the Common Planning Studies based on TYNDP2014 Vision 4. | 1 | New Investment | Based on the results by the Common Planning Studies based on Vision 4.Project will increase the transfer capacity between BA and HR in order to accommodate connection of RES and improve market integration. | 31/12/2030 | 2030 | 1 |  | 1 | Đakovo | Gradačac | Overhead Line | AC | 500 | 400 | 46.2 | Upgrade | 241 | 1277 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | Upgrading of existing 220 kV line between SS Dakovo (HR) and Gradacac (BA) to 400 kV line | 1 | Rescheduled |  | 31/12/2032 | 2032 | 1 |  | Dakovo | Gradacac | Overhead Line | AC | 400 | 241 | 1277 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | Upgrading of existing 220 kV line between SS Dakovo (HR) and Gradacac (BA) to 400 kV line | The project necessity stems for the need to increase the target transfer capacity between HR and BA in order to accommodate market integration and exploitation of RES, according to the results by the Common Planning Studies based on TYNDP2014 Vision 4. | 1 | Investment on time |  | 2033 | 2033 | 1 | HOPS NOS-BIH |  | 0 | 1 | Dakovo | Gradacac | ACTransmissionLine | AC | 46.2 | MostlyUpgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2033 | 3 | 17 | BIH;HRV | Dakovo | Gradacac | 45.3081 | 18.4116 | 44.8781 | 18.4255
126 | 2016 | 2020 | [2016, 2018, 2020] | 1278 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 241 | 1278 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | Upgrading existing 220 kV SS Đakovo to 400 kV | Upgrading existing 220 kV SS Đakovo to 400 kV enables connection between SS Đakovo (HR) and SS Tuzla/Gradačac (BA) by 400 kV lines. | 1 | New Investment | Based on the results by the Common Planning Studies based on Vision 4.Project will increase the transfer capacity between BA and HR in order to accommodate connection of RES and improve market integration. | 31/12/2030 | 2030 | 1 |  | 0 | Đakovo |  | Substation |  | 500 | 400 |  | Upgrade | 241 | 1278 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | Upgrading existing 220 kV SS Dakovo to 400 kV | 1 | Rescheduled |  | 31/12/2032 | 2032 | 1 |  | Dakovo | Dakovo | Substation | AC | 400 | 241 | 1278 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | Upgrading existing 220 kV SS Dakovo to 400 kV | Upgrading existing 220 kV SS Dakovo to 400 kV enables connection between SS Dakovo (HR) and TPP Tuzla/Gradacac (BA) by 400 kV lines. | 1 | Investment on time |  | 2033 | 2033 | 1 | HOPS NOS-BIH |  | 1 | 1 | Dakovo | Dakovo | OnshoreSubstation | AC | 0 | MostlyUpgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2033 | 3 | 17 | BIH;HRV | Dakovo | Dakovo | 45.3081 | 18.4116 | 45.3081 | 18.4116
127 | 2016 | 2020 | [2016, 2018, 2020] | 1279 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 241 | 1279 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | New double 400 kV line between SS Đakovo and location Razbojište | New double 400 kV line between SS Đakovo and location Razbojište enables connection of planned 400 kV SS Đakovo to existing 400 kV line Žerjavinec - Ernestinovo | 1 | New Investment | Based on the results by the Common Planning Studies based on Vision 4.Project will increase the transfer capacity between BA and HR in order to accommodate connection of RES and improve market integration. | 31/12/2030 | 2030 | 1 |  | 0 | Đakovo | Razbojište | Overhead Line | AC | 500 | 400 | 25 | New | 241 | 1279 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | New double 400 kV line between SS Dakovo and location Razbojiste | 1 | Rescheduled |  | 31/12/2032 | 2032 | 1 |  | Dakovo | Razbojiste | Overhead Line | AC | 400 | 241 | 1279 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | New double 400 kV line between SS Dakovo and location Razbojiste | New double 400 kV line between SS Dakovo and location Razbojiste enables connection of planned 400 kV SS Dakovo to existing 400 kV line Zerjavinec - Ernestinovo | 1 | Investment on time |  | 2033 | 2033 | 1 | HOPS NOS-BIH |  | 0 | 1 | Dakovo | Razbojiste | ACTransmissionLine | AC | 25 | MostlyUpgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2033 | 3 | 17 | BIH;HRV | Dakovo | Razbojiste | 45.3081 | 18.4116 | 43.0283 | 18.0026
128 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 128 | Cancelled | 128 | New 400kV double circuit OHL between Bâtiaz and Châtelard. New 2x 400kV cable connection between Châtelard and Nant de Drance. Total length: 22km. | 3 | 2014 | 2014 | 1 | Bâtiaz (CH) | Nant de Drance (CH) | 91 | 91. 128 | New 400kV double circuit OHL between Bâtiaz and Châtelard. New 2x 400kV cable connection between Châtelard and Nant de Drance. Total length: 22km. | 3 | Delays due to authorization process. | 2016 | 2016 | 1 | Bâtiaz (CH) | Nant de Drance (CH) | 91. 128 | 91. 128 | New 400kV double circuit OHL between Bâtiaz and Châtelard. New 2x 400kV cable connection between Châtelard and Nant de Drance. Total length: 22km. | 3 | Long permitting procedure (comprising several phases) | 2020 | 2020 | 1 | Bâtiaz (CH) | Nant de Drance (CH) | 91 | 128 | Swiss Ellipse | New 400kV double circuit OHL between Bâtiaz and Châtelard. New 2x 400kV cable connection between Châtelard and Nant de Drance. Total length: 22km. | 3 | Delayed | long permitting procedure (comprising several phases) | 2020 | 2020 | 1 | Bâtiaz (CH) | Nant de Drance (CH) | 128 | New 400kV double circuit OHL between Bâtiaz and Châtelard. New 2x 400kV cable connection between Châtelard and Nant de Drance. Total length: 22km. | 3 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Bâtiaz (CH) | Nant de Drance (CH) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2014 | 2020 | 6 | 10 | CHE | Bâtiaz | Nant De Drance | 46.105 | 7.0693 | 46.0631 | 6.9046
129 | 2016 | 2020 | [2016, 2018, 2020] | 1281 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 173 | 1281 | FR-BE Phase 2 (study): Aubange-Moulaine | Aubange-Moulaine: PSTs (under study) | The reference solution consists of the installation of two phase shifting transformers, one on each of the 225kV circuits of the Aubange-Moulaine cross-border overhead line. | 1 | New Investment | Project introduced in TYNDP16 related to congestion signals picked up vibilateral studies and confirmed in RG NS Common Planning Study. | 01/01/2020 | 2020 | 1 |  | 1 | Aubange (BE) | Moulaine (FR) | Phase Shift Transformer |  |  | 225 |  | Upgrade | 173 | 1281 | FR-BE II: PSTs Aubange-Moulaine | Aubange-Moulaine: PSTs | 2 | Rescheduled |  | 2021 | 2021 | 1 | ELIA;RTE | Aubange (BE) | Moulaine (FR) | Phase Shift Transformer | AC | 220 | 173 | 1281 | FR-BE: PSTs Aubange-Moulaine | Aubange-Moulaine: PSTs | "Investment consists of the installation of two phase shifting transformers in Aubang, one on each of the 225kV circuits of the Aubange-Moulaine interconnector." | 4 | Investment on time |  | 2021 | 2021 | 1 | ELIA RTE |  | 1 | 1 | Aubange (BE) | Moulaine (FR) | PhaseShiftingTransformer | AC | 0 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2021 | 1 | 5 | BEL;FRA | Aubange | Moulaine | 49.5672 | 5.8045 | 49.5018 | 5.8171
130 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1282 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 231 | 1282 | Concept Project DE-CH | 380 kV Grid Reinforcement Beznau - Tiengen | This projects helps to increase the cross border capacity between Switzerland and Germany by upgrading an existing line from 220 kV to 380 kV including internal reinforcements. | 2 | New Investment |  | 01/01/2030 | 2030 | 1 |  | 1 | Beznau (CH) | Tiengen (DE) | Overhead Line | AC |  | 380 |  | Upgrade | 231 | 1282 | Concept project Germany-Switzerland | 380 kV Grid Reinforcement Beznau - Tiengen | 1 | Investment on time |  | 2030 | 2030 | 1 | swissgrid; TransnetBW; Amprion | Beznau (CH) | Tiengen (DE) | Overhead Line | AC | 380 | 231 | 1282 | Beznau - Tiengen | 380 kV Grid Reinforcement Beznau - Tiengen | This projects helps to increase the cross border capacity between Switzerland and Germany by upgrading an existing line from 220 kV to 380 kV including internal reinforcements. | 1 | Investment on time |  | 2030 | 2030 | 1 | AMPRION SWISSGRID |  | 1 | 1 | Beznau (CH) | Tiengen (DE) | ACTransmissionLine | AC | 11 | Upgrade | 231 | 1282 | Beznau - Tiengen | 380 kV Grid Reinforcement Beznau - Tiengen | This projects helps to increase the cross border capacity between Switzerland and Germany by upgrading an existing line from 220 kV to 380 kV including internal reinforcements. | 1 | Investment on time |  | 12-2030 | 2030 | 1 | Amprion, Swissgrid |  | 1 | 1 | Beznau (CH) | Tiengen (DE) | ACTransmissionLine | AC | 0 | 380 | 11 | Upgrade | 231 | 1282 | Beznau - Tiengen | 380 kV Grid Reinforcement Beznau - Tiengen | This projects helps to increase the cross border capacity between Switzerland and Germany by upgrading an existing line from 220 kV to 380 kV including internal reinforcements. | 2 | Investment on time |  | 12-2035 | 2035 | 1 | Amprion, Swissgrid |  | 1 | 1 | Beznau (CH) | Tiengen (DE) | ACTransmissionLine | AC | 0 | 380 | 11 | Upgrade | 231 | 1282 | Beznau - Tiengen | 380 kV Grid Reinforcement Beznau - Tiengen | This projects helps to increase the cross border capacity between Switzerland and Germany by upgrading an existing line from 220 kV to 380 kV including internal reinforcements. | 2 |  | 12-2035 | 2035 | 1 | Amprion, Swissgrid | 1 | XX | XX | Upgrade | 2030 | 2035 | 5 | 19 | CHE;DEU | Beznau | Tiengen | 47.5542 | 8.2297 | 47.9842 | 7.7153
131 | 2016 | 2016 | [2016] | 1283 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 21 | 1283 | Italy-France | Vado-Vignole | Removing limitations on the existing 380 kV Vado-Vignole | 2 | Investment on time |  | 2019 | 2019 | 1 |  | 0 | Vado(IT) | Vignole(IT) | Overhead Line | AC | 300 | 380 | 67 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2019 | 0 | 3 | ITA | Vado | Vignole | 44.3175 | 11.2582 | 46.1397 | 12.1252
132 | 2016 | 2020 | [2016, 2018, 2020] | 1284 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 264 | 1284 | Swiss Roof I | Pradella - La Punt | Reinforcement of the existing route | 3 | Investment on time |  | 01/01/2020 | 2020 | 1 |  | 0 | Pradella | La Punt | Overhead Line | AC |  | 380 |  |  | 264 | 1284 | Swiss Roof I | Pradella - La Punt | 4 | Investment on time |  | 2021 | 2021 | 1 |  | Pradella | La Punt | Overhead Line | AC | 380 | 264 | 1284 | Swiss Roof I | Pradella - La Punt | Reinforcement of the existing route | 4 | Delayed | sundry reasons | 2022 | 2022 | 1 | SWISSGRID |  | 0 | 0 | Pradella | La Punt | ACTransmissionLine | AC | 49 | MostlyNew | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2022 | 2 | 6 | CHE | Pradella | La Punt | 46.8039 | 10.3292 | 46.5789 | 9.9254
133 | 2016 | 2018 | [2016, 2018] | 1285 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 266 | 1285 | Swiss Ellipse I | Magadino | New construction to connect the Avegno - Gorduno line to the Magadino substation | 3 | Investment on time |  | 01/01/2019 | 2019 | 1 |  | 0 |  |  | Overhead Line | AC |  |  |  |  | 266 | 1285 | Swiss Ellipse I | Magadino | 2 | Delayed | reschedule | 2024 | 2024 | 1 |  | Magadino | Magadino | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2024 | 5 | 8 |  | Magadino | Magadino | 46.1474 | 8.8559 | 46.1474 | 8.8559
134 | 2016 | 2020 | [2016, 2018, 2020] | 1286 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 266 | 1286 | Swiss Ellipse I | Chippis - Lavorgo | Reinforcement by new construction of a 380 kV route including a new 380/220 kV transformer in Mörel | 3 | Investment on time |  | 01/01/2024 | 2024 | 1 |  | 0 | Chippis | Lavorgo | Overhead Line | AC |  | 380 |  |  | 266 | 1286 | Swiss Ellipse I | Chippis - Lavorgo | 3 | Investment on time |  | 2024 | 2024 | 1 |  | Chippis | Lavorgo | Overhead Line | AC | 380 | 266 | 1286 | Swiss Ellipse I | Chippis - Lavorgo | Reinforcement by construction of a new 380 kV route including a new 380/220 kV transformer in Mörel | 3 | Delayed | Permitting Procedure | 2029 | 2029 | 1 | SWISSGRID |  | 1 | 0 | Chippis | Lavorgo | ACTransmissionLine | AC | 124 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2024 | 2029 | 5 | 13 | CHE | Chippis | Lavorgo | 46.2805 | 7.5406 | 46.4418 | 8.8404
135 | 2016 | 2020 | [2016, 2018, 2020] | 1287 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 264 | 1287 | Swiss Roof I | Bassecourt - Mühleberg | Optimization of the existing route by voltage conversion to 380 kV including a new 380/220 kV transformer in Mühleberg. | 3 | Investment on time |  | 01/01/2025 | 2025 | 1 |  | 0 | Bassecourt | Mühleberg | Overhead Line | AC |  | 380 |  |  | 264 | 1287 | Swiss Roof I | Bassecourt - Mühleberg | 3 | Investment on time |  | 2025 | 2025 | 1 |  | Bassecourt | Mühleberg | Overhead Line | AC | 380 | 264 | 1287 | Swiss Roof I | Bassecourt - Mühleberg | Reinforcement of the existing route by voltage conversion to 380 kV including a new 380/220 kV transformer in Mühleberg. | 3 | Delayed | Permitting Procedure | 2027 | 2027 | 1 | SWISSGRID |  | 0 | 0 | Bassecourt | Mühleberg | ACTransmissionLine | AC | 45.4 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2027 | 2 | 11 | CHE | Bassecourt | Mühleberg | 47.338 | 7.24 | 46.9534 | 7.2616
136 | 2016 | 2020 | [2016, 2018, 2020] | 1288 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 264 | 1288 | Swiss Roof I | Mettlen - Ulrichen | Reinforcement of the existing 220 kV line to 380 kV | 3 | Investment on time |  | 01/01/2025 | 2025 | 1 |  | 0 | Mettlen | Ulrichen | Overhead Line | AC |  | 220 |  |  | 264 | 1288 | Swiss Roof I | Mettlen - Ulrichen | 3 | Delayed | preliminary clarifications | 2030 | 2030 | 1 |  | Mettlen | Ulrichen | Overhead Line | AC | 380 | 264 | 1288 | Swiss Roof I | Mettlen - Ulrichen | Reinforcement of the existing 220 kV line to 380 kV | 3 | Delayed | preliminary clarifications | 2035 | 2035 | 1 | SWISSGRID |  | 1 | 0 | Mettlen | Ulrichen | ACTransmissionLine | AC | 87.1 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2035 | 10 | 19 | CHE | Mettlen | Ulrichen | 47.5311 | 9.1236 | 46.5066 | 8.305
137 | 2016 | 2016 | [2016] | 1289 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 265 | 1289 | Swiss Ellipse II | Lago Bianco connection | new 380 kV substation in Golbia | 2 | Investment on time |  | 01/01/2029 | 2029 | 1 |  | 0 |  |  | Overhead Line | AC |  | 380 | [6 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2029 | 2029 | 0 | 13 | CHE
138 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 129 | Cancelled | 129 | Upgrade of the existing 65km double circuit 220kV OHL to 400kV. | 3 | 2015 | 2015 | 1 | Beznau (CH) | Mettlen (CH) | 90 | 90. 129 | Upgrade of the existing 65km double circuit 220kV OHL to 400kV. | 3 | Progresses as planned | 2015 | 2015 | 1 | Beznau (CH) | Mettlen (CH) | 90. 129 | 90. 129 | Upgrade of the existing 65km double circuit 220kV OHL to 400kV. | 3 | Long permitting procedure (comprising several phases). In this case, Federal Court decision for partial cabling. | 2020 | 2020 | 1 | Beznau (CH) | Mettlen (CH) | 90 | 129 | Swiss Roof | Upgrade of the existing 65km double circuit 220kV OHL to 400kV. | 3 | Delayed | long permitting procedure (comprising several phases). In this case, Federal Court decision for partial cabling. | 2020 | 2020 | 1 | Beznau (CH) | Mettlen (CH) | 129 | Upgrade of the existing 65km double circuit 220kV OHL to 400kV. | 3 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Beznau (CH) | Mettlen (CH) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2020 | 5 | 10 | CHE | Beznau | Mettlen | 47.5542 | 8.2297 | 47.5311 | 9.1236
139 | 2016 | 2020 | [2016, 2018, 2020] | 1290 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 265 | 1290 | Swiss Ellipse II | Magadino - Ulrichen | reinforcement of the infrastructure in canton Tessin | 2 | Investment on time |  | 01/01/2029 | 2029 | 1 |  | 0 |  |  | Overhead Line | AC |  | 380 |  |  | 265 | 1290 | Tessin | Magadino - Ulrichen | 2 | Delayed | reschedule | 2035 | 2035 | 1 | Swissgrid | Magadino | Ulrichen | Overhead Line | AC | 220 | 265 | 1290 | Tessin | Magadino - Ulrichen | Replacement and extension of the lines in Western part of canton Tessin. The details are given in the link that is included in the project sheet: https://www.swissgrid.ch/content/swissgrid/en/home/projects/project-overview/allacqua-magadino.html | 2 | Investment on time |  | 2035 | 2035 | 1 | SWISSGRID |  | 1 | 0 | Magadino | Ulrichen | ACTransmissionLine | AC | 1 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2029 | 2035 | 6 | 19 | CHE | Magadino | Ulrichen | 46.1474 | 8.8559 | 46.5066 | 8.305
140 | 2016 | 2016 | [2016] | 1291 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 22 | 1291 | Lake Geneva West | Foretaille - Verbois | reinforcement of the existing 220 kV double line | 3 | New Investment | Investment Foretaille - Verbois 1. Improves the security of supply in the area of Geneva 2. Ensures that the CH-FR GTC can be further increased once the investment Génissiat-Verbois has been realised | 01/01/2023 | 2023 | 1 |  | 0 | Foretaille (CH) | Verbois (CH) | Overhead Line | AC |  | 220 | [6 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | CHE | Foretaille | Verbois | 46.2444 | 6.1342 | 46.193 | 6.0289
141 | 2016 | 2016 | [2016] | 1297 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 282 | 1297 | ASEI: Abengoa Southern Europe Interconnection | ASEI: Abengoa Southern Europe Interconnection | ASEI Projct consists on a subsea multiterminal (with Voltage Source Converters) High Voltage Direct Current cable with 2,000 Megawatt of power grid transfer capability | 1 | New Investment |  | 2025 | 2025 | 1 |  | 0 | Vandellos | La Spezia |  | DC | [8 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 9 | ESP;FRA;ITA | Vandellos | La Spezia | 40.9985 | 0.84935 | 44.2384 | 9.6912
142 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 130 | Cancelled | 130 | Installation of the second circuit on existing towers of a double-circuit 400kV OHL (50km). | 2 | 2015 | 2015 | 1 | La Punt (CH) | Pradella / Ova Spin (CH) | 90 | 90. 130 | Installation of the second circuit on existing towers of a double-circuit 400kV OHL (50km). | 2 | Delays due to authorization process. | 2017 | 2017 | 1 | La Punt (CH) | Pradella / Ova Spin (CH) | 90. 130 | 90. 130 | Installation of the second circuit on existing towers of a double-circuit 400kV OHL (50km). | 2 |  | 2017 | 2017 | 1 | La Punt (CH) | Pradella / Ova Spin (CH) | 90 | 130 | Swiss Roof | Installation of the second circuit on existing towers of a double-circuit 400kV OHL (50km). | 2 | Investment on time | none | 2017 | 2017 | 1 | La Punt (CH) | Pradella / Ova Spin (CH) | 130 | Installation of the second circuit on existing towers of a double-circuit 400kV OHL (50km). | 2 | Investment on time | Progressed as planned | 2017 | 2017 | 1 | La Punt (CH) | Pradella / Ova Spin (CH) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2017 | 2 | 7 | CHE | La Punt | Pradella Ova Spin | 46.5789 | 9.9254 | 46.7458 | 10.2373
143 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 133 | Cancelled | 133 | Upgrade of the existing 180km double circuit 220kV OHL into 400kV. | 1 | 2020 | 2020 | 1 | Bonaduz (CH) | Mettlen (CH) | 90 | 90. 133 | Upgrade of the existing 180km double circuit 220kV OHL into 400kV. | 1 | Progresses as planned | 2020 | 2020 | 1 | Bonaduz (CH) | Mettlen (CH) | 90. 133 | 90. 133 | Upgrade of the existing 180km double circuit 220kV OHL into 400kV. | 1 |  | 2020 | 2020 | 1 | Bonaduz (CH) | Mettlen (CH) | 90 | 133 | Swiss Roof | Upgrade of the existing 180km double circuit 220kV OHL into 400kV. | 1 | Investment on time | none | 2020 | 2020 | 1 | Bonaduz (CH) | Mettlen (CH) | 133 | Upgrade of the existing 180km double circuit 220kV OHL into 400kV. | 1 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Bonaduz (CH) | Mettlen (CH) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 10 | CHE | Bonaduz | Mettlen | 46.8113 | 9.3984 | 47.5311 | 9.1236
144 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 134 | Cancelled | 134 | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 140km. | 3 | 2012 | 2012 | 1 | Bassecourt (CH) | Romanel (CH) | 90 | 90. 134 | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 140km. | 3 | Delays due to authorization process. | 2015 | 2015 | 1 | Bassecourt (CH) | Romanel (CH) | 90. 134 | 90. 134 | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV lines. Total length: 140km. | 3 | Long permitting procedure (comprising several phases) | 2020 | 2020 | 1 | Bassecourt (CH) | Romanel (CH) | 90 | 134 | Swiss Roof | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV lines; total length: 140km. Construction of a new 400/220 kV substation in Mühleberg (= former investment 132 'Mühleberg Substation') | 3 | Delayed | lines: long permitting procedure (comprising several phases)- Mühleberg substation: under construction | 2020 | 2020 | 1 | Bassecourt (CH) | Romanel (CH) | 134 | Construction of different new 400kV line sections and voltage upgrade of existing 225kV lines into 400kV lines Construction of a new 400/220 kV substation in Mühleberg (= former investment 132 'Mühleberg Substation') | 3 | Investment on time | the part between Mühleberg and Romanel is not part of the grid development plan | 2020 | 2020 | 1 | Bassecourt (CH) | Romanel (CH) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2012 | 2020 | 8 | 10 | CHE | Bassecourt | Romanel | 47.338 | 7.24 | 46.5564 | 6.5101
145 | 2016 | 2018 | [2016, 2018] | 1356 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 294 | 1356 | Maali | Maali | ​A subsea HVDC interconnector between Shetland and Norway | 1 |  | Viking Windfarm Shetland and HVDC to Scotland | 2023 | 2023 | 1 |  | 0 | Kergord Shetland tba | tba near Bergen-Mongstad or Karsto- Blafalli |  | DC |  |  |  |  | 294 | 1356 | Maali | Maali | 1 | Delayed | Maali was listed and recommend for inclusion in the PCI list at the TEN-E regional groups meeting in Brussels 27th June 2017, however it was not supported by all member states in a closed meeting on 13th July due to a proposal to connect Shetland to Scotland with a 60MW distribution cable which would not have supported Maali. The 60MW connection was subsequently rejected by the GB Regulator Ofgem on 30th November 2018 opening the way for the planned >=600MW connection to Scotland and facilitating the connection of Maali. | 2025 | 2025 | 1 | Element Power | Kergord Shetland | tba e.g. Mongstad, Kollsnes, Fana | Subsea Cable | DC | 320 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2025 | 2 | 9 | NOR | Kergord Shetland | Tba E.G. Mongstad Kollsnes Fana
146 | 2014 | 2016 | [2014, 2015, 2016] | 136 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 90 | 136 | Swiss Roof | 380 kV Rüthi – Meiningen and 380 kV Meiningen - Border Area AT-DE | 2 | Investment on time | investment 136 now comprises the cross-border part of former investment 136, and investment 1099 is the Swiss part of former investment 136. | 2022 | 2022 | 1 | Border area (DE-AT) | Rüthi (CH) | 136 | 380 kV Rüthi – Meiningen and 380 kV Meiningen - Border Area AT-DE | 1 | Investment on time | Progressed as planned | 2022 | 2022 | 1 | Border area (DE-AT) | Rüthi (CH) | 198 | 136 | Area of Lake Constance | DE-AT-CH connection | 380 kV Rüthi – Meiningen and 380 kV Meiningen - Border Area AT-DE | 1 | Delayed | Due to the changed market and grid situation in this area, there is a need for an update of the current study and its findings. | 1/ 1/ 2023 | 2023 | 1 |  | 1 | Border area (DE-AT) | Rüthi (CH) | Overhead Line | AC | 1200 | 380 | 45 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2023 | 1 | 9 | CHE | Border Area | Rüthi |  |  | 47.2558 | 9.7003
147 | 2014 | 2016 | [2014, 2015, 2016] | 136 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 90 | 136 | Swiss Roof | 380 kV Rüthi – Meiningen and 380 kV Meiningen - Border Area AT-DE | 2 | Investment on time | investment 136 now comprises the cross-border part of former investment 136, and investment 1099 is the Swiss part of former investment 136. | 2022 | 2022 | 1 | Border area (DE-AT) | Rüthi (CH) | 136 | 380 kV Rüthi – Meiningen and 380 kV Meiningen - Border Area AT-DE |  | Investment on time |  | 2022 | 2022 | 1 | Border area (DE-AT) | Rüthi (CH) | 198 | 136 | Area of Lake Constance | DE-AT-CH connection | 380 kV Rüthi – Meiningen and 380 kV Meiningen - Border Area AT-DE | 1 | Delayed | Due to the changed market and grid situation in this area, there is a need for an update of the current study and its findings. | 1/ 1/ 2023 | 2023 | 1 |  | 1 | Border area (DE-AT) | Rüthi (CH) | Overhead Line | AC | 1200 | 380 | 45 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2023 | 1 | 9 | CHE | Border Area | Rüthi |  |  | 47.2558 | 9.7003
148 | 2014 | 2016 | [2014, 2015, 2016] | 136 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 198 | 136 | Area of Lake Constance | 380 kV Rüthi – Meiningen and 380 kV Meiningen - Border Area AT-DE | 2 | Investment on time | investment 136 now comprises the cross-border part of former investment 136, and investment 1099 is the Swiss part of former investment 136. | 2022 | 2022 | 1 | Border area (DE-AT) | Rüthi (CH) | 136 | 380 kV Rüthi – Meiningen and 380 kV Meiningen - Border Area AT-DE | 1 | Investment on time | Progressed as planned | 2022 | 2022 | 1 | Border area (DE-AT) | Rüthi (CH) | 198 | 136 | Area of Lake Constance | DE-AT-CH connection | 380 kV Rüthi – Meiningen and 380 kV Meiningen - Border Area AT-DE | 1 | Delayed | Due to the changed market and grid situation in this area, there is a need for an update of the current study and its findings. | 1/ 1/ 2023 | 2023 | 1 |  | 1 | Border area (DE-AT) | Rüthi (CH) | Overhead Line | AC | 1200 | 380 | 45 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2023 | 1 | 9 | CHE | Border Area | Rüthi |  |  | 47.2558 | 9.7003
149 | 2014 | 2016 | [2014, 2015, 2016] | 136 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 198 | 136 | Area of Lake Constance | 380 kV Rüthi – Meiningen and 380 kV Meiningen - Border Area AT-DE | 2 | Investment on time | investment 136 now comprises the cross-border part of former investment 136, and investment 1099 is the Swiss part of former investment 136. | 2022 | 2022 | 1 | Border area (DE-AT) | Rüthi (CH) | 136 | 380 kV Rüthi – Meiningen and 380 kV Meiningen - Border Area AT-DE |  | Investment on time |  | 2022 | 2022 | 1 | Border area (DE-AT) | Rüthi (CH) | 198 | 136 | Area of Lake Constance | DE-AT-CH connection | 380 kV Rüthi – Meiningen and 380 kV Meiningen - Border Area AT-DE | 1 | Delayed | Due to the changed market and grid situation in this area, there is a need for an update of the current study and its findings. | 1/ 1/ 2023 | 2023 | 1 |  | 1 | Border area (DE-AT) | Rüthi (CH) | Overhead Line | AC | 1200 | 380 | 45 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2023 | 1 | 9 | CHE | Border Area | Rüthi |  |  | 47.2558 | 9.7003
150 | 2016 | 2016 | [2016] | 1369 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 290 | 1369 | Greenwire North | Greenwire North | ​HVAC link 1 from windfarm collector substation to HVDC hub​ | 2 | Delayed | Awaiting international contracts for renewable energy | 2023 | 2023 | 1 |  | 0 | Greenwire North Hub | Woodlands or new Midlands 400/220V substations tba | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | GBR;IRL | Greenwire North | Woodlands Or New Midlands V Substations Tba
151 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1378 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 283 | 1378 | TuNur | TuNur | ​TuNur is aimed to connect to the European network a Concentrated Solar Power plant with storage to be located in Rejim Maatoug, Kebili, Tunisia. The connection point to the ENTSO-E network is located in Montalto di Castro, Lazio, Italy. The transmission project will comprise +/- 500kV DC submarine cables from the Tunisian Northern coast to Montalto di Castro, DC overhead lines in Tunisia from the power plant to the shoring point, and HVDC converter stations at the terminal points.​ | 3 |  |  | 2020 | 2020 | 1 |  | 0 | Rejim Maatoug 400kV | Montalto 400kV |  | DC |  |  |  |  | 283 | 1378 | TuNur | TuNur DC | 3 | Delayed | The Tunisian regulatory framework has been settled only recently and this delayed the overall permitting process | 2025 | 2025 | 1 | TuNur Limited | Rejim Maatoug (TN) VSC HVDC - 400 kV AC +/- 500 kV DC – 2x 1GW | Montalto di Castro (IT) VSC HVDC - 400 kV AC +/- 500 kV DC – 2x 1GW | Subsea Cable | DC | 500 | 283 | 1378 | TuNur | TuNur DC | TuNur DC consists in a +/- 500 kV DC overhead line in Tunisia from the CSP plant to the shoring point, submarine cables from the Tunisian Northern coast to Montalto di Castro in Italy and VSC HVDC converter stations at both terminal points. | 1 | Delayed | The Tunisian regulatory framework has been settled only recently and this delayed the overall permitting process. | 2026 | 2026 | 1 | TuNur Ltd |  | 1 | 1 | Rejim Maatoug (TN) VSC HVDC - 400 kV AC +/- 500 kV DC – 2x 1GW | Montalto di Castro (IT) VSC HVDC - 400 kV AC +/- 500 kV DC – 2x 1GW | OffshoreDCTransmissionCable | DC | 1270 | New | 283 | 1378 | TuNur Italy | TuNur DC | The HVDC transmission architecture is based on two independent bipolar +/-525 kV systems of 1GW. The HVDC converter is based on VSC (Voltage Source Converter) technology, providing high reliability and efficiency of the transmission system. TuNur DC will consist of two independent bipolar +/-525 kV systems of 1GW. Each bipolar system will consist of a DC overhead line in Tunisia spanning from the power plant to the shoring point, submarine cable from the Tunisian Northern coast to Montalto di Castro, and VSC HVDC converter stations at both terminal points. | 1 | Delayed | The Tunisian regulatory framework has been settled only recently and this delayed the overall permitting process. | 12-2028 | 2028 | 1 | TuNur Ltd |  | 1 | 1 | Rejim Maatoug (TUN) VSC HVDC - +/- 500 kV DC – 2x 1GW | Montalto di Castro (ITA) VSC HVDC - +/- 500 kV DC - 400 kV AC– 2x 1GW | OffshoreDCTransmissionCable | DC | 2000 | 525 | 1308 | New | 283 | 1378 | TuNur Italy | TuNur DC | The HVDC transmission architecture is based on two independent bipolar +/-525 kV systems of 1GW. The HVDC converter is based on VSC (Voltage Source Converter) technology, providing high reliability and efficiency of the transmission system. TuNur DC will consist of two independent bipolar +/-525 kV systems of 1GW. Each bipolar system will consist of a DC overhead line in Tunisia spanning from the power plant to the shoring point, submarine cable from the Tunisian Northern coast to Montalto di Castro, and VSC HVDC converter stations at both terminal points. | 1 | Delayed | The project timeline has been delayed due to the evolution of the regulatory frameworks and supply chain constraints (specifically HVDC cable supply). | 02-2034 | 2034 | 1 | TuNur Ltd |  | 1 | 1 | Rejim Maatoug (TUN) VSC HVDC - +/- 500 kV DC – 2x 1GW | Montalto di Castro (ITA) VSC HVDC - +/- 500 kV DC - 400 kV AC – 2x 1GW | OffshoreDCTransmissionCable | DC | 2000 | 525 | 1308 | New | 283 | 1378 | TuNur Italy | TuNur DC | The HVDC transmission architecture is based on a single bipolar +/-525 kV system of 2GW. The HVDC converter is based on VSC (Voltage Source Converter) technology, providing high reliability and efficiency of the transmission system. TuNur DC will consist of one bipolar +/-525 kV system of 2GW. The bipolar system will consist of a DC overhead line in Tunisia spanning from the power plant to the shoring point, a 660km submarine cable from the Tunisian Northern coast to Montalto di Castro, and VSC HVDC converter stations at both terminal points. | 1 |  | 02-2034 | 2034 | 1 | TuNur Ltd | 1 | XX | XX | New | 2020 | 2034 | 14 | 18 | ITA;TUN | Rejim Maatoug | Montalto Di Castro | 33.32 | 8.033 | 42.3515 | 11.6073
152 | 2016 | 2016 | [2016] | 1379 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 281 | 1379 | ANAI: Abengoa Northern Atlantic Interconnection | ANAI: Abengoa Northern Atlantic Interconnection | ANAI project consists on a subsea multiterminal (with Voltage Source Converters) High Voltage Direct Current cable with 2,000 Megawatt of power grid transfer capability. | 1 |  | Under evaluation by ENTSO-E | 2026 | 2026 | 1 |  | 0 | Soto de Ribera | Exeter |  | DC | [8 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2026 | 2026 | 0 | 10 | ESP;FRA;GBR | Soto De Ribera | Exeter | 43.3088 | -5.8765 | 48.1275 | -1.6565
153 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1380 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 210 | 1380 | Wurmlach (AT) - Somplago (IT) Interconnection | Wurmlach (AT) - Somplago (IT) Interconnection | Somplago - Wurmlach interconnection is a third party cross-border electrical line promoted by Alpe Adria Energia SpA​. The project concerns a 220kV a.c. merchant line, 300 MVA from Somplago substation to Wurmlach substation, including a 300MW Phase Shift​ Transformer, located in Austria .​ | 3 | Delayed |  | 2018 | 2018 | 1 |  | 0 | SOMPLAGO | WURMLACH |  | AC |  | 220 |  |  | 210 | 1380 | Wurmlach (AT) - Somplago (IT) interconnection | Wurmlach (AT) - Somplago (IT) interconnection | 3 | Delayed | PERMITTING - Delays due to environmental problems (including re-routing) | 2021 | 2021 | 1 | Alpe Adria Energia Srl | SOMPLAGO | WURMLACH | Underground Cable | AC | 220 | 210 | 1380 | Wurmlach (AT) - Somplago (IT) interconnection | Wurmlach (AT) - Somplago (IT) interconnection | "Wurmlach (AT) – Somplago (IT) Interconnection is a cross-border electrical line promoted by Alpe Adria Energia Srl. The project concerns a 220kV a.c. merchant line, 300 MW thermal capacity from Somplago substation to new Wurmlach substation, including a Phase Shifter Transformer located in Austria" | 3 | Delayed | PERMITTING - Delays due to environmental problems (including re-routing) and delay of EIA assessment due to change of EIA Commission (2019) | 2023 | 2023 | 1 | Alpe Adria Energia Srl | PCI 3.4 | 1 | 1 | SOMPLAGO | WURMLACH | ACTransmissionLine | AC | 51 | New | 210 | 1380 | Würmlach (AT) - Somplago (IT) interconnection | Würmlach (AT) - Somplago (IT) interconnection | "Wurmlach (AT) – Somplago (IT) Interconnection is a cross-border electrical line promoted by Alpe Adria Energia Srl. The project concerns a 220kV a.c. merchant line, 300 MW thermal capacity from Somplago substation to new Wurmlach substation, including a Phase Shifter Transformer located in Austria" | 3 | Delayed | PERMITTING - Delays due to environmental problems (including re-routing) and delay of EIA assessment due to change of EIA Commission (2019) | 01-2026 | 2026 | 1 | Alpe Adria Energia Srl |  | 1 | 1 | SOMPLAGO | WURMLACH | ACTransmissionLine | AC | 0 | 220 | 51 | New | 210 | 1380 | Würmlach (AT) - Somplago (IT) interconnection | Würmlach (AT) - Somplago (IT) interconnection | "Wurmlach (AT) – Somplago (IT) Interconnection is a cross-border electrical line promoted by Alpe Adria Energia Srl. The project concerns a 220kV a.c. merchant line, 300 MW thermal capacity from Somplago substation to new Wurmlach substation, including a Phase Shifter Transformer located in Austria" | 3 | Delayed | PERMITTING - Due to the timing of the release of the exemption decision by the EC as preparatory to the start of the grid connection process in Austria. Furthermore, the commissioning of the line is linked to the construction of the new Wurmlach power station by the TSO and expected in 2029. | 09-2029 | 2029 | 1 | Alpe Adria Energia Srl | 2.4 | 1 | 1 | SOMPLAGO | WURMLACH | ACTransmissionLine | AC | 0 | 220 | 51 | New | 210 | 1380 | Würmlach (AT) - Somplago (IT) interconnection | Würmlach (AT) - Somplago (IT) interconnection | "Wurmlach (AT) – Somplago (IT) Interconnection is a cross-border electrical line promoted by Alpe Adria Energia Srl. The project concerns a 220kV a.c. merchant line, 300 MW thermal capacity from Somplago substation to new Wurmlach substation, including a Phase Shifter Transformer located in Austria" |  |  | 09-2029 | 2029 | 1 | Alpe Adria Energia Srl | 1 | XX | XX | New | 2018 | 2029 | 11 | 13 | AUT;ITA | Somplago | Wurmlach | 46.3485 | 13.0679 | 46.6575 | 13.0154
154 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1381 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 247 | 1381 | AQUIND Interconnector | AQUIND Interconnector | ​AQUIND Interconnector is being promoted by Aquind Limited, a UK-based company. The project is a high capacity double-circuit interconnector with the capacity of up to 2000MW between the AC transmission networks in France and the United Kingdom. To maintain the asynchronous nature of these two networks, the interconnector will use the DC technology.The interconnector will land and connect to the UK grid in the South East of England in Portsmouth area. The connection point in France will be on the Normandy Coast.​ Particular substations on both sides are to be determined. The DC transmission voltage is still to be confirmed, but is anticipated to be in the range between ±320kV and ±563kV, depending upon the final configuration of the scheme. Underground cables of 20 – 30km will link the French converter station to a transition joint on the coast at a point south-west of Le Havre. Submarine cables of 170 – 190km will run across La Manche (the English Channel) to the south coast of the United Kingdom. Underground cables of 15 – 25km will run from the transition joint at the coast landing point to the British converter station. Desktop studies of the coast landing points and the submarine route have been performed, but the final cable routing will be dependent on detailed land and marine surveys. The promoter has completed the project definition stage and has commenced the development stage of the project consisting of more detailed engineering and other studies, supply chain selection and the scope of work definition, obtaining of various permits, authorisations, licenses and connections agreements. | 2 | New Investment | Planning status (though the project is simultaneously progressing some elements of the design and permitting activities) | 2020 | 2020 | 1 |  | 0 | Lovedean (UK) | Le Havre (FR) |  | DC |  |  |  |  | 247 | 1381 | AQUIND Interconnector | AQUIND Interconnector | 3 | Delayed | The project programme was delayed comparing to the initial application for TYNDP 2016 due to two main factors. Firstly, the studies performed in conjunction with National Grid in order to determine a connection location in the UK, which commenced at the time of the application for TYNDP 2016, took longer time than expected. The studies were successfully completed in the late 2015. Secondly, two connection points were initially suggested in France - Le Havre and Barnabos. Further studies were required to determine the point of connection with the least impact on the national transmission system and greater feasibility of implementation. As an outcome, AQUIND accepted the PTF from RTE in respect of Barnabos substation. The project promoter commenced the studies with National Grid and RTE approximately at the same time as applying for TYNDP 2016 and at that stage such circumstances were not foreseeable. | 2022 | 2022 | 1 | Aquind Limited | Lovedean (GB) | Barnabos (FR) | Subsea Cable | DC | 320 | 247 | 1381 | AQUIND Interconnector | AQUIND Interconnector | AQUIND Interconnector is a proposed High Voltage Direct Current (HVDC) subsea and underground electric power transmission link between Great Britain (Lovedean substation, Hampshire) and France (Barnabos substation, Seine-Maritime) with a net transmission capacity of 2,000 MW. The Interconnector is designed as two parallel monopole 1000 MW circuits employing Voltage Source Converter technology. | 3 | Delayed | In 2018 UK Government, in accordance with the Planning Act 2008, designated AQUIND Interconnector as a Nationally Significant Infrastructure Project. This designation enables AQUIND Interconnector to apply for a Development Consent Order that would include all or nearly all permits and conditions necessary to start construction. Due to the "front-loading" approach and extremely robust evaluation and consultation requirements, which might have impact over more than one constituency, the DCO has been specifically designed to enable significant infrastructure developments. However, this process also takes longer than conventional planning application under the Town and Country Planning Act. Therefore commissioning of AQUIND was postponed by approximately a year from the date declared in the TYNDP 2018. The application for the DCO has been submitted on 14 November 2019. | 2023 | 2023 | 1 | Aquind Limited |  | 1 | 1 | Lovedean (GB) | Barnabos (FR) | OffshoreDCTransmissionCable | DC | 240 | New | 247 | 1381 | AQUIND Interconnector | AQUIND Interconnector | AQUIND Interconnector is a proposed High Voltage Direct Current (HVDC) subsea and underground electric power transmission link between Great Britain (Lovedean substation, Hampshire) and France (Barnabos substation, Seine-Maritime) with a net transmission capacity of 2,000 MW. The Interconnector is designed as two parallel monopole 1000 MW circuits employing Voltage Source Converter technology. | 3 | Delayed | Since TYNDP 2020, the situation with COVID and ongoing negotiations on Brexit and the Trade and Cooperation Agreement resulted in a delay with permitting and regulatory procedures in GB and France. Respectively commissioning of the project moved to 2026. | 09-2026 | 2026 | 1 | Aquind Limited (UK) and AQUIND SAS (France, 100% subsidiary of Aquind Limited) |  | 1 | 1 | Lovedean (GB) | Barnabos (FR) | OffshoreDCTransmissionCable | DC | 2075 | 320 | 240 | New | 247 | 1381 | AQUIND Interconnector | AQUIND Interconnector | AQUIND Interconnector is a proposed High Voltage Direct Current (HVDC) subsea and underground electric power transmission link between Great Britain (Lovedean substation, Hampshire) and France (Barnabos substation, Seine-Maritime) with a net transmission capacity of 2,000 MW. The Interconnector is designed as two parallel monopole 1000 MW circuits employing Voltage Source Converter technology. | 3 | Delayed | Since TYNDP 2022, ongoing delay in implementation of energy chapter of the Trade and Cooperation Agreement together with the delay of the third Cap&Floor window by Ofgem resulted in a delay with permitting and regulatory procedures in GB and France. Respectively commissioning of the project moved to 2028. | 09-2028 | 2028 | 1 | Aquind Limited (UK) and AQUIND SAS (France, 100% subsidiary of Aquind Limited) |  | 1 | 1 | Lovedean (GB) | Barnabos (FR) | OffshoreDCTransmissionCable | DC | 2075 | 320 | 240 | New | 247 | 1381 | AQUIND Interconnector | AQUIND Interconnector | AQUIND Interconnector is a proposed High Voltage Direct Current (HVDC) subsea and underground electric power transmission link between Great Britain (Lovedean substation, Hampshire) and France (Barnabos substation, Seine-Maritime) with a net transmission capacity of 2,000 MW. The Interconnector is designed as two parallel monopole 1000 MW circuits employing Voltage Source Converter technology. |  |  | 12-2030 | 2030 | 1 | Aquind Limited (UK) and AQUIND SAS (France, 100% subsidiary of Aquind Limited) | 1 | XX | XX | New | 2020 | 2030 | 10 | 14 | FRA;GBR | Lovedean | Barnabos | 50.9083 | -1.0226 | 49.6599 | 0.9888
155 | 2016 | 2022 | [2016, 2018, 2020, 2022] | 1382 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 190 | 1382 | NorthConnect | NorthConnect | ​​​​A 650 km long subsea interconnector between Norway and Scotland is planned to be realized in 2022. The main driver for the project is to integrate the hydro-based Norwegian system with the thermal/nuclear/wind-based British system. The interconnector will improve security of supply both in Norway in dry years and in Great Britain in periods with negative power balance (low wind, low solar, high demand etc.). Additionally the interconnector will be positive both for the European market integration, for facilitating renewable energy and also for preparing for a power system with lower CO2-emissions. The interconnector is planned to be a 500 kV 1400 MW HVDC subsea interconnector between western Norway and eastern Scotland.​ | 3 | Delayed |  | 2022 | 2022 | 1 |  | 0 | Sima | Peterhead |  | DC |  | 500 |  |  | 190 | 1382 | NorthConnect | NorthConnect | 1 |  |  | 2022 | 2022 | 1 | NorthConnect KS | Sima | Peterhead | Subsea Cable | DC | 500 | 190 | 1382 | NorthConnect | NorthConnect | A 665 km long subsea interconnector between Norway and Scotland is planned to be realized in 2024. The main driver for the project is to integrate the hydro-based Norwegian system with the thermal/nuclear/wind-based British system. The interconnector will improve security of supply both in Norway in dry years and in Great Britain in periods with negative power balance (low wind, low solar, high demand etc.). Additionally the interconnector will be positive both for the European market integration, for facilitating renewable energy and also for preparing for a power system with lower CO2-emissions. The interconnector is planned to be a 500 kV 1400 MW HVDC subsea interconnector between western Norway and eastern Scotland. | 3 | Delayed | Permitting process in Norway | 2024 | 2024 | 1 | NorthConnect | 1.10.2 | 1 | 1 | Sima | Peterhead | OffshoreDCTransmissionCable | DC | 665 | New | 190 | 1382 | NorthConnect | NorthConnect | A 665 km long subsea interconnector between Norway and Scotland is planned to be realized in 2024. The main driver for the project is to integrate the hydro-based Norwegian system with the thermal/nuclear/wind-based British system. The interconnector will improve security of supply both in Norway in dry years and in Great Britain in periods with negative power balance (low wind, low solar, high demand etc.). Additionally the interconnector will be positive both for the European market integration, for facilitating renewable energy and also for preparing for a power system with lower CO2-emissions. The interconnector is planned to be a 500 kV 1400 MW HVDC subsea interconnector between western Norway and eastern Scotland. | 1 | Delayed | Permitting process in Norway | 12-2027 | 2027 | 1 | NorthConnect |  | 1 | 1 | Sima | Peterhead | OffshoreDCTransmissionCable | DC | 1400 | 500 | 665 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2027 | 5 | 11 | GBR;NOR | Sima | Peterhead |  |  | 57.5053 | -1.7813
156 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1383 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 285 | 1383 | GridLink | GridLink | ​UK-France, 1.5GW HVDC Interconnector | 2 | New Investment |  | 2021 | 2021 | 1 |  | 0 | Kemsley (Sittingbourne, UK) | Warande (Gravelines, France) |  | DC |  |  |  |  | 285 | 1383 | GridLink | GridLink | 2 |  |  | 2022 | 2022 | 1 | iCON Infrastructure LLP | Kingsnorth (UK) | "Warande (Gravelines, France)" | Subsea Cable | DC | 0 | 285 | 1383 | GridLink | GridLink | UK-France, 1.5GW HVDC Interconnector | 2 |  |  | 2022 | 2022 | 1 | Elan Energy Ltd National Grid RTE Nationalgrid ESO | 1.7.5 | 1 | 1 | Kingsnorth (UK) | Warande (Gravelines, France) | OffshoreDCTransmissionCable | DC | 156 | New | 285 | 1383 | GridLink | GridLink | UK-France, 1.4GW HVDC Interconnector | 3 | Delayed | Brexit - investment request submitted but declared void on 24 December 2020 as there were no provisions in the FTA which would allow the French & UK regulators to continue to have competence to decide the investment request. A new investment request was submitted solely to CRE in March 2021. | 12-2025 | 2025 | 1 | iCON Infrastructure |  | 1 | 1 | Kingsnorth (UK) | Warande (Gravelines, France) | OffshoreDCTransmissionCable | DC | 1400 | 525 | 158 | New | 285 | 1383 | GridLink | GridLink | UK-France, 1.4GW HVDC Interconnector | 3 | Delayed | Brexit - investment request submitted but declared void on 24 December 2020 as there were no provisions in the FTA which would allow the French & UK regulators to continue to have competence to decide the investment request. A new investment request was submitted solely to CRE in March 2021. | 12-2025 | 2025 | 1 | iCON Infrastructure |  | 1 | 1 | Kingsnorth (UK) | Warande (Gravelines, France) | OffshoreDCTransmissionCable | DC | 1400 | 525 | 158 | New | 285 | 1383 | GridLink | GridLink | 1.25 GW HVDC Interconnector between the UK and France |  |  | 12-2030 | 2030 | 1 | iCON Infrastructure | 1 | XX | XX | New | 2021 | 2030 | 9 | 14 | FRA;GBR | Kingsnorth | Warande | 51.1166 | 0.86081 | 50.9483 | 2.1732
157 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1384 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 250 | 1384 | Merchant line "Castasegna (CH) - Mese (IT)" | Merchant line "Castasegna (CH) - Mese (IT)" | The planned Transmission project is a merchant line on the swiss-italian border between Castasegna (CH) and Mese (IT). The planned Cable connection in 220 kV AC has a length of around 14 km, 13.5 of witch in Italy. In connection with the realisation of the project a Rationalisation of the 380 and 132 kV Grid in the region Mese (Provincia di Sondrio) is planned. The expected NTC increase is around 200 MW. The main Project elements are (merchant line):220 kV Connection to the Swiss HVG in Castasegna220 kV Cable line of around 14 km between Castasegna and Mese220/380 kV Substation with PST 250 MVA in Mese The Grid Rationalisation in the Region of Mese foresees the following actions:Displacement of 2 km of the 380 kV Line "Soazza – Bulciago"Realisation of a new 380/132 kV Substation in Mese (Transformation 2 x 250 MVA)Displacement of 0.8 km of 132 kV LinesRealisation of 2.6 km of 132 kV Cable connectionsDemolition of 2.45 km of 380 kV line and 2.3 km of 132 kV lines |  |  |  | 2019 | 2019 | 1 |  | 0 | Castasegna | Mese |  | AC |  | 220 |  |  | 250 | 1384 | "Merchant line ""Castasegna (CH) - Mese (IT)""" | "Merchant line ""Castasegna (CH) - Mese (IT)""" | 3 | Delayed | The permitting phase in Italy is ongoing since April 2014 but we are still facing some challenges regarding Environmental impact of the 380/132kV Substation Terna in Mese. Commissioning expected in 2021. | 2021 | 2021 | 1 | Mera srl (a 100% subsidiary of Repower AG) | Castasegna | Mese | Underground Cable | AC | 220 | 250 | 1384 | Merchant line Castasegna (CH) - Mese (IT) | Merchant line "Castasegna (CH) - Mese (IT)" | The planned Transmission project is a merchant line on the swiss-italian border between Castasegna (CH) and Mese (IT). The planned Cable connection in 220 kV AC has a length of around 14 km, 13.5 of witch in Italy. In connection with the realisation of the project a Rationalisation of the 380 and 132 kV Grid in the region Mese (Provincia di Sondrio) is planned. The expected NTC increase is around 200 MW.The main Project elements are (merchant line): 220 kV Connection to the Swiss HVG in Castasegna; 220 kV Cable line of around 14 km between Castasegna and Mese; 220/380 kV Substation with PST 250 MVA in Mese. The Grid Rationalisation in the Region of Mese foresees the following actions: Displacement of 2 km of the 380 kV Line """"Soazza - Bulciago""; ""Realisation of a new 380/132 kV Substation in Mese (Transformation 2 x 250 MVA); Displacement of 0.8 km of 132 kV Lines; Realisation of 2.6 km of 132 kV Cable connections; Demolition of 2.45 km of 380 kV line and 2.3 km of 132 kV lines.""" | 3 | Delayed | The permitting phase in Italy is ongoing since April 2014 but we are still facing some challenges regarding Environmental impact of the 380/132kV Substation Terna in Mese. Commissioning expected in 2024. | 2024 | 2024 | 1 | Repower MERA SRL |  | 1 | 1 | Castasegna | Mese | ACTransmissionLine | AC | 14 | New | 250 | 1384 | Merchant line Castasegna (CH) - Mese (IT) | Merchant line "Castasegna (CH) - Mese (IT)" | The planned Transmission project is a merchant line on the swiss-italian border between Castasegna (CH) and Mese (IT). The planned Cable connection in 220 kV AC has a length of around 14 km, 13.5 of witch in Italy. In connection with the realisation of the project a Rationalisation of the 380 and 132 kV Grid in the region Mese (Provincia di Sondrio) is planned. The expected NTC increase is around 200 MW.The main Project elements are (merchant line): 220 kV Connection to the Swiss HVG in Castasegna; 220 kV Cable line of around 14 km between Castasegna and Mese; 220/380 kV Substation with PST 250 MVA in Mese. The Grid Rationalisation in the Region of Mese foresees the following actions: Displacement of 2 km of the 380 kV Line "Soazza - Bulciago"; "Realisation of a new 380/132 kV Substation in Mese (Transformation 2 x 250 MVA); Displacement of 0.8 km of 132 kV Lines; Realisation of 2.6 km of 132 kV Cable connections; Demolition of 2.45 km of 380 kV line and 2.3 km of 132 kV lines." | 3 | Delayed | The permitting phase in Italy is ongoing since April 2014 but we are still facing some challenges regarding Environmental impact of the 380/132kV Substation Terna in Mese. Commissioning expected in 2025. | 03-2025 | 2025 | 1 | Repower, MERA SRL |  | 1 | 1 | Castasegna | Mese | ACTransmissionLine | AC | 0 | 220 | 14 | New | 250 | 1384 | Merchant line Castasegna (CH) - Mese (IT) | Merchant line "Castasegna (CH) - Mese (IT)" | The planned Transmission project is a merchant line on the swiss-italian border between Castasegna (CH) and Mese (IT). The planned Cable connection in 220 kV AC has a length of around 14 km, 13.5 of witch in Italy. In connection with the realisation of the project a Rationalisation of the 380 and 132 kV Grid in the region Mese (Provincia di Sondrio) is planned. The expected NTC increase is around 200 MW.The main Project elements are (merchant line): 220 kV Connection to the Swiss HVG in Castasegna; 220 kV Cable line of around 14 km between Castasegna and Mese; 220/380 kV Substation with PST 250 MVA in Mese. The Grid Rationalisation in the Region of Mese foresees the following actions: Displacement of 2 km of the 380 kV Line "Soazza - Bulciago"; "Realisation of a new 380/132 kV Substation in Mese (Transformation 2 x 250 MVA); Displacement of 0.8 km of 132 kV Lines; Realisation of 2.6 km of 132 kV Cable connections; Demolition of 2.45 km of 380 kV line and 2.3 km of 132 kV lines." | 3 | Delayed | The permitting phase in Italy is ongoing since April 2014 but we are still facing some challenges regarding Environmental impact of the 380/132kV Substation Terna in Mese. Commissioning expected in 2025. | 03-2025 | 2025 | 1 | Repower, MERA SRL |  | 1 | 1 | Castasegna | Mese | ACTransmissionLine | AC | 0 | 220 | 14 | New | 250 | 1384 | Merchant line Castasegna (CH) - Mese (IT) | Merchant line "Castasegna (CH) - Mese (IT)" | The planned Transmission project is a merchant line on the swiss-italian border between Castasegna (CH) and Mese (IT). The planned Cable connection in 220 kV AC has a length of around 14 km, 13.5 of witch in Italy. In connection with the realisation of the project a Rationalisation of the 380 and 132 kV Grid in the region Mese (Provincia di Sondrio) is planned. The expected NTC increase is around 200 MW.The main Project elements are (merchant line): 220 kV Connection to the Swiss HVG in Castasegna; 220 kV Cable line of around 14 km between Castasegna and Mese; 220/380 kV Substation with PST 250 MVA in Mese. The Grid Rationalisation in the Region of Mese foresees the following actions: Displacement of 2 km of the 380 kV Line "Soazza - Bulciago"; "Realisation of a new 380/132 kV Substation in Mese (Transformation 2 x 250 MVA); Displacement of 0.8 km of 132 kV Lines; Realisation of 2.6 km of 132 kV Cable connections; Demolition of 2.45 km of 380 kV line and 2.3 km of 132 kV lines." |  |  | 03-2030 | 2030 | 1 | Repower, MERA SRL | 1 | XX | XX | New | 2019 | 2030 | 11 | 14 | CHE;ITA | Castasegna | Mese | 46.3342 | 9.5174 | 47.294 | 8.2283
158 | 2016 | 2022 | [2016, 2018, 2020, 2022] | 1385 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 286 | 1385 | Greenlink | Greenlink | ​A subsea HVDC interconnector between Wales and Ireland​ | 3 | Delayed | A pure interconnector with Ofgem IPA approval. | 2022 | 2022 | 1 |  | 0 | Great Island (to be confirmed) | Pembroke (to be confirmed) |  | DC |  |  |  |  | 286 | 1385 | Greenlink | Greenlink | 2 | Delayed | The PCI was delayed due to regulatory processes in the Republic of Ireland which have now been remedied. The Commission for Regulation of Utilities (CRU), on 21 October 2017, directed EirGrid to progress grid applications from interconnectors with PCI status, including Greenlink; also the CRU issued an information paper on 21 March 2018 acknowledging Greenlink’s application and setting out the timeframe to develop, consult, and make an initial decision on, Greenlink’s application by 30 September 2018. | 2023 | 2023 | 1 | Element Power | Great Island | Pembroke | Subsea Cable | DC | 320 | 286 | 1385 | Greenlink | Greenlink | A subsea HVDC interconnector between Wales and Ireland | 2 | Delayed | The PCI was delayed due to regulatory processes in the Republic of Ireland which have now been remedied. The Commission for Regulation of Utilities (CRU), on 21 October 2017, directed EirGrid to progress grid applications from interconnectors with PCI status, including Greenlink; also the CRU issued an information paper on 21 March 2018 acknowledging Greenlink’s application and setting out the timeframe to develop, consult, and make an initial decision on, Greenlink’s application by 30 September 2018. | 2023 | 2023 | 1 | Element Power Statkraft | 1.9.1 | 1 | 1 | Great Island | Pembroke | OffshoreDCTransmissionCable | DC | 195 | New | 286 | 1385 | Greenlink | Greenlink | A subsea HVDC interconnector between Wales and Ireland | 4 | Rescheduled | The PCI was rescheduled due 2 main reasons. 1) Regulatory processes in the Republic of Ireland has taken longer than anticipated. 2) Irish planning process has taken longer than planned. The project has now received approvals from regulators from both UK and Ireland and its planning permission. The project expects financial close in December 21 | 11-2024 | 2024 | 1 | Greenlink Interconnector Limited |  | 1 | 1 | Great Island | Pembroke | OffshoreDCTransmissionCable | DC | 504 | 320 | 200 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2024 | 2 | 8 | GBR;IRL | Great Island | Pembroke | 51.0431 | -1.7522 | 51.674 | -4.9087
159 | 2016 | 2016 | [2016] | 1386 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 289 | 1386 | MAREX UK-Ireland Intrconnector | MAREX UK-Ireland Intrconnector | ​1500MW VSC HVDC bipole inetrconnector drom 400kV AC Connah's Quay UK-Finglas Dublin 400kV AC-Bellacorick Mayo 400kV AC | 1 |  |  | 2020 | 2020 | 1 |  | 0 | Connah's Quay | Finglas Dublin |  | DC | [8 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 4 | GBR;IRL | Connahs Quay | Finglas Dublin | 53.2328 | -3.0832 | 53.3952 | -6.2952
160 | 2016 | 2016 | [2016] | 1387 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 289 | 1387 | MAREX UK-Ireland Intrconnector | MAREX UK-Ireland Intrconnector | ​​This describes the underground cable-OHL-subsea cable combination transmission from Mayo to Dublin | 1 |  |  | 2020 | 2020 | 1 |  | 0 | Finglas Dublin | Bellacorick Mayo | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 4 | GBR;IRL | Finglas Dublin | Bellacorick Mayo | 53.3952 | -6.2952 | 54.1194 | -9.5794
161 | 2016 | 2016 | [2016] | 1388 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 172 | 1388 | ElecLink | ElecLink | ​​ElecLink is a new FR - UK interconnection cable with 1000 MW capacity though the channel Tunnel between Sellindge (UK) and Mandarins (FR). Converter stations will be located on Eurotunnel concession at Folkestone and Coquelles. This HVDC interconnection is a PCI project (Project of Common Interest) no. 1.7.3. |  |  |  | 2018 | 2018 | 1 |  | 0 | Sellindge (UK) | Mandarins (FR) |  | DC |  | 320 | [6 empty] | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2018 | 0 | 2 | FRA;GBR | Sellindge | Mandarins | 51.1086 | 0.98837
162 | 2016 | 2016 | [2016] | 1389 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1389 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | HVDC Platform​ | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Argyll Hub | [11 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Argyll
163 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 139 | Commissioned | 139 | This project is the conversion of existing 220kV double circuit line Krajnik (PSE Operator) - Vierraden (50Hertz Transmission) into a 400kV line together with installation of phase shifting transformers in Krajnik (PSE Operator) and Mikułowa (PSE Operator). | 3 | before 2013 | 2013 | 1 | Vierraden (DE) | Krajnik (PL) | 94 | 94. 139 | Upgrade of existing 220 kV line Vierraden-Krajnik to double circuit 400 kV OHL. | 3 | Expected date of commissioning was adjusted due to long permitting process and strong local public resistance. | long term |  | 1 | Vierraden (DE) | Krajnik (PL) | 94. 139 | 94. 139 | Upgrade of existing 220 kV line Vierraden-Krajnik to double circuit 400 kV OHL. | 3 | After bilateral agreements the commissioning date is agreed to 2016. | 2016 | 2016 | 1 | Vierraden (DE) | Krajnik (PL) | 94 | 139 | GerPol Improvements | Upgrade of existing 220 kV line Vierraden-Krajnik to double circuit 400 kV OHL. | 3 | Investment on time | A delay in the permit process for the line Neuenhagen-Bertikow-Vierraden (DE) as a prerequisite caused an adaptation in the time schedule for the line between Vierraden and Krajnik from to 2017. | 2017 | 2017 | 1 | Vierraden (DE) | Krajnik (PL) | 139 | Upgrade of existing 220 kV line Vierraden-Krajnik to double circuit 400 kV OHL. | 4 | Investment on time | Investment on time. | 2017 | 2017 | 1 | Vierraden (DE) | Krajnik (PL) | 94 | 139 | GerPol Improvements | Krajnik-Vierraden | Upgrade of existing 220 kV line Vierraden-Krajnik to double circuit 400 kV OHL. | 4 | Delayed | Finalization of the investment in due date (2017) was not possible because of permit granting reasons (regarding building of the “Uckermark” line) on 50Hertz side. Therefore the schedule for switching off of the existing 220 kV line to 400 kV has been changed. The interconnector will be temporally disconnected until 2018 in order to perform necessary works in the substations Krajnik and Vierraden. In 2018 first two PST in Vierraden will be installed and the line will be connected on 400 kV through a 220/400 kV transformer. The project is planned to operate in final shape (4 PSTs in SS Vierraden and the 2x400 kV interconnector) by 2020, depending on the permit granting process for the “Uckermark” line. | 31/ 12/ 2018 | 2018 | 1 |  | 1 | Vierraden (DE) | Krajnik (PL) | Overhead Line | AC | 1200 | 400 | 26 | New | 94 | 139 | GerPol Improvements | Krajnik-Vierraden | 4 | Investment on time |  | 31/12/2020 | 2020 | 1 | 50Hertz Transmission, PSE | Vierraden (DE) | Krajnik (PL) | Overhead Line | AC | 400 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2013 | 2020 | 7 | 10 | DEU;POL | Vierraden | Krajnik | 53.0978 | 14.2961 | 53.1974 | 14.4697
164 | 2016 | 2016 | [2016] | 1390 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1390 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​HVDC Platform | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Coleraine Hub | [11 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Coleraine
165 | 2016 | 2016 | [2016] | 1391 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1391 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​HVDC Platform | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | coolkeeragh hub | [11 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Coolkeeragh |  | 55.0377 | -7.2514
166 | 2016 | 2016 | [2016] | 1392 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1392 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​101km, 1GW subsea cable from Argyll hub to Coleraine. | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Argyll hub | Coleraine | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Argyll | Coleraine
167 | 2016 | 2016 | [2016] | 1393 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1393 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​43 km subsea cable from Coolkeeragh hub to nshore landing point, 10 km onshore cable to Coolkeeragh substation. | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Coolkeeragh | Coolkeeragh hub | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Coolkeeragh | Coolkeeragh | 55.0377 | -7.2514 | 55.0377 | -7.2514
168 | 2016 | 2016 | [2016] | 1394 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1394 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​41km, 1GW subsea DC cable from Coleraine substation to Coolkeeragh hub | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Coleraine substation | Coolkeeragh hub | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Coleraine | Coolkeeragh |  |  | 55.0377 | -7.2514
169 | 2016 | 2016 | [2016] | 1395 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1395 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​HVDC Platform | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Southern Hub | [11 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Southern
170 | 2016 | 2016 | [2016] | 1396 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1396 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | 53km, 500MW subsea​ DC cable from Coleraine hub to Coolkeeragh hub | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Coleraine hub | Coolkeeragh hub | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Coleraine | Coolkeeragh |  |  | 55.0377 | -7.2514
171 | 2016 | 2016 | [2016] | 1397 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1397 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Subsea cable | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Southern Hub UK | Trawsfynydd | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Southern Uk | Trawsfynydd |  |  | 52.9011 | -3.9238
172 | 2016 | 2016 | [2016] | 1398 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1398 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​348km, 1GW subseaDC cable from Hunterston to Coleraine | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Hunterston | Coleraine | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Hunterston | Coleraine
173 | 2016 | 2016 | [2016] | 1399 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1399 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​DC Cable | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Southern Hub | Trawsfynydd | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Southern | Trawsfynydd |  |  | 52.9011 | -3.9238
174 | 2014 | 2015 | [2014, 2015] | 140 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 58 | 140 | GerPol Power Bridge | Construction of new 400 kV double circuit line Plewiska (PL)-Eisenhüttenstadt (DE) creating an interconnector between Poland and Germany. | 2 | Rescheduled | The investment in planning phase. Expected problems with the routing cause adoption of commissioning date. | 2030 | 2030 | 1 | Eisenhüttenstadt (DE) | Plewiska (PL) | 140 | Construction of new 400 kV double circuit line Plewiska (PL)- Eisenhüttenstadt (DE) creating an interconnector between Poland and Germany. | 1 | Rescheduled | The decision on the realization of the investment has been postponed. Alternative developments (internal reinforcements) will be realized to ensure the same cross border effect. | 2030 | 2030 | 1 | Eisenhüttenst adt (DE) | Plewiska (PL) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | DEU;POL | Eisenhüttenst Adt | Plewiska |  |  | 52.3665 | 16.8098
175 | 2016 | 2016 | [2016] | 1400 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1400 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Substation | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Trawsfynydd |  |  | DC | [8 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Trawsfynydd |  | 52.9011 | -3.9238
176 | 2016 | 2016 | [2016] | 1401 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1401 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​subsea cable | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Southern Hub | Pembroke | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Southern | Pembroke |  |  | 51.674 | -4.9087
177 | 2016 | 2016 | [2016] | 1402 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1402 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Onshore cable | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Southern Hub | Pembroke | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Southern | Pembroke |  |  | 51.674 | -4.9087
178 | 2016 | 2016 | [2016] | 1403 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1403 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​offshore cable | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Southern Hub | Lodgewood | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Southern | Lodgewood |  |  | 52.5844 | -6.5299
179 | 2016 | 2016 | [2016] | 1404 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1404 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Onshore cable | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Southern Hub | Lodgewood | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Southern | Lodgewood |  |  | 52.5844 | -6.5299
180 | 2016 | 2016 | [2016] | 1405 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 284 | 1405 | LEG1 | LEG1 | 3000 MW HVDC Submarine cable not deeper than 2500 m​ | 1 |  |  | 2019 | 2019 | 1 |  | 0 | SALOUM (EG), TOBRUK (LIBYA) | MIRES (GR Crete) |  | DC | [8 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2019 | 0 | 3 | LBY | Saloum Eg Tobruk | Mires
181 | 2016 | 2016 | [2016] | 1406 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1406 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Substation | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Pembroke | [11 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Pembroke |  | 51.674 | -4.9087
182 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1407 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 219 | 1407 | EuroAsia Interconnector | EuroAsia Interconnector | The Euro Asia Interconnector consists of a 400 kV DC underwater electric cable and any essential equipment and/or installation for interconnecting the Cypriot, Israeli and the Greek transmission networks (offshore). The Interconnector will have a capacity of 2000 MW and a total length of around 820 nautical miles/around 1518 km (approx. 329 km between CY and IL, 879 km between CY and Crete and 310 km between Crete and Athens) and allow for reverse transmission of electricity. | 2 |  |  | 2019 | 2019 | 1 |  | 0 | Hadera Site | Vasilikos Site |  | DC |  | 500 |  |  | 219 | 1407 | EuroAsia Interconnector | EuroAsia Interconnector | 3 | Rescheduled | The National Regulatory Authorities of Greece and Cyprus approved the submitted Investment Request for the Project and agreed on the CBCA between them. The decision "Cross-Border Cost Allocation Between the Hellenic Regulatory Authority for Energy (RAE) and the Cyprus Energy Regulatory Authority (CERA)" provided on 10th of October 2017 concerned the implementation of PCIs 3.10.2 & 3.10.3. With the corresponding decision for PCI 3.10.1 not yet received, and to avoid delays in the implementation of the Project and to be in line with the obligations and commitments arising from the CBCA approval, the Project Promoter decided to amend the order of implementation of the three PCIs consisting PCI 3.10 as follows, with PCIs 3.10.2 & 3.10.3 implemented concurrently: PCI 3.10.3 Interconnection between Korakia, Crete and Attica region(EL) PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY) | 2020 | 2020 | 1 | EuroAsia Interconnector | Hadera Site | Kofinou Site | Subsea Cable | DC | 500 | 219 | 1407 | EuroAsia Interconnector | EuroAsia Interconnector | Investment 1407- PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY) , is part of the PCI 3.10 EuroAsia Interconnector . The Euro Asia Interconnector consists of a 500 kV HVDC underwater electric cable and any essential equipment and/or installation for interconnecting the Cypriot, Israeli and the Greek transmission networks (offshore). The Interconnector have a total capacity of 2000 MW and a total length of 1208 km and allow for bidirectional transmission of electricity. The system to be used is HVDC (high voltage direct current) technology. Subsea cables and converter stations with a total capacity of 2,000MW The interconnector allows bidirectional power flow. The converter stations are of Voltage Source Converter (VSC) technology and connected to subsea electrodes. | 3 | Rescheduled | The National Regulatory Authorities of Greece and Cyprus approved the submitted Investment Request for the Project and agreed on the CBCA between them. The decision "Cross-Border Cost Allocation Between the Hellenic Regulatory Authority for Energy (RAE) and the Cyprus Energy Regulatory Authority (CERA)" provided on 10th of October 2017 concerned the implementation of PCIs 3.10.2 & 3.10.3. With the corresponding decision for PCI 3.10.1 not yet received, and to avoid delays in the implementation of the Project and to be in line with the obligations and commitments arising from the CBCA approval, the Project Promoter decided to amend the order of implementation of the three PCIs consisting PCI 3.10 as follows, with PCIs 3.10.2 & 3.10.3 implemented concurrently: PCI 3.10.3 Interconnection between Korakia, Crete and Attica region(EL) PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY) | 2023 | 2023 | 1 | EuroAsia Interconnector Interconnector | 3.10 | 1 | 1 | Hadera Site | Kofinou Site | OffshoreDCTransmissionCable | DC | 310 | New | 219 | 1407 | EuroAsia Interconnector | EuroAsia Interconnector | The EuroAsia Interconnector consists of a 500 kV DC underwater electric cable and any essential equipment and/or installation for interconnecting the Cypriot, Israeli and the Greek transmission networks (offshore). The Interconnector will have a capacity of 2000 MW and a total length of around 820 nautical miles/around 1200 km (approx. 329 km between CY and IL, 879 km between CY and Crete) and allow for reverse transmission of electricity. | 3 | Delayed | The National Regulatory Authorities of Greece and Cyprus approved the submitted Investment Request for the Project and agreed on the CBCA between them. The decision "Cross-Border Cost Allocation Between the Hellenic Regulatory Authority for Energy (RAE) and the Cyprus Energy Regulatory Authority (CERA)" provided on 10th of October 2017 concerned the implementation of PCIs 3.10.2 & 3.10.3. With the corresponding decision for PCI 3.10.1 not yet received, and to avoid delays in the implementation of the Project and to be in line with the obligations and commitments arising from the CBCA approval, the Project Promoter decided to amend the order of implementation of the three PCIs consisting PCI 3.10 as follows, with PCIs 3.10.2 & 3.10.3 implemented concurrently: PCI 3.10.3 Interconnection between Korakia, Crete and Attica region(EL) PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY). The CBCA has been updated on 23.04.2021 | 12-2026 | 2026 | 1 | EuroAsia Interconnector | 3.10.1 and 3.10.2 | 1 | 1 | Hadera Site | Kofinou Site | OffshoreDCTransmissionCable | DC | 1040 | 500 | 325 | New | 219 | 1407 | Great Sea Interconnector | Great Sea Interconnector | New VSC HVDC link between Cyprus and Israel. | 4 | Delayed | We are currently in discussions to finalize the Cyprus-Israel link and move towards the construction phase, focusing on the investment requirements | 12-2029 | 2029 | 1 | IPTO | 2.6.1 and 2.6.2 | 1 | 1 | Hadera Site | Kofinou Site | OffshoreDCTransmissionCable | DC | 1040 | 500 | 325 | New | 219 | 1407 | Great Sea Interconnector | Great Sea Interconnector | New VSC HVDC link between Cyprus and Israel. |  |  | 12-2032 | 2032 | 1 | IPTO | 1 | XX | XX | New | 2019 | 2032 | 13 | 16 | CYP;GRC;ISR | Hadera Site | Kofinou Site
183 | 2016 | 2016 | [2016] | 1408 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1408 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Substation | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Lodgewood | [11 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Lodgewood |  | 52.5844 | -6.5299
184 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1409 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 219 | 1409 | EuroAsia Interconnector | EuroAsia Interconnector | The Euro Asia Interconnector consists of a 400 kV DC underwater electric cable and any essential equipment and/or installation for interconnecting the Cypriot, Israeli and the Greek transmission networks (offshore). The Interconnector will have a capacity of 2000 MW and a total length of around 820 nautical miles/around 1518 km (approx. 329 km between CY and IL, 879 km between CY and Crete and 310 km between Crete and Athens) and allow for reverse transmission of electricity. | 2 |  |  | 2022 | 2022 | 1 |  | 0 | Vasilikos Site | Korakia (Crete)Site |  | DC |  |  |  |  | 219 | 1409 | EuroAsia Interconnector | EuroAsia Interconnector | 3 | Rescheduled | The National Regulatory Authorities of Greece and Cyprus approved the submitted Investment Request for the Project and agreed on the CBCA between them. The decision "Cross-Border Cost Allocation Between the Hellenic Regulatory Authority for Energy (RAE) and the Cyprus Energy Regulatory Authority (CERA)" provided on 10th of October 2017 concerned the implementation of PCIs 3.10.2 & 3.10.3. With the corresponding decision for PCI 3.10.1 not yet received, and to avoid delays in the implementation of the Project and to be in line with the obligations and commitments arising from the CBCA approval, the Project Promoter decided to amend the order of implementation of the three PCIs consisting PCI 3.10 as follows, with PCIs 3.10.2 & 3.10.3 implemented concurrently: PCI 3.10.3 Interconnection between Korakia, Crete and Attica region(EL) PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY) | 2021 | 2021 | 1 |  | Kofinou Site | Korakia (Crete)Site | Subsea Cable | DC | 500 | 219 | 1409 | EuroAsia Interconnector | EuroAsia Interconnector | Investment 1409 - PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) is part of the PCI 3.10 EuroAsia Interconnector . The Euro Asia Interconnector consists of a 500 kV HVDC underwater electric cable and any essential equipment and/or installation for interconnecting the Cypriot, Israeli and the Greek transmission networks (offshore). The Interconnector have a total capacity of 2000 MW and a total length of 1208 km and allow for bidirectional transmission of electricity. The system to be used is HVDC (high voltage direct current) technology. Subsea cables and converter stations with a total capacity of 2,000MW The interconnector allows bidirectional power flow. The converter stations are of Voltage Source Converter (VSC) technology and connected to subsea electrodes. | 3 | Rescheduled | The National Regulatory Authorities of Greece and Cyprus approved the submitted Investment Request for the Project and agreed on the CBCA between them. The decision "Cross-Border Cost Allocation Between the Hellenic Regulatory Authority for Energy (RAE) and the Cyprus Energy Regulatory Authority (CERA)" provided on 10th of October 2017 concerned the implementation of PCIs 3.10.2 & 3.10.3. With the corresponding decision for PCI 3.10.1 not yet received, and to avoid delays in the implementation of the Project and to be in line with the obligations and commitments arising from the CBCA approval, the Project Promoter decided to amend the order of implementation of the three PCIs consisting PCI 3.10 as follows, with PCIs 3.10.2 & 3.10.3 implemented concurrently: PCI 3.10.3 Interconnection between Korakia, Crete and Attica region(EL) PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY) | 2023 | 2023 | 1 | EuroAsia Interconnector Interconnector | 3.10 | 1 | 1 | Kofinou Site | Korakia (Crete)Site | OffshoreDCTransmissionCable | DC | 898 | New | 219 | 1409 | EuroAsia Interconnector | EuroAsia Interconnector | The Euro Asia Interconnector consists of a 500 kV DC underwater electric cable and any essential equipment and/or installation for interconnecting the Cypriot, Israeli and the Greek transmission networks (offshore). The Interconnector will have a capacity of 2000 MW and a total length of around 820 nautical miles/around 1200 km (approx. 329 km between CY and IL, 879 km between CY and Crete) and allow for reverse transmission of electricity. | 3 | Delayed | The National Regulatory Authorities of Greece and Cyprus approved the submitted Investment Request for the Project and agreed on the CBCA between them. The decision "Cross-Border Cost Allocation Between the Hellenic Regulatory Authority for Energy (RAE) and the Cyprus Energy Regulatory Authority (CERA)" provided on 10th of October 2017 concerned the implementation of PCIs 3.10.2 & 3.10.3. With the corresponding decision for PCI 3.10.1 not yet received, and to avoid delays in the implementation of the Project and to be in line with the obligations and commitments arising from the CBCA approval, the Project Promoter decided to amend the order of implementation of the three PCIs consisting PCI 3.10 as follows, with PCIs 3.10.2 & 3.10.3 implemented concurrently: PCI 3.10.3 Interconnection between Korakia, Crete and Attica region(EL) PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY). The CBCA has been updated on 23.04.2021 | 12-2026 | 2026 | 1 | EuroAsia Interconnector | 3.10.1 and 3.10.2 | 1 | 1 | Kofinou Site | Korakia (Crete)Site | OffshoreDCTransmissionCable | DC | 1000 | 500 | 921 | New | 219 | 1409 | Great Sea Interconnector | Great Sea Interconnector | New VSC HVDC link between Cyprus and Greece (Crete). | 4 | Investment on time | The National Regulatory Authorities of Greece and Cyprus approved the submitted Investment Request for the Project and agreed on the CBCA between them. The decision "Cross-Border Cost Allocation Between the Hellenic Regulatory Authority for Energy (RAE) and the Cyprus Energy Regulatory Authority (CERA)" provided on 10th of October 2017 concerned the implementation of PCIs 3.10.2 & 3.10.3. With the corresponding decision for PCI 3.10.1 not yet received, and to avoid delays in the implementation of the Project and to be in line with the obligations and commitments arising from the CBCA approval, the Project Promoter decided to amend the order of implementation of the three PCIs consisting PCI 3.10 as follows, with PCIs 3.10.2 & 3.10.3 implemented concurrently: PCI 3.10.3 Interconnection between Korakia, Crete and Attica region(EL) PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY). The CBCA has been updated on 23.04.2021 and on 21.07.2023 | 12-2029 | 2029 | 1 | IPTO | 2.6.1 and 2.6.2 | 1 | 1 | Kofinou Site | Korakia (Crete)Site | OffshoreDCTransmissionCable | DC | 1000 | 500 | 921 | New | 219 | 1409 | Great Sea Interconnector | Great Sea Interconnector | New VSC HVDC link between Cyprus and Greece (Crete). | 4 |  | 12-2029 | 2029 | 1 | IPTO | 1 | XX | XX | New | 2022 | 2029 | 7 | 13 | CYP;GRC;ISR | Kofinou Site | Korakia |  |  | 37.3603 | 23.0641
185 | 2014 | 2020 | [2014, 2015, 2016, 2018, 2020] | 141 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 36 | 141 | Kriegers Flak CGS | Three offshore windfarms connected to shore combined with 400 MW interconnection between both countries | 3 | Investment on time | Commissioning date must be achieved in order to ensure grid connection for further renewable energy. | 2018 | 2018 | 1 | Ishøj / Bjæverskov (DK) | Bentwisch (DE) | 141 | Three offshore windfarms connected to shore combined with 400 MW interconnection between both countries. New technical solution: HVDC VSC Converter moved from offshore to shore | 3 | Investment on time | New design due to result of tendering process offers exceeding expected prices by far. | 2018 | 2018 | 1 | Ishøj / Bjæverskov (DK) | Bentwisch (DE) | 36 | 141 | Kriegers Flak CGS | 141 | Three offshore windfarms connected to shore combined with 400 MW interconnection between both countries.New technical solution 220/150 kV; HVDC VSC Converter moved from offshore to shore | 4 | Investment on time | New design due to result of first tendering process, where the offers exceeded expected prices by far. Second tendering process and construction is ongoing | 1/ 1/ 2018 | 2018 | 1 |  | 1 | Ishøj / Bjæverskov (DK) | Bentwisch (DE) | Subsea Cable | AC | 400 | 220 | 210 | New | 36 | 141 | Kriegers Flak CGS | Kriegers Flak CGS, TYNDP ID: 36.141 | 4 | Investment on time |  | 31/12/2018 | 2018 | 1 | 50Hertz Transmission, Energinet.dk | Ishøj / Bjæverskov (DK) | Bentwisch (DE) | Subsea Cable | AC | 150 | 36 | 141 | Kriegers Flak CGS | Kriegers Flak CGS | Four offshore windfarms connected to shore combined with 400 MW interconnection between both countries. New technical solution connecting 220 and 150 kV AC offshore grid and onshore HVDC VSC Back-to-Back Converter. | 4 | Delayed | Difficulties during construction | 2020 | 2020 | 1 | Energinet.dk 50HERTZ |  | 1 | 1 | Ishøj / Bjæverskov (DK) | Bentwisch (DE) | OffshoreACTransmissionCable | AC | 24 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2020 | 2 | 6 | DEU;DNK | Ishøj Bjæverskov | Bentwisch |  |  | 54.1162 | 12.2022
186 | 2016 | 2018 | [2016, 2018] | 1410 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 219 | 1410 | EuroAsia Interconnector | EuroAsia Interconnector | The Euro Asia Interconnector consists of a 400 kV DC underwater electric cable and any essential equipment and/or installation for interconnecting the Cypriot, Israeli and the Greek transmission networks (offshore). The Interconnector will have a capacity of 2000 MW and a total length of around 820 nautical miles/around 1518 km (approx. 329 km between CY and IL, 879 km between CY and Crete and 310 km between Crete and Athens) and allow for reverse transmission of electricity. |  |  |  | 2020 | 2020 | 1 |  | 0 | Korakia (Crete)Site | Athens Site |  | DC |  | 500 |  |  | 219 | 1410 | EuroAsia Interconnector | EuroAsia Interconnector | 3 | Rescheduled | The National Regulatory Authorities of Greece and Cyprus approved the submitted Investment Request for the Project and agreed on the CBCA between them. The decision "Cross-Border Cost Allocation Between the Hellenic Regulatory Authority for Energy (RAE) and the Cyprus Energy Regulatory Authority (CERA)" provided on 10th of October 2017 concerned the implementation of PCIs 3.10.2 & 3.10.3. With the corresponding decision for PCI 3.10.1 not yet received, and to avoid delays in the implementation of the Project and to be in line with the obligations and commitments arising from the CBCA approval, the Project Promoter decided to amend the order of implementation of the three PCIs consisting PCI 3.10 as follows, with PCIs 3.10.2 & 3.10.3 implemented concurrently: PCI 3.10.3 Interconnection between Korakia, Crete and Attica region(EL) PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY) | 2020 | 2020 | 1 |  | Korakia (Crete)Site | Athens Site | Subsea Cable | DC | 500 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 4 | GRC | Korakia | Athens Site | 37.3603 | 23.0641
187 | 2016 | 2016 | [2016] | 1411 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1411 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | DC cable | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Central Hub | Southern Hub | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Central | Southern
188 | 2016 | 2016 | [2016] | 1412 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1412 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Platform Hub | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Central Hub | [11 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Central
189 | 2016 | 2016 | [2016] | 1413 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1413 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​cable | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Central Hub | Dunstown | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Central | Dunstown
190 | 2016 | 2016 | [2016] | 1414 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1414 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Onshore DC cable |  |  |  | 9999 |  | 1 |  | 0 | Central Hub | Dunstown | [15 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [9 empty] | IRL;GBR | Central | Dunstown
191 | 2016 | 2016 | [2016] | 1415 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1415 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​offshore cable |  |  |  | 9999 |  | 1 |  | 0 | Central hub | Trawsfynydd | [15 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [9 empty] | IRL;GBR | Central | Trawsfynydd |  |  | 52.9011 | -3.9238
192 | 2016 | 2016 | [2016] | 1416 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1416 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Onshore cable |  |  |  | 9999 |  | 1 |  | 0 | Central Hub | Trawsfynydd | [15 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [9 empty] | IRL;GBR | Central | Trawsfynydd |  |  | 52.9011 | -3.9238
193 | 2016 | 2016 | [2016] | 1417 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1417 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | Hub |  |  |  | 9999 |  | 1 |  | 0 | Trawsfynydd | [16 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [9 empty] | IRL;GBR | Trawsfynydd |  | 52.9011 | -3.9238
194 | 2016 | 2016 | [2016] | 1418 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1418 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Hub |  |  |  | 9999 |  | 1 |  | 0 | Dunstown | [16 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [9 empty] | IRL;GBR | Dunstown
195 | 2016 | 2016 | [2016] | 1419 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1419 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Offshore DC Cable |  |  |  | 9999 |  | 1 |  | 0 | Central Hub | Woodland | [15 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [9 empty] | IRL;GBR | Central | Woodland |  |  | 53.293 | -6.1987
196 | 2012 | 2020 | [2012, 2013, 2014, 2015, 2016, 2018, 2020] | 142 | Commissioned | [5 empty] | 0 |  |  | 37 | 37. 142 | Nord.Link/NorGer: a new HVDC connection between Southern Norway and Northern Germany. Estimated subsea cable length: 520 - 600km. Capacity: 1000 MW. | 3 | Revised capacity and progress postponed, due to more demanding system operations and time needed to obtain necessary government permits for reinforcing the national grid. | 2018/2021 | 2021 | 1 | Tonstad (NO) | Wilster (DE) | 37. 142 | 37. 142 | Nord.Link/NorGer: a new HVDC connection between Southern Norway and Northern Germany. Estimated subsea cable length: 520 - 600km. Capacity: 1400 MW. | 3 | Agreement with Tennet-DE on commissioning date | 2018 | 2018 | 1 | Tonstad (NO) | Wilster (DE) | 37 | 142 | Southern Norway - Germany | A 514 km 500 kV HVDC subsea interconnector between southern Norway and northern Germany. | 3 | Investment on time | Agreement between the two TSOs on commissioning date. | 2018 | 2018 | 1 | Tonstad (NO) | Wilster (DE) | 142 | A 514 km 500 kV HVDC subsea interconnector between southern Norway and northern Germany. | 3 | Investment on time | Progressed as planned | 2018 | 2018 | 1 | Tonstad (NO) | Wilster (DE) | 37 | 142 | Norway - Germany, NordLink | Norway - Germany HVDC | A 514 km 500 kV HVDC subsea interconnector between southern Norway and northern Germany. | 4 | Investment on time | Agreement between the two TSOs on commissioning date. | 01/ 01/ 2020 | 2020 | 1 |  | 1 | Tonstad (NO) | Wilster (DE) | Subsea Cable | DC | 1400 | 500 | 520 | New | 37 | 142 | "Norway - Germany, NordLink" | Norway - Germany HVDC | 4 | Investment on time |  | 01/ 01/ 2020 | 2020 | 1 | STATNETT;TENNET-DE | Tonstad (NO) | Wilster (DE) | Subsea Cable | DC | 500 | 37 | 142 | Norway - Germany, NordLink | Norway - Germany HVDC | A 623 km 500 kV HVDC interconnector between southern Norway and northern Germany. 514 km of the interconnector is subsea | 4 | Investment on time |  | 2020 | 2020 | 1 | STATNETT TenneT DE | 1.8.1 | 1 | 1 | Tonstad (NO) | Wilster (DE) | OffshoreDCTransmissionCable | DC | 623 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2020 | -1 | 8 | DEU;NOR | Tonstad | Wilster | 58.6646 | 6.7161 | 53.9234 | 9.3741
197 | 2016 | 2016 | [2016] | 1420 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1420 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Onshore Cable |  |  |  | 9999 |  | 1 |  | 0 | Central Hub | Woodland | [15 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [9 empty] | IRL;GBR | Central | Woodland |  |  | 53.293 | -6.1987
198 | 2016 | 2016 | [2016] | 1421 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1421 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Subsea cable |  |  |  | 9999 |  | 1 |  | 0 | Northern Hub | Central Hub | [15 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [9 empty] | IRL;GBR | Northern | Central
199 | 2016 | 2016 | [2016] | 1422 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1422 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | Platform Hub |  |  |  | 9999 |  | 1 |  | 0 | Northern Hub | [16 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [9 empty] | IRL;GBR | Northern
200 | 2016 | 2016 | [2016] | 1423 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1423 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Offshore DC Cable | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Northern Hub | Louth | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Northern | Louth |  |  | 53.9063 | -6.5321
201 | 2016 | 2016 | [2016] | 1424 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1424 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Offshore DC Cable | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Northern Hub | Louth | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Northern | Louth |  |  | 53.9063 | -6.5321
202 | 2016 | 2016 | [2016] | 1425 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1425 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Onshore DC cable | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Northern Hub | Louth | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Northern | Louth |  |  | 53.9063 | -6.5321
203 | 2016 | 2016 | [2016] | 1426 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1426 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​Platform Hub | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Louth | [11 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Louth |  | 53.9063 | -6.5321
204 | 2016 | 2016 | [2016] | 1427 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1427 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | Substation | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Woodland | [11 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Woodland |  | 53.293 | -6.1987
205 | 2016 | 2016 | [2016] | 1428 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1428 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | ​offshore cable | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Northern Hub | Louth | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Northern | Louth |  |  | 53.9063 | -6.5321
206 | 2016 | 2016 | [2016] | 1429 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 189 | 1429 | Irish Scottish Links on Energy Study (ISLES) | Irish Scottish Links on Energy Study (ISLES) | Offshore Cable | 1 |  |  | 1/1/2030 | 2030 | 1 |  | 0 | Northern Hub | Louth |  | DC |  | 300 | [6 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | IRL;GBR | Northern | Louth |  |  | 53.9063 | -6.5321
207 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1430 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 283 | 1430 | TuNur | TuNur | ​TuNur is aimed to connect to the European network a Concentrated Solar Power plant with storage to be located in Rejim Maatoug, Kebili, Tunisia. The connection point to the ENTSO-E network is located in Montalto di Castro, Lazio, Italy. The transmission project will comprise +/- 500kV DC submarine cables from the Tunisian Northern coast to Montalto di Castro, DC overhead lines in Tunisia from the power plant to the shoring point, and HVDC converter stations at the terminal points.​ This section covers the AC part of the link. | 3 |  |  | 2020 | 2020 | 1 |  | 0 | Rejim Maatoug 400 kV | Montalto 400 kV | [6 empty] | 283 | 1430 | TuNur | TuNur AC | 3 | Delayed | The Tunisian regulatory framework has been settled only recently and this delayed the overall permitting process | 2025 | 2025 | 1 |  | Montalto di Castro (IT) VSC HVDC - 400 kV AC +/- 500 kV DC – 2x 1GW | Montalto di Castro (IT) Terna station 400 kV AC | Underground Cable | AC | 400 | 283 | 1430 | TuNur | TuNur AC | 400 kV AC underground cables from the HVDC converter in Montalto to Terna’s 400 kV station in Montalto. CAPEX includes 2 circuit breaker bays within Terna’s station. | 1 | Delayed | The Tunisian regulatory framework has been settled only recently and this delayed the overall permitting process. | 2026 | 2026 | 1 | TuNur Ltd |  | 0 | 1 | Montalto di Castro (IT) VSC HVDC - 400 kV AC +/- 500 kV DC – 2x 1GW | Montalto di Castro (IT) Terna station 400 kV AC | ACTransmissionLine | AC | 2 | New | 283 | 1430 | TuNur Italy | TuNur AC | 400 kV AC underground cables from the HVDC converter in Montalto to Terna’s 400 kV station in Montalto. CAPEX includes 2 circuit breaker bays within Terna’s station. | 1 | Delayed | The Tunisian regulatory framework has been settled only recently and this delayed the overall permitting process. | 09-2028 | 2028 | 1 | TuNur Ltd |  | 0 | 1 | Montalto di Castro (ITA) VSC HVDC - +/- 500 kV DC - 400 kV AC – 2x 1GW | Montalto di Castro (IT) Terna station 400 kV AC | ACTransmissionLine | AC | 0 | 400 | 2 | New | 283 | 1430 | TuNur Italy | TuNur AC | 400 kV AC underground cables from the HVDC converter in Montalto to Terna’s 400 kV station in Montalto. CAPEX includes 2 circuit breaker bays within Terna’s station. | 1 | Delayed | The project timeline has been delayed due to the evolution of the regulatory frameworks and supply chain constraints (specifically HVDC cable supply). | 02-2034 | 2034 | 1 | TuNur Ltd |  | 0 | 1 | Montalto di Castro (ITA) VSC HVDC - +/- 500 kV DC - 400 kV AC – 2x 1GW | Montalto di Castro (IT) Terna station 400 kV AC | OnshoreACTransmissionCable | AC | 0 | 400 | 2 | New | 283 | 1430 | TuNur Italy | TuNur AC | 400 kV AC underground cables from the HVDC converter in Montalto to Terna’s 400 kV station in Montalto. CAPEX includes 2 circuit breaker bays within Terna’s station | 1 |  | 02-2034 | 2034 | 1 | TuNur Ltd | 1 | XX | XX | New | 2020 | 2034 | 14 | 18 | ITA;TUN | Montalto Di Castro | Montalto Di Castro | 42.3515 | 11.6073 | 42.3515 | 11.6073
208 | 2016 | 2022 | [2016, 2018, 2020, 2022] | 1431 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 293 | 1431 | Southern Aegean Interconnector | Southern Aegean Interconnector | ​New DC link (2 converter SS + 270 km DC subm. cable) to connect 582MW of offshore WF generation to the mainland (Area of Athens)​ |  | Investment on time |  | 2020 | 2020 | 1 |  | 0 | LAVRIO | LEVITHA |  | DC |  | 220 |  |  | 293 | 1431 | Southern Aegean Interconnector | Southern Aegean Interconnector | 3 | Investment on time |  | 2024 | 2024 | 1 | Kykladika Meltemia SA | LAVRIO | LEVITHA | Subsea Cable | DC | 320 | 293 | 1431 | Southern Aegean Interconnector | Southern Aegean Interconnector | New DC link (2 converter SS + 245 km DC subm. cable) to connect 582MW of offshore WF generation to the mainland (Area of Athens and Crete Island) | 1 | Investment on time |  | 2024 | 2024 | 1 | Kykladika Meltemia SA |  | 1 | 0 | Lavrio | Levitha | OffshoreDCTransmissionCable | DC | 245 | New | 293 | 1431 | Southern Aegean Interconnector | Lavrio - Levitha | New DC link (2 converter SS + 245 km DC subm. cable) to connect 582MW of offshore WF generation to the mainland (Area of Athens) | 1 | Investment on time |  | 01-2025 | 2025 | 1 | Southern Aegean Interconnector SMSA (Member of Eunice Energy Group) |  | 1 | 0 | Lavrio | Levitha | OffshoreDCTransmissionCable | DC | 600 | 320 | 245 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2025 | 5 | 9 | GRC | Lavrio | Levitha | 37.7143 | 24.0548 | 37.0057 | 26.4645
209 | 2016 | 2022 | [2016, 2018, 2020, 2022] | 1432 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 293 | 1432 | Southern Aegean Interconnector | Southern Aegean Interconnector | ​​Facilitates future connection of the Crete to the Greek Mainland via Levitha substation. | 3 | Investment on time |  | 2021 | 2021 | 1 |  | 0 | LEVITHA | KORAKIA CRETE |  | DC |  | 320 |  |  | 293 | 1432 | Southern Aegean Interconnector | Southern Aegean Interconnector | 3 | Investment on time |  | 2026 | 2026 | 1 | Kykladika Meltemia SA | LEVITHA | KORAKIA CRETE | Subsea Cable | DC | 320 | 293 | 1432 | Southern Aegean Interconnector | Southern Aegean Interconnector | Interconnection of the Crete Island to the Greek Mainland via Levitha converter station. | 1 | Investment on time |  | 2026 | 2026 | 1 | Kykladika Meltemia SA |  | 0 | 0 | Levitha | Atherinolakkos Crete | OffshoreDCTransmissionCable | DC | 250 | New | 293 | 1432 | Southern Aegean Interconnector | Levitha - Crete | Interconnection of the Crete Island to the Greek Mainland via Levitha converter station. | 1 | Investment on time |  | 01-2026 | 2026 | 1 | Southern Aegean Interconnector SMSA (Member of Eunice Energy Group) |  | 0 | 0 | Levitha | Atherinolakkos Crete | OffshoreDCTransmissionCable | DC | 600 | 320 | 250 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2026 | 5 | 10 | GRC | Levitha | Atherinolakkos Crete | 37.0057 | 26.4645 | 35.0093 | 26.1287
210 | 2016 | 2022 | [2016, 2018, 2020, 2022] | 1433 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 293 | 1433 | Southern Aegean Interconnector | Southern Aegean Interconnector | ​Connection Wind Farms with AC Substations at Levitha and Syrna | 3 | Investment on time |  | 2020 | 2020 | 1 |  | 0 | Levitha | Syrna |  | AC |  | 500 |  |  | 293 | 1433 | Southern Aegean Interconnector | Southern Aegean Interconnector | 3 | Investment on time |  | 2025 | 2025 | 1 |  | Levitha | Syrna | Subsea Cable | AC | 220 | 293 | 1433 | Southern Aegean Interconnector | Southern Aegean Interconnector | Connection Wind Farms with AC Substations at Levitha and Syrna | 1 | Investment on time |  | 2025 | 2025 | 1 | Kykladika Meltemia SA |  | 0 | 0 | Levitha | Syrna | OffshoreACTransmissionCable | AC | 81 | New | 293 | 1433 | Southern Aegean Interconnector | Levitha - Syrna | Connection Wind Farms with AC Substations at Levitha and Syrna | 1 | Investment on time |  | 02-2025 | 2025 | 1 | Southern Aegean Interconnector SMSA (Member of Eunice Energy Group) |  | 0 | 0 | Levitha | Syrna | OffshoreACTransmissionCable | AC | 0 | 220 | 81 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2025 | 5 | 9 | GRC | Levitha | Syrna | 37.0057 | 26.4645 | 36.3429 | 26.6817
211 | 2016 | 2022 | [2016, 2018, 2020, 2022] | 1434 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 293 | 1434 | Southern Aegean Interconnector | Southern Aegean Interconnector | ​​AC Submarine cable to connect Kinaros Offshore Wind Farm HiV sub station to the AC side of Levitha Converter SS | 3 | Investment on time |  | 2021 | 2021 | 1 |  | 0 | KINAROS | LEVITHA |  | AC |  | 220 |  |  | 293 | 1434 | Southern Aegean Interconnector | Southern Aegean Interconnector | 3 | Investment on time |  | 2024 | 2024 | 1 |  | KINAROS | LEVITHA | Subsea Cable | AC | 220 | 293 | 1434 | Southern Aegean Interconnector | Southern Aegean Interconnector | AC Submarine cable to connect Kinaros substation to the AC side of Levitha Substation | 1 | Investment on time |  | 2024 | 2024 | 1 | Kykladika Meltemia SA |  | 0 | 0 | Kinaros | Levitha | OffshoreACTransmissionCable | AC | 14 | New | 293 | 1434 | Southern Aegean Interconnector | Kinaros - Levitha | AC Submarine cable to connect Kinaros substation to the AC side of Levitha Substation | 1 | Investment on time |  | 12-2024 | 2024 | 1 | Southern Aegean Interconnector SMSA (Member of Eunice Energy Group) |  | 0 | 0 | Kinaros | Levitha | OffshoreACTransmissionCable | AC | 0 | 220 | 15 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2024 | 3 | 8 | GRC | Kinaros | Levitha | 36.9804 | 26.2873 | 37.0057 | 26.4645
212 | 2016 | 2020 | [2016, 2018, 2020] | 1435 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 293 | 1435 | Southern Aegean Interconnector | Southern Aegean Interconnector | ​AC Submarine cable to connect Kandeliousa OffsHore Wind Farm HV substation to Syrna SS | 3 | Investment on time |  | 2021 | 2021 | 1 |  | 0 | Kandeliousa | Syrna |  | AC |  | 220 |  |  | 293 | 1435 | Southern Aegean Interconnector | Southern Aegean Interconnector | 3 | Investment on time |  | 2025 | 2025 | 1 |  | Kandeliousa | Syrna | Subsea Cable | AC | 220 | 293 | 1435 | Southern Aegean Interconnector | Southern Aegean Interconnector | HVAC Submarine cable to connect Kandeliousa OffsHore Wind Farm HV substation to Syrna HV Subsation | 1 | Investment on time |  | 2025 | 2025 | 1 | Kykladika Meltemia SA |  | 0 | 0 | Kandeliousa | Syrna | OffshoreACTransmissionCable | AC | 34 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2025 | 4 | 9 | EGY;GRC | Kandeliousa | Syrna |  |  | 36.3429 | 26.6817
213 | 2016 | 2020 | [2016, 2018, 2020] | 1436 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 293 | 1436 | Southern Aegean Interconnector | Southern Aegean Interconnector | ​AC Submarine cable connect Kandeliousa offshore Wind Farm HV substation to Pergousa SS | 3 | Investment on time |  | 2021 | 2021 | 1 |  | 0 | Kandeliousa | Pergousa |  | AC |  | 220 |  |  | 293 | 1436 | Southern Aegean Interconnector | Southern Aegean Interconnector | 3 | Investment on time |  | 2025 | 2025 | 1 |  | Kandeliousa | Pergousa | Subsea Cable | AC | 220 | 293 | 1436 | Southern Aegean Interconnector | Southern Aegean Interconnector | HVAC Submarine cable connect Kandeliousa offshore Wind Farm HV substation to Pergousa HV Substation | 1 | Investment on time |  | 2025 | 2025 | 1 | Kykladika Meltemia SA |  | 0 | 0 | Kandeliousa | Pergousa | OffshoreACTransmissionCable | AC | 14 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2025 | 4 | 9 | EGY;GRC | Kandeliousa | Pergousa |  |  | 36.5876 | 27.0381
214 | 2016 | 2020 | [2016, 2020] | 1437 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 296 | 1437 | Britib | Britib | Interconnection project between South-West England (United Kingdom), Cordemais (France) and Basque Country (Spain) in a multiterminal VSC HVDC bipole configuration of +/- 525-600 kV with 3 inputs/outputs of 1800 MW each, and a mostly subsea route from Spain to Great Britain along the French coast of about 1330 km in total. | 1 |  | Information provided from TSO | 2020 | 2020 | 1 |  | 0 | Gatica/Hernani, Cordemais and Langage/Indian Queens | Gatica/Hernani, Cordemais and Langage/Indian Queens |  | DC |  | 320 | [11 empty] | 0 | [6 empty] | 296 | 1437 | Britib | Britib | Interconnection project between South-West England (United Kingdom), Cordemais (France) and Basque Country (Spain) in a multiterminal VSC HVDC bipole configuration of +/- 500-600 kV with 3 inputs/outputs of 1800 MW each, and a mostly subsea route from Spain to Great Britain along the French coast of about 1330 km in total. | 1 | Rescheduled | Awaiting PCI status | 2026 | 2026 | 1 | ACS Cobra |  | 1 | 1 | Gatica/Hernani (Spain), Cordemais (France) and Langage/Indian Queens (United Kingdom) | Gatica/Hernani (Spain), Cordemais (France) and Langage/Indian Queens (United Kingdom) | OffshoreDCTransmissionCable | DC | 1330 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2026 | 6 | 10 | ESP;FRA;GBR | Gaticahernani Spain Cordemais France And Langageindian Queens | Gaticahernani Spain Cordemais France And Langageindian Queens
215 | 2016 | 2016 | [2016] | 1438 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 295 | 1438 | Gallant | Gallant | ​A subsea HVDC interconnector between South West Scotland and Northern Ireland​ | 1 |  | Dumfries and Galloway strategic reinforcement | 2023 | 2023 | 1 |  | 0 | Glenluce | Kilroot |  | DC | [8 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | IRL | Glenluce | Kilroot | 54.6161 | -5.8561 | 54.7317 | -5.7682
216 | 2016 | 2016 | [2016] | 1439 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 287 | 1439 | Greenwire South | Greenwire South | ​An HVDC link between Wales and Ireland | 2 | Delayed | Awaiting international contracts for renewable energy | 2023 | 2023 | 1 |  | 0 | Grenwire South Hub | Pembroke (to be confirmed) |  | DC | [8 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | GBR;IRL | Grenwire South | Pembroke |  |  | 51.674 | -4.9087
217 | 2012 | 2020 | [2012, 2013, 2014, 2015, 2016, 2018, 2020] | 144 | Commissioned | [5 empty] | 0 |  |  | 39 | 39. 144 | Step 3 in the Danish-German agreement to upgrade the Jutland-DE transfer capacity. It consists of partially an upgrade of existing 400kV line and partially a new 400kV route in Denmark. In Germany new 400kV line mainly in the trace of a existing 220kV line. The total length of this OHL is 114km. | 1 | Progresses as planned | 2017 | 2017 | 1 | Audorf (DE) | Kassö (DK) | 39. 144 | 39. 144 | Step 3 in the Danish-German agreement to upgrade the Jutland-DE transfer capacity. It consists of a new 400kV route in Denmark and In Germany new 400kV line mainly in the trace of a existing 220kV line. | 2 | Planning ongoing - minor delay due to coordination with project 43.A90 | 2018 | 2018 | 1 | Audorf (DE) | Kassö (DK) | 39 | 144 | DKW-DE, step 3 | Step 3 in the Danish-German agreement to upgrade the Jutland-DE transfer capacity. It consists of a new 400kV route in Denmark and In Germany new 400kV line mainly in the trace of a existing 220kV line. | 2 | Delayed | Planning ongoing - minor delay due to coordination with project 183.1018 | 2019 | 2019 | 1 | Audorf (DE) | Kassö (DK) | 144 | Step 3 in the Danish-German agreement to upgrade the Jutland-DE transfer capacity. It consists of a new 400kV route in Denmark and In Germany new 400kV line mainly in the trace of a existing 220kV line. | 2 | Rescheduled | Planning ongoing minor delay due to coordination with project 183.1018 | 2020 | 2020 | 1 | Audorf (DE) | Kassö (DK) | 39 | 144 | DKW-DE, step 3 | Audorf - Kassoe | Step 3 in the Danish-German agreement to upgrade the Jutland-DE transfer capacity. It consists of a new 400kV route in Denmark and In Germany new 400kV line mainly in the trace of a existing 220kV line. | 3 | Investment on time | step forward from planning to permitting | 31/ 12/ 2020 | 2020 | 1 |  | 1 | Audorf (DE) | Kassö (DK) | Overhead Line | AC | 720 | 400 | 124 | Upgrade | 39 | 144 | "DKW-DE, step 3" | Audorf - Kassoe | 4 | Investment on time |  | 31/ 12/ 2020 | 2020 | 1 | Energinet.dk; TENNET-DE | Audorf (DE) | Kassoe (DK) | Overhead Line | AC | 380 | 39 | 144 | DKW-DE, step 3 | Audorf - Kassoe | Step 3 in the Danish-German agreement to upgrade the Jutland-DE transfer capacity. It consists of a new 400kV route in Denmark and In Germany new 400kV line mainly in the trace of a existing 220kV line. | 4 | Investment on time |  | 2020 | 2020 | 1 | Energinet.dk TenneT DE |  | 1 | 1 | Audorf (DE) | Kassoe (DK) | ACTransmissionLine | AC | 110 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2020 | 3 | 8 | DEU;DNK | Audorf | Kassoe | 54.3132 | 9.7185 | 55.0368 | 9.2343
218 | 2016 | 2016 | [2016] | 1440 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 290 | 1440 | Greenwire North | Greenwire North | An HVDC link between Wales and Ireland​ | 2 | Delayed | Awaiting international contracts for renewable energy | 2023 | 2023 | 1 |  | 0 | Greenwire North Hub | Pentir (to be confirmed) |  | DC | [8 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | GBR;IRL | Greenwire North | Pentir |  |  | 53.1959 | -4.1608
219 | 2016 | 2016 | [2016] | 1441 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 287 | 1441 | Greenwire South | Greenwire South | ​HVDC link between Greenwire South HVDC backbone and EirGrid​ | 2 | Delayed | Awaiting international contracts for renewable energy | 2023 | 2023 | 1 |  | 0 | Grenwire South Hub | Dunstown, Laois or other tbc | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | GBR;IRL | Grenwire South | Dunstown Laois Or Other Tbc
220 | 2016 | 2016 | [2016] | 1442 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 287 | 1442 | Greenwire South | Greenwire South | ​HVAC link 1 from windfarm collector substation to HVDC hub​ | 2 | Delayed | Awaiting international contracts for renewable energy | 2023 | 2023 | 1 |  | 0 | Grenwire South Hub | Greenwire South substation AC1 | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | GBR;IRL | Grenwire South | Greenwire South Ac
221 | 2016 | 2016 | [2016] | 1443 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 287 | 1443 | Greenwire South | Greenwire South | ​HVAC link 2 from windfarm collector substation to HVDC hub​ | 2 | Delayed | Awaiting international contracts for renewable energy | 2023 | 2023 | 1 |  | 0 | Grenwire South Hub | Greenwire South substation AC2 | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | GBR;IRL | Grenwire South | Greenwire South Ac
222 | 2016 | 2016 | [2016] | 1444 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 287 | 1444 | Greenwire South | Greenwire South | ​HVAC link 3 from windfarm collector substation to HVDC hub​ | 2 | Delayed | Awaiting international contracts for renewable energy | 2023 | 2023 | 1 |  | 0 | Grenwire South Hub | Greenwire South substation AC3 | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | GBR;IRL | Grenwire South | Greenwire South Ac
223 | 2016 | 2016 | [2016] | 1445 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 287 | 1445 | Greenwire South | Greenwire South | ​HVAC link 4 from windfarm collector substation to HVDC hub​ | 2 | Delayed | Awaiting international contracts for renewable energy | 2023 | 2023 | 1 |  | 0 | Grenwire South Hub | Greenwire South substation AC4 | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | GBR;IRL | Grenwire South | Greenwire South Ac
224 | 2016 | 2016 | [2016] | 1446 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 287 | 1446 | Greenwire South | Greenwire South | ​HVAC link 5 from windfarm collector substation to HVDC hub​ | 2 | Delayed | Awaiting international contracts for renewable energy | 2023 | 2023 | 1 |  | 0 | Grenwire South Hub | Greenwire South substation AC5 | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | GBR;IRL | Grenwire South | Greenwire South Ac
225 | 2016 | 2016 | [2016] | 1447 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 290 | 1447 | Greenwire North | Greenwire North | ​HVDC link between Greenwire North HVDC backbone and EirGrid​ | 2 | Delayed | Awaiting international contracts for renewable energy | 2023 | 2023 | 1 |  | 0 | Greenwire North Hub | Woodlands or new Midlands 400/220V substation tba | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | GBR;IRL | Greenwire North | Woodlands Or New Midlands V Tba
226 | 2016 | 2016 | [2016] | 1448 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 290 | 1448 | Greenwire North | Greenwire North | ​HVAC link 2 from windfarm collector substation to HVDC hub​ | 2 | Delayed | Awaiting international contracts for renewable energy | 2023 | 2023 | 1 |  | 0 | Greenwire North Hub | Greenwire North substation AC2 | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | GBR;IRL | Greenwire North | Greenwire North Ac
227 | 2016 | 2016 | [2016] | 1449 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 290 | 1449 | Greenwire North | Greenwire North | ​HVAC link 3 from windfarm collector substation to HVDC hub​ | 2 | Delayed | Awaiting international contracts for renewable energy | 2023 | 2023 | 1 |  | 0 | Greenwire North Hub | Greenwire North substation AC3 | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | GBR;IRL | Greenwire North | Greenwire North Ac
228 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 145 | Commissioned | 145 | New 400kV line double circuit DE-NL interconnection line. Length:60km. | 3 | 2013 | 2013 | 1 | Niederrhein (DE) | Doetinchem (NL) | 103 | 103. 145 | New 400kV line double circuit DE-NL interconnection line. Length:60km. | 3 | Delays due to authorization process. | >=2013 | 2013 | 1 | Niederrhein (DE) | Doetinchem (NL) | 103. 145 | 103. 145 | New 400kV line double circuit DE-NL interconnection line. Length:60km. | 3 | Permitting procedures take longer than expected | 2016 | 2016 | 1 | Niederrhein (DE) | Doetinchem (NL) | 113 | 145 | Doetinchem - Niederrhein | New 400kV line double circuit DE-NL interconnection line. Length:57km. | 3 | Delayed | Permitting procedures take longer than expected | 2016 | 2016 | 1 | Niederrhein (DE) | Doetinchem (NL) | 145 | New 400kV line double circuit DE-NL interconnection line. Length:57km. | 3 | Delayed | Permitting procedures take longer than expected | 2017 | 2017 | 1 | Niederrhein (DE) | Doetinchem (NL) | 113 | 145 | Doetinchem - Niederrhein | Doetinchem-Niederrhein | New 400kV line double circuit DE-NL interconnection line. | 4 | Investment on time | New 400kV line double circuit DE-NL interconnection line, to facilitate the market. | 1/ 1/ 2017 | 2017 | 1 |  | 1 | Niederrhein (DE) | Doetinchem (NL) | Overhead Line | AC | 1500 | 400 | 57 | New | 113 | 145 | Doetinchem - Niederrhein | Doetinchem-Niederrhein | 4 | Investment on time |  | 2018 | 2018 | 1 | AMPRION;TENNET-NL | Niederrhein (DE) | Doetinchem (NL) | Overhead Line | AC | 380 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2013 | 2018 | 5 | 8 | DEU;NLD | Niederrhein | Doetinchem | 51.4013 | 6.5096 | 51.9585 | 6.2815
229 | 2016 | 2016 | [2016] | 1450 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 290 | 1450 | Greenwire North | Greenwire North | ​HVAC link 4 from windfarm collector substation to HVDC hub​ | 2 | Delayed | Awaiting international contracts for renewable energy | 2023 | 2023 | 1 |  | 0 | Greenwire North Hub | Greenwire North substation AC4 | [10 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | GBR;IRL | Greenwire North | Greenwire North Ac
230 | 2016 | 2016 | [2016] | 1452 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 279 | 1452 | Third interconnector between Bulgaria and Greece | Maritsa East 1 (BG)- Nea Santa (GR) 2nd line | The project concerns the construction of a new 400kV AC line between Bulgaria and Greece. The project necessity stems from the need to increase the transfer capacity between Greece and Bulgaria in order to accomodate connection of RES and improve market integration, according to the results by the Common Planning Studies based on TYNDP2014 Vision 4. | 1 | Investment on time |  | 20/10/2030 | 2030 | 1 |  | 1 | Maritsa East 1 (BG) | Nea Santa (GR) | Overhead Line | AC | 500 | 400 | 130 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 14 | BGR;GRC | Maritsa East | Nea Santa | 42.1826 | 24.3565 | 40.8423 | 22.9204
231 | 2016 | 2016 | [2016] | 1453 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 292 | 1453 | Greenconnect | interconnection | A subsea HVDC interconnector between Wales and Ireland | 1 | New Investment |  | 2023 | 2023 | 1 |  | 1 | Dublin Area ( to be agreed) | Pentir (to be agreed) | Subsea Cable | DC | [8 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 7 | IRL | Dublin Area | Pentir |  |  | 53.1959 | -4.1608
232 | 2016 | 2016 | [2016] | 1454 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 291 | 1454 | Greenwire Loop | Greenwire Loop Cable | An onshore underground link in Ireland between Greenwire North and Greenwire South to create loop flow potential between North Wales (e.g. Pentir) and South Wales (e.g. Pembroke)​ | 1 | New Investment |  | 2022 | 2022 | 1 |  | 1 | Greenwire North Hub | Grenwire South Hub | Overhead Line | DC | [8 empty] | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2022 | 0 | 6 | GBR;IRL | Greenwire North | Grenwire South
233 | 2016 | 2018 | [2016, 2018] | 1455 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 255 | 1455 | Connection Navarra-Basque Country | New line 400 kV Castejón-Ichaso | North axis Project between Navarra and the Basque Country. New input/output in Ichaso 400 kV for RES integration | 2 | New Investment |  | 2020 | 2020 | 1 |  | 0 | Castejón | Ichaso | Overhead Line | AC |  | 400 | 169 | New | 255 | 1455 | Connection Navarra-Basque Country | New line 400 kV Castejon-Ichaso | 3 | Delayed | Delay due to long permitting process | 2023 | 2023 | 1 |  | Castejon | Ichaso | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2023 | 3 | 7 |  | Castejon | Ichaso |  |  | 43.0724 | -2.2579
234 | 2016 | 2020 | [2016, 2018, 2020] | 1456 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 252 | 1456 | Internal Belgian Backbone East | Massenhoven - Van Eyck |  | 1 | Investment on time | The need for this project towards 2020-2025 horizon is to be further monitored in accordance with the evolution of transitflux/interconnection capacity on the surrounding borders, and with the perspective of evolution in the production park. | 01/01/2025 | 2025 | 1 |  | 0 | Massenhoven (BE) | Van Eyck (BE) | Overhead Line | AC |  | 380 | 90 | Upgrade | 252 | 1456 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | Massenhoven - Van Eyck: HTLS upgrade | 1 | Investment on time |  | 31/12/2024 | 2024 | 1 |  | Massenhoven (BE) | Van Eyck (BE) | Overhead Line | AC | 380 | 252 | 1456 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | Massenhoven - Van Eyck: HTLS upgrade | Installation of a second circuit (in HTLS) and upgrade of existing circuit to HTLS | 3 | Investment on time |  | 2024 | 2024 | 1 | ELIA |  | 1 | 0 | Massenhoven (BE) | Van Eyck (BE) | ACTransmissionLine | AC | 90 | Upgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2024 | -1 | 8 | BEL | Massenhoven | Van Eyck | 51.199 | 4.635 | 51.2108 | 4.4116
235 | 2016 | 2018 | [2016, 2018] | 1457 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 231 | 1457 | Concept Project DE-CH | Additional measures |  | 1 | New Investment |  | 2030 | 2030 | 1 |  | 1 |  |  | Overhead Line | AC |  | 380 |  |  | 231 | 1457 | Concept project Germany-Switzerland | Additional measures | 1 |  |  | 2035 | 2035 | 1 |  | Germany | Switzerland | Overhead Line | DC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2035 | 5 | 19 | CHE;DEU | Germany | Switzerland
236 | 2016 | 2026 | [2016, 2018, 2020, 2022, 2024, 2026] | 1458 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 299 | 1458 | SACOI3 | SACOI3 | New HVDC line between Italy mainland, Corsica and Sardinia replacing existing link SACOI2 | 3 | Investment on time | Project rescheduled to meet the target commissioning date 2023 | 2023 | 2023 | 1 |  | 0 | Codrongianos | Suvereto | Subsea Cable | DC |  |  |  | Upgrade | 299 | 1458 | SACOI3 | SACOI3 | 3 | Investment on time |  | 2023 | 2023 | 1 | Terna; EDF | Codrongianos - Lucciana | Suvereto | Subsea Cable | DC | 200 | 299 | 1458 | SACOI3 | SACOI3 | New HVDC triterminal link between Italy mainland, Corsica and Sardinia replacing existing link SACOI2 | 3 | Investment on time |  | 2024 | 2024 | 1 | TERNA EDF | 2.4 | 1 | 1 | Codrongianos - Lucciana | Suvereto | DCTransmissionLine | DC | 300 | Upgrade | 299 | 1458 | SACOI3 | SACOI3 | New HVDC triterminal link between Italy mainland, Corsica and Sardinia replacing existing link SACOI2 | 3 | Delayed | Delayed due to permitting reasons. | 12-2027 | 2027 | 1 | Terna, EDF | 2.4 | 1 | 1 | Codrongianos - Lucciana | Suvereto | DCTransmissionLine | DC | 400 | 200 | 300 | Upgrade | 299 | 1458 | SACOI 3 | SACOI 3 | New HVDC triterminal link between Italy mainland, Corsica and Sardinia replacing existing link SACOI 2 | 4 | Investment on time |  | 12-2027 | 2027 | 1 | Terna, EDF | 1.10 | 1 | 1 | Codrongianos - Lucciana | Suvereto | DCTransmissionLine | DC | 400 | 200 | 410 | New | 299 | 1458 | SACOI 3 | SACOI 3 | New HVDC triterminal link between Italy mainland, Corsica and Sardinia replacing existing link SACOI 2 | 4 |  | 12-2029 | 2029 | 1 | Terna, EDF | 1 | XX | XX | New | 2023 | 2029 | 6 | 13 | FRA;ITA | Codrongianos - Lucciana | Suvereto |  |  | 43.079 | 10.6787
237 | 2014 | 2020 | [2014, 2015, 2016, 2018, 2020] | 146 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 92 | 146 | ALEGrO | ALEGrO Connection between Germany and Belgium including new 100 km HVDC underground cable with convertor stations and extension of existing 380 kV substations. The assessment of the Final Investment Decision is planned in 2015. | 3 | Delayed | BE: Several months delay due to authorisation procedure in Belgium longer than expected (modification of "Plan de secteur" in Wallonia). DE: Delay due to unclear permitting framework (legal framework for planning approval is presently under development | 2019 | 2019 | 1 | Area of Oberzier - Aachen/Düren (DE) | Area of Lixhe - Liège (BE) | 146 | Connection between Germany (Oberzier) and Belgium (Lixhe)including a +-100km HVDC underground cable, and 2 convertor stations to integrate with substations at Lixhe & Oberzier. | 3 | Investment on time | The expected commissioning date of 2019 is based on the hypothesis of acquiring all necessary permits as planned, followed by the assessment of the final investment decision currently planned in 2016. | 2019 | 2019 | 1 | Area of Oberzier - Aachen/Düre n (DE) | Area of Lixhe - Liège (BE) | 92 | 146 | ALEGrO | ALEGrO | Connection between the Oberzier substation in Germany and the Lixhe substation in Belgium via a +-100 km HVDC underground cable, including 2 DC/AC convertor stations to integrate the DC cable with the AC substations at Lixhe & Oberzier. | 3 | Delayed | The expected commissioning date of 2020 is based on the hypothesis of acquiring all necessary permits as planned. | 01/ 01/ 2020 | 2020 | 1 |  | 1 | Area of Oberzier - Aachen/Düren (DE) | Area of Lixhe - Liège (BE) | Underground Cable | DC | 1000 | 320 | 94 | New | 92 | 146 | ALEGrO | ALEGrO | 3 | Investment on time |  | 2020 | 2020 | 1 | AMPRION;ELIA | Oberzier (DE) | Lixhe (BE) | Underground Cable | DC | 320 | 92 | 146 | ALEGrO | ALEGrO | "Connection between the Oberzier substation in Germany and the Lixhe substation in Belgium via a +-100 km HVDC underground cable, including 2 DC/AC convertor stations to integrate the DC cable with the AC substations at Lixhe & Oberzier." | 4 | Investment on time |  | 2020 | 2020 | 1 | AMPRION ELIA |  | 1 | 1 | Oberzier (DE) | Lixhe (BE) | DCTransmissionLine | DC | 90 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2020 | 1 | 6 | BEL;DEU | Oberzier | Lixhe | 50.8658 | 6.4739 | 50.7551 | 5.6801
238 | 2018 | 2018 | [2018] | 1460 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 240 | 1460 | 380-kV-grid enhancement between Area Güstrow and Wolmirstedt | AC Enhancement Güstrow-Wolmirstedt | 3 | Investment on time |  | 2021 | 2021 | 1 | 50Hertz Transmission | Güstrow (DE) | Wolmirstedt (DE) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2021 | 0 | 3 | DEU | Güstrow | Wolmirstedt | 53.7936 | 12.1765 | 52.2485 | 11.6267
239 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 147 | Commissioned | 147 | New 400kV double circuit OHL Dollern - Hamburg/Nord including one new 400/230kV transformer in substation Hamburg/Nord and new 400kV switchgear Kummerfeld. Length:43km. | 3 | 1. circuit midterm; 2. circuit long-term |  | 1 | Dollern (DE) | Hamburg/Nord (DE) | 44 | 44. 147 | New 400kV double circuit OHL Dollern - Hamburg/Nord including one new 400/230kV transformer in substation Hamburg/Nord and new 400kV switchgear Kummerfeld. Length:43km. | 3 | Delays due to authorization process. | mid term |  | 1 | Dollern (DE) | Hamburg/Nord (DE) | 44. 147 | 44. 147 | New 400kV double circuit OHL Dollern - Hamburg/Nord including one new 400/230kV transformer in substation Hamburg/Nord and new 400kV switchgear Kummerfeld. Length:43km. | 3 | Delay due to long permitting process | 2015 | 2015 | 1 | Dollern (DE) | Hamburg/Nord (DE) | 209 | 147 | Reinforcement Northeastern DE | New 380kV double circuit OHL Dollern - Hamburg/Nord. Length:43km. First circuit 2015, second circuit 2017 | 4 | Delayed | Delay due to long permitting process | 2017 | 2017 | 1 | Dollern (DE) | Hamburg/Nord (DE) | 147 | New 380kV double circuit OHL Dollern - Hamburg/Nord. Length:43km. First circuit 2015, second cicuit 2017 | 4 | Delayed | Delay due to long permitting process | 2017 | 2017 | 1 | Dollern (DE) | Hamburg/No rd (DE) | 251 | 147 | Audorf-Dollern | Dollern - Hamburg/Nord | New 380kV double circuit OHL Dollern - Hamburg/Nord. Length - 43km.First circuit 2015, second cicuit 2017 | 4 | Delayed | Delay due to long permitting process | 1/ 1/ 2018 | 2018 | 1 |  | 0 | Dollern (DE) | Hamburg/Nord (DE) | Overhead Line | AC | 2008 | 380 | 43 | New | 251 | 147 | Audorf-Dollern | Dollern - Hamburg/Nord | 4 | Delayed | Delay due to long permitting process | 2018 | 2018 | 1 | TenneT-DE | Dollern (DE) | Hamburg/Nord (DE) | Overhead Line | AC | 380 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2018 |  | 8 | DEU | Dollern | Hamburgnord | 53.5378 | 9.5385
240 | 2018 | 2024 | [2018, 2020, 2022, 2024] | 1472 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 312 | 1472 | St. Peter - Tauern (AT internal) | St. Peter - Tauern (AT internal) | 3 | Delayed | Duration of permitting process. | 2022 | 2022 | 1 | APG | St. Peter | Tauern | Overhead Line | AC | 380 | 312 | 1472 | St. Peter (AT) - Tauern (AT) | St. Peter (AT) - Tauern (AT) | new 380-kV-Line | 4 | Delayed | Duration of permitting process. | 2025 | 2025 | 1 | Austrian Power Grid | 3.1.2 | 1 | 0 | St. Peter | Tauern | ACTransmissionLine | AC | 128 | New | 312 | 1472 | St. Peter (AT) - Tauern (AT) | St. Peter (AT) - Tauern (AT) | new 380-kV-Line | 4 | Delayed | Duration of permitting process. | 12-2025 | 2025 | 1 | Austrian Power Grid | 3.1.2 | 1 | 0 | St. Peter | Tauern | ACTransmissionLine | AC | 0 | 380 | 128 | New | 312 | 1472 | St. Peter (AT) - Tauern (AT) | St. Peter (AT) - Tauern (AT) | new 380-kV-Line | 4 | Delayed | Duration of permitting process. | 12-2025 | 2025 | 1 | Austrian Power Grid | 2.1.2 | 1 | 0 | St. Peter | Tauern | ACTransmissionLine | AC | 0 | 380 | 128 | New | [5 empty] | 5 | Commissioned |  |  | 0 | [5 empty] | 2022 | 2025 | 3 | 7 | AUT | St. Peter | Tauern | 46.6202 | 14.335 | 47.4678 | 10.7622
241 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1473 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 313 | 1473 | Isar/Altheim/Ottenhofen (DE) - St.Peter (AT) | Isar/Altheim/Ottenhofen - St. Peter | 3 | Delayed | Delay due to long permitting process | 2021 | 2021 | 1 | TenneT-DE; APG | Isar/Altheim/Ottenhofen (DE) | St. Peter (AT) | Overhead Line | AC | 380 | 313 | 1473 | Isar/Altheim/Ottenhofen (DE) - St.Peter (AT) | Isar/Altheim/Ottenhofen - St. Peter | New 380kV double circuit OHL Isar/Altheim/Ottenhofen - St. Peter including new 380kV switchgears Altheim, Pirach, Simbach and St. Peter. | 3 | Delayed | Delay due to complex and long permitting process | 2024 | 2024 | 1 | Austrian Power Grid TenneT DE | PCI 3.1.1 | 1 | 1 | Isar/Altheim/Ottenhofen (DE) | St. Peter (AT) | ACTransmissionLine | AC | 90 | New | 313 | 1473 | Isar/Altheim/Ottenhofen (DE) - St.Peter (AT) | Isar/Altheim/Ottenhofen - St. Peter | New 380kV double circuit OHL Isar/Altheim/Ottenhofen - St. Peter including new 380kV switchgears Altheim, Pirach, Simbach and St. Peter. | 3 | Delayed | Delay due to complex and long permitting process | 12-2026 | 2026 | 1 | Austrian Power Grid, TenneT DE | 3.1.1 | 1 | 1 | Isar/Altheim/Ottenhofen (DE) | St. Peter (AT) | ACTransmissionLine | AC | 0 | 380 | 90 | New | 313 | 1473 | Isar/Altheim/Ottenhofen (DE) - St.Peter (AT) | Isar/Altheim/Ottenhofen - St. Peter | New 380kV double circuit OHL Isar/Altheim/Ottenhofen - St. Peter including new 380kV switchgears Altheim, Pirach, Simbach and St. Peter. | 3 | Delayed | Delay due to complex and long permitting process | 12-2027 | 2027 | 1 | Austrian Power Grid, TenneT DE | 2.1.1 | 1 | 1 | Isar/Altheim/Ottenhofen (DE) | St. Peter (AT) | ACTransmissionLine | AC | 0 | 380 | 90 | New | 313 | 1473 | Isar/Altheim/Ottenhofen (DE) - St.Peter (AT) | Isar/Altheim/Ottenhofen - St. Peter | New 380kV double circuit OHL Isar/Altheim/Ottenhofen - St. Peter including new 380kV switchgears Altheim, Pirach, Simbach and St. Peter. |  |  | 12-2027 | 2027 | 1 | Austrian Power Grid, TenneT DE | 1 | XX | XX | New | 2021 | 2027 | 6 | 9 | AUT;DEU | Isaraltheimottenhofen | St. Peter |  |  | 46.6202 | 14.335
242 | 2018 | 2018 | [2018] | 1475 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 321 | 1475 | Herbertingen - Tiengen | Herbertingen - Tiengen | 2 | Investment on time |  | 2025 | 2025 | 1 | Amprion | Herbertingen | Tiengen | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 7 |  | Herbertingen | Tiengen | 48.0601 | 9.4347 | 47.9842 | 7.7153
243 | 2018 | 2022 | [2018, 2020, 2022] | 1476 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 322 | 1476 | Wullenstetten - Border Area (DE-AT) | Wullenstetten - Border Area (DE-AT) | 3 | Investment on time |  | 2020 | 2020 | 1 | Amprion, VUEN | Wullenstetten (DE) | Austrian National border (AT) | Overhead Line | AC | 380 | 322 | 1476 | Wullenstetten - Border Area (DE-AT) | Wullenstetten - Border Area (DE-AT) | Between point Wullenstetten and point border area (DE-AT) an upgrade of an existing 380-kV-line is necessary (grid enhancement). Thereby, a significantly higher transmission capacity is realized. Between switching point Neuravensburg and Austrian National border (AT) a new line with a significantly higher transmission capacity will be constructed in an existing corridor (grid enhancement). | 3 | Delayed | Scope of the project changed due to technical reasons. | 2025 | 2025 | 1 | AMPRION VUEN |  | 1 | 0 | Wullenstetten (DE) | Austrian National border (AT) | ACTransmissionLine | AC | 95 | Upgrade | 263 | 1476 | Lake Constance East | Wullenstetten - Border Area (DE-AT) | Between point Wullenstetten and point Niederwangen an upgrade of an existing 380-kV-line is necessary. Furthermore, between switching point Neuravensburg and Austrian National border (AT) a new line with a significantly higher transmission capacity will be constructed in an existing corridor. | 2 | Rescheduled | Scope of the project changed due to technical reasons. Investment 1476 Wullenstetten – National Border DE-AT was previously under Project 322. | 12-2030 | 2030 | 1 | Swissgrid, VUEN, Amprion, Transnet-BW |  | 1 | 1 | Wullenstetten (DE) | Austrian National border (AT) | ACTransmissionLine | AC | 0 | 380 | 95 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2030 | 10 | 12 | AUT;CHE;DEU | Wullenstetten | Austrian National Border | 48.3164 | 10.0689
244 | 2018 | 2018 | [2018] | 1477 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 322 | 1477 | Wullenstetten - Border Area (DE-AT) | Herbertingen - Neuravensburg | 2 | Investment on time |  | 2030 | 2030 | 1 |  | Herbertingen | Neuravensburg | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 12 | AUT;DEU | Herbertingen | Neuravensburg | 48.0601 | 9.4347
245 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1478 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 323 | 1478 | Dekani (SI) - Zaule (IT) interconnection | Dekani (SI) - Zaule (IT) interconnection | 3 | New Investment |  | 2020 | 2020 | 1 | Adria Link Srl, E3 d.o.o., HSE d.o.o.. | DEKANI | ZAULE | Underground Cable | AC | 110 | 323 | 1478 | Dekani (SI) - Zaule (IT) interconnection | Dekani (SI) - Zaule (IT) interconnection | The Zaule (IT) - Dekani (SI) interconnection is a third party cross-border electrical line promoted by Adria Link Srl, E3 d.o.o. and HSE d.o.o.. The project concerns an underground cable 110kV a.c. merchant line, 150 MW from Zaule (IT) substation to Dekani substation, including a 110/135 kV Phase Shifter Transformer. | 3 | Delayed | The promoters asked to the respective NRA for the NTC recalculation not subject to conditions (EG. third party network reinforcements), which will be guaranteed for the exemption period and from the entry into the new commercial operation date (COD) of the interconnector. | 2025 | 2025 | 1 | HSE d.o.o. (Holding Slovenske Elektrarne, d.o.o.) E3 d.o.o. (ENERGETIKA, EKOLOGIJA, EKONOMIJA, d.o.o) Adria Link Srl |  | 1 | 1 | DEKANI | ZAULE | ACTransmissionLine | AC | 11 | New | 323 | 1478 | Dekani (SI) - Zaule (IT) interconnection | Dekani (SI) - Zaule (IT) interconnection | The Zaule (IT) - Dekani (SI) interconnection is a third party cross-border electrical line promoted by Adria Link Srl, E3 d.o.o. and HSE d.o.o.. The project concerns an underground cable 110kV a.c. merchant line, 150 MW from Zaule (IT) substation to Dekani substation, including a 110/135 kV Phase Shifter Transformer. | 3 | Delayed | The promoters asked to the respective NRA for the NTC recalculation not subject to conditions (EG. third party network reinforcements), which will be guaranteed for the exemption period and from the entry into the new commercial operation date (COD) of the interconnector. The process is still ongoing. | 04-2025 | 2025 | 1 | HSE d.o.o. (Holding Slovenske Elektrarne, d.o.o.) - E3 d.o.o. (ENERGETIKA, EKOLOGIJA, EKONOMIJA, d.o.o) - Adria Link Srl |  | 1 | 1 | DEKANI | ZAULE | ACTransmissionLine | AC | 0 | 110 | 11 | New | 323 | 1478 | Dekani (SI) - Zaule (IT) interconnection | Dekani (SI) - Zaule (IT) interconnection | The Zaule (IT) - Dekani (SI) interconnection is a third party cross-border electrical line promoted by Adria Link Srl, E3 d.o.o. and HSE d.o.o.. The project concerns an underground cable 110kV a.c. merchant line, 150 MW from Zaule (IT) substation to Dekani substation, including a 110/135 kV Phase Shifter Transformer. | 3 | Delayed | The promoter asked the respective NRA for the NTC recalculation not subject to conditions (eg third party network reinforcements), which will be guaranteed for the exemption period and from the entry into the new commercial operation date (COD) of the interconnector. The process was concluded in July 2023. | 08-2026 | 2026 | 1 | HSE d.o.o. (Holding Slovenske Elektrarne, d.o.o.) - E3 d.o.o. (ENERGETIKA, EKOLOGIJA, EKONOMIJA, d.o.o) - Adria Link Srl |  | 1 | 1 | DEKANI | ZAULE | ACTransmissionLine | AC | 0 | 110 | 11 | New | 323 | 1478 | Dekani (SI) - Zaule (IT) interconnection | Dekani (SI) - Zaule (IT) interconnection | The Zaule (IT) - Dekani (SI) interconnection is a third party cross-border electrical line promoted by Adria Link Srl, E3 d.o.o. and HSE d.o.o.. The project concerns an underground cable 110kV a.c. merchant line, 150 MW from Zaule (IT) substation to Dekani substation, including a 110/135 kV Phase Shifter Transformer. |  |  | 09-2026 | 2026 | 1 | HSE d.o.o. (Holding Slovenske Elektrarne, d.o.o.) - E3 d.o.o. (ENERGETIKA, EKOLOGIJA, EKONOMIJA, d.o.o) - Adria Link Srl | 1 | XX | XX | New | 2020 | 2026 | 6 | 8 | ITA;SVN | Dekani | Zaule | 45.5483 | 13.8103 | 45.6021 | 13.8073
246 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 148 | Commissioned | 148 | New 400kV double circuit OHL Audorf - Hamburg/Nord including two new 400/230kV transformers in substation Audorf. Length: 65km. | 2 | long term |  | 1 | Audorf (DE) | Hamburg/Nord (DE) | 44 | 44. 148 | New 400kV double circuit OHL Audorf - Hamburg/Nord including two new 400/230kV transformers in substation Audorf. Length: 65km. | 3 | This investment was schedulted for 2015. Presently it is foreseen a delay of around 1 year due to permitting process. | mid term |  | 1 | Audorf (DE) | Hamburg/Nord (DE) | 44. 148 | 44. 148 | New 400kV double circuit OHL Audorf - Hamburg/Nord including two new 400/230kV transformers in substation Audorf. Length: 65km. | 3 | Delay due to long permitting process | 2017 | 2017 | 1 | Audorf (DE) | Hamburg/Nord (DE) | 209 | 148 | Reinforcement Northeastern DE | New 380kV double circuit OHL Audorf - Hamburg/Nord including two new 380/220kV transformers in substation Audorf and new 380 kV Switchgear in Kummerfeld. Length: 65km. | 3 | Delayed | delay due to long permitting process | 2017 | 2017 | 1 | Audorf (DE) | Hamburg/Nord (DE) | 148 | New 380kV double circuit OHL Audorf - Hamburg/Nord including two new 380/220kV transformers in substation Audorf and new 380 kV Switchgear in Kummerfeld. Length: 65km. | 4 | Delayed | Delay due to long permitting process | 2017 | 2017 | 1 | Audorf (DE) | Hamburg/No rd (DE) | 251 | 148 | Audorf-Dollern | Audorf - Hamburg/Nord | New 380kV double circuit OHL Audorf - Hamburg/Nord including two new 380/220kV transformers in substation Audorf and new 380 kV Switchgear in Kummerfeld. Length - 65km. | 4 | Delayed | Delay due to long permitting process | 1/ 1/ 2018 | 2018 | 1 |  | 0 | Audorf (DE) | Hamburg/Nord (DE) | Overhead Line | AC | 2410 | 380 | 65 | New | 251 | 148 | Audorf-Dollern | Audorf - Hamburg/Nord | 4 | Investment on time |  | 2017 | 2017 | 1 |  | Audorf (DE) | Hamburg/Nord (DE) | Overhead Line | AC | 380 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2017 |  | 7 | DEU | Audorf | Hamburgnord | 54.3132 | 9.7185
247 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1482 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 324 | 1482 | Redipuglia (IT) - Vrtojba (SI) interconnection | Redipuglia (IT) - Vrtojba (SI) Interconnection | 3 | New Investment |  | 2020 | 2020 | 1 | Adria Link Srl, E3 d.o.o., HSE d.o.o.. | REDIPUGLIA | VRTOJBA | Underground Cable | AC | 110 | 324 | 1482 | Redipuglia (IT) - Vrtojba (SI) interconnection | Redipuglia (IT) - Vrtojba (SI) Interconnection | "The Redipuglia (IT) - Vrtojba (SI) interconnection is a third party cross-border electrical line promoted by Adria Link Srl, E3 d.o.o. and HSE d.o.o.. The project concerns an underground cable 110kV a.c. merchant line, 150 MW from Redipuglia (IT) substation to Vrtojba (SI) substation, including a 110/135 kV Phase Shifter Transformer." | 3 | Delayed | The promoter asked the respective NRA for the NTC recalculation not subject to conditions (eg third party network reinforcements), which will be guaranteed for the exemption period and from the entry into the new commercial operation date (COD) of the interconnector. | 2023 | 2023 | 1 | HSE d.o.o. (Holding Slovenske Elektrarne, d.o.o.) E3 d.o.o. (ENERGETIKA, EKOLOGIJA, EKONOMIJA, d.o.o) Adria Link Srl |  | 1 | 1 | REDIPUGLIA | VRTOJBA | ACTransmissionLine | AC | 22.5 | New | 324 | 1482 | Redipuglia (IT) - Vrtojba (SI) interconnection | Redipuglia (IT) - Vrtojba (SI) Interconnection | "The Redipuglia (IT) - Vrtojba (SI) interconnection is a third party cross-border electrical line promoted by Adria Link Srl, E3 d.o.o. and HSE d.o.o.. The project concerns an underground cable 110kV a.c. merchant line, 150 MW from Redipuglia (IT) substation to Vrtojba (SI) substation, including a 110/135 kV Phase Shifter Transformer." | 3 | Delayed | The promoter asked the respective NRA for the NTC recalculation not subject to conditions (eg third party network reinforcements), which will be guaranteed for the exemption period and from the entry into the new commercial operation date (COD) of the interconnector. The process is still ongoing. | 06-2024 | 2024 | 1 | HSE d.o.o. (Holding Slovenske Elektrarne, d.o.o.) E3 d.o.o. (ENERGETIKA, EKOLOGIJA, EKONOMIJA, d.o.o) Adria Link Srl |  | 1 | 1 | REDIPUGLIA | VRTOJBA | ACTransmissionLine | AC | 0 | 110 | 22.5 | New | 324 | 1482 | Redipuglia (IT) - Vrtojba (SI) interconnection | Redipuglia (IT) - Vrtojba (SI) Interconnection | "The Redipuglia (IT) - Vrtojba (SI) interconnection is a third party cross-border electrical line promoted by Adria Link Srl, E3 d.o.o. and HSE d.o.o.. The project concerns an underground cable 110kV a.c. merchant line, 150 MW from Redipuglia (IT) substation to Vrtojba (SI) substation, including a 110/135 kV Phase Shifter Transformer." | 3 | Delayed | The promoter asked the respective NRA for the NTC recalculation not subject to conditions (eg third party network reinforcements), which will be guaranteed for the exemption period and from the entry into the new commercial operation date (COD) of the interconnector. The process was concluded in July 2023. | 08-2026 | 2026 | 1 | Adria Link Srl - HSE d.o.o. (Holding Slovenske Elektrarne, d.o.o.) - E3 d.o.o. (ENERGETIKA, EKOLOGIJA, EKONOMIJA, d.o.o) |  | 1 | 1 | REDIPUGLIA | VRTOJBA | ACTransmissionLine | AC | 0 | 110 | 22.5 | New | 324 | 1482 | Redipuglia (IT) - Vrtojba (SI) interconnection | Redipuglia (IT) - Vrtojba (SI) Interconnection | "The Redipuglia (IT) - Vrtojba (SI) interconnection is a third party cross-border electrical line promoted by Adria Link Srl, E3 d.o.o. and HSE d.o.o.. The project concerns an underground cable 110kV a.c. merchant line, 150 MW from Redipuglia (IT) substation to Vrtojba (SI) substation, including a 110/135 kV Phase Shifter Transformer." |  |  | 09-2026 | 2026 | 1 | Adria Link Srl - HSE d.o.o. (Holding Slovenske Elektrarne, d.o.o.) - E3 d.o.o. (ENERGETIKA, EKOLOGIJA, EKONOMIJA, d.o.o) | 1 | XX | XX | New | 2020 | 2026 | 6 | 8 | ITA;SVN | Redipuglia | Vrtojba | 45.8472 | 13.489 | 45.912 | 13.6354
248 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1483 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 325 | 1483 | AT, SI, IT - South-East Alps Project | Upgrade Obersielach (AT) - Podlog (SI) | 1 | New Investment |  | 2035-2040 | 2040 | 1 | APG; TERNA; ELES | Obersielach (AT) | Podlog (SI) | Overhead Line | AC | 380 | 325 | 1483 | Obersielach (AT) - Podlog (SI) | Upgrade Obersielach (AT) - Podlog (SI) | upgrade from 220 kV to 380 kV | 1 | New Investment |  | 2034 | 2034 | 1 | Austrian Power Grid ELES |  | 1 | 1 | Obersielach (AT) | Podlog (SI) | ACTransmissionLine | AC | 70 | Upgrade | 325 | 1483 | Obersielach (AT) - Podlog (SI) | Upgrade Obersielach (AT) - Podlog (SI) | upgrade from 220 kV to 380 kV | 1 | Investment on time |  | 06-2034 | 2034 | 1 | Austrian Power Grid, Eles |  | 1 | 1 | Obersielach (AT) | Podlog (SI) | ACTransmissionLine | AC | 0 | 380 | 70 | Upgrade | 325 | 1483 | Obersielach (AT) - Podlog (SI) | Upgrade Obersielach (AT) - Podlog (SI) | upgrade from 220 kV to 380 kV | 1 | Investment on time |  | 06-2035 | 2035 | 1 | Austrian Power Grid, Eles |  | 1 | 1 | Obersielach (AT) | Podlog (SI) | ACTransmissionLine | AC | 0 | 380 | 70 | Upgrade | 325 | 1483 | Obersielach (AT) - Podlog (SI) | Upgrade Obersielach (AT) - Podlog (SI) | upgrade from 220 kV to 380 kV | 1 |  | 06-2044 | 2044 | 1 | Austrian Power Grid, Eles | 1 | XX | XX | Upgrade | 2040 | 2044 | 4 | 26 | AUT;SVN | Obersielach | Podlog | 46.6631 | 14.684 | 45.5263 | 15.1896
249 | 2018 | 2018 | [2018] | 1485 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 381 | 1485 | OWP Northsea Part 4 | BorWin 6 (NOR-7-2) | 2 | Investment on time |  | 2030 | 2030 | 1 |  | Cluster BorWin 6 (NOR-7-2) | Hanekenfähr | Subsea Cable | DC | 320 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 12 |  | Cluster Borwin | Hanekenfähr
250 | 2018 | 2020 | [2018, 2020] | 1487 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 172 | 1487 | ElecLink | ElecLink | 4 | Investment on time | In 2016 the project experienced material delays beyond reasonable control as reported to the Commission and the commercial operations date was readjusted. Project is currently on schedule. | 2019 | 2019 | 1 | ElecLink | Sellindge (UK) | Mandarins (FR) | Underground Cable | DC | 320 | 172 | 1487 | ElecLink | ElecLink | ElecLink is a new FR – UK interconnection cable with 1000 MW capacity through the Channel Tunnel between Sellindge (UK) and Mandarins (FR). Converter stations will be located on Eurotunnel concession at Folkestone and Coquelles. This HVDC interconnection is a PCI project (Project of Common Interest) no. 1.7.3 | 4 | Investment on time | In 2016 the project experienced material delays beyond reasonable control as reported to the Commission and the commercial operations date was readjusted. Project is currently on schedule. | 2021 | 2021 | 1 | ElecLink | 1.7.3 | 1 | 1 | Sellindge (UK) | Mandarins (FR) | DCTransmissionLine | DC | 69 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2021 | 2 | 3 | FRA;GBR | Sellindge | Mandarins | 51.1086 | 0.98837
251 | 2018 | 2022 | [2018, 2020, 2022] | 1488 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 103 | 1488 | Reinforcements Ring NL phase I | Diemen-Lelystad-Ens | 4 | Investment on time |  | 2020 | 2020 | 1 | TENNET-NL | Diemen | Ens | Overhead Line | AC | 380 | 103 | 1488 | Reinforcements Ring NL phase I | Diemen-Lelystad-Ens | Upgrade of existing 380kV circuits between Diemen, Lelystad and Ens from 2* 2,5 kA to 2* 4kA circuits by replacing the conductors with HTLS conductors | 4 | Rescheduled |  | 2022 | 2022 | 1 | TENNET-NL |  | 1 | 0 | Diemen | Ens | ACTransmissionLine | AC | 75 | Upgrade | 103 | 1488 | Reinforcements Ring NL phase I | Diemen-Lelystad-Ens | Upgrade of existing 380kV circuits between Diemen, Lelystad and Ens from 2* 2,5 kA to 2* 4kA circuits by replacing the conductors with HTLS conductors | 4 | Rescheduled |  | 06-2022 | 2022 | 1 | TenneT NL |  | 1 | 0 | Diemen | Ens | ACTransmissionLine | AC | 0 | 380 | 75 | Upgrade | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2022 | 2 | 4 | NLD | Diemen | Ens | 52.335 | 4.9843 | 52.2765 | 6.8867
252 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 149 | Cancelled | 149 | New 400kV double circuit OHL Dollern - Stade including new 400kV switchgear in Stade. Length:14km. | 3 | mid term |  | 1 | Dollern (DE) | Stade (DE) | 41 | 41. 149 | New 400kV double circuit OHL Dollern - Stade including new 400kV switchgear in Stade. Length:14km. | 3 | This investment depends on the commissioning of a conventional power plant in the area. The additional reason for delay is the long permitting procedure associated with this investment. | mid term |  | 1 | Dollern (DE) | Stade (DE) | 41. 149 | 41. 149 | New 400kV double circuit OHL Dollern - Stade including new 400kV switchgear in Stade. Length:14km. | 3 | The investment is delayed because of changes in the investment driver | 2017 | 2017 | 1 | Dollern (DE) | Stade (DE) | 164 | 149 | N-S Eastern DE_central section | New 380kV double circuit OHL Dollern - Stade including new 380kV switchgear in Stade. Length:14km. | 3 | Delayed | The investment is delayed because of changes in the investment driver | 2022 | 2022 | 1 | Dollern (DE) | Stade (DE) | 149 | New 380kV double circuit OHL Dollern - Stade including new 380kV switchgear in Stade. Length:14km. | 3 | Investment on time | on time relative to TYNDP14 | 2022 | 2022 | 1 | Dollern (DE) | Stade (DE) | 164 | 149 | N-S Eastern DE_central section | Dollern - Stade | New 380kV double circuit OHL Dollern - Stade including new 380kV switchgear in Stade. Length 14km. | 3 | Delayed | Delay due to long permitting process | 1/ 1/ 2023 | 2023 | 1 |  | 0 | Dollern (DE) | Stade (DE) | Overhead Line | AC | 3749 | 380 | 14 | New | 164 | 149 | N-S Eastern DE_central section | Dollern - Stade | 3 | Ahead of time |  | 2021 | 2021 | 1 | TENNET-DE | Dollern (DE) | Stade (DE) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2021 |  | 11 | DEU | Dollern | Stade | 53.5378 | 9.5385 | 53.5998 | 9.4754
253 | 2018 | 2022 | [2018, 2020, 2022] | 1490 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 103 | 1490 | Reinforcements Ring NL phase I | Ens-Zwolle | 2 | Investment on time |  | 2022 | 2022 | 1 |  | Ens | Zwolle | Overhead Line | AC | 380 | 103 | 1490 | Reinforcements Ring NL phase I | Ens-Zwolle | Upgrade of existing 380kV circuits between Ens and Zwolle from 2* 2,5 kA to 2* 4kA circuits by replacing the conductors with HTLS conductors | 3 | Rescheduled |  | 2024 | 2024 | 1 | TENNET-NL |  | 0 | 0 | Ens | Zwolle | ACTransmissionLine | AC | 32 | Upgrade | 103 | 1490 | Reinforcements Ring NL phase I | Ens-Zwolle | Upgrade of existing 380kV circuits between Ens and Zwolle from 2* 2,5 kA to 2* 4kA circuits by replacing the conductors with HTLS conductors | 4 | Rescheduled |  | 06-2024 | 2024 | 1 | TenneT NL |  | 0 | 0 | Ens | Zwolle | ACTransmissionLine | AC | 0 | 380 | 32 | Upgrade | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2024 | 2 | 6 | NLD | Ens | Zwolle | 52.2765 | 6.8867 | 52.5146 | 6.0977
254 | 2018 | 2018 | [2018] | 1492 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 94 | 1492 | GerPol Improvements | PST in Mikulowa |  | Investment on time |  | 30/06/2016 | 2016 | 1 |  | Mikulowa (PL) | Mikulowa (PL) | PST | AC | 400 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2016 | 0 | -2 | POL | Mikulowa | Mikulowa | 51.0808 | 15.1087 | 51.0808 | 15.1087
255 | 2018 | 2024 | [2018, 2020, 2022, 2024] | 1493 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 94 | 1493 | GerPol Improvements | PST Vierraden | 4 | Investment on time |  | 31/12/2018 | 2018 | 1 |  | Vierraden (DE) | Vierraden (DE) | Phase Shift Transformer | AC | 400 | 94 | 1493 | GerPol Improvements | PST Vierraden | Installation of new PSTs in Vierraden | 4 | Delayed | Permitting is delayed | 2022 | 2022 | 1 | 50HERTZ |  | 1 | 1 | Vierraden | Vierraden | PhaseShiftingTransformer | AC | 0 | Upgrade | 94 | 1493 | GerPol Improvements | PST Vierraden | Installation of new PSTs in Vierraden | 4 | Delayed | Due to a court case, an enforceable building permission for the Uckermark-line was delayed. As the court case was settled in July 2022 the upgrade of the Uckermark-line is proceeding. | 11-2025 | 2025 | 1 | 50Hertz |  | 1 | 1 | Vierraden | Vierraden | PhaseShiftingTransformer | AC | 0 | 400 | 0 | Upgrade | 94 | 1493 | GerPol Improvements | PST Vierraden | Installation of new PSTs in Vierraden | 4 | Delayed | Due to a court case, an enforceable building permission for the Uckermark-line was delayed. As the court case was settled in July 2022 the upgrade of the Uckermark-line is proceeding. | 11-2025 | 2025 | 1 | 50Hertz |  | 1 | 1 | Vierraden | Vierraden | PhaseShiftingTransformer | AC | 0 | 400 | 0 | Upgrade | [5 empty] | 5 | Commissioned |  |  | 0 | [5 empty] | 2018 | 2025 | 7 | 7 | DEU;POL | Vierraden | Vierraden | 53.0978 | 14.2961 | 53.0978 | 14.2961
256 | 2018 | 2022 | [2018, 2020, 2022] | 1496 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 333 | 1496 | PST Foretaille | PST Foretaille | 1 | New Investment |  | 2031 | 2031 | 1 | Swissgrid | Foretaille | Foretaille | Phase Shift Transformer | AC | 220 | 333 | 1496 | PST Foretaille | PST Foretaille | Installation of two PSTs in Foretaille that control the flow on the Foretaille - Verbois 220 kV double line | 1 | Investment on time |  | 2031 | 2031 | 1 | SWISSGRID |  | 1 | 0 | Foretaille | Foretaille | PhaseShiftingTransformer | AC | 0 | New | 333 | 1496 | PST Foretaille | PST Foretaille | Installation of two PSTs in Foretaille that control the flow on the Foretaille - Verbois 220 kV double line | 1 | Investment on time |  | 12-2031 | 2031 | 1 | Swissgrid |  | 1 | 0 | Foretaille | Foretaille | PhaseShiftingTransformer | AC | 0 | 220 | 0 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2031 | 2031 | 0 | 13 | CHE | Foretaille | Foretaille | 46.2444 | 6.1342 | 46.2444 | 6.1342
257 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1498 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 330 | 1498 | 4th 400kV CZ-SK interconnector | New CZ-SK 400 kV interconnector | 1 | New Investment |  | 2035 | 2035 | 1 | CEPS,SEPS | Otrokovice (CZ) | Ladce (SK) | Overhead Line | AC | 400 | 330 | 1498 | 4th 400kV CZ-SK interconnector | New CZ-SK 400 kV interconnector | This investment consists of single circuit 400 kV OHL Otrokovice (CZ) - Ladce (SK). | 1 | New Investment |  | 2035 | 2035 | 1 | CEPS SEPS |  | 1 | 1 | Otrokovice (CZ) | Ladce (SK) | ACTransmissionLine | AC | 78 | New | 330 | 1498 | 4th 400kV CZ-SK interconnector | New CZ-SK 400 kV interconnector | This investment consists of single circuit 400 kV OHL Otrokovice (CZ) - Ladce (SK). | 1 | New Investment |  | 12-2035 | 2035 | 1 | CEPS, SEPS |  | 1 | 1 | Otrokovice (CZ) | Ladce (SK) | ACTransmissionLine | AC | 0 | 400 | 78 | New | 330 | 1498 | 4th 400kV CZ-SK interconnector | New CZ-SK 400 kV interconnector | This investment consists of single circuit 400 kV OHL Otrokovice (CZ) - Ladce (SK). | 1 | New Investment |  | 12-2035 | 2035 | 1 | CEPS, SEPS | 2.7 | 1 | 1 | Otrokovice (CZ) | Ladce (SK) | ACTransmissionLine | AC | 0 | 400 | 78 | New | 330 | 1498 | 4th 400kV CZ-SK interconnector | New CZ-SK 400 kV interconnector | This investment consists of single circuit 400 kV OHL Otrokovice (CZ) - Ladce (SK). | 2 |  | 12-2038 | 2038 | 1 | CEPS, SEPS | 1 | XX | XX | New | 2035 | 2038 | 3 | 20 | CZE;SVK | Otrokovice | Ladce | 49.2088 | 17.5354 | 49.0374 | 18.2873
258 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1499 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 330 | 1499 | 4th 400kV CZ-SK interconnector | New 400 kV substation Ladce | 2 | New Investment |  | 2027 | 2027 | 1 |  | Ladce (SK) | Ladce (SK) | Substation | AC | 400 | 330 | 1499 | 4th 400kV CZ-SK interconnector | Extension of the new 400 kV substation Ladce | This investment consists of extension the new 400 kV substation Ladce, in order to loop 400 kV cross-border OHL from Ladce (SK) to Otrokovice (CZ). The new 400 kV substation Ladce will replace existing 220 kV substation Považská Bystrica and will therefore increase security of supply in this particular region. After commissioning this new 400 kV substation it will be possible to commission new 400 kV cross-border OHL from Ladce (SK) to Otrokovice (CZ). | 2 | New Investment |  | 2027 | 2027 | 1 | CEPS SEPS |  | 0 | 1 | Ladce (SK) | Ladce (SK) | OnshoreSubstation | AC | 0 | New | 330 | 1499 | 4th 400kV CZ-SK interconnector | New 400 kV substation Ladce | This investment consists of the new 400 kV substation Ladce, which will replace existing 220 kV substation Považská Bystrica and will therefore increase security of supply in this particular region. After commissioning this new 400 kV substation it will be possible to build new 400 kV cross-border OHL from Ladce (SK) to Otrokovice (CZ). | 2 | New Investment |  | 12-2026 | 2026 | 1 | CEPS, SEPS |  | 0 | 1 | Ladce (SK) | Ladce (SK) | OnshoreSubstation | AC | 0 | 400 | 0 | New | 330 | 1499 | 4th 400kV CZ-SK interconnector | Extension of 400 kV substation Ladce | This investment consists of the extension of 400 kV substation Ladce, which will replace existing 220 kV substation Považská Bystrica and will therefore increase security of supply in this particular region. After commissioning this new 400 kV substation it will be possible to build new 400 kV cross-border OHL from Ladce (SK) to Otrokovice (CZ). | 2 | New Investment |  | 12-2035 | 2035 | 1 | CEPS, SEPS | 2.7 | 0 | 1 | Ladce (SK) | Ladce (SK) | OnshoreSubstation | AC | 0 | 400 | 0 | New | 330 | 1499 | 4th 400kV CZ-SK interconnector | Extension of 400 kV substation Ladce | This investment consists of the extension of 400 kV substation Ladce, which will replace existing 220 kV substation Považská Bystrica and will therefore increase security of supply in this particular region. After commissioning this new 400 kV substation it will be possible to build new 400 kV cross-border OHL from Ladce (SK) to Otrokovice (CZ). | 2 |  | 12-2038 | 2038 | 1 | CEPS, SEPS | 1 | XX | XX | New | 2027 | 2038 | 11 | 20 | CZE;SVK | Ladce | Ladce | 49.0374 | 18.2873 | 49.0374 | 18.2873
259 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 150 | Commissioned | 150 | New 400kV double circuit ( underground cable+OHL) Conneforde - Maade including new 400kV switchgear Maade. Length: 37km. | 3 | long term |  | 1 | Conneforde (DE) | Maade (DE) | 41 | 41. 150 | New 400kV double circuit ( underground cable+OHL) Conneforde - Maade including new 400kV switchgear Maade. Length: 37km. | 3 | Progresses as planned | long term |  | 1 | Conneforde (DE) | Maade (DE) | 41. 150 | 41. 150 | New 400kV double circuit (OHL, partly underground) Conneforde - Wilhelmshaven (Fedderwarden, former Maade) including new 400kV switchgear Fedderwarden. Length: 35 km. | 3 |  | 2016 | 2016 | 1 | Conneforde (DE) | Fedderwarden (DE) | 208 | 150 | N-S Western DE_section North_1 | New 380kV double circuit (OHL, partly underground) Conneforde - Wilhelmshaven (Fedderwarden, former Maade) including new 400kV switchgear Fedderwarden. Length: 35 km. | 3 | Investment on time |  | 2018 | 2018 | 1 | Conneforde (DE) | Fedderwarden (DE) | 150 | New 380kV double circuit (OHL, partly underground) Conneforde - Wilhelmshaven (Fedderwarden, former Maade) including new 400kV switchgear Fedderwarden. Length: 35 km. | 3 | Investment on time | Progressed as planned | 2018 | 2018 | 1 | Conneforde (DE) | Fedderwarde n (DE) | 208 | 150 | RES-Integration in North-West Germany 1 | Conneforde-Wilhelmshaven | New 380kV double circuit (OHL, partly underground) Conneforde - Wilhelmshaven (Fedderwarden, former Maade) including new 380kV switchgear Fedderwarden. Length&#58; 35 km. | 3 | Delayed | Delay due to long permitting process | 1/ 1/ 2020 | 2020 | 1 |  | 0 | Conneforde (DE) | Fedderwarden (DE) | Overhead Line | AC | 3668 | 380 | 35 | New | 208 | 150 | N-S Western DE_section North_1 | Conneforde-Wilhelmshaven | 3 | Investment on time |  | 2020 | 2020 | 1 | AMPRION;TENNET-DE | Conneforde (DE) | Wilhelmshaven (DE) | Overhead Line | AC | 380 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2020 |  | 10 | DEU | Conneforde | Wilhelmshaven | 53.3258 | 8.0578 | 53.5279 | 8.1063
260 | 2018 | 2020 | [2018, 2020] | 1500 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 48 | 1500 | New SK-HU intercon. - phase 1 | 1. SK-HU interconnection | 3 | Delayed | The approval of the Contract for Construction of PCI No 3.16.1. and PCI No 3.17 between the project promoters MAVIR and SEPS was delayed compared to the initial schedule. The approval and signing fo the Contract caused two years delay in the commissioning of the overhead lines. The Contract was signed on March 1st, 2017 and sets a new commissioning date of end 2020. MAVIR and SEPS do not foresee any additional delay in commissioning. | 2020 | 2020 | 1 |  | Gabcikovo (SK) | Gonyu (HU) | Overhead Line | AC | 400 | 48 | 1500 | New SK-HU intercon. - phase 1 | 1. SK-HU interconnection | "New interconnection (new 2x400 kV tie-line) between SK and HU starting from Gabcikovo substation (SK) to the Gonyu substation (HU), with one circuit connected to Velky Dur (SK) substation. Project does not include the erection of new switching station Gabcikovo next to the existing one. It includes extension of the new Gabcikovo substation by the two 400 kV bays where the new double line will be connected." | 4 | Investment on time |  | 2020 | 2020 | 1 | MAVIR SEPS | 3.16, 3.17 | 1 | 1 | Gabcikovo (SK) | Gonyu (HU) | ACTransmissionLine | AC | 110 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 2 | HUN;SVK | Gabcikovo | Gonyu | 47.88 | 17.4645 | 47.7331 | 17.8279
261 | 2018 | 2020 | [2018, 2020] | 1501 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 48 | 1501 | New SK-HU intercon. - phase 1 | 2. SK-HU interconnection | 3 | Delayed | The approval of the Contract for Construction of PCI No 3.16.1. and PCI No 3.17 between the project promoters MAVIR and SEPS was delayed compared to the initial schedule. The approval and signing fo the Contract caused two years delay in the commissioning of the overhead lines. The Contract was signed on March 1st, 2017 and sets a new commissioning date of end 2020. MAVIR and SEPS do not foresee any additional delay in commissioning. | 2020 | 2020 | 1 |  | Rimavska Sobota (SK) | Sajoivanka (HU) | Overhead Line | AC | 400 | 48 | 1501 | New SK-HU intercon. - phase 1 | 2. SK-HU interconnection | Connection of the two existing substations Rimavska Sobota (SK) - Sajoivanka (HU) by the new double 400 kV OHL armed only with one circuit on the both sides. | 4 | Investment on time |  | 2020 | 2020 | 1 | MAVIR SEPS | 3.16, 3.17 | 1 | 1 | Rimavska Sobota (SK) | Sajoivanka (HU) | ACTransmissionLine | AC | 48 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 2 | HUN;SVK | Rimavska Sobota | Sajoivanka | 48.3834 | 20.0181 | 48.2661 | 20.5794
262 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1503 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 28 | 1503 | Italy-Montenegro | Second HVDC Module IT-ME | 4 | Rescheduled | posteponed | 2026 | 2026 | 1 |  | Villanova (IT) | Lastva (ME) | Subsea Cable | DC | 500 | 28 | 1503 | Italy-Montenegro | Second HVDC Module IT-ME | Second HVDC Module (600 MW) of interconnection line between Italy and Montenegro via 445 km 500kV DC subsea cable and converter stations at both ending points. | 4 | Rescheduled | posteponed | 2026 | 2026 | 1 | TERNA CGES |  | 1 | 1 | Villanova (IT) | Lastva (ME) | DCTransmissionLine | DC | 445 | New | 28 | 1503 | Italy-Montenegro | Second HVDC Module IT-ME | Second HVDC Module (600 MW) of interconnection line between Italy and Montenegro via 445 km 500kV DC subsea cable and converter stations at both ending points. | 4 | Investment on time | Commissioning under review. An update will be given in next TYNDP. | 12-2026 | 2026 | 1 | Terna, CGES |  | 1 | 1 | Villanova (IT) | Lastva (ME) | DCTransmissionLine | DC | 600 | 500 | 445 | New | 28 | 1503 | Italy-Montenegro | Second HVDC pole of the IT-ME interconnection (600 MW) | Second HVDC pole of the interconnection between Italy and Montenegro (600 MW) via 445 km 500kV DC subsea cable | 4 | Investment on time | - | 12-2027 | 2027 | 1 | Terna, CGES |  | 1 | 1 | Villanova (IT) | Lastva (ME) | OffshoreDCTransmissionCable | DC | 600 | 500 | 445 | New | 28 | 1503 | Italy-Montenegro | Second HVDC pole of the IT-ME interconnection (600 MW) | Second HVDC pole of the interconnection between Italy and Montenegro (600 MW) via 445 km 500kV DC subsea cable | 4 |  | 12-2032 | 2032 | 1 | Terna, CGES | 1 | XX | XX | New | 2026 | 2032 | 6 | 14 | ITA;MNE | Villanova | Lastva | 43.0071 | 12.3278 | 42.8396 | 19.249
263 | 2018 | 2024 | [2018, 2020, 2022, 2024] | 1504 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 335 | 1504 | North Sea Wind Power Hub | Power Link Island | 1 | New Investment |  | 2035-2040 | 2040 | 1 | TenneT-NL, Energinet, TenneT-DE | 0 | 0 | Substation | AC | 0 | 335 | 1504 | Project 335 - North Sea Wind Power Hub | Power Link Island | Artificial island central in the North Sea (best location for the first hub is under investigation) with a 'copper plate' type electrical installation suitable to connect 12GW of HVDC systems to shore and up to 12GW of nearby offshore wind. The artificial island is large enough to host all equipment HVDC converters and O&M facilities. Reduction of the total system cost is essential to facilitate large scale offshore wind and interconnection capacity deployment and all options in design, installation and operation should be considered to further reduce cost, including the use of a power hub as an island. Realising a power hub as an island located centrally in the North Sea has been assessed to be technically feasible, based on - amongst others - bathymetry, extreme wind speed and hydraulic conditions (wave heights, surge levels, etc.) and geotechnical data. | 1 | New Investment |  | 2035 | 2035 | 1 | Energinet.dk TENNET-NL TenneT DE | 1.19 | 1 | 1 | 0 | 0 | OffshoreSubstation | AC | 0 | New | 335 | 1504 | North Sea Wind Power Hub | Danish Hub | Hub installation suitable to connect 2GW of HVDC systems to Danish shore and up to 4GW of nearby offshore wind. Danish hub is connected to German and Dutch hub with 2 GW HVDC systems each. | 1 | Investment on time |  | 01-2032 | 2032 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 1.19 | 1 | 1 | 0 | 0 | OffshoreSubstation | AC | 0 | 0 | 0 | New | 335 | 1504 | North Sea Wind Power Hub | Danish Hub | Hub installation suitable to connect 2GW of HVDC systems to Danish shore and up to 4GW of nearby offshore wind. Danish hub is connected to German and Dutch hub with 2 GW HVDC systems each. | 1 | Investment on time |  | 01-2032 | 2032 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 4.1 | 1 | 1 | 0 | 0 | OffshoreSubstation | AC | 0 | 0 | 0 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2040 | 2032 | -8 | 14 | DEU;DNK;NLD
264 | 2018 | 2024 | [2018, 2020, 2022, 2024] | 1505 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 335 | 1505 | North Sea Wind Power Hub | Interconnection DKw to Power Link Island | 1 | New Investment |  | 2035-2040 | 2040 | 1 |  | Endrup, DKw | Power Link Island DKw | Subsea Cable | DC | 0 | 335 | 1505 | Project 335 - North Sea Wind Power Hub | Interconnection DKw to Power Link Island | HVDC connector including substations interfacing the Power Link Island and the Western Danish power system. | 1 | New Investment |  | 2035 | 2035 | 1 | Energinet.dk TENNET-NL TenneT DE | 1.19 | 0 | 1 | "Endrup, DKw" | Power Link Island DKw | OffshoreDCTransmissionCable | DC | 328 | New | 335 | 1505 | North Sea Wind Power Hub | Interconnection DKw to Danish hub | HVDC connector including substations interfacing the Danish hub and the Western Danish power system. | 1 | Investment on time |  | 01-2032 | 2032 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 1.19 | 0 | 1 | REVSING | Danish hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 256 | New | 335 | 1505 | North Sea Wind Power Hub | Interconnection DKw to Danish hub | HVDC connector including substations interfacing the Danish hub and the Western Danish power system. | 1 | Investment on time |  | 01-2032 | 2032 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 4.1 | 0 | 1 | REVSING | Danish hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 256 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2040 | 2032 | -8 | 14 | DEU;DNK;NLD | Revsing | Danish | 55.5073 | 9.1751
265 | 2018 | 2024 | [2018, 2020, 2022, 2024] | 1506 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 335 | 1506 | North Sea Wind Power Hub | Interconnection NL Maasvlakte to Power Link Island | 1 | New Investment |  | 2035-2040 | 2040 | 1 |  | Maasvlakte 380 kV | Power Link Island NL1 | Subsea Cable | DC | 0 | 335 | 1506 | Project 335 - North Sea Wind Power Hub | Interconnection NL Maasvlakte to Power Link Island | One of two HVDC connectors including substations interfacing the Power Link Island and the Dutch power system. | 1 | New Investment |  | 2035 | 2035 | 1 | Energinet.dk TENNET-NL TenneT DE | 1.19 | 0 | 1 | Maasvlakte 380 kV | Power Link Island NL1 | OffshoreDCTransmissionCable | DC | 360 | New | 335 | 1506 | North Sea Wind Power Hub | Interconnection NL Maasvlakte to Dutch hub (#1) | One of two HVDC connectors including substations interfacing the Dutch hub and the Dutch power system. | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 1.19 | 0 | 1 | Maasvlakte 380 kV | Dutch hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 356 | New | 335 | 1506 | North Sea Wind Power Hub | Interconnection NL Maasvlakte to Dutch hub (#1) | One of two HVDC connectors including substations interfacing the Dutch hub and the Dutch power system. | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 4.1 | 0 | 1 | Maasvlakte 380 kV | Dutch hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 356 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2040 | 2035 | -5 | 17 | DEU;DNK;NLD | Maasvlakte | Dutch | 51.9544 | 4.0198
266 | 2018 | 2024 | [2018, 2020, 2022, 2024] | 1507 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 335 | 1507 | North Sea Wind Power Hub | Interconnection NL Eemshaven to Power Link Island | 1 | New Investment |  | 2035-2040 | 2040 | 1 |  | Eemshaven 380 kV | Power Link Island NL2 | Subsea Cable | DC | 0 | 335 | 1507 | Project 335 - North Sea Wind Power Hub | Interconnection NL Eemshaven to Power Link Island | One of two HVDC connectors including substations interfacing the Power Link Island and the Dutch power system. | 1 | New Investment |  | 2035 | 2035 | 1 | Energinet.dk TENNET-NL TenneT DE | 1.19 | 0 | 1 | Eemshaven 380 kV | Power Link Island NL2 | OffshoreDCTransmissionCable | DC | 290 | New | 335 | 1507 | North Sea Wind Power Hub | Interconnection NL Maasvlakte to Dutch hub (#2) | One of two HVDC connectors including substations interfacing the Dutch hub and the Dutch power system. | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 1.19 | 0 | 1 | Maasvlakte 380 kV | Dutch hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 356 | New | 335 | 1507 | North Sea Wind Power Hub | Interconnection NL Maasvlakte to Dutch hub (#2) | One of two HVDC connectors including substations interfacing the Dutch hub and the Dutch power system. | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 4.1 | 0 | 1 | Maasvlakte 380 kV | Dutch hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 356 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2040 | 2035 | -5 | 17 | DEU;DNK;NLD | Maasvlakte | Dutch | 51.9544 | 4.0198
267 | 2018 | 2024 | [2018, 2020, 2022, 2024] | 1508 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 335 | 1508 | North Sea Wind Power Hub | Interconnection DE (area of Brunsbüttel) to Power Link Island | 1 | New Investment |  | 2035-2040 | 2040 | 1 |  | German substation located in the area of Brunsbüttel (north of the Elbe) | Power Link Island DE1 | Subsea Cable | DC | 0 | 335 | 1508 | Project 335 - North Sea Wind Power Hub | Interconnection DE (area of Brunsbüttel) to Power Link Island | One of three HVDC connectors including substations interfacing the Power Link Island and the German power system. | 1 | New Investment |  | 2035 | 2035 | 1 | Energinet.dk TENNET-NL TenneT DE | 1.19 | 0 | 1 | German substation located in the area of Brunsbüttel (north of the Elbe) | Power Link Island DE1 | OffshoreDCTransmissionCable | DC | 390 | New | 335 | 1508 | North Sea Wind Power Hub | Interconnection DE (Heide(West)) to German hub | One of three HVDC connectors including substations interfacing the German hub and the German power system. | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 1.19 | 0 | 1 | Heide(West) | German hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 348 | New | 335 | 1508 | North Sea Wind Power Hub | Interconnection DE (Heide(West)) to German hub | One of three HVDC connectors including substations interfacing the German hub and the German power system. | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 4.1 | 0 | 1 | Heide(West) | German hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 348 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2040 | 2035 | -5 | 17 | DEU;DNK;NLD | Heide | German | 54.1949 | 9.0928
268 | 2018 | 2024 | [2018, 2020, 2022, 2024] | 1509 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 335 | 1509 | North Sea Wind Power Hub | Interconnection DE (area of Oldenburg) to Power Link Island | 1 | New Investment |  | 2035-2040 | 2040 | 1 |  | German substation located in the area of Oldenburg | Power Link Island DE2 | Subsea Cable | DC | 0 | 335 | 1509 | Project 335 - North Sea Wind Power Hub | Interconnection DE (area of Oldenburg) to Power Link Island | One of three HVDC connectors including substations interfacing the Power Link Island and the German power system. | 1 | New Investment |  | 2035 | 2035 | 1 | Energinet.dk TENNET-NL TenneT DE | 1.19 | 0 | 1 | German substation located in the area of Oldenburg | Power Link Island DE2 | OffshoreDCTransmissionCable | DC | 400 | New | 335 | 1509 | North Sea Wind Power Hub | Interconnection DE (area north of Bremen) to German hub | One of three HVDC connectors including substations interfacing the German hub and the German power system. | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 1.19 | 0 | 1 | German substation located in the area north of Bremen | German hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 423 | New | 335 | 1509 | North Sea Wind Power Hub | Interconnection DE (area north of Bremen) to German hub | One of three HVDC connectors including substations interfacing the German hub and the German power system. | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 4.1 | 0 | 1 | German substation located in the area north of Bremen | German hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 423 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2040 | 2035 | -5 | 17 | DEU;DNK;NLD | German Located In The Area North Of Bremen | German
269 | 2010 | 2020 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020] | 151 | Cancelled | 151 | New line, extension of existing and erection of substations, erection of 380/110kV-transformers. | 3 | mid term |  | 1 | Wehrendorf (DE) | Ganderkesee (DE) | 44 | 44. 151 | New line (length: ca. 95km), extension of existing and erection of substations, erection of 380/110kV-transformers. | 3 | Delays due to authorization process. | mid term |  | 1 | Wehrendorf (DE) | Ganderkesee (DE) | 44. 151 | 44. 151 | New line (length: ca. 95km), extension of existing and erection of substations, erection of 380/110kV-transformers. | 3 | Delay due to long permitting process | 2017 | 2017 | 1 | Wehrendorf (DE) | Ganderkesee (DE) | 208 | 151 | N-S Western DE_section North_1 | New line (length: ca. 95km), extension of existing and erection of substations, erection of 380/110kV-transformers. | 3 | Delayed | delay due to long permitting process | 2017 | 2017 | 1 | Wehrendorf (DE) | Ganderkesee (DE) | 151 | New line (length: ca. 95km), extension of existing and erection of substations, erection of 380/110kV-transformers. | 3 | Delayed | Delay due to long permitting process | 2017 | 2017 | 1 | Wehrendorf (DE) | Ganderkesee (DE) | 208 | 151 | RES-Integration in North-West Germany 1 | Ganderkesee - Wehrendorf | New line (length&#58; ca. 95km), extension of existing and erection of substations, erection of 380/110kV-transformers. | 3 | Delayed | Long permitting process and additional longer constructing phase due to requirement of underground cable in some parts of the line. | 1/ 1/ 2021 | 2021 | 1 |  | 0 | Wehrendorf (DE) | Ganderkesee (DE) | Overhead Line | AC | 3538 | 380 | 95 | New | 208 | 151 | N-S Western DE_section North_1 | Ganderkesee - Wehrendorf | 3 | Investment on time |  | 2021 | 2021 | 1 |  | Wehrendorf (DE) | Ganderkesee (DE) | Overhead Line | AC | 380 | 208 | 151 | N-S Western DE_section North_1 | Ganderkesee - Wehrendorf | New line (length ca. 95km), extension of existing and erection of substations, erection of 380/110kV-transformers. | 4 | Delayed | Due to complex and long permitting process | 2023 | 2023 | 1 | AMPRION TenneT DE |  | 1 | 0 | Wehrendorf (DE) | Ganderkesee (DE) | ACTransmissionLine | AC | 95 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2023 |  | 13 | DEU | Wehrendorf | Ganderkesee | 52.3322 | 8.3133 | 53.0345 | 8.5451
270 | 2018 | 2018 | [2018] | 1510 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 337 | 1510 | Conneforde-Merzen | Cloppenburg East - Merzen | 2 | Delayed | Delay due to complex multi-stage permitting process | 2023 | 2023 | 1 | Amprion; TenneT-DE | Cloppenburg East (DE) | Merzen (DE) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 5 | DEU | Cloppenburg East | Merzen |  |  | 52.4776 | 7.8308
271 | 2018 | 2024 | [2018, 2020, 2022, 2024] | 1511 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 335 | 1511 | North Sea Wind Power Hub | Interconnection DE (area of Krümmel) to Power Link Island | 1 | New Investment |  | 2035-2040 | 2040 | 1 |  | German substation located in the area of Krümmel | Power Link Island DE3 | Subsea Cable | DC | 0 | 335 | 1511 | Project 335 - North Sea Wind Power Hub | Interconnection DE (area of Krümmel) to Power Link Island | One of three HVDC connectors including substations interfacing the Power Link Island and the German power system. | 1 | New Investment |  | 2035 | 2035 | 1 | Energinet.dk TENNET-NL TenneT DE | 1.19 | 0 | 1 | German substation located in the area of Krümmel | Power Link Island DE3 | OffshoreDCTransmissionCable | DC | 490 | New | 335 | 1511 | North Sea Wind Power Hub | Interconnection DE (area of Rastede) to German hub | One of three HVDC connectors including substations interfacing the German hub and the German power system. | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 1.19 | 0 | 1 | German substation located in the area of Rastede | German hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 369 | New | 335 | 1511 | North Sea Wind Power Hub | Interconnection DE (area of Rastede) to German hub | One of three HVDC connectors including substations interfacing the German hub and the German power system. | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 4.1 | 0 | 1 | German substation located in the area of Rastede | German hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 369 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2040 | 2035 | -5 | 17 | DEU;DNK;NLD | German Located In The Rastede | German
272 | 2018 | 2018 | [2018] | 1512 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 337 | 1512 | Conneforde-Merzen | Conneforde - Cloppenburg | 2 | Delayed | Delay due to complex multi-stage permitting process | 2023 | 2023 | 1 |  | Conneforde (DE) | Cloppenburg (DE) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 5 | DEU | Conneforde | Cloppenburg | 53.3258 | 8.0578 | 52.8461 | 8.0439
273 | 2018 | 2018 | [2018] | 1513 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 191 | 1513 | OWP TenneT Northsea Part 2 | DolWin3 | 4 | Investment on time |  | 2018 | 2018 | 1 |  | Cluster DolWin3 (DE) | Dörpen/West (DE) | Subsea Cable | DC | 320 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2018 | 0 | 0 | DEU | Cluster Dolwin | Dörpenwest
274 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1514 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 244 | 1514 | Vigy - Uchtelfangen area | Power flow control between Vigy - Uchtelfangen | 2 | New Investment |  | 2027 | 2027 | 1 |  | Vigy (FR) | Uchtelfangen (DE) | Phase Shift Transformer | AC | 400 | 244 | 1514 | Vigy - Uchtelfangen area | Power flow control between Vigy and Ensdorf | Installation of Phase Shift Transformers (PSTs) in Ensdorf substation to allow an optimal use of the capacity increase. | 2 | Investment on time |  | 2027 | 2027 | 1 | AMPRION RTE |  | 0 | 1 | Vigy (FR) | Ensdorf (DE) | PhaseShiftingTransformer | AC | 0 | MostlyUpgrade | 244 | 1514 | Vigy - Uchtelfangen area | Power flow control between Vigy and Ensdorf | Installation of Phase Shift Transformers (PSTs) in Ensdorf substation to allow an optimal use of the capacity increase. | 2 | Rescheduled |  | 12-2029 | 2029 | 1 | Amprion, Rte |  | 0 | 1 | Vigy (FR) | Ensdorf (DE) | PhaseShiftingTransformer | AC | 0 | 400 | 0 | MostlyUpgrade | 244 | 1514 | Vigy - Uchtelfangen area | Power flow control between Vigy and Ensdorf | Installation of Phase Shift Transformers (PSTs) in Ensdorf substation to allow an optimal use of the capacity increase. | 3 | Investment on time |  | 12-2029 | 2029 | 1 | Amprion, Rte |  | 0 | 1 | Vigy (FR) | Ensdorf (DE) | PhaseShiftingTransformer | AC | 0 | 400 | 0 | MostlyUpgrade | 244 | 1514 | Vigy - Uchtelfangen area | Power flow control between Vigy and Ensdorf | Installation of Phase Shift Transformers (PSTs) in Ensdorf substation to allow an optimal use of the capacity increase. |  |  | 12-2029 | 2029 | 1 | Amprion, Rte | 1 | XX | XX | Mostly upgrade | 2027 | 2029 | 2 | 11 | DEU;FRA | Vigy | Ensdorf | 49.2039 | 6.298 | 49.3511 | 11.916
275 | 2018 | 2022 | [2018, 2020, 2022] | 1515 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 252 | 1515 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | Gramme - Courcelles: HTLS upgrade | 1 | Investment on time |  | 2033 | 2033 | 1 |  | Gramme | Courcelles | Overhead Line | AC | 380 | 252 | 1515 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | Gramme - Courcelles: HTLS upgrade | Upgrade of this double-circuit axis to HTLS conductors | 2 | Investment on time |  | 2033 | 2033 | 1 | ELIA |  | 0 | 0 | Gramme | Courcelles | ACTransmissionLine | AC | 60 | Upgrade | 252 | 1515 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | Gramme - Courcelles: HTLS upgrade | Upgrade of this double-circuit axis to HTLS conductors | 2 | Rescheduled |  | 12-2038 | 2038 | 1 | Elia |  | 0 | 0 | Gramme | Courcelles | ACTransmissionLine | AC | 0 | 380 | 60 | Upgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2033 | 2038 | 5 | 20 | BEL | Gramme | Courcelles | 50.4163 | 4.447 | 50.4575 | 4.376
276 | 2018 | 2022 | [2018, 2020, 2022] | 1516 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 252 | 1516 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | Bruegel - Courcelles: HTLS upgrade | 1 | Investment on time |  | 2035 | 2035 | 1 |  | Bruegel | Courcelles | Overhead Line | AC | 380 | 252 | 1516 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | Bruegel - Courcelles: HTLS upgrade | Upgrade of this double-circuit axis to HTLS conductors | 2 | Investment on time |  | 2035 | 2035 | 1 | ELIA |  | 0 | 0 | Bruegel | Courcelles | ACTransmissionLine | AC | 47 | Upgrade | 252 | 1516 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | Bruegel - Courcelles: HTLS upgrade | Upgrade of this double-circuit axis to HTLS conductors | 2 | Investment on time |  | 12-2035 | 2035 | 1 | Elia |  | 0 | 0 | Bruegel | Courcelles | ACTransmissionLine | AC | 0 | 380 | 47 | Upgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 17 | BEL | Bruegel | Courcelles | 50.9635 | 4.4498 | 50.4575 | 4.376
277 | 2018 | 2022 | [2018, 2020, 2022] | 1517 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 252 | 1517 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | Mercator - Bruegel: HTLS upgrade | 1 | Investment on time |  | 2025 | 2025 | 1 |  | Mercator | Bruegel | Overhead Line | AC | 380 | 252 | 1517 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | Mercator - Bruegel: HTLS upgrade | Upgrade of this double-circuit axis to HTLS conductors | 2 | Investment on time |  | 2025 | 2025 | 1 | ELIA |  | 0 | 0 | Mercator | Bruegel | ACTransmissionLine | AC | 16 | Upgrade | 252 | 1517 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | Mercator - Bruegel: HTLS upgrade | Upgrade of this double-circuit axis to HTLS conductors | 3 | Delayed |  | 12-2026 | 2026 | 1 | Elia |  | 1 | 0 | Mercator | Bruegel | ACTransmissionLine | AC | 0 | 380 | 16 | Upgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2026 | 1 | 8 | BEL | Mercator | Bruegel | 50.9097 | 4.3963 | 50.9635 | 4.4498
278 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1518 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 329 | 1518 | Stevin-Izegem/Avelgem (Kustlus): new corridor | Stevin-Izegem/Avelgem: new corridor | 1 | Rescheduled |  | 2028 | 2028 | 1 | ELIA | Stevin | Avelgem | Overhead Line | AC | 380 | 329 | 1518 | Stevin-Izegem/Avelgem (Ventilus): new corridor | Stevin-Izegem/Avelgem: new corridor | Realisation of a new AC corridor up to 6 GW capacity | 2 | Investment on time |  | 2028 | 2028 | 1 | ELIA |  | 1 | 0 | Stevin | Courcelles | ACTransmissionLine | AC | 90 | New | 329 | 1518 | Stevin-Izegem/Avelgem (Ventilus): new corridor | Stevin-Izegem/Avelgem: new corridor | Realisation of a new AC corridor up to 6 GW capacity | 3 | Investment on time |  | 12-2028 | 2028 | 1 | Elia |  | 1 | 0 | Stevin | Courcelles | ACTransmissionLine | AC | 0 | 380 | 90 | New | 329 | 1518 | Stevin-Izegem/Avelgem (Ventilus): new corridor | Stevin-Izegem/Avelgem: new corridor | Realisation of a new AC corridor up to 6 GW capacity | 3 | Investment on time |  | 12-2028 | 2028 | 1 | Elia |  | 1 | 0 | Stevin | Avelgem | ACTransmissionLine | AC | 0 | 380 | 82 | New | 329 | 1518 | Stevin-Izegem/Avelgem (Ventilus): new corridor | Stevin-Izegem/Avelgem: new corridor | Realisation of a new AC corridor up to 6 GW capacity |  |  | 08-2029 | 2029 | 1 | Elia | 0 | XX | XX | New | 2028 | 2029 | 1 | 11 | BEL | Stevin | Avelgem | 51.2065 | 3.2226 | 50.7775 | 3.4497
279 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1519 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 340 | 1519 | Avelgem-Center: new corridor | Avelgem-Center: new corridor | 1 | Investment on time |  | 2028 | 2028 | 1 | ELIA | Avelgem | Center (TBD) | Overhead Line | AC | 380 | 340 | 1519 | Avelgem-Center: new corridor (Boucle du Hainaut) | Avelgem-Center: new corridor | Realisation of a 6 GW new corridor including PSTs | 2 | Investment on time |  | 2028 | 2028 | 1 | ELIA |  | 1 | 0 | Avelgem | Center (TBD) | ACTransmissionLine | AC | 100 | New | 340 | 1519 | Avelgem-Courcelles (Boucle du Hainaut): new corridor | Avelgem-Courcelles | Realisation of a 6 GW new corridor including PSTs | 3 | Investment on time |  | 12-2029 | 2029 | 1 | Elia |  | 1 | 0 | Avelgem | Courcelles | ACTransmissionLine | AC | 0 | 380 | 100 | New | 340 | 1519 | Avelgem-Courcelles (Boucle du Hainaut): new corridor | Avelgem-Courcelles | Realisation of a 6 GW new corridor | 3 | Delayed | Permitting procedure | 12-2030 | 2030 | 1 | Elia |  | 1 | 0 | Avelgem | Courcelles | ACTransmissionLine | AC | 0 | 380 | 90 | New | 340 | 1519 | Avelgem-Courcelles (Boucle du Hainaut): new corridor | Avelgem-Courcelles | Realisation of a 6 GW new corridor |  |  | 06-2032 | 2032 | 1 | Elia | 0 | XX | XX | New | 2028 | 2032 | 4 | 14 | BEL | Avelgem | Courcelles | 50.7775 | 3.4497 | 50.4575 | 4.376
280 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1520 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 342 | 1520 | Central Balkan Corridor | Sofia West (BG) - Nis 2 (RS) 2nd | 1 | Investment on time |  | 2034 | 2034 | 1 | EMS, ESO | SS Sofia West | SS Nis 2 | Overhead Line | AC | 400 | 342 | 1520 | Central Balkan Corridor | Sofia West (BG) - Nis 2 (RS) 2nd | Second interconnection line on the border between Bulgaria and Serbia | 2 | Investment on time |  | 2034 | 2034 | 1 | EMS ESO |  | 1 | 1 | SS Sofia West | SS Nis 2 | ACTransmissionLine | AC | 123 | MostlyUpgrade | 342 | 1520 | Central Balkan Corridor | Sofia West (BG) - Nis 2 (RS) 2nd | Second interconnection line on the border between Bulgaria and Serbia | 2 | Investment on time |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD, CGES, NOS BiH |  | 1 | 1 | SS Sofia West | SS Nis 2 | ACTransmissionLine | AC | 0 | 400 | 123 | MostlyUpgrade | 342 | 1520 | Central Balkan Corridor | SS Bobov Dol (BG) - SS Leskovac 2 (RS) | Second interconnection line on the border between Bulgaria and Serbia | 2 | Investment on time |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD |  | 1 | 1 | SS Bobov Dol | SS Leskovac 2 | ACTransmissionLine | AC | 0 | 400 | 123 | MostlyUpgrade | 342 | 1520 | Central Balkan Corridor | OHL 400 kV SS Bobov Dol (BG) - SS Leskovac 2 (RS) | Second interconnection line on the border between Bulgaria and Serbia | 2 |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD | 1 | XX | XX | Mostly new | 2034 | 2034 | 0 | 16 | BGR;SRB | Bobov Dol | Leskovac | 42.3662 | 23.0074 | 42.9951 | 21.9464
281 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1521 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 338 | 1521 | Adriatic HVDC link | New HVDC line between Villanova and Fano existing 400 kV substations | 1 | New Investment |  | 2027 | 2027 | 1 | TERNA | Villanova | Fano | Subsea Cable | DC | 500 | 338 | 1521 | Adriatic HVDC link | New HVDC line between Villanova and Fano existing 400 kV substations | HVDC lines | 2 | New Investment |  | 2030 | 2030 | 1 | TERNA |  | 1 | 0 | Villanova | Fano | OffshoreDCTransmissionCable | DC | 400 | New | 338 | 1521 | Adriatic HVDC link | New HVDC line between Villanova and Fano existing 400 kV substations | The project envisages a new HVDC interconnection between the Centro Sud (SE Villanova) and Centro Nord (SE Fano) market sections with a capacity increase of 1000 MW. In addition, the interconnection will bring further benefits to the electricity system, including improving the dynamic stability of the grid and the system's response to possible disturbances. | 2 | New Investment |  | 12-2028 | 2028 | 1 | Terna |  | 1 | 0 | Villanova | Fano | OffshoreDCTransmissionCable | DC | 1000 | 500 | 560 | New | 338 | 1521 | Adriatic HVDC link | New HVDC line between Villanova and Fano existing 400 kV substations | HVDC lines | 3 | New Investment |  | 12-2028 | 2028 | 1 | Terna |  | 1 | 0 | Villanova | Fano | OffshoreDCTransmissionCable | DC | 1000 | 500 | 560 | New | 338 | 1521 | Adriatic HVDC link | New HVDC line between Villanova and Fano existing 400 kV substations | HVDC lines | 4 |  | 12-2029 | 2029 | 1 | Terna | 0 | XX | XX | New | 2027 | 2029 | 2 | 11 | ITA | Villanova | Fano | 43.0071 | 12.3278 | 43.8424 | 13.0147
282 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1522 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 342 | 1522 | Central Balkan Corridor | Upgrade of exsisting OHL 220 kV to 400 kV SS Nis 2 - SS Kruševac 1 | 1 | Investment on time |  | 2034 | 2034 | 1 |  | SS Nis 2 | SS Krusevac 1 | Overhead Line | AC | 400 | 342 | 1522 | Central Balkan Corridor | Upgrade of exsisting OHL 220 kV to 400 kV SS Nis 2 - SS Kruševac 1 | Upgrade of exsisting OHL 220 kV to 400 kV SS Nis 2 - SS Kruševac 1 | 2 | Investment on time |  | 2034 | 2034 | 1 | EMS ESO |  | 0 | 1 | SS Nis 2 | SS Krusevac 1 | ACTransmissionLine | AC | 72 | MostlyUpgrade | 342 | 1522 | Central Balkan Corridor | Upgrade of existing OHL 220 kV to 400 kV SS Nis 2 - SS Krusevac 1 | Upgrade of existing OHL 220 kV to 400 kV SS Nis 2 - SS Krusevac 1 | 2 | Investment on time |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD, CGES, NOS BiH |  | 0 | 1 | SS Nis 2 | SS Krusevac 1 | ACTransmissionLine | AC | 0 | 400 | 72 | MostlyUpgrade | 342 | 1522 | Central Balkan Corridor | Upgrade of existing OHL 220 kV to 400 kV SS Nis 2 - SS Krusevac 1 | Upgrade of existing OHL 220 kV to 400 kV SS Nis 2 - SS Krusevac 1 | 2 | Investment on time |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD |  | 0 | 1 | SS Nis 2 | SS Krusevac 1 | ACTransmissionLine | AC | 0 | 400 | 72 | MostlyUpgrade | 342 | 1522 | Central Balkan Corridor | OHL 400 kV SS Leskovac 2 (RS) - SS Kruševac 1 (RS) | New line between existing SS Leskovac 2 and SS Kruševac 1 (after its upgrade to 400 kV) | 2 |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD | 1 | XX | XX | Mostly new | 2034 | 2034 | 0 | 16 | BGR;SRB | Nis | Krusevac | 43.3529 | 24.4123 | 43.5826 | 21.3265
283 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1523 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 342 | 1523 | Central Balkan Corridor | Upgrading SS 220/110 kV Krusevac 1 to 400 kV | 1 | Investment on time |  | 2034 | 2034 | 1 |  | SS Krusevac 1 | SS Krusevac 1 | Substation | AC | 400 | 342 | 1523 | Central Balkan Corridor | Upgrading SS 220/110 kV Krusevac 1 to 400 kV | Upgrading SS 220/110 kV Krusevac 1 to 400 kV | 2 | Investment on time |  | 2034 | 2034 | 1 | EMS ESO |  | 0 | 1 | SS Krusevac 1 | SS Krusevac 1 | OnshoreSubstation | AC | 0 | MostlyUpgrade | 342 | 1523 | Central Balkan Corridor | Upgrading SS 220/110 kV Krusevac 1 to 400 kV | Upgrading SS 220/110 kV Krusevac 1 to 400 kV | 2 | Investment on time |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD, CGES, NOS BiH |  | 0 | 1 | SS Krusevac 1 | SS Krusevac 1 | OnshoreSubstation | AC | 0 | 400 | 0 | MostlyUpgrade | 342 | 1523 | Central Balkan Corridor | Upgrading SS 220/110 kV Krusevac 1 to 400 kV | Upgrading SS 220/110 kV Krusevac 1 to 400 kV | 2 | Investment on time |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD |  | 0 | 1 | SS Krusevac 1 | SS Krusevac 1 | OnshoreSubstation | AC | 0 | 400 | 0 | MostlyUpgrade | 342 | 1523 | Central Balkan Corridor | Upgrading SS 220/110 kV Kruševac 1 to 400 kV | Upgrading SS 220/110 kV Kruševac 1 to 400 kV | 2 |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD | 1 | XX | XX | Mostly new | 2034 | 2034 | 0 | 16 | BGR;SRB | Krusevac | Krusevac | 43.5826 | 21.3265 | 43.5826 | 21.3265
284 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1524 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 342 | 1524 | Central Balkan Corridor | Upgrading of exsisting OHL 220 kV to 400 kV SS Krusevac 1 - SS Kraljevo 3 | 1 | Investment on time |  | 2034 | 2034 | 1 |  | SS Krusevac 1 | SS Kraljevo 3 | Overhead Line | AC | 400 | 342 | 1524 | Central Balkan Corridor | Upgrading of exsisting OHL 220 kV to 400 kV SS Krusevac 1 - SS Kraljevo 3 | Upgrading of exsisting OHL 220 kV to 400 kV SS Krusevac 1 - SS Kraljevo 3 | 2 | Investment on time |  | 2034 | 2034 | 1 | EMS ESO |  | 0 | 1 | SS Krusevac 1 | SS Kraljevo 3 | ACTransmissionLine | AC | 48 | MostlyUpgrade | 342 | 1524 | Central Balkan Corridor | Upgrade of existing OHL 220 kV to 400 kV SS Krusevac 1 - SS Kraljevo 3 | Upgrade of existing OHL 220 kV to 400 kV SS Krusevac 1 - SS Kraljevo 3 | 2 | Investment on time |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD, CGES, NOS BiH |  | 0 | 1 | SS Krusevac 1 | SS Kraljevo 3 | ACTransmissionLine | AC | 0 | 400 | 48 | MostlyUpgrade | 342 | 1524 | Central Balkan Corridor | Upgrade of existing OHL 220 kV to 400 kV SS Krusevac 1 - SS Kraljevo 3 | Upgrade of existing OHL 220 kV to 400 kV SS Krusevac 1 - SS Kraljevo 3 | 2 | Investment on time |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD |  | 0 | 1 | SS Krusevac 1 | SS Kraljevo 3 | ACTransmissionLine | AC | 0 | 400 | 48 | MostlyUpgrade | 342 | 1524 | Central Balkan Corridor | Upgrade of existing OHL 220 kV to 400 kV SS Kruševac 1 - SS Kraljevo 3 | Upgrade of existing OHL 220 kV to 400 kV SS Kruševac 1 - SS Kraljevo 3 | 2 |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD | 1 | XX | XX | Mostly new | 2034 | 2034 | 0 | 16 | BGR;SRB | Krusevac | Kraljevo | 43.5826 | 21.3265 | 44.1021 | 18.9788
285 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1525 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 342 | 1525 | Central Balkan Corridor | Uprading exsisting OHL 220 kV to 400 kV SS Kraljevo 3 - Vardiste | 1 | Investment on time |  | 2033 | 2033 | 1 |  | EMS | EMS | Overhead Line | AC | 400 | 342 | 1525 | Central Balkan Corridor | Uprading exsisting OHL 220 kV to 400 kV SS Kraljevo 3 - SY Pozega | Uprading exsisting OHL 220 kV to 400 kV SS Kraljevo 3 - SY Pozega | 2 | New Investment |  | 2034 | 2034 | 1 | EMS ESO |  | 0 | 1 | EMS | EMS | ACTransmissionLine | AC | 70 | MostlyUpgrade | 342 | 1525 | Central Balkan Corridor | Upgrade of existing OHL 220 kV to 400 kV SS Kraljevo 3 - SY Pozega | Upgrade of existing OHL 220 kV to 400 kV SS Kraljevo 3 - SY Pozega | 2 | Investment on time |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD, CGES, NOS BiH |  | 0 | 1 | SS Kraljevo 3 | SY Pozega | ACTransmissionLine | AC | 0 | 400 | 70 | MostlyUpgrade | 342 | 1525 | Central Balkan Corridor | Upgrade of existing OHL 220 kV to 400 kV SS Kraljevo 3 - SY Pozega | Upgrade of existing OHL 220 kV to 400 kV SS Kraljevo 3 - SY Pozega | 2 | Investment on time |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD |  | 0 | 1 | SS Kraljevo 3 | SY Pozega | ACTransmissionLine | AC | 0 | 400 | 70 | MostlyUpgrade | 342 | 1525 | Central Balkan Corridor | Upgrade of existing OHL 220 kV to 400 kV SS Kraljevo 3 - SY Požega | Upgrade of existing OHL 220 kV to 400 kV SS Kraljevo 3 - SY Požega | 2 |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD | 1 | XX | XX | Mostly new | 2033 | 2034 | 1 | 16 | BGR;SRB | Kraljevo | Sy Pozega | 44.1021 | 18.9788
286 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1526 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 227 | 1526 | Transbalkan Corridor | 400 kV OHL Lastva - Pljevlja | 4 | Delayed | Due to the delay of B. Basta - Obrenovac and B. Basta - Pljevlja investments | 2019 | 2019 | 1 |  | SS Lastva | SS Pljevlja | Overhead Line | AC | 400 | 227 | 1526 | Transbalkan Corridor | 400 kV OHL Lastva - Pljevlja | 400 kV OHL Lastva - Pljevlja | 4 | Delayed | Due to the delay of B. Basta - Obrenovac and B. Basta - Pljevlja investments | 2019 | 2019 | 1 | EMS NOS-BIH CGES |  | 0 | 1 | SS Lastva | SS Pljevlja | ACTransmissionLine | AC | 151 | MostlyNew | 227 | 1526 | Transbalkan Corridor | 400 kV OHL Lastva - Pljevlja | 400 kV OHL Lastva - Pljevlja | 4 | Delayed | Adjusted to match the remainder of the project. | 09-2022 | 2022 | 1 | EMS, NOS-BIH, CGES |  | 0 | 1 | SS Lastva | SS Pljevlja | ACTransmissionLine | AC | 0 | 400 | 151 | MostlyNew | 227 | 1526 | Transbalkan Corridor | 400 kV OHL Lastva - Pljevlja | 400 kV OHL Lastva - Pljevlja | 4 | Delayed | Adjusted to match the remainder of the project. Also, the project faced some issues regarding the land ownership. Those will not harm the construction. | 09-2024 | 2024 | 1 | EMS, NOS-BIH, CGES |  | 0 | 1 | SS Lastva | SS Pljevlja | ACTransmissionLine | AC | 0 | 400 | 151 | MostlyNew | 227 | 1526 | Transbalkan Corridor | 400 kV OHL Lastva - Pljevlja | 400 kV OHL Lastva - Pljevlja | 4 |  | 12-2025 | 2025 | 1 | EMS, NOS-BIH, CGES | 1 | XX | XX | Mostly new | 2019 | 2025 | 6 | 7 | BIH;MNE;SRB | Lastva | Pljevlja | 42.8396 | 19.249 | 43.3562 | 19.3579
287 | 2018 | 2022 | [2018, 2020, 2022] | 1527 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 227 | 1527 | Transbalkan Corridor | 400 kV OHL Kragujevac-Kraljevo | 4 | Investment on time |  | 2020 | 2020 | 1 |  | SS Kragujevac | SS Kraljevo | Overhead Line | AC | 400 | 227 | 1527 | Transbalkan Corridor | 400 kV OHL Kragujevac-Kraljevo | 400 kV OHL Kragujevac-Kraljevo | 4 | Investment on time |  | 2020 | 2020 | 1 | EMS NOS-BIH CGES |  | 0 | 1 | SS Kragujevac | SS Kraljevo | ACTransmissionLine | AC | 60 | MostlyNew | 227 | 1527 | Transbalkan Corridor | 400 kV OHL SS Kragujevac 2 - SS Kraljevo 3 | 400 kV OHL SS Kragujevac 2 - SS Kraljevo 3 | 4 | Delayed | Slightly delayed due to the long contractor choice process. | 09-2022 | 2022 | 1 | EMS, NOS-BIH, CGES |  | 0 | 1 | SS Kragujevac 2 | SS Kraljevo 3 | ACTransmissionLine | AC | 0 | 400 | 59.4 | MostlyNew | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2022 | 2 | 4 | BIH;ITA;MNE;SRB | Kragujevac | Kraljevo | 43.9072 | 19.262 | 44.1021 | 18.9788
288 | 2018 | 2022 | [2018, 2020, 2022] | 1528 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 227 | 1528 | Transbalkan Corridor | Upgrade of SS Kraljevo | 4 | Investment on time |  | 2020 | 2020 | 1 |  | SS Kraljevo | SS Kraljevo | Substation | AC | 400 | 227 | 1528 | Transbalkan Corridor | Upgrade of SS Kraljevo | Upgrade of SS Kraljevo | 4 | Investment on time |  | 2020 | 2020 | 1 | EMS NOS-BIH CGES |  | 0 | 1 | SS Kraljevo | SS Kraljevo | OnshoreSubstation | AC | 0 | MostlyNew | 227 | 1528 | Transbalkan Corridor | Upgrade of SS Kraljevo 3 to 400 kV voltage level | Upgrade of SS Kraljevo 3 to 400 kV voltage level. | 4 | Delayed | Slightly delayed due to the long contractor choice process. | 09-2022 | 2022 | 1 | EMS, NOS-BIH, CGES |  | 0 | 1 | SS Kraljevo 3 | SS Kraljevo 3 | OnshoreSubstation | AC | 0 | 400 | 0 | MostlyNew | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2022 | 2 | 4 | BIH;ITA;MNE;SRB | Kraljevo | Kraljevo | 44.1021 | 18.9788 | 44.1021 | 18.9788
289 | 2018 | 2018 | [2018] | 1529 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 256 | 1529 | Study to upgrade interconnection DE-NL | Upgrade interconnection DE-NL | 1 | Investment on time |  | 2035 | 2035 | 1 |  | tbd | tbd | Phase Shift Transformer | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 17 | DEU;NLD
290 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 153 | Commissioned | 153 | Upgrade of 230kV connection Redwitz - Grafenrheinfeld to 400kV, including new 400kV switchgear Eltmann. Line length: 97km. | 3 | mid term |  | 1 | Redwitz (DE) | Grafenrheinfeld (DE) | 45 | 45. 153 | Upgrade of 230kV connection Redwitz - Grafenrheinfeld to 400kV, including new 400kV switchgear Eltmann. Line length: 97km. | 3 | Investment delay due to delay in the implementation of the line Halle-Schweinfurt(investment 45. 193) | mid term |  | 1 | Redwitz (DE) | Grafenrheinfeld (DE) | 45. 153 | 45. 153 | Upgrade of 230kV connection Redwitz - Grafenrheinfeld to 400kV, including new 400kV switchgear Eltmann. Line length: 97km. | 3 | Delayed due to delaye of related investment 45.193 and unexspected long permitting process of the investment itself | 2014 | 2014 | 1 | Redwitz (DE) | Grafenrheinfeld (DE) | 205 | 153 | N-S transmission DE_par_line_1 | Upgrade of 220kV connection Redwitz - Grafenrheinfeld to 380kV, including new 380kV switchgear Eltmann. Line length: 97km. | 3 | Delayed | Delayed due to delayed of related investment 45.193 and unexpected long permitting process of the investment itself | 2015 | 2015 | 1 | Redwitz (DE) | Grafenrheinfeld (DE) | 153 | Upgrade of 220kV connection Redwitz - Grafenrheinfeld to 380kV, including new 380kV switchgear Eltmann. Line length: 97km. | 3 | Delayed | Delayed due to delay of related investment 45.193 and unexpected long permitting process of the investment itself | 2015 | 2015 | 1 | Redwitz (DE) | Grafenrheinf eld (DE) | 205 | 153 | South-West Interconnector | Redwitz - Grafenrheinfeld | Upgrade of 220kV connection Redwitz - Grafenrheinfeld to 380kV, including new 380kV switchgear Eltmann. Line length -97km. | 5 | Commissioned | in time relative to TYNDP14 | 1/ 1/ 2015 | 2015 | 1 |  | 0 | Redwitz (DE) | Grafenrheinfeld (DE) | Overhead Line | AC | 2473 | 380 | 97 | Upgrade | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2015 |  | 5 | DEU | Redwitz | Grafenrheinfeld | 50.1692 | 11.2084 | 49.9907 | 10.2099
291 | 2018 | 2020 | [2018, 2020] | 1530 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 241 | 1530 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | Upgrading of existing 220 kV line between SS Gradacac (BA) and TPP Tuzla (BA) to 400 kV line | 1 | Rescheduled |  | 2032 | 2032 | 1 |  | SS Gradacac (BA) | TPP Tuzla (BA) | Overhead Line | AC | 400 | 241 | 1530 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | Upgrading of existing 220 kV line between SS Gradacac (BA) and TPP Tuzla (BA) to 400 kV line | Upgrading of existing 220 kV line between SS Gradacac (BA) and TPP Tuzla (BA) to 400 kV line | 1 | Investment on time |  | 2032 | 2032 | 1 | HOPS NOS-BIH |  | 0 | 1 | SS Gradacac (BA) | TPP Tuzla (BA) | ACTransmissionLine | AC | 47.8 | MostlyUpgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2032 | 2032 | 0 | 14 | BIH;HRV | Gradacac | Tpp Tuzla | 44.8781 | 18.4255
292 | 2018 | 2020 | [2018, 2020] | 1531 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 241 | 1531 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | Upgrading existing 220 kV SS Gradacac (BA) to 400 kV | 1 | Rescheduled |  | 2032 | 2032 | 1 |  | SS Gradacac (BA) | SS Gradacac (BA) | Substation | AC | 400 | 241 | 1531 | Upgrading of existing 220 kV lines between HR and BA to 400 kV lines | Upgrading existing 220 kV SS Gradacac (BA) to 400 kV | Upgrading existing 220 kV SS Gradacac (BA) to 400 kV | 1 | Investment on time |  | 2032 | 2032 | 1 | HOPS NOS-BIH |  | 0 | 1 | SS Gradacac (BA) | SS Gradacac (BA) | OnshoreSubstation | AC | 0 | MostlyUpgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2032 | 2032 | 0 | 14 | BIH;HRV | Gradacac | Gradacac | 44.8781 | 18.4255 | 44.8781 | 18.4255
293 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1532 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 343 | 1532 | CSE1 New | New OHL 400 kV Banja Luka - Lika | 2 | Rescheduled |  | 2030 | 2030 | 1 | HOPS, NOS BIH | Banja Luka (BA) | Lika (HR) | Overhead Line | AC | 400 | 343 | 1532 | CSE1 New | New OHL 400 kV Banja Luka - Lika | New OHL 400 kV Banja Luka - Lika | 2 | Rescheduled |  | 2030 | 2030 | 1 | HOPS NOS-BIH |  | 0 | 1 | Banja Luka (BA) | Lika (HR) | ACTransmissionLine | AC | 180 | New | 343 | 1532 | CSE1 New | New OHL 400 kV Banja Luka - Lika | New OHL 400 kV Banja Luka - Lika | 2 | Rescheduled | This investment item is postponed due to mutual agreement | 12-2033 | 2033 | 1 | HOPS, NOS-BIH |  | 0 | 1 | Banja Luka (BA) | Lika (HR) | ACTransmissionLine | AC | 0 | 400 | 180 | New | 343 | 1532 | CSE1 New | New OHL 400 kV Banja Luka - Lika | New OHL 400 kV Banja Luka - Lika | 2 | Rescheduled | This investment item is postponed due to mutual agreement | 12-2035 | 2035 | 1 | HOPS, NOS-BIH |  | 0 | 1 | Banja Luka (BA) | Lika (HR) | ACTransmissionLine | AC | 0 | 400 | 180 | New | 343 | 1532 | CSE1 New | New OHL 400 kV Banja Luka - Lika | New OHL 400 kV Banja Luka - Lika | 2 |  | 12-2035 | 2035 | 1 | HOPS, NOS-BIH | 1 | XX | XX | New | 2030 | 2035 | 5 | 17 | BIH;HRV | Banja Luka | Lika | 44.7721 | 17.1918 | 44.6259 | 15.3436
294 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1533 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 343 | 1533 | CSE1 New | New OHL 400 kV Lika – Melina | 2 | Rescheduled |  | 2030 | 2030 | 1 |  | Lika (HR) | Melina (HR) | Overhead Line | AC | 400 | 343 | 1533 | CSE1 New | New OHL 400 kV Lika – Melina | New OHL 400 kV Lika – Melina | 2 | Investment on time |  | 2030 | 2030 | 1 | HOPS NOS-BIH |  | 0 | 1 | Lika (HR) | Melina (HR) | ACTransmissionLine | AC | 68 | New | 343 | 1533 | CSE1 New | New OHL 400 kV Lika – Melina | New OHL 400 kV Lika – Melina | 2 | Investment on time |  | 12-2030 | 2030 | 1 | HOPS, NOS-BIH |  | 0 | 1 | Lika (HR) | Melina (HR) | ACTransmissionLine | AC | 0 | 400 | 68 | New | 343 | 1533 | CSE1 New | New OHL 2x400 kV Lika – Melina | New OHL 2x400 kV Lika – Melina | 3 | Rescheduled |  | 12-2035 | 2035 | 1 | HOPS, NOS-BIH |  | 0 | 1 | Lika (HR) | Melina (HR) | ACTransmissionLine | AC | 0 | 400 | 68 | New | 343 | 1533 | CSE1 New | New OHL 2x400 kV Lika – Melina | New OHL 2x400 kV Lika – Melina |  |  | 12-2035 | 2035 | 1 | HOPS, NOS-BIH | 1 | XX | XX | New | 2030 | 2035 | 5 | 17 | BIH;HRV | Lika | Melina | 44.6259 | 15.3436 | 44.3731 | 17.4549
295 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1534 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 343 | 1534 | CSE1 New | New OHL 400 kV Lika – Konjsko | 2 | Rescheduled |  | 2030 | 2030 | 1 |  | Lika (HR) | Konjsko (HR) | Overhead Line | AC | 400 | 343 | 1534 | CSE1 New | New OHL 400 kV Lika – Konjsko | New OHL 400 kV Lika – Konjsko | 2 | Investment on time |  | 2030 | 2030 | 1 | HOPS NOS-BIH |  | 1 | 1 | Lika (HR) | Konjsko (HR) | ACTransmissionLine | AC | 203 | New | 343 | 1534 | CSE1 New | New OHL 400 kV Lika – Konjsko | New OHL 400 kV Lika – Konjsko | 2 | Investment on time |  | 12-2030 | 2030 | 1 | HOPS, NOS-BIH |  | 1 | 1 | Lika (HR) | Konjsko (HR) | ACTransmissionLine | AC | 0 | 400 | 203 | New | 343 | 1534 | CSE1 New | New OHL 2x400 kV Lika – Konjsko | New OHL 2x400 kV Lika – Konjsko | 3 | Rescheduled |  | 12-2034 | 2034 | 1 | HOPS, NOS-BIH |  | 1 | 1 | Lika (HR) | Konjsko (HR) | ACTransmissionLine | AC | 0 | 400 | 203 | New | 343 | 1534 | CSE1 New | New OHL 2x400 kV Lika – Konjsko | New OHL 2x400 kV Lika – Konjsko |  |  | 12-2034 | 2034 | 1 | HOPS, NOS-BIH | 1 | XX | XX | New | 2030 | 2034 | 4 | 16 | BIH;HRV | Lika | Konjsko | 44.6259 | 15.3436 | 42.6444 | 18.4769
296 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1535 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 343 | 1535 | CSE1 New | New Substation 400/110 kV Lika | 2 | Rescheduled |  | 2029 | 2029 | 1 |  | Lika (HR) | Lika (HR) | Substation | AC | 400 | 343 | 1535 | CSE1 New | New Substation 400/110 kV Lika | New Substation 400/110 kV Lika | 2 | Rescheduled |  | 2029 | 2029 | 1 | HOPS NOS-BIH |  | 0 | 1 | Lika (HR) | Lika (HR) | OnshoreSubstation | AC | 0 | New | 343 | 1535 | CSE1 New | New Substation 400/110 kV Lika | New Substation 400/110 kV Lika | 2 | Investment on time |  | 12-2030 | 2030 | 1 | HOPS, NOS-BIH |  | 0 | 1 | Lika (HR) | Lika (HR) | OnshoreSubstation | AC | 0 | 400 | 0 | New | 343 | 1535 | CSE1 New | New Substation 400/110 kV Lika | New Substation 400/110 kV Lika | 3 | Rescheduled |  | 12-2034 | 2034 | 1 | HOPS, NOS-BIH |  | 0 | 1 | Lika (HR) | Lika (HR) | OnshoreSubstation | AC | 0 | 400 | 0 | New | 343 | 1535 | CSE1 New | New Substation 400/110 kV Lika | New Substation 400/110 kV Lika |  |  | 12-2034 | 2034 | 1 | HOPS, NOS-BIH | 1 | XX | XX | New | 2029 | 2034 | 5 | 16 | BIH;HRV | Lika | Lika | 44.6259 | 15.3436 | 44.6259 | 15.3436
297 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1536 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 341 | 1536 | North CSE Corridor | Portile de Fier (RO) - Djerdap (RS) 2nd | 1 | Investment on time |  | 2030 | 2030 | 1 | EMS, Transelectrica | Portile de Fier | Djerdap | Overhead Line | AC | 400 | 341 | 1536 | North CSE Corridor | Portile de Fier (RO) - Djerdap (RS) 2nd | Portile de Fier (RO) - Djerdap (RS) 2nd . Doubling the existing OHL 400 kV (1.5 km on Serbian (thermal limit 1800 A) and 0.5 km on Romanian( thermal limit 2192 A) Side) | 1 | Investment on time |  | 2030 | 2030 | 1 | EMS TRANSELECTRICA |  | 1 | 1 | Portile de Fier | Djerdap | ACTransmissionLine | AC | 2 | MostlyNew | 341 | 1536 | North CSE Corridor | Portile de Fier (RO) - Djerdap (RS) 2nd | Portile de Fier (RO) - Djerdap (RS) 2nd . Doubling the existing OHL 400 kV (1.5 km on Serbian (thermal limit 1800 A) and 0.5 km on Romanian( thermal limit 2192 A) Side) | 2 | Ahead of time |  | 09-2029 | 2029 | 1 | EMS, Transelectrica |  | 1 | 1 | Portile de Fier | Djerdap | ACTransmissionLine | AC | 0 | 400 | 2 | MostlyNew | 341 | 1536 | North CSE Corridor | Portile de Fier (RO) - Djerdap (RS) 2nd | Portile de Fier (RO) - Djerdap (RS) 2nd . Doubling the existing OHL 400 kV (1.5 km on Serbian (thermal limit 1800 A) and 0.5 km on Romanian( thermal limit 2192 A) Side) | 2 | Investment on time |  | 09-2029 | 2029 | 1 | EMS, Transelectrica |  | 1 | 1 | Portile de Fier | Djerdap | ACTransmissionLine | AC | 0 | 400 | 2 | MostlyNew | 341 | 1536 | North CSE Corridor | OHL 400 kV SS Portile de Fier (RO) - SY Ðerdap 1 (RS) | New 400 kV line across the Danube river, connecting the existing SS Portile de Fier in Romania with SY Ðerdap 1 on the Serbian side. | 2 |  | 09-2029 | 2029 | 1 | EMS, Transelectrica | 1 | XX | XX | Mostly new | 2030 | 2029 | -1 | 11 | ROU;SRB | Portile De Fier | Djerdap | 46.6075 | 23.8328 | 44.6713 | 22.5294
298 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1537 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 341 | 1537 | North CSE Corridor | New SS 400/110 kV Belgrade West | 1 | Investment on time |  | 2030 | 2030 | 1 |  | Belgrade West | Belgrade West | Substation | AC | 400 | 341 | 1537 | North CSE Corridor | New SS 400/110 kV Belgrade West | New SS 400/110 kV Belgrade West | 1 | Investment on time |  | 2030 | 2030 | 1 | EMS TRANSELECTRICA |  | 0 | 1 | Belgrade West | Belgrade West | Transformer | AC | 0 | MostlyNew | 341 | 1537 | North CSE Corridor | New SS 400/110 kV Belgrade 50 | New SS 400/110 kV Belgrade 50 (former name Belgrade West) | 2 | Ahead of time |  | 09-2028 | 2028 | 1 | EMS, Transelectrica |  | 0 | 1 | Belgrade 50 | Belgrade 50 | Transformer | AC | 0 | 400 | 0 | MostlyNew | 341 | 1537 | North CSE Corridor | New SS 400/110 kV Belgrade 50 | New SS 400/110 kV Belgrade 50 (former name Belgrade West) | 3 | Investment on time |  | 09-2028 | 2028 | 1 | EMS, Transelectrica |  | 0 | 1 | Belgrade 50 | Belgrade 50 | Transformer | AC | 0 | 400 | 0 | MostlyNew | 341 | 1537 | North CSE Corridor | New SS 400/110 kV Belgrade 50 | New SS 400/110 kV Belgrade 50 (former name Belgrade West) |  |  | 09-2028 | 2028 | 1 | EMS, Transelectrica | 1 | XX | XX | Mostly new | 2030 | 2028 | -2 | 10 | ROU;SRB | Belgrade | Belgrade | 47.6689 | 19.0757 | 47.6689 | 19.0757
299 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1538 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 341 | 1538 | North CSE Corridor | New OHL 400 kV WPP Cibuk - SS Belgrade West | 1 | Investment on time |  | 2030 | 2030 | 1 |  | WPP Cibuk | Belgrade West | Overhead Line | AC | 400 | 341 | 1538 | North CSE Corridor | New OHL 400 kV WPP Cibuk - SS Belgrade West | """New OHL 400 kV WPP Cibuk - SS Belgrade West""" | 1 | Investment on time |  | 2030 | 2030 | 1 | EMS TRANSELECTRICA |  | 0 | 1 | WPP Cibuk | Belgrade West | ACTransmissionLine | AC | 60 | MostlyNew | 341 | 1538 | North CSE Corridor | New OHL 400 kV WPP Cibuk - SS Belgrade 50 | New OHL 400 kV WPP Cibuk - SS Belgrade 50 | 2 | Ahead of time |  | 09-2028 | 2028 | 1 | EMS, Transelectrica |  | 0 | 1 | WPP Cibuk | SS Belgrade 50 | ACTransmissionLine | AC | 0 | 400 | 83 | MostlyNew | 341 | 1538 | North CSE Corridor | New OHL 400 kV WPP Cibuk - SS Belgrade 50 | New OHL 400 kV WPP Cibuk - SS Belgrade 50 | 3 | Investment on time |  | 09-2028 | 2028 | 1 | EMS, Transelectrica |  | 0 | 1 | WPP Cibuk | SS Belgrade 50 | ACTransmissionLine | AC | 0 | 400 | 83 | MostlyNew | 341 | 1538 | North CSE Corridor | New OHL 400 kV SY Cibuk 1 - SS Belgrade 50 | New OHL 400 kV SY Cibuk 1 - SS Belgrade 50 |  |  | 09-2028 | 2028 | 1 | EMS, Transelectrica | 1 | XX | XX | Mostly new | 2030 | 2028 | -2 | 10 | ROU;SRB | Wpp Cibuk | Belgrade |  |  | 47.6689 | 19.0757
300 | 2018 | 2022 | [2018, 2020, 2022] | 1539 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 103 | 1539 | Reinforcements Ring NL phase I | Krimpen-Geertruidenberg | 3 | Investment on time |  | 2020 | 2020 | 1 |  | Krimpen | Geertruidenberg | Overhead Line | AC | 380 | 103 | 1539 | Reinforcements Ring NL phase I | Krimpen-Geertruidenberg | Upgrade of existing 380kV circuits between Krimpen and Geertruidenberg from 2* 2,5 kA to 2* 4kA circuits by replacing the conductors with HTLS conductors | 3 | Rescheduled |  | 2023 | 2023 | 1 | TENNET-NL |  | 0 | 0 | Krimpen | Geertruidenberg | ACTransmissionLine | AC | 35 | Upgrade | 103 | 1539 | Reinforcements Ring NL phase I | Krimpen-Geertruidenberg | Upgrade of existing 380kV circuits between Krimpen and Geertruidenberg from 2* 2,5 kA to 2* 4kA circuits by replacing the conductors with HTLS conductors | 4 | Rescheduled |  | 06-2023 | 2023 | 1 | TenneT NL |  | 0 | 0 | Krimpen | Geertruidenberg | ACTransmissionLine | AC | 0 | 380 | 35 | Upgrade | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2023 | 3 | 5 | NLD | Krimpen | Geertruidenberg | 51.9144 | 4.5888 | 51.6962 | 4.8778
301 | 2018 | 2022 | [2018, 2020, 2022] | 1540 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 103 | 1540 | Reinforcements Ring NL phase I | Eindhoven-Maasbracht | 3 | Investment on time |  | 2023 | 2023 | 1 |  | Eindhoven | Maasbracht | Overhead Line | AC | 380 | 103 | 1540 | Reinforcements Ring NL phase I | Eindhoven-Maasbracht | Upgrade of existing 380kV circuits between Eindhoven and Maasbracht from 2* 2,5 kA to 2* 4kA circuits by replacing the conductors with HTLS conductors | 3 | Rescheduled |  | 2025 | 2025 | 1 | TENNET-NL |  | 0 | 0 | Eindhoven | Maasbracht | ACTransmissionLine | AC | 50 | Upgrade | 103 | 1540 | Reinforcements Ring NL phase I | Eindhoven-Maasbracht | Upgrade of existing 380kV circuits between Eindhoven and Maasbracht from 2* 2,5 kA to 2* 4kA circuits by replacing the conductors with HTLS conductors | 4 | Rescheduled |  | 06-2025 | 2025 | 1 | TenneT NL |  | 0 | 0 | Eindhoven | Maasbracht | ACTransmissionLine | AC | 0 | 380 | 50 | Upgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2025 | 2 | 7 | NLD | Eindhoven | Maasbracht | 51.4486 | 5.4501 | 51.1429 | 5.8831
302 | 2018 | 2020 | [2018, 2020] | 1541 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 344 | 1541 | Reinforcements Ring NL phase II | Zwolle-Hengelo-Doetinchem-Dodewaard | 1 | Investment on time |  | 2035 | 2035 | 1 | TENNET-NL | Zwolle | Dodewaard | Overhead Line | AC | 380 | 344 | 1541 | Reinforcements Ring NL phase II | Zwolle-Hengelo-Doetinchem-Dodewaard | Upgrade of existing 380kV circuits between Zwolle, Hengelo, Doetinchem and Dodewaard from 2* 2,5 kA to 2* 4kA circuits by replacing the conductors with HTLS conductors | 1 | Rescheduled |  | 2040 | 2040 | 1 | TENNET-NL |  | 1 | 0 | Zwolle | Dodewaard | ACTransmissionLine | AC | 165 | Upgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2040 | 5 | 22 | NLD | Zwolle | Dodewaard | 52.5146 | 6.0977 | 51.914 | 5.6569
303 | 2018 | 2018 | [2018] | 1542 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 345 | 1542 | Northern East-West connection NL | Northern East-West connection NL | 1 | New Investment |  | 2040 | 2040 | 1 | TENNET-NL | tbd | tbd | Overhead Line | AC | 0 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2040 | 2040 | 0 | 22 | NLD
304 | 2018 | 2018 | [2018] | 1543 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 346 | 1543 | ZuidWest380 NL | ZuidWest380 West | 4 | Investment on time |  | 2021 | 2021 | 1 | TENNET-NL | Borssele | Rilland | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2021 | 0 | 3 | NLD | Borssele | Rilland | 51.4255 | 3.7379 | 51.4165 | 4.1812
305 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1544 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 346 | 1544 | ZuidWest380 NL | ZuidWest3808 Oost | 3 | Investment on time |  | 2025 | 2025 | 1 |  | Rilland | Tilburg | Overhead Line | AC | 380 | 346 | 1544 | ZuidWest380 NL Oost | ZuidWest3808 Oost | New 380 kV substation Tilburg; New 380 kV double circuit line 2645MVA between Rilland and Tilburg | 3 | Rescheduled |  | 2029 | 2029 | 1 | TENNET-NL |  | 1 | 0 | Rilland | Tilburg | ACTransmissionLine | AC | 80 | New | 346 | 1544 | ZuidWest380 NL Oost | ZuidWest380 Oost | New 380 kV substation Tilburg; New 380 kV double circuit line 2645MVA between Rilland and Tilburg | 3 | Delayed | Complicated permitting procedures | 06-2029 | 2029 | 1 | TenneT-NL |  | 1 | 0 | Rilland | Tilburg | ACTransmissionLine | AC | 0 | 380 | 80 | New | 346 | 1544 | ZuidWest380 NL Oost | ZuidWest380 Oost | New 380 kV substation Tilburg; New 380 kV double circuit line 2645MVA between Rilland and Tilburg | 3 | Delayed | Complicated permitting procedures | 06-2029 | 2029 | 1 | TenneT-NL |  | 1 | 0 | Rilland | Tilburg | ACTransmissionLine | AC | 0 | 380 | 80 | New | 346 | 1544 | ZuidWest380 NL Oost | ZuidWest380 Oost | New 380 kV substation Tilburg; New 380 kV double circuit line 2645MVA between Rilland and Tilburg | 4 |  | 06-2031 | 2031 | 1 | TenneT-NL | 0 | XX | XX | New | 2025 | 2031 | 6 | 13 | BEL;NLD | Rilland | Tilburg | 51.4165 | 4.1812 | 51.5856 | 5.0661
306 | 2018 | 2018 | [2018] | 1545 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 347 | 1545 | Maasvlakte – Noord Brabant connection NL | Maasvlakte – Noord Brabant connection | 1 | New Investment |  | 2040 | 2040 | 1 | TENNET-NL | Krimpen | Geertruidenberg | Overhead Line | AC | 0 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2040 | 2040 | 0 | 22 | NLD | Krimpen | Geertruidenberg | 51.9144 | 4.5888 | 51.6962 | 4.8778
307 | 2018 | 2020 | [2018, 2020] | 1546 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 348 | 1546 | NoordWest380 NL | NoordWest380 | 4 | Investment on time |  | 2021 | 2021 | 1 | TENNET-NL | Eemshaven Oude Schip | Vierverlaten | Overhead Line | AC | 380 | 348 | 1546 | NoordWest380 NL | NoordWest380 | Upgrade of existing 220kV circuits between Eemshaven and Vierverlaten to 2* 380kV – 2645MVA circuits; New 380kV substation Vierverlaten | 4 | Rescheduled |  | 2023 | 2023 | 1 | TENNET-NL |  | 1 | 0 | Eemshaven Oude Schip | Vierverlaten | ACTransmissionLine | AC | 40 | Upgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2023 | 2 | 5 | NLD | Eemshaven Oude Schip | Vierverlaten |  |  | 53.2131 | 6.4853
308 | 2018 | 2018 | [2018] | 1547 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 351 | 1547 | Eastern HVDC Link | Eastern HVDC Link | 1 | Rescheduled |  | 2024 | 2024 | 1 | NGET; SHETL | Peterhead (GB) | Hawthorn Pit (GB) | Subsea Cable | DC | 500 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2024 | 2024 | 0 | 6 | GBR | Peterhead | Hawthorn Pit | 57.5053 | -1.7813
309 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1555 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 375 | 1555 | Lienz (AT) - Veneto region (IT) 220 kV | Lienz (AT) - Veneto region (IT) | 3 | New Investment |  | 2024 | 2024 | 1 | TERNA; APG | Lienz (AT) | Veneto region (IT) | Overhead Line | AC | 220 | 375 | 1555 | Lienz (AT) - Veneto region (IT) 220 kV | Lienz (AT) - Veneto region (IT) | Reconstruction of the existing 220kV-interconnection line between Lienz and Veneto Region (IT) | 2 | New Investment |  | 2027 | 2027 | 1 | Austrian Power Grid TERNA |  | 1 | 1 | Lienz (AT) | Veneto region (IT) | ACTransmissionLine | AC | 140 | Upgrade | 375 | 1555 | Lienz (AT) - Veneto region (IT) 220 kV | Lienz (AT) - Veneto region (IT) | Reconstruction of the existing 220kV-interconnection line between Lienz and Veneto Region (IT) | 2 | New Investment |  | 12-2035 | 2035 | 1 | Austrian Power Grid, Terna |  | 1 | 1 | Lienz (AT) | Veneto region (IT) | ACTransmissionLine | AC | 0 | 220 | 140 | Upgrade | 375 | 1555 | Lienz (AT) - Veneto region (IT) 220 kV | Lienz (AT) - Veneto region (IT) | Reconstruction of the existing 220kV-interconnection line between Lienz and Veneto Region (IT) | 2 | New Investment |  | 12-2035 | 2035 | 1 | Austrian Power Grid, Terna | 2.8 | 1 | 1 | Lienz (AT) | Veneto region (IT) | ACTransmissionLine | AC | 0 | 220 | 140 | Upgrade | 375 | 1555 | Lienz (AT) - Veneto region (IT) 220 kV | Lienz (AT) - Veneto region (IT) | Reconstruction of the existing 220kV-interconnection line between Lienz and Veneto Region (IT) | 2 |  | 12-2036 | 2036 | 1 | Austrian Power Grid, Terna | 1 | XX | XX | Upgrade | 2024 | 2036 | 12 | 18 | AUT;ITA | Lienz | Veneto Region | 46.8299 | 12.7681
310 | 2018 | 2020 | [2018, 2020] | 1556 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 336 | 1556 | Prati (IT) – Steinach (AT) | Prati (IT) – Steinach (AT) | 4 | New Investment |  | 2019 | 2019 | 1 | Terna; Tinetz | Prati di Vizze (IT) | Steinach (AT) | Overhead Line | AC | 132 | 336 | 1556 | Prati (IT) – Steinach (AT) | Prati (IT) – Steinach (AT) | New Italy-Austria tie-line between the existing 110kV Steinach substation in Austria and 132 kV Brennero substation, including PST; and connection to 132 kV Prati di Vizze substation." | 4 | New Investment | rescheduled | 2023 | 2023 | 1 | TERNA Tinetz |  | 1 | 1 | Prati di Vizze (IT) | Steinach (AT) | ACTransmissionLine | AC | 139 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2023 | 4 | 5 | AUT;ITA | Prati Di Vizze | Steinach | 46.9015 | 11.4829 | 47.0918 | 11.4653
311 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1557 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 339 | 1557 | Italian HVDC tri-terminal link | Italian HVDC tri-terminal link | 1 | New Investment |  | 2027 | 2027 | 1 |  | SARDINIA REGION | SICILY REGION - CENTRAL SOUTH OF ITALY | Subsea Cable | DC | 0 | 339 | 1557 | Italian HVDC tri-terminal link | Italian HVDC tri-terminal link | Italian HVDC tri-terminal link | 2 | Investment on time |  | 2025 | 2025 | 1 | TERNA |  | 1 | 0 | SARDINIA REGION | SICILY REGION - SOUTH OF ITALY | OffshoreDCTransmissionCable | DC | 900 | New | 339 | 1557 | Tyrrhenian link | Tyrrhenian HVDC link - West | The project foresees a new HVDC interconnection between Sardinia (SE Selargius) and Sicily (SE Caracoli). The design solution envisages a two-terminal plant configuration as it will allow greater reliability to the link by increasing the security and stability of the two islands, as well as an increase in NTC between the two market areas of 1000 MW. | 3 | Investment on time |  | 12-2027 | 2027 | 1 | Terna |  | 1 | 0 | Caracoli | Selargius | OffshoreDCTransmissionCable | DC | 1000 | 500 | 900 | New | 339 | 1557 | Tyrrhenian link | Tyrrhenian HVDC link - West | Italian HVDC tri-terminal link | 4 | Investment on time |  | 12-2027 | 2027 | 1 | Terna |  | 1 | 0 | Caracoli | Selargius | OffshoreDCTransmissionCable | DC | 1000 | 500 | 900 | New | 339 | 1557 | Tyrrhenian link | Tyrrhenian HVDC link - West | Italian HVDC tri-terminal link | 4 |  | 12-2027 | 2027 | 1 | Terna | 0 | XX | XX | New | 2027 | 2027 | 0 | 9 | ITA | Caracoli | Selargius | 37.9669 | 13.7255 | 39.257 | 9.1676
312 | 2018 | 2020 | [2018, 2020] | 1558 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 320 | 1558 | Slovenia-Hungary/Croatia interconnection | Double 400 kV OHL Cirkovce(SI)-Heviz(HU)/Zerjavinec(HR) | 3 | Delayed | The main reasons for the delay are environmental problems in the permitting process (including problems with different authorities included in the process) and acquisition of or access to land. | 2018 | 2018 | 1 | ELES; MAVIR; HOPS | Cirkovce (SI) | Heviz (HU) \ Zerjavinec (HR) | Overhead Line | AC | 400 | 320 | 1558 | Slovenia-Hungary/Croatia interconnection | Double 400 kV OHL Cirkovce(SI)-Heviz(HU)/Zerjavinec(HR) | New double circuit 400kV overhead line in Slovenia (section Cirkovce-Pince) and a new 400 kV substation Cirkovce (SI). The new OHL will be connected to one circuit of the existing double circuit 400kV OHL Heviz(HU)-Zerjavinec(HR), creating two new cross-border lines: Heviz(HU)-Cirkovce(SI) and Cirkovce (SI)-Zerjavinec (HR). | 4 | Investment on time |  | 2021 | 2021 | 1 | ELES HOPS MAVIR | 3.9.1 | 1 | 1 | Cirkovce (SI) | Heviz (HU) \ Zerjavinec (HR) | ACTransmissionLine | AC | 80 | MostlyNew | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2021 | 3 | 3 | HRV;HUN;SVN | Cirkovce | Heviz Hu Zerjavinec | 46.3949 | 15.7274
313 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1559 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 376 | 1559 | Refurbishment of the 400kV Meliti(GR)-Bitola(MK) interconnector | New investment | 1 | New Investment |  | 2030 | 2030 | 1 | MEPSO(MK), IPTO(GR) | Bitola (MK) | Meliti (GR) | Overhead Line | AC | 400 | 376 | 1559 | Refurbishment of the 400kV Meliti(GR)-Bitola(MK) interconnector | Refurbishment of the 400kV Meliti (GR)-Bitola (MK) interconnector | Reconductoring of the existing 400kV interconnection line Meliti (GR)-Bitola (MK) | 1 | New Investment |  | 2036 | 2036 | 1 | Admie MEPSO |  | 1 | 1 | Meliti (GR) | Bitola (MK) | ACTransmissionLine | AC | 35.512 | Upgrade | 376 | 1559 | Refurbishment of the 400kV Meliti(GR)-Bitola(MK) interconnector | Refurbishment of the 400kV Meliti (GR)-Bitola (MK) interconnector | Reconductoring of the existing 400kV interconnection line Meliti (GR)-Bitola (MK) | 1 | Investment on time |  | 06-2035 | 2035 | 1 | Admie, MEPSO |  | 1 | 1 | Meliti (GR) | Bitola (MK) | ACTransmissionLine | AC | 0 | 400 | 35.512 | Upgrade | 376 | 1559 | Refurbishment of the 400kV Meliti(GR)-Bitola(MK) interconnector | Refurbishment of the 400kV Meliti (GR)-Bitola (MK) interconnector | Reconductoring of the existing 400kV interconnection line Meliti (GR)-Bitola (MK) | 1 | Investment on time |  | 12-2035 | 2035 | 1 | Admie, MEPSO |  | 1 | 1 | Meliti (GR) | Bitola (MK) | ACTransmissionLine | AC | 0 | 400 | 35.512 | Upgrade | 376 | 1559 | Refurbishment of the 400kV Meliti(GR)-Bitola(MK) interconnector | Refurbishment of the 400kV Meliti (GR)-Bitola (MK) interconnector | Reconductoring of the existing 400kV interconnection line Meliti (GR)-Bitola (MK) | 1 |  | 12-2035 | 2035 | 1 | Admie, MEPSO | 1 | XX | XX | Upgrade | 2030 | 2035 | 5 | 17 | GRC;MKD | Meliti | Bitola | 40.8512 | 25.8323 | 41.0316 | 21.3303
314 | 2010 | 2020 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020] | 156 | Cancelled | 156 | New 400kV double circuit OHL Dörpen - Niederrhein including extension of existing substations. Length: 167km. | 3 | long term |  | 1 | Niederrhein (DE) | Dörpen/West (DE) | 44 | 44. 156 | New 400kV double circuit OHL Dörpen - Niederrhein including extension of existing substations. Length: 167km. | 3 | Delays due to authorization process. | mid term |  | 1 | Niederrhein (DE) | Dörpen/West (DE) | 44. 156 | 44. 156 | New 400kV double circuit OHL Dörpen - Niederrhein including extension of existing substations. | 3 | The investment is delayed due to delays in public-law and private-law licensing procedures. | 2017 | 2017 | 1 | Niederrhein (DE) | Dörpen/West (DE) | 208 | 156 | N-S Western DE_section North_1 | New 380 kV double circuit overhead line Dörpen - Niederrhein including extension of existing substations. | 3 | Delayed | The project is delayed due to delays in public-law and civil-law licensing procedures. | 2018 | 2018 | 1 | Niederrhein (DE) | Dörpen/West (DE) | 156 | New 380 kV double circuit overhead line Dörpen - Niederrhein including extension of existing substations. | 3 | Investment on time | Progressed as planned | 2018 | 2018 | 1 | Niederrhein (DE) | Dörpen/West (DE) | 208 | 156 | RES-Integration in North-West Germany 1 | Niederrhein-Dörpen | New 380 kV double circuit overhead line Dörpen - Niederrhein including extension of existing substations. | 3 | Delayed | Delay due to long permitting process | 1/ 1/ 2019 | 2019 | 1 |  | 0 | Niederrhein (DE) | Dörpen/West (DE) | Overhead Line | AC | 988 | 380 | 162 | New | 208 | 156 | N-S Western DE_section North_1 | Niederrhein-Dörpen | 3 | Investment on time |  | 2021 | 2021 | 1 |  | Niederrhein (DE) | Dörpen/West (DE) | Overhead Line | AC | 380 | 208 | 156 | N-S Western DE_section North_1 | Niederrhein-Dörpen | New 380 kV double circuit overhead line Dörpen - Niederrhein including extension of existing substations. | 4 | Delayed | Due to complex and long permitting process | 2023 | 2023 | 1 | AMPRION TenneT DE |  | 0 | 0 | Niederrhein (DE) | Dörpen/West (DE) | ACTransmissionLine | AC | 182 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2023 |  | 13 | DEU | Niederrhein | Dörpenwest | 51.4013 | 6.5096
315 | 2018 | 2018 | [2018] | 1560 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 103 | 1560 | Reinforcements Ring NL phase I | Randstad380 noordring | 4 | Investment on time |  | 2018 | 2018 | 1 |  | Beverwijk | Bleiswijk | Overhead Line | AC | 380 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2018 | 0 | 0 | NLD | Beverwijk | Bleiswijk | 52.4788 | 4.6728 | 52.011 | 4.5311
316 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1561 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 377 | 1561 | Upgrade BE-NL interconnector VanEyck-Maasbracht | BE-NL interconnector: upgrade VanEyck-Maasbracht | 1 | Investment on time |  | 2030 | 2030 | 1 | Elia, TENNET-NL | VanEyck | Maasbracht | Overhead Line | AC | 380 | 377 | 1561 | Upgrade BE-NL interconnector VanEyck-Maasbracht | BE-NL interconnector: upgrade VanEyck-Maasbracht | Upgrade of existing interconnection between Van Eyck (BE) and Maasbracht (NL), by adding PST(s) and/or replacing existing conductors by HTLS. The study is to confirm the appropriate implementation option and phasing of this implementation also with respect to evolution of DE-NL interconnectors. | 1 | Investment on time |  | 2030 | 2030 | 1 | ELIA TENNET-NL |  | 1 | 1 | VanEyck | Maasbracht | ACTransmissionLine | AC | 12 | Upgrade | 377 | 1561 | Upgrade BE-NL interconnector VanEyck-Maasbracht | BE-NL interconnector: upgrade VanEyck-Maasbracht | Upgrade of existing interconnection between Van Eyck (BE) and Maasbracht (NL), by adding PST(s) and/or replacing existing conductors by HTLS. The study is to confirm the appropriate implementation option and phasing of this implementation also with respect to evolution of DE-NL interconnectors. | 1 | Rescheduled | The project has been rescheduled to be in line with the timing of other grid reinforcements to be compliant with the Clean Energy Package. | 12-2032 | 2032 | 1 | Elia, TenneT-NL |  | 1 | 1 | VanEyck | Maasbracht | ACTransmissionLine | AC | 0 | 380 | 12 | Upgrade | 377 | 1561 | Upgrade BE-NL interconnector VanEyck-Maasbracht | BE-NL interconnector: upgrade VanEyck-Maasbracht | Upgrade of existing interconnection between Van Eyck (BE) and Maasbracht (NL), by adding PST(s) and/or replacing existing conductors by HTLS. The study is to confirm the appropriate implementation option and phasing of this implementation also with respect to evolution of DE-NL interconnectors. | 1 | Investment on time |  | 12-2032 | 2032 | 1 | Elia, TenneT-NL |  | 1 | 1 | VanEyck | Maasbracht | ACTransmissionLine | AC | 0 | 380 | 12 | Upgrade | 377 | 1561 | Upgrade BE-NL interconnector VanEyck-Maasbracht | BE-NL interconnector: upgrade VanEyck-Maasbracht | Upgrade of existing interconnection between Van Eyck (BE) and Maasbracht (NL), by adding PST(s) and/or replacing existing conductors by HTLS. The study is to confirm the appropriate implementation option and phasing of this implementation also with respect to evolution of DE-NL interconnectors. | 1 |  | 12-2034 | 2034 | 1 | Elia, TenneT-NL | 1 | XX | XX | Upgrade | 2030 | 2034 | 4 | 16 | BEL;NLD | Vaneyck | Maasbracht |  |  | 51.1429 | 5.8831
317 | 2018 | 2018 | [2018] | 1564 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 170 | 1564 | Baltics synchro with CE | New 110 kV OHL Pagegiai-Bitenai near LT-RU border | 4 | New Investment |  | 2019 | 2019 | 1 |  | Pagegiai | Bitenai | Overhead Line | AC | 110 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2019 | 0 | 1 | LTU | Pagegiai | Bitenai | 55.1333 | 21.9104
318 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1565 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 170 | 1565 | Baltics synchro with CE | Reconstruction of 330 kV OHL LE-Vilnius | 4 | Investment on time |  | 2018 | 2018 | 1 |  | LE | Vilnius | Overhead Line | AC | 330 | 170 | 1565 | Baltic States Synchronization with Continental Europe | Reconstruction of 330 kV OHL LE-Vilnius | Reconstruction of 330 kV OHL LE-Vilnius from single-circuit into double-circuit | 5 | Investment on time |  | 2020 | 2020 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Lietuvos E | Vilnius | ACTransmissionLine | AC | 41 | New | 170 | 1565 | Baltic States Synchronization with Continental Europe | Reconstruction of 330 kV OHL LE-Vilnius | Reconstruction of 330 kV OHL LE-Vilnius from single-circuit into double-circuit line. | 5 | Investment on time |  | 11-2020 | 2020 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Lietuvos E | Vilnius | ACTransmissionLine | AC | 0 | 330 | 41 | MostlyNew | 170 | 1565 | Baltic States Synchronization with Continental Europe | Reconstruction of 330 kV OHL LE-Vilnius | Reconstruction of 330 kV OHL LE-Vilnius from single-circuit into double-circuit line. | 5 | Investment on time |  | 11-2020 | 2020 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Lietuvos E | Vilnius | ACTransmissionLine | AC | 0 | 330 | 40.9 | MostlyNew | 170 | 1565 | Baltic States Synchronization with Continental Europe | Reconstruction of 330 kV OHL LE-Vilnius | Reconstruction of 330 kV OHL LE-Vilnius from single-circuit into double-circuit line. | 5 | Commissioned | 11-2020 | 2020 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2018 | 2020 | 2 | 2 | EST;LTU;LVA;POL | Lietuvos E | Vilnius | 55.9006 | 23.2596 | 54.687 | 25.2829
319 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1566 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 170 | 1566 | Baltics synchro with CE | Reconstructions in North Eastern Lithuania | 4 | New Investment |  | 2021 | 2021 | 1 |  | - | - | Substation | AC | 330 | 170 | 1566 | Baltic States Synchronization with Continental Europe | Reconstructions in North Eastern Lithuania | Utenos TP substations and 330/1110/10 kV Ignalinos AE TP substations reconstruction. Relocation of HV equipment (from 330/110/10 kV Ignalinos AE TP substation to 330/110/10 kV Lietuvos E TP substation) and changing topology of 330 kV overhead lines | 4 | Investment on time |  | 2021 | 2021 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | - | - |  | AC | 0 | New | 170 | 1566 | Baltic States Synchronization with Continental Europe | Reconstructions in North Eastern Lithuania | Reconstruction of 330 kV Utenos and 330 kV Ignalinos AE substations. Relocation of HV equipment (from 330/110/10 kV Ignalinos AE substation to 330/110/10 kV Lietuvos E substation) and changing topology of 330 kV overhead lines. | 5 | Investment on time |  | 12-2021 | 2021 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Utena | Ignalinos AE | OnshoreSubstation | AC | 0 | 330 | 0 | MostlyNew | 170 | 1566 | Baltic States Synchronization with Continental Europe | Reconstructions in North Eastern Lithuania | Reconstruction of 330 kV Utenos and 330 kV Ignalinos AE substations. Relocation of HV equipment (from 330/110/10 kV Ignalinos AE substation to 330/110/10 kV Lietuvos E substation) and changing topology of 330 kV overhead lines. | 5 | Investment on time |  | 12-2021 | 2021 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Utena | Ignalinos AE | OnshoreSubstation | AC | 0 | 330 | 0 | MostlyNew | 170 | 1566 | Baltic States Synchronization with Continental Europe | Reconstructions in North Eastern Lithuania | Reconstruction of 330 kV Utenos and 330 kV Ignalinos AE substations. Relocation of HV equipment (from 330/110/10 kV Ignalinos AE substation to 330/110/10 kV Lietuvos E substation) and changing topology of 330 kV overhead lines. | 5 | Commissioned | 12-2021 | 2021 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2021 | 2021 | 0 | 3 | EST;LTU;LVA;POL | Utena | Ignalinos Ae | 55.4984 | 25.6026 | 55.6072 | 26.4271
320 | 2018 | 2018 | [2018] | 1567 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 170 | 1567 | Baltics synchro with CE | Reinforcements of 110 kV lines near LT-BY border | 2 | New Investment |  | 2023 | 2023 | 1 |  | Griskonys | Valkininkai | Overhead Line | AC | 110 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 5 | LTU | Griskonys | Valkininkai | 54.5104 | 24.2092 | 54.3589 | 24.8417
321 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1568 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 170 | 1568 | Baltics synchro with CE | Construction of new 400/330 kV autotransformers in Alytus substation | 2 | New Investment |  | 2021 | 2021 | 1 |  | Alytus | - | Substation | AC | 400 | 170 | 1568 | Baltic States Synchronization with Continental Europe | Upgrades in Alytus substation (LT) | Construction of three new 400/330 kV autotransformers in Alytus substation, to make LT-PL border operation in AC mode. | 4 | Investment on time |  | 2021 | 2021 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Alytus | - |  | AC | 0 | New | 170 | 1568 | Baltic States Synchronization with Continental Europe | Upgrades in Alytus substation (LT) | Construction of three new 400/330 kV autotransformers in Alytus substation, to connect Lithuania and Poland transmission systems in AC mode. | 5 | Investment on time |  | 12-2021 | 2021 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Alytus | - | Transformer | AC | 0 | 400 | 0 | MostlyNew | 170 | 1568 | Baltic States Synchronization with Continental Europe | Upgrades in Alytus substation (LT) | Construction of three new 400/330 kV autotransformers in Alytus substation, to connect Lithuania and Poland transmission systems in AC mode. | 5 | Investment on time |  | 12-2021 | 2021 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Alytus | - | Transformer | AC | 0 | 400 | 0 | MostlyNew | 170 | 1568 | Baltic States Synchronization with Continental Europe | Upgrades in Alytus substation (LT) | Construction of three new 400/330 kV autotransformers in Alytus substation, to connect Lithuania and Poland transmission systems in AC mode. | 5 | Commissioned | 12-2021 | 2021 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2021 | 2021 | 0 | 3 | EST;LTU;LVA;POL | Alytus
322 | 2018 | 2018 | [2018] | 1569 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 170 | 1569 | Baltics synchro with CE | Rerouting of exicting HVDC converter in Alytus | 2 | New Investment |  | 2024 | 2024 | 1 |  | Alytus | - | LCC converter station | DC | 0 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2024 | 2024 | 0 | 6 |  | Alytus
323 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 157 | Cancelled | 157 | New 400kV double circuit OHL Wahle - Mecklar including two new substations. Length: 210km. | 3 | long term |  | 1 | Wahle (DE) | Mecklar (DE) | 44 | 44. 157 | New 400kV double circuit OHL Wahle - Mecklar including two new substations. Length: 210km. | 3 | Delays due to authorization process. | mid term |  | 1 | Wahle (DE) | Mecklar (DE) | 44. 157 | 44. 157 | New 400kV double circuit OHL Wahle - Mecklar including two new substations. Length: 210km. | 3 | Delay due to long permitting process | 2018 | 2018 | 1 | Wahle (DE) | Mecklar (DE) | 164 | 157 | N-S Eastern DE_central section | New 380kV double circuit OHL Wahle - Mecklar including two new substations. Length: 210km. | 3 | Delayed | delay due to long permitting process | 2018 | 2018 | 1 | Wahle (DE) | Mecklar (DE) | 157 | New 380kV double circuit OHL Wahle - Mecklar including two new substations. Length: 210km. | 3 | Investment on time | no delay to TYNDP14 | 2018 | 2018 | 1 | Wahle (DE) | Mecklar (DE) | 164 | 157 | N-S Eastern DE_central section | Wahle - Mecklar | New 380kV double circuit OHL Wahle - Mecklar including two new substations. Length: 210km. | 3 | Delayed | Delay due to long permitting process | 1/ 1/ 2021 | 2021 | 1 |  | 0 | Wahle (DE) | Mecklar (DE) | Overhead Line | AC | 2264 | 380 | 210 | New | 164 | 157 | N-S Eastern DE_central section | Wahle - Mecklar | 3 | Investment on time |  | 2021 | 2021 | 1 |  | Wahle (DE) | Mecklar (DE) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2021 |  | 11 | DEU | Wahle | Mecklar | 52.2718 | 10.3634 | 50.9175 | 9.7612
324 | 2018 | 2018 | [2018] | 1570 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 170 | 1570 | Baltics synchro with CE | Construction of new HVDC converter in Bitenai | 2 | New Investment |  | 2024 | 2024 | 1 |  | Bitenai | - | LCC converter station | DC | 0 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2024 | 2024 | 0 | 6 |  | Bitenai
325 | 2018 | 2022 | [2018, 2020, 2022] | 1571 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 170 | 1571 | Baltics synchro with CE | New voltage control units (such as SVC) in LT | 2 | New Investment |  | 2023 | 2023 | 1 |  | - | - | Substation | AC | 0 | 170 | 1571 | Baltic States Synchronization with Continental Europe | New Voltage stabiliser units (SVC), Battery Energy Storage System (BESS) control units in Lithuania, Latvia and Estonia. | If Studies concerning not known today further infrastructure aspects related to the implementation of the synchronisation of the Baltic States’ system with the continental European network, identify the necessity to install additional SVC. New Battery Energy Storage System (BESS) units - for frequency regulation (FCR and FRR) and to ensure power system secure and stable operation. | 1 | Investment on time |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | - | - |  | AC | 0 | New | 170 | 1571 | Baltic States Synchronization with Continental Europe | New Voltage stabiliser units (SVC), Battery Energy Storage System (BESS) control units in Lithuania, Latvia and Estonia. | If Studies concerning not known today further infrastructure aspects related to the implementation of the synchronisation of the Baltic States’ system with the continental European network, identify the necessity to install additional SVC. New Battery Energy Storage System (BESS) units - for frequency regulation (FCR and FRR) and to ensure power system secure and stable operation. | 4 | Investment on time |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | - | - | ReactiveCompensationDevice | AC | 0 | 0 | 0 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2025 | 2 | 7 | EST;LTU;LVA;POL
326 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1572 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 170 | 1572 | Baltics synchro with CE | Preparation works in Baltics: Baltic AGC system, frequency control monitoring system. | 2 | New Investment |  | 2024 | 2024 | 1 |  | - | - | Substation | AC | 0 | 170 | 1572 | Baltic States Synchronization with Continental Europe | Monitoring and control system upgrades in Lithuania, Latvia and Estonia. Upgrading control systems of exicting HVDC connections (EstLink 1 and EstLink 2 and NordBalt). | Upgrade of PSS in power stations. AGC impementation and commissioning in SCADA systems and power plants. WAMS and WAMPAC systems. Upgrade of instrument transformers and metering system in transmission network and is necessary to provide stable metering system during synchronous operation with Continental Europe or during island operation in emergency cases. System upgrades (automatics modernisation), SCADA and dispatcher trainer. In order to ensure system stability after high sudden power imbalance during BSPS island operation, activation of fast frequency reserves within view milliseconds via HVDC’s links is crucial. For this project is necessary to perform research, modelling and upgrading control system of HVDC's. | 2 | Investment on time |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | - | - |  | AC | 0 | New | 170 | 1572 | Baltic States Synchronization with Continental Europe | Monitoring and control system upgrades in Lithuania, Latvia and Estonia. Upgrading control systems of exicting HVDC connections (EstLink 1 and EstLink 2 and NordBalt). | Upgrade of PSS in power stations. AGC impementation and commissioning in SCADA systems and power plants. WAMS and WAMPAC systems. Upgrade of instrument transformers and metering system in transmission network and is necessary to provide stable metering system during synchronous operation with Continental Europe or during island operation in emergency cases. System upgrades (automatics modernisation), SCADA and dispatcher trainer. In order to ensure system stability after high sudden power imbalance during BSPS island operation, activation of fast frequency reserves within view milliseconds via HVDC’s links is crucial. For this project is necessary to perform research, modelling and upgrading control system of HVDC's. | 2 | Investment on time |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | - | - |  | AC | 0 | 0 | 0 | MostlyNew | 170 | 1572 | Baltic States Synchronization with Continental Europe | Further infrastructure aspects related to the implementation of the synchronisation of the Baltic States’ system with the continental European network. | This generic project shall implement the first phase of improvements in system control and stability required for synchronous operation with Continental Europe, including: - development of Baltic AGC and frequency stability assessment systems with special protection schemes; - upgrades of SCADAs and other IT systems and their environment needed for real time operation and planning (WAMS and WAMPAC systems in Latvia, Lithuania and Estonia); - PMU system in Latvia; - upgrade control systems of HVDC connectors (Estlink1, Estlink2 and Nordbalt); - construction of three synchronous condensers, one in each country - in Püssi (Estonia), Ventspils (Latvia) and Alytus (Lithuania); - BESS (Battery Energy Storage System) in Latvia. Further infrastructure aspects ‘not-known-today’ related to the implementation of the synchronisation of the Baltic States’ system with the continental European Network arising from ongoing synchronisation studies. | 4 | Investment on time |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | - | - | OnshoreSubstation | AC | 0 | 0 | 0 | MostlyNew | 170 | 1572 | Baltic States Synchronization with Continental Europe | Further infrastructure aspects related to the implementation of the synchronisation of the Baltic States’ system with the continental European network. | This generic project shall implement the first phase of improvements in system control and stability required for synchronous operation with Continental Europe, including: - development of Baltic AGC and frequency stability assessment systems with special protection schemes; - upgrades of SCADAs and other IT systems and their environment needed for real time operation and planning (WAMS and WAMPAC systems in Latvia, Lithuania and Estonia); - PMU system in Latvia; - upgrade control systems of HVDC connectors (Estlink1, Estlink2 and Nordbalt); - construction of three synchronous condensers, one in each country - in Püssi (Estonia), Ventspils (Latvia) and Alytus (Lithuania); - BESS (Battery Energy Storage System) in Latvia. - measures for protection of critical Synchronisation infrastructure in the Baltic States and Poland. This investment item is relevant to all four project promoters: Litgrid, AST, Elering and PSE. |  |  | 12-2029 | 2029 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2024 | 2029 | 5 | 11 | EST;LTU;LVA;POL
327 | 2018 | 2022 | [2018, 2020, 2022] | 1583 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 263 | 1583 | Lake Constance East | Vorarlberg | 1 | Rescheduled | under consideration, commissioning year 2035 | 2035 | 2035 | 1 |  | Rüthi | Border area (DE-AT) | Overhead Line | AC | 380 | 263 | 1583 | Lake Constance East | Vorarlberg | Voltage increase of all existing lines to 380 kV (without an increase of the line cross-section) and 2 new 380/22'0 kV transformers in Bürs | 1 | Investment on time |  | 2035 | 2035 | 1 | SWISSGRID VUEN |  | 1 | 1 | Rüthi | Border area (DE-AT) | ACTransmissionLine | AC | 1 | MostlyNew | 263 | 1583 | Lake Constance East | Vorarlberg | Voltage increase of all existing lines to 380 kV (without an increase of the line cross-section) and 2 new 380/220 kV transformers in Bürs | 1 | Investment on time |  | 12-2035 | 2035 | 1 | Swissgrid, VUEN, Amprion, Transnet-BW |  | 1 | 1 | Rüthi | Border area (DE-AT) | ACTransmissionLine | AC | 0 | 380 | 1 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 17 | AUT;CHE;DEU | Rüthi | Border Area | 47.2558 | 9.7003
328 | 2018 | 2024 | [2018, 2020, 2022, 2024] | 1584 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 378 | 1584 | Transformer Gatica | Transformer Gatica | 2 | New Investment |  | 2025 | 2025 | 1 | REE | Gatica 400 | Gatica 220 | Substation | AC | 220 | 378 | 1584 | Transformer Gatica | Transformer Gatica | Only 400 to 220 kV transformer. Not the whole substation | 2 | New Investment |  | 2025 | 2025 | 1 | Red Eléctrica de España |  | 1 | 0 | GATICA 400 | GATICA 220 | OnshoreSubstation | AC | 0 | New | 378 | 1584 | Transformer Gatica | Transformer Gatica | Only 400 to 220 kV transformer. Not the whole substation | 2 | Rescheduled |  | 12-2027 | 2027 | 1 | Red Eléctrica |  | 1 | 0 | GATICA 400 | GATICA 220 | OnshoreSubstation | AC | 0 | 220 | 0 | New | 378 | 1584 | Transformer Gatica | Transformer Gatica | Only 400 to 220 kV transformer. Not the whole substation | 2 | Rescheduled |  | 12-2027 | 2027 | 1 | Red Eléctrica |  | 1 | 0 | GATICA 400 | GATICA 220 | OnshoreSubstation | AC | 0 | 220 | 0 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2025 | 2027 | 2 | 9 | ESP | Gatica | Gatica
329 | 2018 | 2024 | [2018, 2020, 2022, 2024] | 1593 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 379 | 1593 | Uprate Gatica lines | Uprate Gatica-Guenes | 1 | New Investment |  | 2025 | 2025 | 1 | REE | Gatica | Guenes | Overhead Line | AC | 400 | 379 | 1593 | Uprate Gatica lines | Uprate Gatica-Guenes | Uprate 400 kV Gatica-Guenes substation | 1 | New Investment |  | 2025 | 2025 | 1 | Red Eléctrica de España |  | 1 | 0 | Gatica | Guenes | ACTransmissionLine | AC | 38.8 | Upgrade | 379 | 1593 | Uprate Gatica lines | Uprate Gatica-Guenes | Uprate 400 kV Gatica-Guenes substation | 2 | Investment on time |  | 12-2026 | 2026 | 1 | Red Eléctrica |  | 1 | 0 | Gatica | Guenes | ACTransmissionLine | AC | 0 | 400 | 38.8 | Upgrade | 379 | 1593 | Uprate Gatica lines | Uprate Gatica-Guenes | Uprate 400 kV Gatica-Guenes substation | 2 | Investment on time |  | 12-2026 | 2026 | 1 | Red Eléctrica |  | 1 | 0 | Gatica | Guenes | ACTransmissionLine | AC | 0 | 400 | 38.8 | Upgrade | [5 empty] | 5 | Commissioned |  |  | 0 | [5 empty] | 2025 | 2026 | 1 | 8 | ESP | Gatica | Guenes |  |  | 43.209 | -3.0945
330 | 2018 | 2024 | [2018, 2020, 2022, 2024] | 1595 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 379 | 1595 | Uprate Gatica lines | Uprate Gatica-Amorebieta-Ichaso | 1 | New Investment |  | REE |  | 1 |  | Gatica | Ichaso | Overhead Line | AC | 400 | 379 | 1595 | Uprate Gatica lines | Uprate Gatica-Amorebieta-Ichaso | Uprate the 400 kV axis Gatica-Amorebieta-Ichaso | 1 | New Investment |  | 2025 | 2025 | 1 | Red Eléctrica de España |  | 0 | 0 | Gatica | Ichaso | ACTransmissionLine | AC | 69.12 | Upgrade | 379 | 1595 | Uprate Gatica lines | Uprate Gatica-Amorebieta-Ichaso | Uprate the 400 kV axis Gatica-Amorebieta-Ichaso | 2 | Investment on time |  | 12-2026 | 2026 | 1 | Red Eléctrica |  | 0 | 0 | Gatica | Ichaso | ACTransmissionLine | AC | 0 | 400 | 69.12 | Upgrade | 379 | 1595 | Uprate Gatica lines | Uprate Gatica-Amorebieta-Ichaso | Uprate the 400 kV axis Gatica-Amorebieta-Ichaso | 2 | Investment on time |  | 12-2026 | 2026 | 1 | Red Eléctrica |  | 0 | 0 | Gatica | Ichaso | ACTransmissionLine | AC | 0 | 400 | 69.12 | Upgrade | [5 empty] | 5 | Commissioned |  |  | 0 | [6 empty] | 2026 |  | 8 | ESP | Gatica | Ichaso |  |  | 43.0724 | -2.2579
331 | 2018 | 2024 | [2018, 2020, 2022, 2024] | 1597 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 379 | 1597 | Uprate Gatica lines | Uprate Gatica-Azpeitia | 1 | New Investment |  | 2025 | 2025 | 1 |  | Gatica | Azpeitia | Overhead Line | AC | 400 | 379 | 1597 | Uprate Gatica lines | Uprate Gatica-Azpeitia | Uprate the 400 kV Gatica-Azpeitia line | 1 | New Investment |  | 2025 | 2025 | 1 | Red Eléctrica de España |  | 0 | 0 | Gatica | Azpeitia | ACTransmissionLine | AC | 57 | Upgrade | 379 | 1597 | Uprate Gatica lines | Uprate Gatica-Azpeitia | Uprate the 400 kV Gatica-Azpeitia line | 2 | Investment on time |  | 12-2026 | 2026 | 1 | Red Eléctrica |  | 0 | 0 | Gatica | Azpeitia | ACTransmissionLine | AC | 0 | 400 | 57 | Upgrade | 379 | 1597 | Uprate Gatica lines | Uprate Gatica-Azpeitia | Uprate the 400 kV Gatica-Azpeitia line | 2 | Investment on time |  | 12-2026 | 2026 | 1 | Red Eléctrica |  | 0 | 0 | Gatica | Azpeitia | ACTransmissionLine | AC | 0 | 400 | 57 | Upgrade | [5 empty] | 5 | Commissioned |  |  | 0 | [5 empty] | 2025 | 2026 | 1 | 8 | ESP | Gatica | Azpeitia |  |  | 43.1839 | -2.2657
332 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 160 | Commissioned | 160 | New line consisting of underground +subsea cable with a total length of 35km. | 3 | mid term |  | 1 | Offshore- Wind park Nordergründe (DE) | Inhausen (DE) | 42 | 42. 160 | New AC-cable connection with a total length of 35km. | 3 | Progresses depend on development of the off shore wind farm | mid term |  | 1 | Offshore- Wind park Nordergründe (DE) | Inhausen (DE) | 42. 160 | 42. 160 | New AC-cable connection with a total length of 35km. | 4 | The investment is delayed accordingly to the delays of windfarms projects. | 2016 | 2016 | 1 | Offshore- Wind park Nordergründe (DE) | Inhausen (DE) | 42 | 160 | OWP TenneT Northsea part 1 | New AC-cable connection with a total length of 32km. | 4 | Delayed | Delay due delay of windfarms | 2016 | 2016 | 1 | Offshore- Wind park Nordergründe (DE) | Inhausen (DE) | 160 | New AC-cable connection with a total length of 32km. | 4 | Investment on time | on time relative to TYNDP14 | 2016 | 2016 | 1 | Offshore- Wind park Nordergründ e (DE) | Inhausen (DE) | 42 | 160 | OWP TenneT Northsea part 1 | Nordergründe | New AC-cable connection with a total length of 32km. | 4 | Investment on time | on time relative to TYNDP14 | 1/ 1/ 2016 | 2016 | 1 |  | 0 | Offshore- Wind park Nordergründe (DE) | Inhausen (DE) | Subsea Cable | AC | 111 | 154 | 32 | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2016 |  | 6 | DEU | - Wind Park Nordergründe | Inhausen |  |  | 48.1144 | 12.5531
333 | 2018 | 2018 | [2018] | 1613 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 248 | 1613 | Offshore Wind Baltic Sea (II) | DC Offshore Connection Cluster 1, 2, 4 | 2 | Investment on time |  | 2027 | 2027 | 1 |  | OWF Cluster Baltic Sea (DE) | Siedenbrünzow/Alt Telin/Bartow (DE) | Subsea Cable | DC | 320 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2027 | 2027 | 0 | 9 | DEU | Owf Cluster Baltic Sea | Siedenbrünzowalt Telinbartow
334 | 2018 | 2018 | [2018] | 1614 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 318 | 1614 | Upgrade of 220 kV line Podlog-Cirkovce to 400 kV | Upgrade of 220 kV line Podlog-Cirkovce to 400 kV | 1 | Investment on time |  | 2035 | 2035 | 1 | ELES | Podlog | Cirkovce | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 17 |  | Podlog | Cirkovce | 45.5263 | 15.1896 | 46.3949 | 15.7274
335 | 2018 | 2018 | [2018] | 1615 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 317 | 1615 | Upgrade of 220 kV line Podlog-Bericevo to 400 kV | Upgrade of internal 220 kV line Podlog-Bericevo to 400 kV | 1 | Investment on time |  | 2035 | 2035 | 1 | ELES | Podlog | Bericevo | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 17 |  | Podlog | Bericevo | 45.5263 | 15.1896
336 | 2018 | 2018 | [2018] | 1616 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 150 | 1616 | Italy-Slovenia | Beričevo - Border IT-SI | 1 |  |  | after 2022 | 2022 | 1 |  | Beričevo (SI) | Border IT-SI | Underground Cable | DC | 500 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2022 | 0 | 4 | SVN | Berievo | Border It-Si |  |  | 46.8686 | 16.2152
337 | 2018 | 2018 | [2018] | 1617 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 316 | 1617 | Upgrade of 220 kV line Bericevo-Divaca to 400 kV | Upgrade of 220 kV line Divaca-Bericevo to 400 kV | 1 | Delayed | Project status was due to problems with permitting process (including problems with different authorities included in the process) changed from "in permitting" to "under consideration". | 2030 | 2030 | 1 | ELES | Divaca | Bericevo | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 12 |  | Divaca | Bericevo | 45.6869 | 14.0125
338 | 2018 | 2020 | [2018, 2020] | 1619 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 284 | 1619 | LEG1 | LEG1 | 2 | Rescheduled | LEG1 has been rescheduled to allow for 150 MW solar power plant (comprising energy storage) to be developped. GreenPower2020 feel this is necessary for 2 reasons: 1. to test and to qualify technologies in a given environment (hence not duplicating previous errors from others) and to identify the appropriate combination (PV + battery, CSP + steam, ...) before the utility-scale deployment of 2 x 1 GW. 2. To include energy generation as part of the project to enable LEG1's bi-lateral power exchange capability immediately. | 2021 | 2021 | 1 | GreenPower 2020 | Tobrouk (Libya) | Linoperamata (Greece, Crete) | Subsea Cable | DC | 400 | 284 | 1619 | LEG1 | LEG1 | 2000 MW subsea interconnector associated to a 150 MW solar power plant. | 2 | Rescheduled | LEG1 has been rescheduled to allow for 150 MW solar power plant (comprising energy storage) to be developped. GreenPower2020 feel this is necessary for 2 reasons: 1. to test and to qualify technologies in a given environment (hence not duplicating previous errors from others) and to identify the appropriate combination (PV + battery, CSP + steam, ...) before the utility-scale deployment of 2 x 1 GW. 2. To include energy generation as part of the project to enable LEG1's bi-lateral power exchange capability immediately. | 2025 | 2025 | 1 | GreenPower 2020 |  | 1 | 1 | Tobrouk (Libya) | "Linoperamata (Greece, Crete)" | OffshoreDCTransmissionCable | DC | 370 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2025 | 4 | 7 | EGY;GRC;LBY | Tobrouk | Linoperamata | 35.3315 | 25.2106 | 35.338 | 25.0504
339 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1620 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 328 | 1620 | Interconnector DE-LUX | Substation Aach | 2 | New Investment |  | 2025 | 2025 | 1 | Amprion, Creos Luxembourg |  |  | Substation | AC | 400 | 328 | 1620 | Interconnector DE-LUX | Substation Aach | New 400/220-kV-substation | 2 | Investment on time |  | 2025 | 2025 | 1 | AMPRION CREOS |  | 0 | 1 |  |  | OnshoreSubstation | AC | 0 | MostlyNew | 328 | 1620 | Interconnector DE-LUX | Substation Aach | New 400/220-kV-substation | 2 | Investment on time |  | 12-2026 | 2026 | 1 | Amprion, Creos |  | 0 | 1 |  |  | OnshoreSubstation | AC | 0 | 400 | 0 | New | 328 | 1620 | Interconnector DE-LUX | Substation Aach | New 400/220-kV-substation | 2 | Investment on time |  | 12-2026 | 2026 | 1 | Amprion, Creos |  | 0 | 1 |  |  | OnshoreSubstation | AC | 0 | 400 | 0 | New | 328 | 1620 | Interconnector DE-LUX | Substation Aach | New 400/220-kV-substation | 2 |  | 12-2026 | 2026 | 1 | Amprion, Creos | 1 | XX | XX | New | 2025 | 2026 | 1 | 8 | DEU;LUX
340 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1622 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 350 | 1622 | South Balkan Corridor | 400kV OHL SS Bitola - SS Elbasan | 3 | New Investment |  | 2020 | 2020 | 1 | MEPSO | Bitola | Elbasan | Overhead Line | AC | 400 | 350 | 1622 | South Balkan Corridor | 400kV OHL SS Bitola - SS Elbasan | New 150km cross-border single circuit 400kV OHL between existing substation Bitola(Macedoonia) and Elbasan(Albania). | 4 | New Investment |  | 2020 | 2020 | 1 | MEPSO |  | 1 | 1 | Bitola | Elbasan | ACTransmissionLine | AC | 161 | New | 350 | 1622 | South Balkan Corridor | 400kV OHL SS Bitola - SS Elbasan | New 150km cross-border single circuit 400kV OHL between existing substation Bitola(Macedoonia) and Elbasan(Albania). | 4 | New Investment |  | 12-2023 | 2023 | 1 | MEPSO |  | 1 | 1 | Bitola | Elbasan | ACTransmissionLine | AC | 0 | 400 | 151 | New | 350 | 1622 | South Balkan Corridor | 400kV OHL SS Bitola - SS Elbasan | New 150km cross-border single circuit 400kV OHL between existing substation Bitola(Macedoonia) and Elbasan(Albania). | 4 | New Investment |  | 12-2024 | 2024 | 1 | MEPSO |  | 1 | 1 | Bitola | Elbasan | ACTransmissionLine | AC | 0 | 400 | 151 | New | 350 | 1622 | South Balkan Corridor | 400kV OHL SS Bitola - SS Elbasan | New 150km cross-border single circuit 400kV OHL between existing substation Bitola(Macedoonia) and Elbasan(Albania). | 4 |  | 12-2027 | 2027 | 1 | MEPSO | 1 | XX | XX | New | 2020 | 2027 | 7 | 9 | ALB;MKD | Bitola | Elbasan | 41.0316 | 21.3303 | 41.1127 | 20.0821
341 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1623 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 350 | 1623 | South Balkan Corridor | 400 kV SS Ohrid | 3 | New Investment |  | 2020 | 2020 | 1 |  |  |  | Substation | AC | 400 | 350 | 1623 | South Balkan Corridor | 400 kV SS Ohrid | New 400/110 kV substation in Ohrid area connected in/out to the new 400 kV line Bitola-Elbasan. This SS will contribute to the security of supply in the internal southern network of the country. | 4 | New Investment |  | 2020 | 2020 | 1 | MEPSO |  | 0 | 1 | missing value | missing value | OnshoreSubstation | AC | 0 | New | 350 | 1623 | South Balkan Corridor | 400 kV SS Ohrid | New 400/110 kV substation in Ohrid area connected in/out to the new 400 kV line Bitola-Elbasan. This SS will contribute to the security of supply in the internal southern network of the country. | 4 | New Investment |  | 12-2023 | 2023 | 1 | MEPSO |  | 0 | 1 | SS Ohrid | missing value | OnshoreSubstation | AC | 0 | 400 | 0 | New | 350 | 1623 | South Balkan Corridor | 400 kV SS Ohrid | New 400/110 kV substation in Ohrid area connected in/out to the new 400 kV line Bitola-Elbasan. This SS will contribute to the security of supply in the internal southern network of the country. | 4 | New Investment |  | 12-2023 | 2023 | 1 | MEPSO |  | 0 | 1 | SS Ohrid | missing value | OnshoreSubstation | AC | 0 | 400 | 0 | New | 350 | 1623 | South Balkan Corridor | 400 kV SS Ohrid | New 400/110 kV substation in Ohrid area connected in/out to the new 400 kV line Bitola-Elbasan. This SS will contribute to the security of supply in the internal southern network of the country. | 4 |  | 12-2027 | 2027 | 1 | MEPSO | 1 | XX | XX | New | 2020 | 2027 | 7 | 9 | ALB;MKD | Ohrid | Missing Value | 41.0661 | 20.6074
342 | 2018 | 2018 | [2018] | 1624 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 350 | 1624 | South Balkan Corridor | 400 kV SS Kumanovo | 1 | New Investment |  | 2030 | 2030 | 1 |  |  |  | Substation | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 12
343 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1625 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 120 | 1625 | MOG II: connection of up to 2 GW additional offshore wind Belgium | MOG II: connection of up to 2 GW additional offshore wind Belgium | 1 | Rescheduled |  | 2030 | 2030 | 1 | ELIA | Offshore (TBD) | Onshore (TBD) | Subsea Cable | AC | 220 | 120 | 1625 | MOG II: connection of up to 2 GW additional offshore wind Belgium | MOG II: connection of up to 2 GW additional offshore wind Belgium | "MOG II envisions the integration of additional wind farms in the Belgian part of the North Sea. One or more offshore platforms centralize the production from these offshore wind farms, and then transport it via 220 kV subsea AC cables to the onshore substation(s)" | 2 | Investment on time |  | 2028 | 2028 | 1 | ELIA |  | 1 | 0 | Offshore (TBD) | Onshore (TBD) | OffshoreSubstation | AC | 50 | New | 120 | 1625 | Belgian Modular Offshore Grid II (MOG II) | AC-part of Belgian Modular Offshore Grid II (MOG II) | One or more offshore substations centralize the production from these offshore wind farms, and then transport it via 220 kV subsea AC cables to the Gezelle 220kV | 2 | Investment on time |  | 03-2028 | 2028 | 1 | Elia |  | 1 | 0 | Offshore (TBD) | Onshore (TBD | OffshoreSubstation | AC | 2100 | 220 | 360 | New | 120 | 1625 | Princess Elisabeth Island (MOG 2) | AC-part of Princess Elisabeth Island | Construction of an artificial island including AC & DC assets to connect +-3,5GW of offshore wind and connect it to the onshore grid | 3 | Rescheduled | Reevaluation of the project's schedule | 02-2029 | 2029 | 1 | Elia |  | 1 | 0 | Princess Elisabeth Island | Onshore (TBD) | OffshoreSubstation | AC | 0 | 220 | 360 | New | 120 | 1625 | Princess Elisabeth Island (MOG 2) | AC-part of Princess Elisabeth Island | Construction of an artificial island including AC & DC assets to connect +-3,5GW of offshore wind and connect it to the onshore grid. The AC part allows connection of 2,1 GW AC offshore power. | 4 |  | 02-2032 | 2032 | 1 | Elia | 0 | XX | XX | New | 2030 | 2032 | 2 | 14 | BEL | Princess Elisabeth Island | Onshore
344 | 2018 | 2018 | [2018] | 1627 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 248 | 1627 | Offshore Wind Baltic Sea (II) | Offshore Connection Cluster 6 | 2 | Investment on time |  | 2029 | 2029 | 1 |  | OWF Cluster Baltic Sea (DE) | Sanitz/Dettmannsdorf | Subsea Cable | AC | 220 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2029 | 2029 | 0 | 11 | DEU | Owf Cluster Baltic Sea | Sanitzdettmannsdorf
345 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1628 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 309 | 1628 | NeuConnect | NeuConnect Interconnector | 2 | New Investment |  | 2022 | 2022 | 1 | Meridiam, Greenage Power, Frontier Power. | Grain 400kV s/s Kent, England | Fedderwarden 380kV s/s Germany | Subsea Cable | DC | 500 | 309 | 1628 | NeuConnect | NeuConnect Interconnector | 1.4GW HVDC Interconnector between UK and Germany | 3 | New Investment |  | 2023/4 | 2023 | 1 | NeuConnect Britain Limited NeuConnect Deutschland GmbH | 1.20 | 1 | 1 | Grain West 400kV Substation | Fedderwarden 380kV Substation | OffshoreDCTransmissionCable | DC | 700 | New | 309 | 1628 | NeuConnect | NeuConnect Interconnector | 1.4GW HVDC Interconnector between UK and Germany | 3 | Delayed | The project connection date is delayed due events outwith of NeuConnect's direct control | 06-2026 | 2026 | 1 | NeuConnect Britain Limited, NeuConnect Deutschland GmbH |  | 1 | 1 | Grain West 400kV Substation | Fedderwarden 380kV Substation | OffshoreDCTransmissionCable | DC | 1400 | 500 | 720 | New | 309 | 1628 | NeuConnect | NeuConnect Interconnector | 1.4GW HVDC Interconnector between UK and Germany | 4 | Delayed | The project connection date is delayed due events outwith of NeuConnect's direct control | 06-2026 | 2026 | 1 | NeuConnect Britain Limited, NeuConnect Deutschland GmbH |  | 1 | 1 | Grain West 400kV Substation | Fedderwarden 380kV Substation | OffshoreDCTransmissionCable | DC | 1400 | 500 | 720 | New | 309 | 1628 | NeuConnect | NeuConnect Interconnector | 1.4GW HVDC Interconnector between UK and Germany | 4 |  | 06-2027 | 2027 | 1 | NeuConnect Britain Limited, NeuConnect Deutschland GmbH | 1 | XX | XX | New | 2022 | 2027 | 5 | 9 | DEU;GBR | Grain West | Fedderwarden | 47.77 | 12.2327 | 53.5629 | 8.0446
346 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1629 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 328 | 1629 | Interconnector DE-LUX | Substation Bofferdange | 2 | New Investment |  | 2025 | 2025 | 1 |  |  |  | Substation | AC | 400 | 328 | 1629 | Interconnector DE-LUX | Substation Bofferdange | New 400/220/110 kV substation including transformer 400/220 kV to be commissioned in Bofferdange (LU) | 2 | Investment on time |  | 2025 | 2025 | 1 | AMPRION CREOS |  | 0 | 1 |  |  | OnshoreSubstation | AC | 0 | MostlyNew | 328 | 1629 | Interconnector DE-LUX | Substation Bofferdange | New 400/220/110 kV substation including transformer 400/220 kV to be commissioned in Bofferdange (LU) | 3 | Investment on time |  | 12-2026 | 2026 | 1 | Amprion, Creos |  | 0 | 1 |  |  | OnshoreSubstation | AC | 0 | 400 | 0 | New | 328 | 1629 | Interconnector DE-LUX | Substation Bofferdange | New 400/220/110 kV substation including transformer 400/220 kV to be commissioned in Bofferdange (LU) | 3 | Investment on time |  | 12-2028 | 2028 | 1 | Amprion, Creos |  | 0 | 1 |  |  | OnshoreSubstation | AC | 0 | 400 | 0 | New | 328 | 1629 | Interconnector DE-LUX | Substation Bofferdange | New 400/220/110 kV substation including transformer 400/220 kV to be commissioned in Bofferdange (LU) |  |  | 06-2029 | 2029 | 1 | Amprion, Creos | 1 | XX | XX | New | 2025 | 2029 | 4 | 11 | DEU;LUX
347 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 163 | Commissioned | 163 | New line consisting of underground +subsea cable with a total length of 145km. Line capacity: aprox. 860MW. This Project includes also a new substation Büttel and connection of this new substation with the existing OHL Brünsbüttel - Wilster. | 3 | mid term |  | 1 | Cluster HelWin1 (DE) | Büttel (DE) | 42 | 42. 163 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 145km. Line capacity: aprox. 690MW. This Project includes also a new substation Büttel and connection of this new substation with the existing OHL Brünsbüttel - Wilster. | 4 | Progresses with delay. | mid term |  | 1 | Cluster HelWin1 (DE) | Büttel (DE) | 42. 163 | 42. 163 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 145km. Line capacity: aprox. 690MW. | 4 |  | 2014 | 2014 | 1 | Cluster HelWin1 (DE) | Büttel (DE) | 42 | 163 | OWP TenneT Northsea part 1 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 133km. Line capacity: approx.. 576 MW. | 4 | Investment on time |  | 2014 | 2014 | 1 | Cluster HelWin1 (DE) | Büttel (DE) | 163 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 133km. Line capacity: aprox. 576 MW. | 5 | Investment on time | in operation | 2014 | 2014 | 1 | Cluster HelWin1 (DE) | Büttel (DE) | 42 | 163 | OWP TenneT Northsea part 1 | HelWin1 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 133km. Line capacity&#58; aprox. 576 MW. | 5 | Commissioned | in operation | 1/ 1/ 2014 | 2014 | 1 |  | 0 | Cluster HelWin1 (DE) | Büttel (DE) | Subsea Cable | DC | 576 | 400 | 133 | New | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2014 |  | 4 | DEU | Cluster Helwin | Büttel |  |  | 53.9 | 9.2284
348 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1630 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 328 | 1630 | Interconnector DE-LUX | AC Overhead Line Aach-Bofferdange | 2 | New Investment |  | 2026 | 2026 | 1 |  | Aach (DE) | Bofferdange (LU) | Overhead Line | AC | 400 | 328 | 1630 | Interconnector DE-LUX | AC Overhead Line Aach-Bofferdange | New AC Overhead Line between Germany and Luxembourg | 2 | Investment on time |  | 2026 | 2026 | 1 | AMPRION CREOS |  | 1 | 1 | Aach (DE) | Bofferdange (LU) | ACTransmissionLine | AC | 40 | MostlyNew | 328 | 1630 | Interconnector DE-LUX | AC Overhead Line Aach-Bofferdange | New AC Overhead Line between Germany and Luxembourg | 3 | Investment on time |  | 12-2026 | 2026 | 1 | Amprion, Creos |  | 1 | 1 | Aach (DE) | Bofferdange (LU) | ACTransmissionLine | AC | 0 | 400 | 40 | New | 328 | 1630 | Interconnector DE-LUX | AC Overhead Line Aach-Bofferdange | New AC Overhead Line between Germany and Luxembourg | 3 | Investment on time |  | 12-2028 | 2028 | 1 | Amprion, Creos |  | 1 | 1 | Aach (DE) | Bofferdange (LU) | ACTransmissionLine | AC | 0 | 400 | 40 | New | 328 | 1630 | Interconnector DE-LUX | AC Overhead Line Aach-Bofferdange | New AC Overhead Line between Germany and Luxembourg |  |  | 06-2029 | 2029 | 1 | Amprion, Creos | 1 | XX | XX | New | 2026 | 2029 | 3 | 11 | DEU;LUX | Aach | Bofferdange | 49.7895 | 6.5907 | 49.6886 | 6.1408
349 | 2018 | 2018 | [2018] | 1631 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 325 | 1631 | AT, SI, IT - South-East Alps Project | Lienz - Italy (AT - IT) | 1 | Rescheduled | Shifted to Long Term due to feasibility reasons - new Mid Term Project introduced. | 2035-2040 | 2040 | 1 |  | Lienz | Veneto Region | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2040 | 2040 | 0 | 22 | AUT;ITA;SVN | Lienz | Veneto Region | 46.8299 | 12.7681
350 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1632 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 170 | 1632 | Baltics synchro with CE | New 330 kV Musa substation | 2 | New Investment |  | 2023 | 2023 | 1 |  | Musa | - | Substation | AC | 330 | 170 | 1632 | Baltic States Synchronization with Continental Europe | New 330 kV Musa substation | New 330 kV Musa substation | 3 | Investment on time |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Musa | - |  | AC | 0 | New | 170 | 1632 | Baltic States Synchronization with Continental Europe | New 330 kV Musa substation | New 330 kV Musa substation. The new substation will create switching capability at the junction of overhead lines Siauliai-Kaunas, Siauliai-Viskali, and Siauliai-Telsiai, which will improve general availability, resilience and throughput of the grid to support synchronization. The project includes territorial planning, land acquisition, procurement, design and construction phases. | 3 | Investment on time |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Musa | - | OnshoreSubstation | AC | 0 | 330 | 0 | MostlyNew | 170 | 1632 | Baltic States Synchronization with Continental Europe | New 330 kV Musa substation | New 330 kV Musa substation. The new substation will create switching capability at the junction of overhead lines Siauliai-Kaunas, Siauliai-Viskali, and Siauliai-Telsiai, which will improve general availability, resilience and throughput of the grid to support synchronization. The project includes territorial planning, land acquisition, procurement, design and construction phases. | 4 | Investment on time |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Musa | - | OnshoreSubstation | AC | 0 | 330 | 0 | MostlyNew | 170 | 1632 | Baltic States Synchronization with Continental Europe | New 330 kV Musa substation | New 330 kV Musa substation. The new substation will create switching capability at the junction of overhead lines Siauliai-Kaunas, Siauliai-Viskali, and Siauliai-Telsiai, which will improve general availability and grid resilience. | 4 |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2023 | 2025 | 2 | 7 | EST;LTU;LVA;POL | Musa |  | 54.9365 | 24.9126
351 | 2018 | 2018 | [2018] | 1633 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 170 | 1633 | Baltics synchro with CE | Reconstruction of 330 kV OHL Klaipeda - Bitenai | 2 | New Investment |  | 2024 | 2024 | 1 |  | Klaipeda | Bitenai | Overhead Line | AC | 330 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2024 | 2024 | 0 | 6 |  | Klaipeda | Bitenai | 55.7128 | 21.135
352 | 2018 | 2026 | [2018, 2020, 2022, 2024, 2026] | 1634 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 170 | 1634 | Baltics synchro with CE | Reconstruction of 330 kV OHL Bitėnai - Jurbarkas | 2 | New Investment |  | 2024 | 2024 | 1 |  | Bitenai | Jurbarkas | Overhead Line | AC | 330 | 170 | 1634 | Baltic States Synchronization with Continental Europe | New 330 kV OHL Bitenai - KHAE | New 330 kV OHL Bitenai-KHAE. One part of the new line will be constructed as second circuit on exicting 330 kV OHL Bitenai-Jurbarkas (44km), one part will be new line (74 km), and as third part of new line will be used part of exicting 330 kV OHL KHAE-Sovetsk. | 3 | Investment on time |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Bitenai | KHAE | ACTransmissionLine | AC | 234 | New | 170 | 1634 | Baltic States Synchronization with Continental Europe | New 330 kV OHL Bitenai - KHAE | New 330 kV OHL Bitenai-KHAE. One part of the new line will be constructed as second circuit on exicting 330 kV OHL Bitenai-Jurbarkas (39 km), one part will be new line (63 km), and as third part of new line will be used part of exicting 330 kV OHL KHAE-Sovetsk (KHAE-Sovetsk will be disconnected until end of 2025). | 3 | Investment on time |  | 10-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Bitenai | KHAE | ACTransmissionLine | AC | 0 | 330 | 211 | MostlyNew | 170 | 1634 | Baltic States Synchronization with Continental Europe | New 330 kV OHL Kruonio HAE - Bitenai | New 330 kV OHL Kruonio HAE - Bitenai. One part of the new line will be constructed as second circuit on existing 330 kV OHL Bitenai-Jurbarkas (39 km), one part will be new line (63 km), and as third part of new line will be used part of exicting 330 kV OHL Kruonio HAE - Sovietsk (Kruonio HAE - Sovietsk will be disconnected until end of 2025). | 4 | Investment on time |  | 10-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | KHAE | Bitenai | ACTransmissionLine | AC | 0 | 330 | 211 | MostlyNew | 170 | 1634 | Baltic States Synchronization with Continental Europe | New 330 kV OHL Kruonio HAE-Bitenai | New 330 kV OHL Kruonio HAE - Bitenai. One part of the new line will be constructed as second circuit on existing 330 kV OHL Bitenai-Jurbarkas (39 km), one part will be new line (63 km), and as third part of new line will be used part of exicting 330 kV OHL Kruonio HAE - Sovietsk (109 km) (Kruonio HAE - Sovietsk will be disconnected until end of 2025). Total OHL lenght - 211 km | 4 |  | 10-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2024 | 2025 | 1 | 7 | EST;LTU;LVA;POL | Khae | Bitenai
353 | 2018 | 2018 | [2018] | 1635 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 170 | 1635 | Baltics synchro with CE | New 330 kV OHL Jurbarkas - KHAE | 2 | New Investment |  | 2024 | 2024 | 1 |  | Jurbarkas | KHAE | Overhead Line | AC | 330 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2024 | 2024 | 0 | 6 |  | Jurbarkas | Khae
354 | 2018 | 2018 | [2018] | 1636 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 325 | 1636 | AT, SI, IT - South-East Alps Project | Lienz - Obersielach | 2 | Rescheduled | Tests and gaining of experience for novel technical solution in progress. | 2026/27 | 2026 | 1 |  | Lienz (AT) | Obersielach (AT) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2026 | 2026 | 0 | 8 | AUT | Lienz | Obersielach | 46.8299 | 12.7681 | 46.6631 | 14.684
355 | 2018 | 2018 | [2018] | 1637 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [10 empty] | 286 | 1637 | Greenlink | New investment | [5 empty] | 1 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0
356 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1638 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 349 | 1638 | MaresConnect | Mares Cable 1: Cross Irish Sea Interconnector Cable | HVDC 750MW 320kV bipole interconnector between UKNG and EIRGRID | 2 | Rescheduled |  | 2025 | 2025 | 1 | Mares Interconnector Holdings Limited |  | 1 | 1 | Bodelwyddan | Maynooth | DCTransmissionLine | DC | 211 | New | 349 | 1638 | MaresConnect | Mares Cable : Irish Sea Interconnector Cable | HVDC 750MW 320kV symmetrical mono-pole interconnector between UKNG and EIRGRID | 2 | Rescheduled |  | 07-2027 | 2027 | 1 | Mares Interconnector Holdings Limited |  | 1 | 1 | Bodelwyddan | Maynooth | DCTransmissionLine | DC | 750 | 320 | 211 | New | 349 | 1638 | MaresConnect | Mares Cable : Irish Sea Interconnector Cable | HVDC 750MW 320kV symmetrical mono-pole interconnector between UKNG and EIRGRID | 3 | Rescheduled |  | 12-2029 | 2029 | 1 | MaresConnect Limited |  | 1 | 1 | Bodelwyddan | Maynooth | DCTransmissionLine | DC | 750 | 320 | 245 | New | 349 | 1638 | MaresConnect | Mares Cable : Irish Sea Interconnector Cable | HVDC 750MW 320kV symmetrical mono-pole interconnector between UKNG and EIRGRID |  |  | 12-2029 | 2029 | 1 | MaresConnect Limited | 1 | XX | XX | New | 2025 | 2029 | 4 | 9 | GBR;IRL | Bodelwyddan | Maynooth | 53.2706 | -3.513 | 54.3669 | -6.5529
357 | 2020 | 2020 | [2020] | 1639 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 349 | 1639 | MaresConnect | Enabling Works 1: Bellacorick-Oldstreet 2 x 245kV OHL | 2 x 400MW 275kV OHL | 2 | New Investment |  | 2025 | 2025 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | Bellacorick Replacement | Oldstreet 400kV | ACTransmissionLine | AC | 160 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 5 | GBR;IRL | Bellacorick Replacement | Oldstreet |  |  | 51.7504 | -2.4863
358 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 164 | Commissioned | 164 | New line consisting of underground +subsea cable with a total length of 210km. Line capacity: aprox. 690MW. | 3 | mid term |  | 1 | Cluster SylWin1 (DE) | Büttel (DE) | 42 | 42. 164 | New line consisting of underground +subsea cable with a total length of 210km. Line capacity: aprox.864MW. | 4 | Progresses as planned | mid term |  | 1 | Cluster SylWin1 (DE) | Büttel (DE) | 42. 164 | 42. 164 | New line consisting of underground +subsea cable with a total length of 210km. Line capacity: aprox.864MW. | 4 |  | 2014 | 2014 | 1 | Cluster SylWin1 (DE) | Büttel (DE) | 42 | 164 | OWP TenneT Northsea part 1 | New line consisting of underground +subsea cable with a total length of 206 km. Line capacity: aprox.864MW. | 4 | Delayed |  | 2015 | 2015 | 1 | Cluster SylWin1 (DE) | Büttel (DE) | 164 | New line consisting of underground +subsea cable with a total length of 206 km. Line capacity: aprox.864MW. | 4 | Investment on time |  | 2015 | 2015 | 1 | Cluster SylWin1 (DE) | Büttel (DE) | 42 | 164 | OWP TenneT Northsea part 1 | SylWin1 | New line consisting of underground +subsea cable with a total length of 206 km. Line capacity&#58; aprox.864MW. | 5 | Commissioned | in operation | 1/ 1/ 2015 | 2015 | 1 |  | 0 | Cluster SylWin1 (DE) | Büttel (DE) | Subsea Cable | DC | 864 | 400 | 206 | New | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2015 |  | 5 | DEU | Cluster Sylwin | Büttel |  |  | 53.9 | 9.2284
359 | 2020 | 2020 | [2020] | 1640 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 349 | 1640 | MaresConnect | Mares Cable 2: Cross Ireland Interconnector Cable | 750MW 320kV VSC HVDC Interconnector | 2 | New Investment |  | 2025 | 2025 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | Maynooth | Bellacorick Replacement | DCTransmissionLine | DC | 255 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 5 | GBR;IRL | Maynooth | Bellacorick Replacement | 54.3669 | -6.5529
360 | 2020 | 2020 | [2020] | 1641 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 349 | 1641 | MaresConnect | Mares Converter Station 3 | 750MW 320kV VSC HVDC Convertor Station to connect to EIRGRID AC | 2 | New Investment |  | 2025 | 2025 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | Bellacorick replacement | Bellacorick replacement | OnshoreSubstation | DC | 0 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 5 | GBR;IRL | Bellacorick Replacement | Bellacorick Replacement
361 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1642 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 349 | 1642 | MaresConnect | Mares Converter Station 2 | 750MW 320kV VSC HVDC Convertor Station to connect to EIRGRID AC | 2 | New Investment |  | 2025 | 2025 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | Maynooth | Maynooth | OnshoreSubstation | DC | 0 | New | 349 | 1642 | MaresConnect | MaresConnect Converter Station Ireland | 750MW 320kV VSC HVDC Convertor Station to connect to EIRGRID AC | 2 | New Investment |  | 07-2027 | 2027 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | Maynooth | Maynooth | OnshoreSubstation | DC | 750 | 320 | 0 | New | 349 | 1642 | MaresConnect | MaresConnect Converter Station Ireland | 750MW 320kV VSC HVDC Convertor Station to connect to EIRGRID AC | 3 | New Investment |  | 12-2029 | 2029 | 1 | MaresConnect Limited |  | 0 | 1 | Maynooth | Maynooth | OnshoreSubstation | DC | 750 | 320 | 0 | New | 349 | 1642 | MaresConnect | MaresConnect Converter Station Ireland | 750MW 320kV VSC HVDC Convertor Station to connect to EIRGRID AC |  |  | 12-2029 | 2029 | 1 | MaresConnect Limited | 1 | XX | XX | New | 2025 | 2029 | 4 | 9 | GBR;IRL | Maynooth | Maynooth | 54.3669 | -6.5529 | 54.3669 | -6.5529
362 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1646 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 349 | 1646 | MaresConnect | Mares Converter Station 1 | 750MW 320kV VSC HVDC Convertor Station to connect to UKNG | 2 | New Investment |  | 2025 | 2025 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | Bodelwyddan | Bodelwyddan | OnshoreSubstation | DC | 0 | New | 349 | 1646 | MaresConnect | Mares Converter Station UK | 750MW 320kV VSC HVDC Convertor Station to connect to UKNG | 2 | New Investment |  | 07-2027 | 2027 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | Bodelwyddan | Bodelwyddan | OnshoreSubstation | DC | 750 | 320 | 0 | New | 349 | 1646 | MaresConnect | Mares Converter Station UK | 750MW 320kV VSC HVDC Convertor Station to connect to UKNG | 3 | New Investment |  | 12-2029 | 2029 | 1 | MaresConnect Limited |  | 0 | 1 | Bodelwyddan | Bodelwyddan | OnshoreSubstation | DC | 750 | 320 | 0 | New | 349 | 1646 | MaresConnect | Mares Converter Station UK | 750MW 320kV VSC HVDC Convertor Station to connect to UKNG |  |  | 12-2029 | 2029 | 1 | MaresConnect Limited | 1 | XX | XX | New | 2025 | 2029 | 4 | 9 | GBR;IRL | Bodelwyddan | Bodelwyddan | 53.2706 | -3.513 | 53.2706 | -3.513
363 | 2020 | 2020 | [2020] | 1647 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 349 | 1647 | MaresConnect | MAREX Wind infeed cable 1 | 245kV 400MW AC cable | 2 | New Investment |  | 2025 | 2025 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | MAREX Wind 1 | Bellacorick Replacement | OnshoreACTransmissionCable | AC | 25 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 5 | GBR;IRL | Marex Wind | Bellacorick Replacement
364 | 2020 | 2020 | [2020] | 1648 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 349 | 1648 | MaresConnect | MAREX Wind Infeed cable 2 | 245kV 400MW AC cable | 2 | New Investment |  | 2025 | 2025 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | MAREX Wind 2 | Bellacorick Replacement | OnshoreACTransmissionCable | AC | 25 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 5 | GBR;IRL | Marex Wind | Bellacorick Replacement
365 | 2020 | 2020 | [2020] | 1649 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 349 | 1649 | MaresConnect | MAREX Wind Infeed cable 3 | 245kV 400MW AC cable | 2 | New Investment |  | 2025 | 2025 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | Marex Wind 3 | Bellacorick Replacement | OnshoreACTransmissionCable | AC | 25 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 5 | GBR;IRL | Marex Wind | Bellacorick Replacement
366 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 165 | Commissioned | 165 | New line consisting of underground +subsea cable with a total length of 155km. Line capacity: 400MW. | 3 | mid term |  | 1 | Cluster DolWin1 (DE) | Dörpen/West (DE) | 42 | 42. 165 | New line consisting of underground +subsea cable with a total length of 155km. Line capacity: 800MW. | 4 | Progresses as planned | mid term |  | 1 | Cluster DolWin1 (DE) | Dörpen/West (DE) | 42. 165 | 42. 165 | New line consisting of underground +subsea cable with a total length of 155km. Line capacity: 800MW. | 4 |  | 2014 | 2014 | 1 | Cluster DolWin1 (DE) | Dörpen/West (DE) | 42 | 165 | OWP TenneT Northsea part 1 | New line consisting of underground +subsea cable with a total length of 167 km. Line capacity: 800MW. | 4 | Delayed |  | 2014 | 2014 | 1 | Cluster DolWin1 (DE) | Dörpen/West (DE) | 165 | New line consisting of underground +subsea cable with a total length of 167 km. Line capacity: 800MW. | 4 | Delayed | delay is due to long permitting process | 2015 | 2015 | 1 | Cluster DolWin1 (DE) | Dörpen/West (DE) | 42 | 165 | OWP TenneT Northsea part 1 | DolWin1 | New line consisting of underground +subsea cable with a total length of 167 km. Line capacity&#58; 800MW. | 5 | Commissioned | due to the project | 1/ 1/ 2015 | 2015 | 1 |  | 0 | Cluster DolWin1 (DE) | Dörpen/West (DE) | Subsea Cable | DC | 800 | 400 | 167 | New | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2015 |  | 5 | DEU | Cluster Dolwin | Dörpenwest
367 | 2020 | 2020 | [2020] | 1650 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 349 | 1650 | MaresConnect | MAREX Wind Infeed Cable 4 | 245kV 400MW AC cable | 2 | New Investment |  | 2025 | 2025 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | MAREX Wind 4 | Bellacorick Replacement | OnshoreACTransmissionCable | AC | 20 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 5 | GBR;IRL | Marex Wind | Bellacorick Replacement
368 | 2020 | 2020 | [2020] | 1651 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 349 | 1651 | MaresConnect | Enabling Works 2: Glinsk Bellacorick Replacement 10 x 245kV bay substation | 12 bay 245kV substation | 2 | New Investment |  | 2025 | 2025 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | Bellacorick Replacement | Bellacorick Replacement | OnshoreSubstation | AC | 0 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 5 | GBR;IRL | Bellacorick Replacement | Bellacorick Replacement
369 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1652 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 349 | 1652 | MaresConnect | Enabling Works 3: 2 x 245kV Connection bays UKNG and associated works | AC Connection to UKNG system Bodelwyddan 2 number 245kV bays and associated works | 2 | New Investment |  | 2025 | 2025 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | Bodelwyddan | Bodelwyddan | OnshoreSubstation | AC | 0 | New | 349 | 1652 | MaresConnect | Enabling Works 1: 1 x 400kV Connection bay UKNG and associated works | AC Connection to UKNG system Bodelwyddan 400kV bays and associated works | 2 | New Investment |  | 07-2027 | 2027 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | Bodelwyddan | Bodelwyddan | OnshoreSubstation | AC | 0 | 245 | 0 | New | 349 | 1652 | MaresConnect | Enabling Works 1: 1 x 400kV Connection bay UKNG and associated works | AC Connection to UKNG system Bodelwyddan 400kV bays and associated works | 3 | New Investment |  | 12-2029 | 2029 | 1 | MaresConnect Limited |  | 0 | 1 | Bodelwyddan | Bodelwyddan | OnshoreSubstation | AC | 0 | 400 | 1 | New | 349 | 1652 | MaresConnect | Enabling Works 1: 1 x 400kV Connection bay UKNG and associated works | AC Connection to UKNG system Bodelwyddan 400kV bays and associated works |  |  | 12-2029 | 2029 | 1 | MaresConnect Limited | 1 | XX | XX | New | 2025 | 2029 | 4 | 9 | GBR;IRL | Bodelwyddan | Bodelwyddan | 53.2706 | -3.513 | 53.2706 | -3.513
370 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1653 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 349 | 1653 | MaresConnect | Enabling Works 4: EIRGRID 2 x 245kV Connection bays at Maynooth and associated works | EIRGRID 2 x 245kV Connection bays at Maynooth and associated works | 2 | New Investment |  | 2025 | 2025 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | Maynooth | Maynooth | OnshoreSubstation | AC | 0 | New | 349 | 1653 | MaresConnect | Enabling Works 2: EIRGRID 1 x 245kV Connection bay at Maynooth and associated works | EIRGRID 1 x 245kV Connection bays at Maynooth and associated works | 2 | New Investment |  | 07-2027 | 2027 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | Maynooth | Maynooth | OnshoreSubstation | AC | 0 | 245 | 0 | New | 349 | 1653 | MaresConnect | Enabling Works 2: EIRGRID 1 x 245kV Connection bay at Maynooth and associated works | EIRGRID 1 x 245kV Connection bays at Maynooth and associated works | 3 | New Investment |  | 12-2029 | 2029 | 1 | MaresConnect Limited |  | 0 | 1 | Maynooth | Maynooth | OnshoreSubstation | AC | 0 | 245 | 1 | New | 349 | 1653 | MaresConnect | Enabling Works 2: EIRGRID 1 x 400kV Connection bay at North County Dublin Fingal Station | EIRGRID 1 x 400kV Connection bay at North County Dublin Fingal Station |  |  | 12-2029 | 2029 | 1 | MaresConnect Limited | 1 | XX | XX | New | 2025 | 2029 | 4 | 9 | GBR;IRL | Maynooth | Maynooth | 54.3669 | -6.5529 | 54.3669 | -6.5529
371 | 2020 | 2020 | [2020] | 1654 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 349 | 1654 | MaresConnect | Enabling Works 5: EIRGRID 2 x 245kV Connection bays at Oldstreet and associated works | 2 x 245kV Connection bays at Oldstreet and associated works | 2 | New Investment |  | 2025 | 2025 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | Oldstreet 220/400kV | Oldstreet 220/400kV | OnshoreSubstation | AC | 0 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 5 | GBR;IRL | Oldstreet | Oldstreet | 51.7504 | -2.4863 | 51.7504 | -2.4863
372 | 2020 | 2020 | [2020] | 1655 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 349 | 1655 | MaresConnect | Enabling Works 6: 2 x 245/400 transformer at EIRGRID 220/400kV Substation Oldstreet | 2 x 245/400 transformer at EIRGRID 220/400kV Substation Oldstreet | 2 | New Investment |  | 2025 | 2025 | 1 | Mares Interconnector Holdings Limited |  | 0 | 1 | Oldstreet 220/400kV | Oldstreet 220/400kV | PhaseShiftingTransformer | AC | 0 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 5 | GBR;IRL | Oldstreet | Oldstreet | 51.7504 | -2.4863 | 51.7504 | -2.4863
373 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1659 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 170 | 1659 | Baltic States Synchronization with Continental Europe | New 330 kV OHL Darbenai-Bitenai | New 330 kV OHL Darbenai-Bitenai | 3 | Investment on time |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Darbenai | Bitenai | ACTransmissionLine | AC | 147 | New | 170 | 1659 | Baltic States Synchronization with Continental Europe | New 330 kV OHL Darbenai-Bitenai | New 330 kV OHL Darbenai-Bitenai. One part of the new line will be constructed as second circuit on existing 330 kV OHL Grobine-Klaipeda (45,5 km), second part will be new line (12,1 km), third part will be constructed as second circuit on existing 330 kV OHL Klaipeda-Sysa-Bitenai (79,5 km). | 3 | Investment on time |  | 07-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Darbenai | Bitenai | ACTransmissionLine | AC | 0 | 330 | 137 | MostlyNew | 170 | 1659 | Baltic States Synchronization with Continental Europe | New 330 kV OHL Darbenai-Bitenai | New 330 kV OHL Darbenai-Bitenai. One part of the new line will be constructed as second circuit on existing 330 kV OHL Grobine-Klaipeda (45,5 km), second part will be new line (12,1 km), third part will be constructed as second circuit on existing 330 kV OHL Klaipeda-Sysa-Bitenai (79,5 km). | 4 | Investment on time |  | 07-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Darbenai | Bitenai | ACTransmissionLine | AC | 0 | 330 | 137 | MostlyNew | 170 | 1659 | Baltic States Synchronization with Continental Europe | New 330 kV OHL Darbenai-Bitenai | New 330 kV OHL Darbenai-Bitenai. One part of the new line will be constructed as second circuit on existing 330 kV OHL Grobine-Klaipeda (45,5 km), second part will be new line (12,1 km), third part will be constructed as second circuit on existing 330 kV OHL Klaipeda-Sysa-Bitenai (79,5 km). | 5 | Commissioned | 01-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2025 | 2025 | 0 | 5 | EST;LTU;LVA;POL | Darbenai | Bitenai | 56.0232 | 21.254
374 | 2016 | 2016 | [2016] | 166 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 42 | 166 | OWP TenneT Northsea part 1 | Riffgat | New AC-cable connection with a total length of 77 km. | 5 | Commissioned | in operation | 1/ 1/ 2014 | 2014 | 1 |  | 0 | Offshore Wind park Riffgat (DE) | Emden /Borßum(DE) | Subsea Cable | AC | 108 | 154 | 77 | New | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2014 | 2014 | 0 | -2 | DEU | Wind Park Riffgat | Emden Borßum |  |  | 53.349 | 7.2269
375 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1660 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 170 | 1660 | Baltic States Synchronization with Continental Europe | New 330 kV Darbenai substation | New 330 kV Darbenai substation, necessary for the connection of the new 330 kV lines as well as new HVDC subsea cable known as Harmony Link. This project includes territory planning, land acquisition and construction phases. | 3 | Investment on time |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Darbenai | - |  | AC | 0 | New | 170 | 1660 | Baltic States Synchronization with Continental Europe | New 330 kV Darbenai substation | New 330 kV Darbenai substation, necessary for the connection of the new 330 kV line Darbenai-Bitenai (inv. 1659), as well as new HVDC subsea cable known as Harmony Link (inv.1034) and offshore wind farm (project 1042). This project includes territory planning, land acquisition and construction phases. | 3 | Investment on time |  | 03-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Darbenai | - | OnshoreSubstation | AC | 0 | 330 | 0 | MostlyNew | 170 | 1660 | Baltic States Synchronization with Continental Europe | New 330 kV Darbenai substation | A new 330 kV AC switchyard in Darbenai is part of cross-border interconnection between Lithuania and Poland. It is designed to be a connection point for 330 kV OHL Darbenai-Bitenai (PCI 3.3.10), which, together with 300 kV OHL Kruonio HAE-Bitenai (PCI 3.3.8.), will reinforce Western Lithuanian transmission network as necessary to assure better market integration. It will also enable full integration of 700MW cross-border interconnection between Poland and Lithuania facilitating security of supply criteria and removing existing bottlenecks in the Baltic power grid. The planned switchyard is designed according to 1.5 breaker-bus system. Commissioning of Darbenai switchyard is prerequisite to timely connection of 330 kV OHL Darbenai-Bitenai and cross-border interconnection. | 4 | Rescheduled | The end of construction of Darbėnai substation is expected to be delayed due to contractor’s delay to finalize technical design documentation of 330 kV Darbėnai switchyard. For this reason, the construction permit was received only on June 12th 2023 (initial plan was January 2023). Respectively, the preparation of detailed design and the construction works are being delayed. | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Darbenai | - | OnshoreSubstation | AC | 0 | 330 | 0 | MostlyNew | 170 | 1660 | Baltic States Synchronization with Continental Europe | New 330 kV Darbenai substation | A new 330 kV AC switchyard in Darbenai is part of cross-border interconnection between Lithuania and Poland. It is designed to be a connection point for 330 kV OHL Darbenai-Bitenai (PCI 3.3.10), which, together with 330 kV OHL Kruonio HAE-Bitenai (PCI 3.3.8.), will reinforce Western Lithuanian transmission network as necessary to assure better market integration. It will also enable full integration of 700MW cross-border interconnection between Poland and Lithuania facilitating security of supply criteria and removing existing bottlenecks in the Baltic power grid. Commissioning of Darbenai switchyard is prerequisite to timely connection of 330 kV OHL Darbenai-Bitenai and cross-border interconnection. | 4 |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2025 | 2025 | 0 | 5 | EST;LTU;LVA;POL | Darbenai |  | 56.0232 | 21.254
376 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1661 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 170 | 1661 | Baltic States Synchronization with Continental Europe | Construction of new 400kV line Dunowo-Zydowo Kierzkowo | Dunowo-Zydowo Kierzkowo 400kV line is necessary to assure that after commissioning of Harmony Link and offshore wind farms, full capabilities would be available on the Polish-Lithuanian subsea interconnector. This project includes reconstruction of Dunowo substation with installation of 400/110 kV transformers and construction of new double-circuit 400 kV. | 2 | New Investment |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Dunowo | Zydowo Kierzkowo | ACTransmissionLine | AC | 57.11 | New | 170 | 1661 | Baltic States Synchronization with Continental Europe | Construction of new 400kV line Dunowo-Zydowo Kierzkowo | Dunowo-Zydowo Kierzkowo 400kV line is necessary to assure that after commissioning of Harmony Link and offshore wind farms, full capabilities would be available on the Polish-Lithuanian subsea interconnector. This project includes reconstruction of Dunowo substation with installation of 400/110 kV transformers and construction of new double-circuit 400 kV. | 3 | New Investment |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Dunowo | Zydowo Kierzkowo | ACTransmissionLine | AC | 0 | 400 | 57.11 | MostlyNew | 170 | 1661 | Baltic States Synchronization with Continental Europe | Construction of new 400kV line Dunowo-Zydowo Kierzkowo | Dunowo-Zydowo Kierzkowo 400kV line is necessary to assure that after commissioning of Harmony Link and offshore wind farms, full capabilities would be available on the Polish-Lithuanian interconnector. This project includes reconstruction of Dunowo substation with installation of 400/110 kV transformers and construction of new double-circuit 400 kV. | 4 | New Investment |  | 12-2027 | 2027 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Dunowo | Zydowo Kierzkowo | ACTransmissionLine | AC | 0 | 400 | 57.11 | MostlyNew | 170 | 1661 | Baltic States Synchronization with Continental Europe | Construction of new 400kV line Dunowo-Zydowo Kierzkowo-Pila Krzewina | Dunowo-Zydowo Kierzkowo-Pila Krzewina 400kV lines are necessary to assure that after commissioning of Harmony Link and offshore wind farms, full capabilities would be available on the Polish-Lithuanian interconnector. This project includes reconstruction of Dunowo and Pila Krzewina substations with installation of 400/110 kV transformers and reactive power compensation devices and construction of new double-circiuit 400 kV lines. | 4 |  | 12-2027 | 2027 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2025 | 2027 | 2 | 7 | EST;LTU;LVA;POL | Dunowo | Zydowo Kierzkowo | 54.1097 | 16.1078 | 54.0252 | 16.707
377 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1662 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 170 | 1662 | Baltic States Synchronization with Continental Europe | Construction of new 400kV line Pila Krzewina-Zydowo Kierzkowo | Pila Krzewina-Zydowo Kierzkowo 400kV line is interrelated with project aiming in building Dunowo-Zydowo Kierzkowo line. This project includes reconstruction and modernization of Pila Krzewina electrical station with installation of 400/110 kV transformers and reactive power compensation devices and construction of new double-circuit 400 kV. | 2 | New Investment |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Pila Krzewina | Zydowo Kierzkowo | ACTransmissionLine | AC | 119 | New | 170 | 1662 | Baltic States Synchronization with Continental Europe | Construction of new 400kV line Pila Krzewina-Zydowo Kierzkowo | Pila Krzewina-Zydowo Kierzkowo 400kV line is interrelated with project aiming in building Dunowo-Zydowo Kierzkowo line. This project includes reconstruction and modernization of Pila Krzewina electrical station with installation of 400/110 kV transformers and reactive power compensation devices and construction of new double-circuit 400 kV. | 3 | New Investment |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Pila Krzewina | Zydowo Kierzkowo | ACTransmissionLine | AC | 0 | 400 | 119 | MostlyNew | 170 | 1662 | Baltic States Synchronization with Continental Europe | Construction of new 400kV line Pila Krzewina-Zydowo Kierzkowo | Pila Krzewina-Zydowo Kierzkowo 400kV line is interrelated with project aiming in building Dunowo-Zydowo Kierzkowo line. This project includes reconstruction and modernization of Pila Krzewina electrical station with installation of 400/110 kV transformers and reactive power compensation devices and construction of new double-circuit 400 kV. | 4 | New Investment |  | 12-2027 | 2027 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Pila Krzewina | Zydowo Kierzkowo | ACTransmissionLine | AC | 0 | 400 | 119 | MostlyNew | 170 | 1662 | Baltic States Synchronization with Continental Europe | Modernization of 400kV OHL Slupsk-Zarnowiec | Modernisation of Slupsk-Zarnowiec 400kV line. | 4 |  | 12-2027 | 2027 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2025 | 2027 | 2 | 7 | EST;LTU;LVA;POL | Pila Krzewina | Zydowo Kierzkowo |  |  | 54.0252 | 16.707
378 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1663 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 170 | 1663 | Baltic States Synchronization with Continental Europe | Modernization of 400kV OHL Krajnik-Morzyczyn | To allow effective energy flows in the north-west part of Poland after commissioning of Harmony Link, modernization of “North Line” (line between Krajnik and Gdansk Blonia) is necessary. The first project of North Line is modernization of Krajnik-Morzyczyn 400kV line. | 2 | New Investment |  | 2023 | 2023 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Krajnik | Morzyczyn | ACTransmissionLine | AC | 41.5 | New | 170 | 1663 | Baltic States Synchronization with Continental Europe | Modernization of 400kV OHL Krajnik-Morzyczyn | To allow effective energy flows in the north-west part of Poland after commissioning of Harmony Link, modernization of “North Line” (line between Krajnik and Gdansk Blonia) is necessary. The first project of North Line is modernization of Krajnik-Morzyczyn 400kV line. | 4 | New Investment |  | 07-2023 | 2023 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Krajnik | Morzyczyn | ACTransmissionLine | AC | 0 | 400 | 41.5 | MostlyNew | 170 | 1663 | Baltic States Synchronization with Continental Europe | Modernization of 400kV OHL Krajnik-Morzyczyn | To allow effective energy flows in the north-west part of Poland after commissioning of Harmony Link, modernization of “North Line” (line between Krajnik and Gdansk Blonia) is necessary. The first project of North Line is modernization of Krajnik-Morzyczyn 400kV line. | 5 | New Investment |  | 05-2023 | 2023 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Krajnik | Morzyczyn | ACTransmissionLine | AC | 0 | 400 | 41.5 | MostlyNew | 170 | 1663 | Baltic States Synchronization with Continental Europe | Modernization of 400kV OHL Krajnik-Morzyczyn-Dunowo | To allow effective energy flows in the north-west part of Poland after commissioning of Harmony Link, modernization of “North Line” (line between Krajnik and Gdansk Blonia) is necessary. The first project of North Line is modernization of Krajnik-Morzyczyn-Dunowo 400kV lines. | 5 | Commissioned | 05-2023 | 2023 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2023 | 2023 | 0 | 3 | EST;LTU;LVA;POL | Krajnik | Morzyczyn | 53.1974 | 14.4697 | 52.4314 | 18.4063
379 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1664 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 170 | 1664 | Baltic States Synchronization with Continental Europe | Modernization of 400kV OHL Morzyczyn-Dunowo-Slupsk-Zarnowiec | Modernisation of Morzyczyn-Dunowo-Slupsk-Zarnowiec 400kV line would be the longest part included in modernization of North Line. Because of its length this project consists of three sections: Modernization of Morzyczyn-Dunowo 400 kV, Modernization of Dunowo-Slupsk 400 kV, Modernization of Slupsk-Zarnowiec 400 kV. | 2 | New Investment |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Morzyczyn | Zarnowiec | ACTransmissionLine | AC | 288.5 | New | 170 | 1664 | Baltic States Synchronization with Continental Europe | Modernization of 400kV OHL Morzyczyn-Dunowo-Slupsk-Zarnowiec | Modernisation of Morzyczyn-Dunowo-Slupsk-Zarnowiec 400kV line would be the longest part included in modernization of North Line. Because of its length this project consists of three sections: Modernization of Morzyczyn-Dunowo 400 kV, Modernization of Dunowo-Slupsk 400 kV, Modernization of Slupsk-Zarnowiec 400 kV. | 2 | New Investment |  | 12-2023 | 2023 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Morzyczyn | Zarnowiec | ACTransmissionLine | AC | 0 | 400 | 288.5 | MostlyNew | 170 | 1664 | Baltic States Synchronization with Continental Europe | Modernization of 400kV OHL Morzyczyn-Dunowo-Slupsk-Zarnowiec | Modernisation of Morzyczyn-Dunowo-Slupsk-Zarnowiec 400kV line would be the longest part included in modernization of North Line. Because of its length this project consists of three sections: Modernization of Morzyczyn-Dunowo 400 kV, Modernization of Dunowo-Slupsk 400 kV, Modernization of Slupsk-Zarnowiec 400 kV. | 4 | New Investment |  | 12-2027 | 2027 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Morzyczyn | Zarnowiec | ACTransmissionLine | AC | 0 | 400 | 288.5 | MostlyNew | 170 | 1664 | Baltic States Synchronization with Continental Europe | Modernization of 400kV OHL Dunowo-Slupsk. | Modernisation of Dunowo-Slupsk 400kV line. | 4 |  | 12-2027 | 2027 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2025 | 2027 | 2 | 7 | EST;LTU;LVA;POL | Morzyczyn | Zarnowiec | 52.4314 | 18.4063
380 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1665 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 170 | 1665 | Baltic States Synchronization with Continental Europe | Modernization of 400kV OHL Zarnowiec-Gdansk/Gdansk Przyjazn-Gdansk Blonia | Modernisation of Zarnowiec-Gdansk/Gdansk Przyjazn-Gdansk Blonia 400kV line would be the last part included in modernization of North Line. | 2 | New Investment |  | 2024 | 2024 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Zarnowiec | Gdansk Blonia | ACTransmissionLine | AC | 77 | New | 170 | 1665 | Baltic States Synchronization with Continental Europe | Modernization of 400kV OHL Zarnowiec-Gdansk/Gdansk Przyjazn-Gdansk Blonia | Modernisation of Zarnowiec-Gdansk/Gdansk Przyjazn-Gdansk Blonia 400kV line would be the last part included in modernization of North Line. | 2 | New Investment |  | 12-2023 | 2023 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Zarnowiec | Gdansk Blonia | ACTransmissionLine | AC | 0 | 400 | 77 | MostlyNew | 170 | 1665 | Baltic States Synchronization with Continental Europe | Modernization of 400kV OHL Zarnowiec-Gdansk/Gdansk Przyjazn-Gdansk Blonia | Modernisation of Zarnowiec-Gdansk/Gdansk Przyjazn-Gdansk Blonia 400kV line would be the last part included in modernization of North Line. | 4 | New Investment |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Zarnowiec | Gdansk Blonia | ACTransmissionLine | AC | 0 | 400 | 77 | MostlyNew | 170 | 1665 | Baltic States Synchronization with Continental Europe | Modernization of 400kV OHL Zarnowiec-Gdansk/Gdansk Przyjazn-Gdansk Blonia | Modernisation of Zarnowiec-Gdansk/Gdansk Przyjazn-Gdansk Blonia 400kV line would be the last part included in modernization of North Line. | 4 |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2024 | 2025 | 1 | 5 | EST;LTU;LVA;POL | Zarnowiec | Gdansk Blonia |  |  | 54.3442 | 18.7003
381 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1669 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 170 | 1669 | Baltic States Synchronization with Continental Europe | Synchronous condensers in Lithuania, Latvia and Estonia | Synchronous condensers providing inertia, voltage stability,frequency stability and short-circuit power in Lithuania, Latvia and Estonia | 3 | Investment on time |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | 330 kV substations in the Baltics | - |  | AC | 0 | New | 170 | 1669 | Baltic States Synchronization with Continental Europe | Synchronous condensers in Lithuania, Latvia and Estonia | Synchronous condensers providing inertia, voltage stability, frequency stability and short-circuit power in Lithuania, Latvia and Estonia. | 3 | Investment on time |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | 330 kV substations in the Baltics | - | ReactiveCompensationDevice | AC | 0 | 0 | 0 | MostlyNew | 170 | 1669 | Baltic States Synchronization with Continental Europe | Synchronous condensers in Lithuania, Latvia and Estonia | Synchronous condensers providing inertia, voltage stability,frequency stability and short-circuit power in Lithuania (Neris, Telsiai), Latvia (Grobina, Liksna) and Estonia (Kiisa and Viru). | 4 | Investment on time |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | 330 kV substations in the Baltics | - | ReactiveCompensationDevice | AC | 0 | 0 | 0 | MostlyNew | 170 | 1669 | Baltic States Synchronization with Continental Europe | Synchronous condensers in Lithuania, Latvia and Estonia | Synchronous condensers providing inertia, voltage stability,frequency stability and short-circuit power in Lithuania (Neris, Telsiai), Latvia (Grobina, Liksna) and Estonia (Kiisa and Viru). | 4 |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2025 | 2025 | 0 | 5 | EST;LTU;LVA;POL | Substations In The Baltics
382 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 167 | Commissioned | 167 | New line consisting of underground +subsea cable with a total length of 205km. Line capacity: 400-800MW. | 3 | mid term |  | 1 | Cluster BorWin2 (DE) | Diele (DE) | 42 | 42. 167 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 205km. Line capacity: 800MW. | 4 | Progresses as planned | mid term |  | 1 | Cluster BorWin2 (DE) | Diele (DE) | 42. 167 | 42. 167 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 205km. Line capacity: 800MW. | 4 |  | 2015 | 2015 | 1 | Cluster BorWin2 (DE) | Diele (DE) | 42 | 167 | OWP TenneT Northsea part 1 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 205km. Line capacity: 800MW. | 4 | Delayed |  | 2015 | 2015 | 1 | Cluster BorWin2 (DE) | Diele (DE) | 167 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 205km. Line capacity: 800MW. | 5 | Investment on time |  | 2015 | 2015 | 1 | Cluster BorWin2 (DE) | Diele (DE) | 42 | 167 | OWP TenneT Northsea part 1 | BorWin2 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 205km. Line capacity&#58; 800MW. | 5 | Commissioned | in operation | 1/ 1/ 2015 | 2015 | 1 |  | 0 | Cluster BorWin2 (DE) | Diele (DE) | Subsea Cable | DC | 800 | 400 | 205 | New | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2015 |  | 5 | DEU | Cluster Borwin | Diele |  |  | 53.1201 | 7.3117
383 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1670 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 85 | 1670 | Integration of RES in Alentejo | Alqueva-Divor | New 75 km single-circuit 400 kV OHL Alqueva-Divor. | 2 | New Investment |  | 2023 | 2023 | 1 | Rede Elétrica Nacional |  | 0 | 0 | Alqueva | Divor | ACTransmissionLine | AC | 75 | MostlyUpgrade | 85 | 1670 | Integration of RES in Alentejo | Alqueva-Divor | New 75 km single-circuit 400 kV OHL Alqueva-Divor. | 2 | Investment on time |  | 12-2023 | 2023 | 1 | Rede Elétrica Nacional |  | 0 | 0 | Alqueva | Divor | ACTransmissionLine | AC | 0 | 400 | 75 | MostlyUpgrade | 85 | 1670 | Integration of RES in Alentejo | Alqueva-Divor | New 75 km double-circuit (only one circuit installed initially) 400 kV OHL Alqueva-Divor . | 3 | Delayed | Delays in permitting | 03-2025 | 2025 | 1 | Rede Elétrica Nacional |  | 0 | 0 | Alqueva | Divor | ACTransmissionLine | AC | 0 | 400 | 75 | MostlyUpgrade | 85 | 1670 | Integration of RES in Alentejo | Alqueva-Divor | New 75 km double-circuit (only one circuit installed initially) 400 kV OHL Alqueva-Divor . |  |  | 12-2026 | 2026 | 1 | Rede Elétrica Nacional | 0 | XX | XX | Mostly upgrade | 2023 | 2026 | 3 | 6 | PRT | Alqueva | Divor | 38.2259 | -7.5371 | 38.6553 | -7.9865
384 | 2020 | 2020 | [2020] | 1673 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 229 | 1673 | GerPol Power Bridge II | Zielona Góra - Polkowice | Construction of new 2x400 kV line from new substation Zielona Góra to existing substation Polkowice | 1 | New Investment |  | 2035 | 2035 | 1 | Polskie Sieci Elektroenergetyczne S.A. 50HERTZ |  | 0 | 1 | Zielona Góra | Polkowice | ACTransmissionLine | AC | 90 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 15 | DEU;POL | Zielona Góra | Polkowice | 52.5114 | 13.4595 | 51.5039 | 16.0713
385 | 2020 | 2020 | [2020] | 1674 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 229 | 1674 | GerPol Power Bridge II | Zielona Góra - Eisenhuettenstadt | Construction of new crossborder 2x400 kV line between new substation Zielona Góra (PL) end existing substation Eisenhuettenstadt (DE) | 1 | New Investment |  | 2035 | 2035 | 1 | Polskie Sieci Elektroenergetyczne S.A. 50HERTZ |  | 1 | 1 | Zielona Góra | Eisenhuettenstadt | ACTransmissionLine | AC | 80 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 15 | DEU;POL | Zielona Góra | Eisenhuettenstadt | 52.5114 | 13.4595 | 52.1449 | 14.6294
386 | 2020 | 2024 | [2020, 2022, 2024] | 1675 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1039 | 1675 | SE North-south long-term reinforcements | SE North-south Long-term reinforcements | Reactive measures in substations and series compensations in order to increase capacity between SE2 and SE3. Replacement of ageing overhead lines that also will contribute to the increased capacity. The need for capacity is driven by RES integration in northern Sweden and nuclear decommission in southern Sweden. | 1 | Investment on time |  | 2040 | 2040 | 1 | Svenska Kraftnät |  | 1 | 0 | SE2 | SE3 | ACTransmissionLine | AC | 950 | MostlyUpgrade | 1039 | 1675 | SE North-south long-term reinforcements | SE North-south Long-term reinforcements | Reactive measures in substations and series compensations in order to increase capacity between SE2 and SE3. Replacement of ageing overhead lines that also will contribute to the increased capacity. The need for capacity is driven by RES integration in northern Sweden and nuclear decommission in southern Sweden. | 1 | Investment on time |  | 01-2040 | 2040 | 1 | Svenska Kraftnät |  | 1 | 0 | SE2 | SE3 | ACTransmissionLine | AC | 0 | 400 | 475 | MostlyUpgrade | 1039 | 1675 | SE North-south long-term reinforcements | SE North-south Long-term reinforcements | Reactive measures in substations and series compensations in order to increase capacity between SE2 and SE3. Replacement of ageing overhead lines that also will contribute to the increased capacity. The need for capacity is driven by RES integration in northern Sweden and nuclear decommission in southern Sweden. | 1 | Investment on time |  | 01-2040 | 2040 | 1 | Svenska Kraftnät |  | 1 | 0 | SE2 | SE3 | ACTransmissionLine | AC | 0 | 400 | 475 | MostlyUpgrade | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2040 | 2040 | 0 | 20 | SWE | Se | Se
387 | 2020 | 2022 | [2020, 2022] | 1676 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 252 | 1676 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | Mercator - Massenhoven: HTLS upgrade | Upgrade of this double-circuit axis to HTLS conductors | 2 | Investment on time |  | 2030 | 2030 | 1 | ELIA |  | 0 | 0 | Mercator | Massenhoven | ACTransmissionLine | AC | 36 | Upgrade | 252 | 1676 | Internal Belgian Backbone Center-East: HTLS upgrade Massenhoven-VanEyck-Gramme-Courcelles-Bruegel-Mercator | Mercator - Massenhoven: HTLS upgrade | Upgrade of this double-circuit axis to HTLS conductors | 2 | Investment on time |  | 12-2030 | 2030 | 1 | Elia |  | 0 | 0 | Mercator | Massenhoven | ACTransmissionLine | AC | 0 | 380 | 36 | Upgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 10 | BEL | Mercator | Massenhoven | 50.9097 | 4.3963 | 51.199 | 4.635
388 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1677 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1040 | 1677 | LirIC | LirIC | New HVDC VSC Monopole sub sea cable between Kilroot 275kV substation in Northern Ireland (TBC) and Hunterston 400kV sub station in Scotland (TBC) | 1 | New Investment |  | 2027 | 2027 | 1 | Transmission Investment |  | 1 | 0 | NI Kilroot 275kV (TBC) | GB Hunterston 400kV (TBC) | OffshoreDCTransmissionCable | DC | 133 | New | 1040 | 1677 | LirIC | LirIC | New HVDC VSC Monopole sub sea cable between Kilroot 275kV substation in Northern Ireland (TBC) and Kilmarnock South 400kV sub station in Scotland (TBC) | 1 | New Investment |  | 12-2028 | 2028 | 1 | Transmission Investment |  | 1 | 0 | NI Kilroot 275kV (TBC) | GB Kilmarnock South 400kV (TBC) | OffshoreDCTransmissionCable | DC | 700 | 320 | 133 | New | 1040 | 1677 | LirIC | LirIC | New HVDC VSC Monopole sub sea cable between Kilroot 275kV substation in Northern Ireland (TBC) and Hunterston 400kV sub station in Scotland (TBC) | 1 | New Investment |  | 09-2030 | 2030 | 1 | Transmission Investment |  | 1 | 0 | NI Kilroot 275kV (TBC) | GB Hunterston 400kV (TBC) | OffshoreDCTransmissionCable | DC | 700 | 320 | 142 | New | 1040 | 1677 | LirIC | LirIC | New HVDC VSC Monopole sub sea cable between Kilroot 275kV substation in Northern Ireland and Hunterston 400kV sub station in Scotland | 1 |  | 10-2032 | 2032 | 1 | Transmission Investment | 0 | XX | XX | New | 2027 | 2032 | 5 | 12 | GBR | Ni Kilroot | Gb Hunterston |  |  | 55.7219 | -4.8894
389 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1682 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1041 | 1682 | GREGY Interconnector | Wadi El Natroon - Acharnes HVDC | Wadi El Natroon - Acharnes HVDC Link. This investment includes two LCC converter stations at both ends of the bipolar 600kV HVDC link along with the grounding electrodes. The interconnection circuits consist of approximately 500km of overhead HVDC lines (ACSR/PLOVER), approximately 30km length of underground cables (Al 1800mm2) and approximately 843km of submarine Cables (Cu 1000mm2, Al 1300mm2). | 1 |  |  | 2028 | 2028 | 1 | ELICA S.A. |  | 1 | 1 | Wadi El Natroon | Acharnes | DCTransmissionLine | DC | 1373 | New | 1041 | 1682 | GREGY Green Energy Interconnector | Wadi El Natroon - Mesogeia / St Stefanos HVDC | Wadi El Natroon - Mesogeia / St Stefanos HVDC Link. This investment includes two VSC converter stations at both ends of the bipolar 525kV HVDC link along with the grounding electrodes. The interconnection circuits consist of approximately 500km of overhead HVDC lines (ACSR/PLOVER), approximately 30km length of underground cables (Al 2200mm2) and approximately 921 or 954 km of submarine Cables (Al 1800mm2). | 1 | Investment on time |  | 01-2028 | 2028 | 1 | ELICA INTERCONNECTOR SINGLE-MEMBER S.A. |  | 1 | 1 | Wadi El Natroon | Mesogeia / St Stefanos | DCTransmissionLine | DC | 3000 | 525 | 1472 | New | 1041 | 1682 | GREGY Green Energy Interconnector | Wadi El Natroon - Mesogeia / St Stefanos HVDC | The HVDC transmission link of 3,000 MW thermal capacity, to be constructed, will consist of two (2) bi-pole systems each of 1,500 MW. Each system having converters at both ends, constitutes submarine HVDC cables from Sidi Barrani shore (Egypt) to Keratea / Kakia Thalassa (Attica, Greece) and from Sidi Barrani shore (Egypt) to Nea Makri (Attica, Greece). Supporting/complementary interconnection infrastructure at the two landing points in Egypt and Greece are also part of the GREGY project. Chapters 3 and 4 of the prefeasibility study provide the selection of technical equipment in more detail. | 1 | Rescheduled | The implementation timeline of GREGY Green Energy Interconnector has been updated by considering the ongoing execution of the final feasibility study. The final feasibility study will have been completed by May 2024. The project will be commissioned by December 2028 at the latest. This is a conservative plan, as the project promoter aims to exploit the possibility of reaching an agreement with the potential suppliers of cables and Electromechanical equipment (e.g., converters, etc.) to reduce the delivery time and hence reduce the overall time required to implement GREGY. | 06-2029 | 2029 | 1 | ELICA MEDITERRANEAN ELECTRICAL INTERCONNECTION SINGLE-MEMBER S.A. | 2.13 | 1 | 1 | Wadi El Natroon | Mesogeia / St Stefanos | DCTransmissionLine | DC | 3000 | 525 | 954 | New | 1041 | 1682 | GREGY Green Energy Interconnector | GREGY Green Energy Interconnector | The HVDC transmission link of 3,000 MW green capacity, to be constructed, will consist of two (2) bi-pole systems each of 1,500 MW. Each system having converters at both ends, constitutes submarine HVDC cables from Sidi Barrani shore (Egypt) to Keratea / Kakia Thalassa (Attica, Greece) and from Sidi Barrani shore (Egypt) to Nea Makri (Attica, Greece). Supporting/complementary interconnection infrastructure at the two landing points in Egypt and Greece are also part of the GREGY project. Chapters 3 and 4 of the prefeasibility study provide the selection of technical equipment in more detail. | 1 |  | 09-2030 | 2030 | 1 | ELICA MEDITERRANEAN ELECTRICAL INTERCONNECTION SINGLE-MEMBER S.A. | 1 | XX | XX | New | 2028 | 2030 | 2 | 10 | EGY;GRC | Wadi El Natroon | Mesogeia St Stefanos
390 | 2020 | 2020 | [2020] | 1684 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 207 | 1684 | Reinforcement Northwestern DE | Conneforde-Wilhelmshaven | New 380kV double circuit (OHL, partly underground) Conneforde - Wilhelmshaven (Fedderwarden, former Maade) including new 380kV switchgear Fedderwarden. Length 35 km. | 4 | Investment on time |  | 2020 | 2020 | 1 | TenneT DE |  | 0 | 0 | Conneforde (DE) | Wilhelmshaven (DE) | ACTransmissionLine | AC | 30 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 0 | DEU | Conneforde | Wilhelmshaven | 53.3258 | 8.0578 | 53.5279 | 8.1063
391 | 2020 | 2020 | [2020] | 1685 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1043 | 1685 | Wahle-Mecklar | Dollern - Stade | New 380kV double circuit OHL Dollern - Stade including new 380kV switchgear in Stade. Length 14km. | 4 | Delayed | Due to complex and long permisstin process | 2021 | 2021 | 1 | TenneT DE |  | 0 | 0 | Dollern (DE) | Stade (DE) | ACTransmissionLine | AC | 14 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2021 | 0 | 1 | DEU | Dollern | Stade | 53.5378 | 9.5385 | 53.5998 | 9.4754
392 | 2020 | 2020 | [2020] | 1686 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1043 | 1686 | Wahle-Mecklar | Wahle - Mecklar | New 380kV double circuit OHL Wahle - Mecklar including two new substations. Length: 210km. | 4 | Investment on time | Due to complex and long permitting process | 2024 | 2024 | 1 | TenneT DE |  | 1 | 0 | Wahle (DE) | Mecklar (DE) | ACTransmissionLine | AC | 210 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2024 | 2024 | 0 | 4 | DEU | Wahle | Mecklar | 52.2718 | 10.3634 | 50.9175 | 9.7612
393 | 2020 | 2020 | [2020] | 1687 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1041 | 1687 | GREGY Interconnector | AC Overhead Line 1 (Ras Ghareb-Nile West) | AC 500KV interconnection line (double circuit OHL) which connects Wind Farms of Ras Ghareb to Nile West point | 1 |  |  | 2028 | 2028 | 1 | ELICA S.A. |  | 1 | 1 | Ras Ghareb Wind Farms Substation | Nile West | ACTransmissionLine | AC | 420 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2028 | 2028 | 0 | 8 | EGY;GRC | Ras Ghareb Wind Farms | Nile West
394 | 2020 | 2024 | [2020, 2022, 2024] | 1688 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1046 | 1688 | N-S Finland P1 stage 3 | Nuojuankangas-Huutokoski | New single circuit 400 kV OHLs will be built from central part of Finland to the northern area to increase the capacity between North and South Finland. Enables integration of renewables to the northern part of the country. | 3 | New Investment |  | 2028 | 2028 | 1 | FINGRID |  | 1 | 0 | Nuojuankangas | Huutokoski | ACTransmissionLine | AC | 290 | New | 1046 | 1688 | Finnish North-South reinforcement | Nuojuankangas-Huutokoski (Järvilinja 2) | New single circuit 400 kV OHLs will be built from central part of Finland to the northern area to increase the capacity between North and South Finland. Enables integration of renewables to the northern part of the country. | 2 | New Investment |  | 06-2026 | 2026 | 1 | Fingrid |  | 1 | 0 | Nuojuankangas | Huutokoski | ACTransmissionLine | AC | 0 | 400 | 290 | New | 1046 | 1688 | Finnish North-South reinforcement | Nuojuankangas-Huutokoski (Järvilinja 2) | New single circuit 400 kV OHLs will be built from central part of Finland to the northern area to increase the capacity between North and South Finland. Enables integration of renewables to the northern part of the country. | 4 | New Investment |  | 06-2026 | 2026 | 1 | Fingrid |  | 1 | 0 | Nuojuankangas | Huutokoski | ACTransmissionLine | AC | 0 | 400 | 290 | New | [5 empty] | 5 | Commissioned |  |  | 0 | [5 empty] | 2028 | 2026 | -2 | 6 | FIN | Nuojuankangas | Huutokoski | 64.573 | 26.7217 | 62.2101 | 27.6889
395 | 2020 | 2024 | [2020, 2022, 2024] | 1689 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1046 | 1689 | N-S Finland P1 stage 3 | Tuomela B-Nuojuankangas | New single circuit 400 kV OHL will be built to the northern part of Finland. Enables the integration of renewables to the northern part of the country and the increasing power transfer from North to South . | 3 | New Investment |  | 2029 | 2029 | 1 | FINGRID |  | 0 | 0 | Tuomela B | Nuojuankangas | ACTransmissionLine | AC | 100 | New | 1046 | 1689 | Finnish North-South reinforcement | Petäjäskoski-Herva-Nuojuankangas | New single circuit 400 kV OHL will be built to the northern part of Finland. Enables the integration of renewables to the northern part of the country and the increasing power transfer from North to South . | 3 | New Investment |  | 06-2027 | 2027 | 1 | Fingrid |  | 0 | 0 | Petäjäskoski | Nuojuankangas | ACTransmissionLine | AC | 0 | 400 | 215 | New | 1046 | 1689 | Finnish North-South reinforcement | Petäjäskoski-Herva-Nuojuankangas | New single circuit 400 kV OHL will be built to the northern part of Finland. Enables the integration of renewables to the northern part of the country and the increasing power transfer from North to South . | 3 | New Investment |  | 06-2027 | 2027 | 1 | Fingrid |  | 0 | 0 | Petäjäskoski | Nuojuankangas | ACTransmissionLine | AC | 0 | 400 | 215 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2029 | 2027 | -2 | 7 | FIN | Petäjäskoski | Nuojuankangas | 66.2716 | 25.3342 | 64.573 | 26.7217
396 | 2020 | 2020 | [2020] | 1690 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1041 | 1690 | GREGY Interconnector | AC Overhead Line 2 (Nile West-Wadi El Natroon EHV) | AC 500KV Interconnection Lines (two double-circuit OHLs) which connect Nile West Point with Wadi El Natroon EHV Center | 1 |  |  | 2028 | 2028 | 1 | ELICA S.A. |  | 1 | 1 | NILE WEST POINT | WADI EL NATROON | ACTransmissionLine | AC | 220 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2028 | 2028 | 0 | 8 | EGY;GRC | Nile West Point | Wadi El Natroon
397 | 2020 | 2022 | [2020, 2022] | 1691 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1047 | 1691 | Emden-Eemshaven | Emden-Eemshaven |  | 1 | New Investment |  | 2035 | 2035 | 1 | TenneT DE |  | 1 | 1 | Emden | Eemshaven | OffshoreACTransmissionCable | AC | 31 | New | 1047 | 1691 | Emden-Eemshaven | Emden-Eemshaven | Increase of the interconnection capacity between the Netherlands (Eemshaven) and Germany (Emden) by adding a new 380kV transmission line. The project is planned as a combination of overhead line, onshore cable and sub sea cable and a PST in Emden. | 1 | Investment on time |  | 12-2035 | 2035 | 1 | TenneT DE |  | 1 | 1 | Emden | Eemshaven | OffshoreACTransmissionCable | AC | 0 | 380 | 31 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 15 | DEU;NLD | Emden | Eemshaven | 53.3671 | 7.2058 | 53.4484 | 6.8465
398 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1692 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1034 | 1692 | HVDC corridor from Northern Germany to Western Germany | HVDC from Wilhelmshaven to Uentrop | HVDC line from Wilhelmshaven to Uentrop to integrate onshore and offshore wind energy in Northern Germany and transport it to the load centers in Western Germany | 2 | New Investment |  | 2030 | 2030 | 1 | AMPRION TenneT DE |  | 1 | 0 | Wilhelmshaven | Uentrop | DCTransmissionLine | DC | 267 | New | 1034 | 1692 | HVDC corridor from Northern Germany to Western Germany | HVDC from Wilhelmshaven to Region Hamm | HVDC line from Wilhelmshaven to Uentrop to integrate onshore and offshore wind energy in Northern Germany and transport it to the load centers in Western Germany | 2 | Delayed | explanation missing | 12-2031 | 2031 | 1 | Amprion | 2.31.2 and 2.31.3 | 1 | 0 | Wilhelmshaven | Region Hamm | DCTransmissionLine | DC | 2000 | 525 | 270 | New | 1034 | 1692 | HVDC corridor from Northern Germany to Western Germany | HVDC from Wilhelmshaven to Region Hamm | HVDC line from Wilhelmshaven to Uentrop to integrate onshore and offshore wind energy in Northern Germany and transport it to the load centers in Western Germany | 2 | Rescheduled | expansion of the project scope because of legislative change (empty tube/ cable tube) | 12-2032 | 2032 | 1 | Amprion | 1.4.2 and 1.4.3 | 1 | 0 | Wilhelmshaven | Region Hamm | DCTransmissionLine | DC | 2000 | 525 | 270 | New | 1034 | 1692 | HVDC corridor from Northern Germany to Western Germany | HVDC from Wilhelmshaven to Region Hamm | HVDC line from Wilhelmshaven to Uentrop to integrate onshore and offshore wind energy in Northern Germany and transport it to the load centers in Western Germany | 2 |  | 12-2032 | 2032 | 1 | Amprion | 0 | XX | XX | New | 2030 | 2032 | 2 | 12 | DEU | Wilhelmshaven | Region Hamm | 53.5279 | 8.1063
399 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1693 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1034 | 1693 | HVDC corridor from Northern Germany to Western Germany | HVDC from Heide/West to Polsum | HVDC line from Heide/West to Polsum to integrate onshore and offshore wind energy in Northern Germany and transport it to the load centers in Western Germany | 2 | New Investment |  | 2030 | 2030 | 1 | AMPRION TenneT DE |  | 0 | 0 | Heide/West | Polsum | DCTransmissionLine | DC | 407 | New | 1034 | 1693 | HVDC corridor from Northern Germany to Western Germany | HVDC from Heide/West to Polsum | HVDC line from Heide/West to Polsum to integrate onshore and offshore wind energy in Northern Germany and transport it to the load centers in Western Germany | 2 | Investment on time |  | 12-2031 | 2031 | 1 | Amprion | 2.31.2 and 2.31.3 | 0 | 0 | Heide/West | Polsum | DCTransmissionLine | DC | 2000 | 525 | 440 | New | 1034 | 1693 | HVDC corridor from Northern Germany to Western Germany | HVDC from Heide/West to Polsum | HVDC line from Heide/West to Polsum to integrate onshore and offshore wind energy in Northern Germany and transport it to the load centers in Western Germany | 2 | Rescheduled | expansion of the project scope because of legislative change (empty tube/ cable tube) | 12-2032 | 2032 | 1 | Amprion | 1.4.2 and 1.4.3 | 0 | 0 | Heide/West | Polsum | DCTransmissionLine | DC | 2000 | 525 | 440 | New | 1034 | 1693 | HVDC corridor from Northern Germany to Western Germany | HVDC from Heide/West to Polsum | HVDC line from Heide/West to Polsum to integrate onshore and offshore wind energy in Northern Germany and transport it to the load centers in Western Germany | 2 |  | 12-2033 | 2033 | 1 | Amprion | 0 | XX | XX | New | 2030 | 2033 | 3 | 13 | DEU | Heidewest | Polsum |  |  | 51.6265 | 7.0528
400 | 2020 | 2020 | [2020] | 1694 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1042 | 1694 | Offshore wind integration | New 330 kV OHL Darbenai-Musa | New 330 kV OHL Darbenai-Musa | 1 | Delayed | Investment depends on plans to build offshore wind farms | 2030 | 2030 | 1 | LITGRID AB |  | 1 | 0 | Darbnai | Muša | ACTransmissionLine | AC | 170 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 10 | LTU | Darbnai | Mua |  |  | 55.9354 | 23.313
401 | 2020 | 2020 | [2020] | 1695 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1042 | 1695 | Offshore wind integration | New 330 kV OHL Panevezys-Musa | New 330 kV OHL Panevežys-Muša | 1 | Delayed | Investment depends on plans to build offshore wind farms | 2030 | 2030 | 1 | LITGRID AB |  | 0 | 0 | Panevežys | Muša | ACTransmissionLine | AC | 72 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 10 | LTU | Paneveys | Mua |  |  | 55.9354 | 23.313
402 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1697 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1046 | 1697 | N-S Finland P1 stage 3 | Petäjävesi-Hikiä | New single circuit 400 kV OHL will be built to the central part of Finland. Enables the integration of renewables and the utilization of full transfer capacity from North to South . | 2 | New Investment |  | 2030 | 2030 | 1 | FINGRID |  | 0 | 0 | Petäjävesi | Hikiä | ACTransmissionLine | AC | 175 | New | 1046 | 1697 | Finnish North-South reinforcement | Petäjävesi/Toivila-Hikiä (2 x OHL) | New 2 x 400 kV OHL will be built to the central part of Finland (+other required investments). Enables the integration of renewables and the utilization of full transfer capacity from North to South . | 2 | New Investment |  | 06-2028 | 2028 | 1 | Fingrid |  | 0 | 0 | Petäjävesi/Toivila | Hikiä | ACTransmissionLine | AC | 0 | 400 | 175 | New | 1046 | 1697 | Finnish North-South reinforcement | Petäjävesi/Toivila-Hikiä (2 x OHL) | New 2 x 400 kV OHL will be built to the central part of Finland (+other required investments). Enables the integration of renewables and the utilization of full transfer capacity from North to South . | 3 | New Investment |  | 06-2028 | 2028 | 1 | Fingrid |  | 0 | 0 | Petäjävesi/Toivila | Hikiä | ACTransmissionLine | AC | 0 | 400 | 175 | New | 1046 | 1697 | Finnish North-South reinforcement | Toivila-Hikiä (2 x OHL) | New 2 x 400 kV OHL will be built to the central part of Finland (+other required investments). Enables the integration of renewables and the utilization of full transfer capacity from North to South . |  |  | 06-2028 | 2028 | 1 | Fingrid | 0 | XX | XX | New | 2030 | 2028 | -2 | 8 | FIN | Petäjävesitoivila | Hikiä |  |  | 60.7538 | 24.9233
403 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1698 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 342 | 1698 | Central Balkan Corridor | New 400 kV SY Pozega | New 400 kV SY Pozega | 2 | New Investment |  | 2034 | 2034 | 1 | EMS ESO |  | 0 | 1 | SS Pozega | SS Pozega | OnshoreSubstation | AC | 0 | MostlyUpgrade | 342 | 1698 | Central Balkan Corridor | New 400 kV SY Pozega | New 400 kV SY Pozega | 2 | Investment on time |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD, CGES, NOS BiH |  | 0 | 1 | SS Pozega | SS Pozega | OnshoreSubstation | AC | 0 | 400 | 0 | MostlyUpgrade | 342 | 1698 | Central Balkan Corridor | New 400 kV SY Pozega | New 400 kV SY Pozega | 2 | Investment on time |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD |  | 0 | 1 | SS Pozega | SS Pozega | OnshoreSubstation | AC | 0 | 400 | 0 | MostlyUpgrade | 342 | 1698 | Central Balkan Corridor | New 400 kV SY Požega | New 400 kV SY Požega | 2 |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD | 1 | XX | XX | Mostly new | 2034 | 2034 | 0 | 14 | BGR;SRB | Pozega | Pozega | 43.846 | 20.0357 | 43.846 | 20.0357
404 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1699 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 342 | 1699 | Central Balkan Corridor | New OHL SS Jagodina 4 - SY Drmno | New OHL SS Jagodina 4 - SY Drmno | 2 | New Investment |  | 2034 | 2034 | 1 | EMS ESO |  | 0 | 1 | SS Jagodina 4 | SY Drmno | ACTransmissionLine | AC | 95 | MostlyUpgrade | 342 | 1699 | Central Balkan Corridor | New OHL SS Jagodina 4 - SY Drmno | New OHL SS Jagodina 4 - SY Drmno | 2 | Ahead of time |  | 09-2027 | 2027 | 1 | JSC EMS, ESO EAD, CGES, NOS BiH |  | 0 | 1 | SS Jagodina 4 | SY Drmno | ACTransmissionLine | AC | 0 | 400 | 95 | MostlyUpgrade | 342 | 1699 | Central Balkan Corridor | New OHL SS Jagodina 4 - SS Pozarevac 3 | New OHL SS Jagodina 4 - SS Pozarevac 3 | 2 | Delayed | Updated consideration of the necessary investments and the scope of work. | 09-2030 | 2030 | 1 | JSC EMS, ESO EAD |  | 0 | 1 | SS Jagodina 4 | SS Pozarevac 3 | ACTransmissionLine | AC | 0 | 400 | 77 | MostlyUpgrade | 342 | 1699 | Central Balkan Corridor | New OHL 2x400 kV SS Jagodina 4 - SS Požarevac 3 | New OHL SS Jagodina 4 - SS Požarevac 3 | 2 |  | 09-2030 | 2030 | 1 | JSC EMS, ESO EAD | 1 | XX | XX | Mostly new | 2034 | 2030 | -4 | 10 | BGR;SRB | Jagodina | Pozarevac | 41.6358 | 24.3523 | 44.62 | 21.1854
405 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1700 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 342 | 1700 | Central Balkan Corridor | OHL SS Pozega - SS Pljevlja | Upgrading 220 kV OHL SS Pozega - node Vardiste to 2x400 kV and conductoring second circuit on 400 kV OHL SS Bajina Basta - SS Pljevlja from node Vardiste to SS Pljevlja. | 2 | New Investment |  | 2034 | 2034 | 1 | EMS ESO |  | 0 | 1 | SY Pozega | SS Pljevlja | ACTransmissionLine | AC | 135 | MostlyUpgrade | 342 | 1700 | Central Balkan Corridor | 400 kV OHL SY Pozega - SS Pljevlja | Upgrading 220 kV OHL SY Pozega - Vardiste to 2x400 kV and conductoring second circuit on 400 kV OHL SS Bajina Basta - SS Pljevlja from Vardiste to SS Pljevlja. | 2 | Investment on time |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD, CGES, NOS BiH |  | 0 | 1 | SY Pozega | SS Pljevlja | ACTransmissionLine | AC | 0 | 400 | 135 | MostlyUpgrade | 342 | 1700 | Central Balkan Corridor | 2x400 kV OHL SY Pozega - Vardiste | Upgrading 220 kV OHL SY Pozega - Vardiste to 2x400 kV | 2 | Investment on time |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD |  | 0 | 1 | SY Pozega | Vardiste | ACTransmissionLine | AC | 0 | 400 | 50 | MostlyUpgrade | 342 | 1700 | Central Balkan Corridor | 2x400 kV OHL SY Požega - Vardište | Upgrading 220 kV OHL SY Požega - Vardište to 2x400 kV | 2 |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD | 1 | XX | XX | Mostly new | 2034 | 2034 | 0 | 14 | BGR;SRB | Sy Pozega | Vardiste |  |  | 43.5045 | 20.8697
406 | 2020 | 2022 | [2020, 2022] | 1701 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 342 | 1701 | Central Balkan Corridor | OHL SS Pozega - SS Visegrad | Upgrading 220 kV OHL SS Pozega - node Vardiste to 2x400 kV and conductoring second circuit on 400 kV OHL SS Bajina Basta - SS Visegrad from node Vardiste to SS Visegrad.. | 2 | New Investment |  | 2034 | 2034 | 1 | EMS ESO |  | 0 | 1 | SY Pozega | SS Visegrad | ACTransmissionLine | AC | 65 | MostlyUpgrade | 342 | 1701 | Central Balkan Corridor | 400 kV OHL SY Pozega - SS Visegrad | Upgrading 220 kV OHL SY Pozega - Vardiste to 2x400 kV and conductoring second circuit on 400 kV OHL SS Bajina Basta - SS Visegrad from Vardiste to SS Visegrad. | 2 | Investment on time |  | 09-2034 | 2034 | 1 | JSC EMS, ESO EAD, CGES, NOS BiH |  | 0 | 1 | SY Pozega | SS Visegrad | ACTransmissionLine | AC | 0 | 400 | 65 | MostlyUpgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2034 | 2034 | 0 | 14 | BGR;BIH;MNE;SRB | Sy Pozega | Visegrad
407 | 2020 | 2022 | [2020, 2022] | 1702 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 170 | 1702 | Baltic States Synchronization with Continental Europe | Common Baltic Frequency Stability Assessment System (FSAS). Modernisation of System Protection Schemes (SPS) and Under Frequency Load Shedding (UFLS). | FSAS is a common Baltic IT platform, necessary to ensure frequency monitoring in Baltic system, in order to ensure frequency stability in the region in synchronous mode with the CEN and in izolated mode after incidents. | 2 | New Investment |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | - | - |  | AC | 0 | New | 170 | 1702 | Baltic States Synchronization with Continental Europe | Common Baltic Frequency Stability Assessment System (FSAS). Modernisation of System Protection Schemes (SPS) and Under Frequency Load Shedding (UFLS). | FSAS is a common Baltic IT platform, necessary to ensure frequency monitoring in Baltic system, in order to ensure frequency stability in the region in synchronous mode with the CEN and in izolated mode after incidents. | 2 | New Investment |  | 06-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | - | - | OnshoreSubstation | AC | 0 | 0 | 0 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 5 | EST;LTU;LVA;POL
408 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1703 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 170 | 1703 | Baltic States Synchronization with Continental Europe | Reconstruction of switchgears with shunt reactors | Due to the synchronisation project the total length of the power lines will increase. Increase in the total length of power lines higher reactive power generation by these lines. In order to reduce the risk that the voltages will rise too high, sufficient amount of reactive power compensation is needed, which can be achieved with the existing shunt reactors. Nevertheless, the shunt reactors need reliable switchgear to help to minimise the risk induced by commutation errors. | 2 | New Investment |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 |  |  |  | AC | 0 | New | 170 | 1703 | Baltic States Synchronization with Continental Europe | Reconstruction of shunt reactors switchgears | Due to the synchronisation project the total length of the power lines will increase. Increase in the total length of power lines higher reactive power generation by these lines. In order to reduce the risk that the voltages will rise too high, sufficient amount of reactive power compensation is needed, which can be achieved with the existing shunt reactors. Nevertheless, the shunt reactors need reliable switchgear to help to minimise the risk induced by commutation errors. | 2 | New Investment |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Aruküla, Balti, Harku, Kiisa, Paide, Rakvere, Sindi substations | Aruküla, Balti, Harku, Kiisa, Paide, Rakvere, Sindi substations | OnshoreSubstation | AC | 0 | 330 | 0 | MostlyNew | 170 | 1703 | Baltic States Synchronization with Continental Europe | Reconstruction of shunt reactors switchgears | Due to the synchronisation project the total length of the power lines will increase. Increase in the total length of power lines higher reactive power generation by these lines. In order to reduce the risk that the voltages will rise too high, sufficient amount of reactive power compensation is needed, which can be achieved with the existing shunt reactors. Nevertheless, the shunt reactors need reliable switchgear to help to minimise the risk induced by commutation errors. | 4 | New Investment |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Aruküla, Balti, Harku, Kiisa, Paide, Rakvere, Sindi substations | Aruküla, Balti, Harku, Kiisa, Paide, Rakvere, Sindi substations | OnshoreSubstation | AC | 0 | 330 | 0 | MostlyNew | 170 | 1703 | Baltic States Synchronization with Continental Europe | Reconstruction of shunt reactors switchgears | Due to the synchronisation project the total length of the power lines will increase. Increase in the total length of power lines higher reactive power generation by these lines. In order to reduce the risk that the voltages will rise too high, sufficient amount of reactive power compensation is needed, which can be achieved with the existing shunt reactors. Nevertheless, the shunt reactors need reliable switchgear to help to minimise the risk induced by commutation errors. | 4 |  | 06-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2025 | 2025 | 0 | 5 | EST;LTU;LVA;POL | Aruküla Balti Harku Kiisa Paide Rakvere Sindi Substations | Aruküla Balti Harku Kiisa Paide Rakvere Sindi Substations
409 | 2020 | 2022 | [2020, 2022] | 1704 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 293 | 1704 | Southern Aegean Interconnector | Southern Aegean Interconnector | HVAC Submarine cable connecting Levitha offshore Wind Farm HV substation to Dodecanese (Kos & Rhodes HV Substation) | 1 | New Investment |  | 2026 | 2026 | 1 | Kykladika Meltemia SA |  | 0 | 0 | Levitha | Kos - Rhodes | OffshoreACTransmissionCable | AC | 170 | New | 293 | 1704 | Southern Aegean Interconnector | Levitha - Kos | HVAC Submarine cable connecting Levitha offshore Wind Farm HV substation to Dodecanese (Kos & Rhodes HV Substation) | 1 | New Investment |  | 03-2026 | 2026 | 1 | Southern Aegean Interconnector SMSA (Member of Eunice Energy Group) |  | 0 | 0 | Levitha | Kos | OffshoreACTransmissionCable | AC | 0 | 220 | 60 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2026 | 2026 | 0 | 6 | GRC | Levitha | Kos | 37.0057 | 26.4645 | 36.7937 | 27.0848
410 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1706 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1049 | 1706 | Cronos Energy Ltd | Converter Stations & Subsea Cabling | 1.4 GW HVDC electricity interconnector between UK and Belgium Voltage Source Converter (VSC)/Bipolar Grid connection point (substations name): Kemsley (UK) and near Zeebrugge (Belgium), exact substation location subject to grid study in Belgium. Total cable length (substation to substation) 230km (1km in UK and 30km in France) Two cables (XLPE) laid in a single trench Nominal voltage: ±525 kV Thermal limit (Imax): 1330 A Mvar capability range at terminals: 460 MVAr Bus-bar to bus-bar losses profile over MW range: 2.3% (33 MW) full load; 0% (0 MW) at zero load. The annual Availability is 98.1% availability, with 1.8% planned outages, and 0.1% forced outages. The maximum single failure according to the design is 1.4GW. The project will enable the reduction of CO2 emissions by substituting electricity from fossil fuels by generation from RES and nuclear power. There are no material anticipated environmental impacts during construction and operation. | 1 | New Investment |  | 2025 | 2025 | 1 | Cronos Energy Ltd |  | 1 | 1 | Kemsley | Zeebrugge | OffshoreDCTransmissionCable | DC | 230 | New | 1049 | 1706 | Cronos Energy Ltd | Converter Stations & Subsea Cabling | 1.4 GW HVDC electricity interconnector between UK and Belgium Voltage Source Converter (VSC)/Bipolar Grid connection point (substations name): Kemsley (UK) and near Zeebrugge (Belgium), exact substation location subject to grid study in Belgium. Total cable length (substation to substation) 230km (1km in UK and 30km in France) Two cables (XLPE) laid in a single trench Nominal voltage: ±525 kV Thermal limit (Imax): 1330 A Mvar capability range at terminals: 460 MVAr Bus-bar to bus-bar losses profile over MW range: 2.3% (33 MW) full load; 0% (0 MW) at zero load. The annual Availability is 98.1% availability, with 1.8% planned outages, and 0.1% forced outages. The maximum single failure according to the design is 1.4GW. The project will enable the reduction of CO2 emissions by substituting electricity from fossil fuels by generation from RES and nuclear power. There are no material anticipated environmental impacts during construction and operation. | 1 | New Investment |  | 12-2029 | 2029 | 1 | Cronos Energy Ltd |  | 1 | 1 | Kemsley, Kent | Kemsley, Kent | OffshoreDCTransmissionCable | DC | 1400 | 525 | 230 | New | 1049 | 1706 | Cronos Energy Ltd | Converter Stations & Subsea Cabling | 1.4 GW HVDC electricity interconnector between UK and Belgium Voltage Source Converter (VSC)/Bipolar Grid connection point (substations name): Kemsley (UK) and in Belgium the exact substation location will be determined by the main grid study to be completed by Elia. Total cable length (substation to substation) 202km. Two cables (XLPE) laid in a single trench Nominal voltage: ±525 kV Thermal limit (Imax): 1330 A Mvar capability range at terminals: 460 MVAr Bus-bar to bus-bar losses profile over MW range: 2.3% (33 MW) full load; 0% (0 MW) at zero load. The annual Availability is 98.1% availability, with 1.8% planned outages, and 0.1% forced outages. The maximum single failure according to the design is 1.4GW. The project will enable the reduction of CO2 emissions by substituting electricity from fossil fuels by generation from RES and nuclear power. There are no material anticipated environmental impacts during construction and operation. | 1 | New Investment |  | 12-2031 | 2031 | 1 | Cronos Energy Ltd | 1.20 | 1 | 1 | Kemsley, Kent | Most appropriate connection site under study | OffshoreDCTransmissionCable | DC | 1400 | 525 | 202 | New | 1049 | 1706 | Cronos Energy Ltd | Converter Stations & Subsea Cabling | 1.4 GW HVDC electricity interconnector between UK and Belgium Voltage Source Converter (VSC)/Bipolar Grid connection point (substations name): Kemsley (UK) and in Belgium the exact substation location will be determined by the main grid study to be completed by Elia. Total cable length (substation to substation) 202km. Two cables (XLPE) laid in a single trench Nominal voltage: ±525 kV Thermal limit (Imax): 1330 A Mvar capability range at terminals: 460 MVAr Bus-bar to bus-bar losses profile over MW range: 2.3% (33 MW) full load; 0% (0 MW) at zero load. The annual Availability is 98.1% availability, with 1.8% planned outages, and 0.1% forced outages. The maximum single failure according to the design is 1.4GW. The project will enable the reduction of CO2 emissions by substituting electricity from fossil fuels by generation from RES and nuclear power. There are no material anticipated environmental impacts during construction and operation. | 1 |  | 12-2032 | 2032 | 1 | Cronos Energy Ltd | 1 | XX | XX | New | 2025 | 2032 | 7 | 12 | BEL;GBR | Kemsley Kent | Most Appropriate Connection Site Under Study | 51.3617 | 0.73496
411 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1707 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1050 | 1707 | Tarchon Energy Ltd | Converter stations and Subsea Cabling | 1.4 GW HVDC electricity interconnector between UK and Germany Voltage Source Converter (VSC)/Bipolar Grid connection point (substations name): Corringham (UK) and near Emden (Germany), exact substation location subject to grid study in Germany. Total cable length (substation to substation) 610km (35km in UK and 25km in Germany) Two cables (XLPE) laid in a single trench Nominal voltage: ±525 kV Thermal limit (Imax): 1330 A Mvar capability range at terminals: 460 MVAr Bus-bar to bus-bar losses profile over MW range: 2.3% (33 MW) full load; 0% (0 MW) at zero load. The annual Availability is 98.1% availability, with 1.8% planned outages, and 0.1% forced outages. The maximum single failure according to the design is 1.4GW. The project will enable the reduction of CO2 emissions by substituting electricity from fossil fuels by generation from RES and nuclear power. There are no material anticipated environmental impacts during construction and operation | 1 | New Investment |  | 2028 | 2028 | 1 | Tarchon Energy Ltd |  | 1 | 1 | corrignham | emden | OffshoreDCTransmissionCable | DC | 610 | New | 1050 | 1707 | Tarchon Energy Ltd | Converter stations and Subsea Cabling | 1.4 GW HVDC electricity interconnector between UK and Germany Voltage Source Converter (VSC)/Bipolar Grid connection point (substations name): Corringham (UK) and near Emden (Germany), exact substation location subject to grid study in Germany. Total cable length (substation to substation) 610km (35km in UK and 25km in Germany) Two cables (XLPE) laid in a single trench Nominal voltage: ±525 kV Thermal limit (Imax): 1330 A Mvar capability range at terminals: 460 MVAr Bus-bar to bus-bar losses profile over MW range: 2.3% (33 MW) full load; 0% (0 MW) at zero load. The annual Availability is 98.1% availability, with 1.8% planned outages, and 0.1% forced outages. The maximum single failure according to the design is 1.4GW. The project will enable the reduction of CO2 emissions by substituting electricity from fossil fuels by generation from RES and nuclear power. There are no material anticipated environmental impacts during construction and operation | 1 | New Investment |  | 12-2030 | 2030 | 1 | Tarchon Energy Ltd |  | 1 | 1 | Corringham, Essex | East Anglia, connection node 400kV Substation | OffshoreDCTransmissionCable | DC | 1400 | 525 | 610 | New | 1050 | 1707 | Tarchon Energy Ltd | Converter stations and Subsea Cabling | 1.4 GW HVDC electricity interconnector between UK and Germany Voltage Source Converter (VSC)/Bipolar Grid connection point (substations name): East Anglia Connection Node (UK) and Niederlangen (Germany), exact substation location subject to grid study in Germany. Total cable length (substation to substation) 610km. Two cables (XLPE) laid in a single trench Nominal voltage: ±525 kV Thermal limit (Imax): 1330 A Mvar capability range at terminals: 460 MVAr Bus-bar to bus-bar losses profile over MW range: 2.3% (33 MW) full load; 0% (0 MW) at zero load. The annual Availability is 98.1% availability, with 1.8% planned outages, and 0.1% forced outages. The maximum single failure according to the design is 1.4GW. The project will enable the reduction of CO2 emissions by substituting electricity from fossil fuels by generation from RES and nuclear power. There are no material anticipated environmental impacts during construction and operation | 1 | New Investment |  | 10-2030 | 2030 | 1 | Tarchon Energy Ltd | 1.21 | 1 | 1 | East Anglia, connection node 400kV Substation | Niederlangen, Germany | OffshoreDCTransmissionCable | DC | 1400 | 525 | 610 | New | 1050 | 1707 | Tarchon Energy Ltd | Converter stations and Subsea Cabling | 1.4 GW HVDC electricity interconnector between UK and Germany Voltage Source Converter (VSC)/Bipolar Grid connection point (substations name): East Anglia Connection Node (UK) and Niederlangen (Germany), exact substation location subject to grid study in Germany. Total cable length (substation to substation) 650km. Two cables (XLPE) laid in a single trench Nominal voltage: ±525 kV Thermal limit (Imax): 1330 A Mvar capability range at terminals: 460 MVAr Bus-bar to bus-bar losses profile over MW range: 2.3% (33 MW) full load; 0% (0 MW) at zero load. The annual Availability is 98.1% availability, with 1.7% planned outages, and 0.2% forced outages. The project will enable the reduction of CO2 emissions by substituting electricity from fossil fuels by generation from RES and nuclear power. There are no material anticipated environmental impacts during construction and operation. | 1 |  | 10-2030 | 2030 | 1 | Tarchon Energy Ltd | 1 | XX | XX | New | 2028 | 2030 | 2 | 10 | DEU;GBR | East Anglia Connection Node | Niederlangen Germany |  |  | 52.857 | 7.282
412 | 2020 | 2022 | [2020, 2022] | 1708 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1051 | 1708 | Aminth Energy Ltd | Converter stations and Subsea cables | 1.4 GW HVDC electricity interconnector between UK and Germany Voltage Source Converter (VSC)/Bipolar Grid connection point (substations name): Norwich Main (UK) and near Revsing (Denmark), exact substation location subject to grid study in Denmark. Total cable length (substation to substation) 610km (35km in UK and 25km in Germany) Two cables (XLPE) laid in a single trench Nominal voltage: ±525 kV Thermal limit (Imax): 1330 A Mvar capability range at terminals: 460 MVAr Bus-bar to bus-bar losses profile over MW range: 2.3% (33 MW) full load; 0% (0 MW) at zero load. The annual Availability is 98.1% availability, with 1.8% planned outages, and 0.1% forced outages. The maximum single failure according to the design is 1.4GW. The project will enable the reduction of CO2 emissions by substituting electricity from fossil fuels by generation from RES and nuclear power. There are no material anticipated environmental impacts during construction and operation. | 1 | New Investment |  | 2028 | 2028 | 1 | Aminth Energy Ltd |  | 1 | 1 | Norwich Main | Revsing | OffshoreDCTransmissionCable | DC | 640 | New | 1051 | 1708 | Aminth Energy Ltd | Converter stations and Subsea cables | 1.4 GW HVDC electricity interconnector between UK and Germany Voltage Source Converter (VSC)/Bipolar Grid connection point (substations name): Norwich Main (UK) and near Revsing (Denmark), exact substation location subject to grid study in Denmark. Total cable length (substation to substation) 610km (35km in UK and 25km in Germany) Two cables (XLPE) laid in a single trench Nominal voltage: ±525 kV Thermal limit (Imax): 1330 A Mvar capability range at terminals: 460 MVAr Bus-bar to bus-bar losses profile over MW range: 2.3% (33 MW) full load; 0% (0 MW) at zero load. The annual Availability is 98.1% availability, with 1.8% planned outages, and 0.1% forced outages. The maximum single failure according to the design is 1.4GW. The project will enable the reduction of CO2 emissions by substituting electricity from fossil fuels by generation from RES and nuclear power. There are no material anticipated environmental impacts during construction and operation. | 1 | New Investment |  | 12-2031 | 2031 | 1 | Aminth Energy Ltd |  | 1 | 1 | Norwich Main | Mablethorpe, Lincolnshire | OffshoreDCTransmissionCable | DC | 1400 | 525 | 640 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2028 | 2031 | 3 | 11 | DNK;GBR | Norwich Main | Mablethorpe Lincolnshire |  |  | 53.3408 | 0.26068
413 | 2020 | 2024 | [2020, 2022, 2024] | 1709 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1048 | 1709 | Greece - Africa Power Interconnector (GAP Interconnector) | Greece Africa Power Interconnector | 2 HVDC Subsea cables interconnecting the Northern coast of Egypt with the island of Crete at Atherinolakkos. At both connection points bipolar HVDC conversion stations will be constructed for the connection to the national HV grids. | 1 | New Investment |  | 2028 | 2028 | 1 | Kykladika Meltemia SA |  | 1 | 1 | Atherinolakkos (Crete) | Mersa Matruh | OffshoreDCTransmissionCable | DC | 450 | New | 1048 | 1709 | Greece - Africa Power Interconnector (GAP Interconnector) | Greece Africa Power Interconnector | 2 HVDC Subsea cables interconnecting the Northern coast of Egypt with the island of Crete at Atherinolakkos. At both connection points bipolar HVDC conversion stations will be constructed for the connection to the national HV grids. | 1 | Investment on time |  | 01-2028 | 2028 | 1 | Greece Africa Power Interconnector SMSA (Member of Eunice Energy Group) |  | 1 | 1 | Atherinolakkos (Crete) | Mersa Matruh | OffshoreDCTransmissionCable | DC | 2000 | 500 | 450 | New | 1048 | 1709 | Greece - Africa Power Interconnector (GAP Interconnector) | Greece Africa Power Interconnector | 2 HVDC Subsea cables interconnecting the Northern coast of Egypt with the island of Crete at Atherinolakkos. At both connection points bipolar HVDC conversion stations will be constructed. | 1 | Rescheduled |  | 08-2030 | 2030 | 1 | Greece Africa Power Interconnector SMSA (Member of Eunice Energy Group) |  | 1 | 1 | Atherinolakkos (Crete) | Mersa Matruh (Egypt) | OffshoreDCTransmissionCable | DC | 600 | 600 | 450 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2028 | 2030 | 2 | 10 | EGY;GRC | Atherinolakkos | Mersa Matruh | 35.0093 | 26.1287
414 | 2020 | 2024 | [2020, 2022, 2024] | 1710 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 111 | 1710 | 3rd AC Finland-Sweden north | Keminmaa-Pyhänselkä | The investment is a 400 kV overhead line in North Finland. It is part of the 3rd AC cross border project between Finland and Sweden and will enable its full capacity to be utilized. The project will also allow integration of new RES generation at Bothnian bay. | 3 | Investment on time |  | 2024 | 2024 | 1 | FINGRID Svenska Kraftnät |  | 0 | 1 | Keminmaa | Pyhänselkä | ACTransmissionLine | AC | 156 | New | 111 | 1710 | Aurora line (3rd AC Finland-Sweden north) | Viitajärvi-Pyhänselkä | The investment is a 400 kV overhead line in North Finland. It is part of the 3rd AC cross border project between Finland and Sweden and will enable its full capacity to be utilized. The project will also allow integration of new RES generation at Bothnian bay. | 3 | Investment on time |  | 12-2024 | 2024 | 1 | Fingrid, Svenska Kraftnät | 4.10.1 and 4.10.2 | 0 | 1 | Viitajärvi | Pyhänselkä | ACTransmissionLine | AC | 0 | 400 | 153 | New | 111 | 1710 | Aurora line (3rd AC Finland-Sweden north) | Viitajärvi-Pyhänselkä | The investment is a 400 kV overhead line in North Finland. It is part of the 3rd AC cross border project between Finland and Sweden and will enable its full capacity to be utilized. The project will also allow integration of new RES generation at Bothnian bay. | 3 | Investment on time |  | 12-2024 | 2024 | 1 | Fingrid, Svenska Kraftnät | 3.4.1 and 3.4.2 | 0 | 1 | Viitajärvi | Pyhänselkä | ACTransmissionLine | AC | 0 | 400 | 153 | New | [5 empty] | 5 | Commissioned |  |  | 0 | [5 empty] | 2024 | 2024 | 0 | 4 | FIN;SWE | Viitajärvi | Pyhänselkä | 61.2068 | 25.0316
415 | 2020 | 2020 | [2020] | 1711 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 200 | 1711 | CZ Northwest-South corridor | R Kocin | Upgrade and extension of the existing 400/110 kV substation, increasing nominal capacity of transformers from 2x250 MVA to 2x350 MVA | 4 | Investment on time |  | 2023 | 2023 | 1 | CEPS | 3.11.1, 3.11.2, 3.11.4 | 0 | 0 | Kocin (CZ) |  | OnshoreSubstation | AC | 0 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 3 | CZE | Kocin |  | 49.9304 | 13.4761
416 | 2020 | 2020 | [2020] | 1712 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 200 | 1712 | CZ Northwest-South corridor | R Vitkov | A construction of a new 400/110 kV substation GIS technology equipped with two transformers with nominal capacity of 2x350 MVA | 4 | Ahead of time |  | 2021 | 2021 | 1 | CEPS | 3.11.1, 3.11.2, 3.11.4 | 0 | 0 | Vitkov (CZ) |  | OnshoreSubstation | AC | 0 | MostlyNew | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2021 | 0 | 1 | CZE | Vitkov |  | 49.7758 | 17.7518
417 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1713 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1052 | 1713 | Lienz (AT) - Obersielach (AT) | Lienz (AT) - Obersielach (AT) | upgrade from 220 kV to 380 kV | 2 | Rescheduled | Tests and gaining of experience for novel technical solution in progress. | 2030 | 2030 | 1 | Austrian Power Grid |  | 1 | 0 | Lienz (AT) | Obersielach (AT) | ACTransmissionLine | AC | 170 | New | 1052 | 1713 | Lienz (AT) - Obersielach (AT) | Lienz (AT) - Obersielach (AT) | upgrade from 220 kV to 380 kV | 2 | Rescheduled | Revision of the grid expansion concept. Cascade effects due to project delays in projects ranked ahead. | 06-2032 | 2032 | 1 | Austrian Power Grid | 3.28 | 1 | 0 | Lienz (AT) | Obersielach (AT) | ACTransmissionLine | AC | 0 | 380 | 170 | MostlyUpgrade | 1052 | 1713 | Lienz (AT) - Malta (AT) - Obersielach (AT) | Lienz (AT) - Malta (AT) - Obersielach (AT) | 380 kV New | 2 | Rescheduled | Revision of the grid expansion concept. Cascade effects due to project delays in projects ranked ahead. | 06-2033 | 2033 | 1 | Austrian Power Grid | 3.28 | 1 | 0 | Lienz (AT) | Obersielach (AT) | ACTransmissionLine | AC | 0 | 380 | 202 | New | 1052 | 1713 | Lienz (AT) - Malta (AT) - Obersielach (AT) | Lienz (AT) - Malta (AT) - Obersielach (AT) | 380 kV New | 2 |  | 12-2034 | 2034 | 1 | Austrian Power Grid | 0 | XX | XX | New | 2030 | 2034 | 4 | 14 | AUT | Lienz | Obersielach | 46.8299 | 12.7681 | 46.6631 | 14.684
418 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1715 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1054 | 1715 | Westtirol (AT) - Zell/Ziller (AT) | Westtirol (AT) - Zell/Ziller (AT) | Upgrade of the existing 220kV-line Westtirol - Zell-Ziller and erection of an additional 220/380kV-Transformer. Line length 105km. | 2 | Rescheduled | Tests and gaining of experience for novel technical solution in progress. | 2027 | 2027 | 1 | Austrian Power Grid | 3.1.4 | 1 | 0 | Westtirol (AT) | Zell-Ziller (AT) | ACTransmissionLine | AC | 105 | MostlyUpgrade | 1054 | 1715 | Westtirol (AT) - Zell/Ziller (AT) | Westtirol (AT) - Zell/Ziller (AT) | Upgrade of the existing 220kV-line Westtirol - Zell-Ziller and erection of an additional 220/380kV-Transformer. Line length 105km. | 2 | Rescheduled | Revision of the expansion concept. Cascade effects due to project delays in projects ranked ahead. | 12-2029 | 2029 | 1 | Austrian Power Grid | 3.1.4 | 1 | 0 | Westtirol (AT) | Zell-Ziller (AT) | ACTransmissionLine | AC | 0 | 220 | 105 | MostlyUpgrade | 1054 | 1715 | 220-kV Westtirol (AT) - Zell/Ziller (AT) | 220-kV Westtirol (AT) - Zell/Ziller (AT) | Upgrade of the existing 220kV-line Westtirol - Zell-Ziller and erection of an additional 220/380kV-Transformer. Line length 104km. | 2 | Rescheduled | Revision of the expansion concept. Cascade effects due to project delays in projects ranked ahead. | 12-2030 | 2030 | 1 | Austrian Power Grid | 2.1.3 | 1 | 0 | Westtirol (AT) | Zell-Ziller (AT) | ACTransmissionLine | AC | 0 | 220 | 104 | MostlyUpgrade | 1054 | 1715 | 220-kV Westtirol (AT) - Zell/Ziller (AT) | 220-kV Westtirol (AT) - Zell/Ziller (AT) | Upgrade of the existing 220kV-line Westtirol - Zell-Ziller and erection of an additional 220/380kV-Transformer. Line length 104km. | 2 |  | 12-2032 | 2032 | 1 | Austrian Power Grid | 0 | XX | XX | Mostly upgrade | 2027 | 2032 | 5 | 12 | AUT | Westtirol | Zell-Ziller | 47.2439 | 10.8743 | 47.2336 | 11.882
419 | 2020 | 2024 | [2020, 2022, 2024] | 1716 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1055 | 1716 | Interconnection of Crete to the Mainland System of Greece | Interconnection between Crete and Peloponnese (Phase I) | New 150 kV AC double circuit submarine and underground cables between Crete and Peloponnese | 4 | New Investment |  | 2020 | 2020 | 1 | Admie |  | 0 | 0 | Chania I | Molai (through Sklavouna Terminal) | ACTransmissionLine | AC | 179 | New | 1055 | 1716 | Interconnection of Crete to the Mainland System of Greece | Interconnection between Crete and Peloponnese (Phase I) | New 150 kV AC double circuit submarine and underground cables between Crete and Peloponnese | 5 | Rescheduled |  | 05-2021 | 2021 | 1 | Admie |  | 0 | 0 | Chania I | Molai (through Sklavouna Terminal) | ACTransmissionLine | AC | 0 | 150 | 179 | New | 1055 | 1716 | Interconnection of Crete to the Mainland System of Greece | Interconnection between Crete and Peloponnese (Phase I) | New 150 kV AC double circuit submarine and underground cables between Crete and Peloponnese | 5 | Commissioned |  | 05-2021 | 2021 | 1 | Admie |  | 0 | 0 | Chania I | Molai (through Sklavouna Terminal) | ACTransmissionLine | AC | 0 | 150 | 179 | New | [9 empty] | 0 | [5 empty] | 2020 | 2021 | 1 | 1 | GRC | Chania I | Molai | 35.5121 | 24.0192 | 36.8042 | 22.8518
420 | 2020 | 2024 | [2020, 2022, 2024] | 1717 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1055 | 1717 | Interconnection of Crete to the Mainland System of Greece | Interconnection between Crete and Attica (Phase II) | New symmetric bipolar submarine HVDC-VSC link between Crete and Attica | 3 | New Investment |  | 2022 | 2022 | 1 | Admie |  | 1 | 0 | Damasta | Koumoundouros | DCTransmissionLine | DC | 373 | New | 1055 | 1717 | Interconnection of Crete to the Mainland System of Greece | Interconnection between Crete and Attica (Phase II) | New symmetric bipolar submarine HVDC-VSC link between Crete and Attica | 4 | Rescheduled |  | 06-2024 | 2024 | 1 | Admie |  | 1 | 0 | Damasta | Koumoundouros | DCTransmissionLine | DC | 1000 | 500 | 373 | New | 1055 | 1717 | Interconnection of Crete to the Mainland System of Greece | Interconnection between Crete and Attica (Phase II) | New symmetric bipolar submarine HVDC-VSC link between Crete and Attica | 4 | Investment on time |  | 09-2024 | 2024 | 1 | Admie |  | 1 | 0 | Damasta | Koumoundouros | DCTransmissionLine | DC | 1000 | 500 | 373 | New | [5 empty] | 5 | Commissioned |  |  | 0 | [5 empty] | 2022 | 2024 | 2 | 4 | GRC | Damasta | Koumoundouros | 35.3537 | 24.923 | 36.9376 | 22.1982
421 | 2020 | 2020 | [2020] | 1718 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1056 | 1718 | Croatian south connection | SS 400 kV ZONE 5 | New 400 kV substation interpolated in existing 400 kV line Konjsko - Mostar | 1 | New Investment |  | 2035 | 2035 | 1 | HOPS |  | 1 | 0 |  |  | OnshoreSubstation | AC | 0 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 15 | HRV
422 | 2020 | 2020 | [2020] | 1719 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1056 | 1719 | Croatian south connection | SS 400/220 kV ZONE 6 | New 400 kV substation for connetion of new generation and increase of security of supply in the southern area near city of Ploce | 1 | New Investment |  | 2035 | 2035 | 1 | HOPS |  | 0 | 0 |  |  | OnshoreSubstation | AC | 0 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 15 | HRV
423 | 2020 | 2020 | [2020] | 1721 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 265 | 1721 | Tessin | Magadino | Connection of the Avegno - Gorduno line to the Magadino substation and new 380/220 kV transformer in Magadino | 2 | Delayed | reschedule | 2035 | 2035 | 1 | SWISSGRID |  | 0 | 0 | Magadino | Magadino | ACTransmissionLine | AC | 0 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 15 | CHE | Magadino | Magadino | 46.1474 | 8.8559 | 46.1474 | 8.8559
424 | 2020 | 2020 | [2020] | 1722 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1057 | 1722 | HVDC CentraLink | HVDC Line C3 | New HVDC line to integrate the additional wind power capacity in the northern Germany in order to supply it to the load centers and storage units in the southern parts of the country. | 1 | New Investment |  | 2035 | 2035 | 1 | TRANSNET-BW |  | 1 | 0 | Schleswig Holstein area | Baden-Württemberg area | DCTransmissionLine | DC | 700 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 15 | DEU | Schleswig Holstein Area | Baden-Württemberg Area
425 | 2020 | 2020 | [2020] | 1723 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1056 | 1723 | Croatian south connection | OHL 2x400 kV ZONE 5 - ZONE 6 | Double 400 kV line connecting SS ZONE 5 and ZONE 6 | 1 | New Investment |  | 2035 | 2035 | 1 | HOPS |  | 0 | 0 | ZONE 5 | ZONE 6 | ACTransmissionLine | AC | 90 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 15 | HRV | Zone | Zone
426 | 2020 | 2020 | [2020] | 1724 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1056 | 1724 | Croatian south connection | OHL 2x220 kV ZONE 6 – Plat | Double 220 kV line connecting SS ZONE 6 and SS Plat | 1 | New Investment |  | 2035 | 2035 | 1 | HOPS |  | 0 | 0 | ZONE 6 | Plat | ACTransmissionLine | AC | 105 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 15 | HRV | Zone | Plat |  |  | 42.61 | 18.2266
427 | 2020 | 2020 | [2020] | 1725 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1056 | 1725 | Croatian south connection | SS 220/110 kV Plat | Construction of two addiotional OHL bays for connection of OHL 220 kV ZONE 6 - Plat | 1 | New Investment |  | 2035 | 2035 | 1 | HOPS |  | 0 | 0 | ZONE 6 | Plat | OnshoreSubstation | AC | 0 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 15 | HRV | Zone | Plat |  |  | 42.61 | 18.2266
428 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1726 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1058 | 1726 | HVDC Interconnector DE-CH | HVDC Line DE-CH | The concept of extending German HVDC-Lines towards Switzerland and Italy offers a further potential to realize a new N-S HVDC corridor. Large developments of variable wind and photovoltaic power, coal and nuclear phaseout, mainly gas-based thermal generation, and the pump storage potentials in the Alps are the main drivers of power system evolution that will challenge the future transmission system in central southern Europe. | 1 | New Investment |  | 2040 | 2040 | 1 | SWISSGRID TRANSNET-BW |  | 1 | 1 | Wendlingen (DE) | Mettlen (CH) | DCTransmissionLine | DC | 0 | New | 1058 | 1726 | HVDC Interconnector DE-CH | HVDC Line DE-CH | The concept of extending German HVDC-Lines towards Switzerland and Italy offers a further potential to realize a new North-South HVDC corridor. Large developments of variable wind and photovoltaic power, coal and nuclear phaseout, mainly gas-based thermal generation, and the pump storage po-tentials in the Alps are the main drivers of power system evolution that will challenge the future trans-mission system in central southern Europe. | 1 | Rescheduled |  | 12-2037 | 2037 | 1 | Swissgrid, TransnetBW |  | 1 | 1 | Oberjettingen (DE) | Mettlen (CH) | DCTransmissionLine | DC | 1000 | 400 | 250 | New | 1058 | 1726 | HVDC Interconnector DE-CH | HVDC Line DE-CH | The concept of extending German HVDC-Lines towards Switzerland and Italy offers a further potential to realize a new North-South HVDC corridor. Large developments of variable wind and photovoltaic power, coal and nuclear phaseout, mainly gas-based thermal generation, and the pump storage potentials in the Alps are the main drivers of power system evolution that will challenge the future transmission system in central southern Europe. | 1 | Investment on time |  | 12-2037 | 2037 | 1 | Swissgrid, TransnetBW |  | 1 | 1 | Oberjettingen (DE) | Mettlen (CH) | DCTransmissionLine | DC | 1000 | 525 | 214 | New | 1058 | 1726 | HVDC Interconnector DE-CH | HVDC Line DE-CH | The concept of extending German HVDC-Lines towards Switzerland and Italy offers a further potential to realize a new North-South HVDC corridor. Large developments of variable wind and photovoltaic power, coal and nuclear phaseout, mainly gas-based thermal generation, and the pump storage potentials in the Alps are the main drivers of power system evolution that will challenge the future transmission system in central southern Europe. | 1 |  | 12-2037 | 2037 | 1 | Swissgrid, TransnetBW | 1 | XX | XX | New | 2040 | 2037 | -3 | 17 | CHE;DEU | Oberjettingen | Mettlen | 48.576 | 8.7743 | 47.5311 | 9.1236
429 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1727 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1059 | 1727 | Southern Italy | Montecorvino-Avellino and Nord-Ben. in Campania | New 400 kV between Montecorvino-Avellino and Nord-Ben. in Campania | 3 | New Investment |  | 2030 | 2030 | 1 | TERNA |  | 1 | 0 | Montecorvino (IT) | Benevento (IT) | ACTransmissionLine | AC | 0 | New | 1059 | 1727 | Southern Italy | Montecorvino-Avellino and Nord-Ben. in Campania | New 400 kV between Montecorvino-Avellino and Nord-Ben. in Campania | 3 | New Investment |  | 12-2028 | 2028 | 1 | Terna |  | 1 | 0 | Montecorvino (IT) | Benevento (IT) | ACTransmissionLine | AC | 0 | 400 | 0 | New | 1059 | 1727 | Southern Italy | Montecorvino-Avellino and Nord-Ben. in Campania | New 400 kV between Montecorvino-Avellino and Nord-Ben. in Campania | 3 | New Investment |  | 12-2029 | 2029 | 1 | Terna |  | 1 | 0 | Montecorvino (IT) | Benevento (IT) | ACTransmissionLine | AC | 0 | 400 | 0 | New | 1059 | 1727 | Southern Italy | Montecorvino-Avellino and Nord-Ben. in Campania | New 400 kV between Montecorvino-Avellino and Nord-Ben. in Campania |  |  | 12-2032 | 2032 | 1 | Terna | 0 | XX | XX | New | 2030 | 2032 | 2 | 12 | ITA | Montecorvino | Benevento | 41.5172 | 15.15 | 41.2476 | 14.7057
430 | 2020 | 2020 | [2020] | 1729 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1061 | 1729 | Reactive compensation for project 197 | Reactive compensation | Reactive compensation in substations to increase the transfer capacity from North to South Finland: installation of STATCOM(s), SVC(s) and/or shunt compensation. | 1 |  |  | 2022 | 2022 | 1 | FINGRID |  | 1 | 0 | North Finland | South Finland | ReactiveCompensationDevice | AC | 0 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2022 | 0 | 2 | FIN | North Finland | South Finland
431 | 2020 | 2020 | [2020] | 1730 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1062 | 1730 | Reactive compensation for project 1046 | Reactive compensation | Reactive compensation measures in substations to increase the transfer capacity from North to South Finland: installation of STATCOM(s), SVC(s) and/or shunt compensation. | 1 |  |  | 2029 | 2029 | 1 | FINGRID |  | 1 | 0 | North Finland | South Finland | ReactiveCompensationDevice | AC | 0 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2029 | 2029 | 0 | 9 | FIN | North Finland | South Finland
432 | 2020 | 2020 | [2020] | 1731 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1063 | 1731 | ZuidWest380 West | ZuidWest380 West | New 380 kV substation Rilland; New 380 kV double circuit line 2645MVA between Borssele and Rilland; Upgrade of existing 380 kV line Borssele-Geertruidenberg to 1975MVA. | 4 |  |  | 2022 | 2022 | 1 | TENNET-NL |  | 1 | 0 | Borssele | Rilland | ACTransmissionLine | AC | 40 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2022 | 0 | 2 | NLD | Borssele | Rilland | 51.4255 | 3.7379 | 51.4165 | 4.1812
433 | 2020 | 2020 | [2020] | 1733 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 266 | 1733 | Swiss Ellipse I | Bickigen - Chippis | Bickigen - Chippis: Optimisation of the existing route by voltage conversion to 380 kV | 3 | Delayed | Permitting procedure | 2027 | 2027 | 1 | SWISSGRID |  | 0 | 0 | Bickigen | Chippis | ACTransmissionLine | AC | 106.6 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2027 | 2027 | 0 | 7 | CHE | Bickigen | Chippis | 47.0908 | 7.649 | 46.2805 | 7.5406
434 | 2020 | 2020 | [2020] | 1734 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 266 | 1734 | Swiss Ellipse I | Chamoson - Chippis | Chamoson - Chippis: Reinforcement by new construction of a 380 kV route New 380/220 kV transformer in Chippis | 4 | Delayed | Permitting procedure | 2022 | 2022 | 1 | SWISSGRID |  | 0 | 0 | Chamoson | Chippis | ACTransmissionLine | AC | 30 | MostlyNew | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2022 | 0 | 2 | CHE | Chamoson | Chippis | 46.2013 | 7.2233 | 46.2805 | 7.5406
435 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1736 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1066 | 1736 | Bulgaria - Turkey | 400kV OHL, Maritsa East 2 (BG) – Vize Havza (TR) | New interconnection line BG-TR by a 150km single circuit 400kV OHL. | 1 | New Investment |  | 2036 | 2036 | 1 | ESO |  | 1 | 1 | Maritsa East 2 (BG) | Vize Havza (TR) | ACTransmissionLine | AC | 150 | New | 1066 | 1736 | Bulgaria - Turkey | 400kV OHL, Maritsa East 2 (BG) – Vize Havza (TR) | New interconnection line BG-TR by a 150km single circuit 400kV OHL. | 1 | New Investment |  | 07-2036 | 2036 | 1 | ESO |  | 1 | 1 | Maritsa East 2 (BG) | Vize Havza (TR) | ACTransmissionLine | AC | 0 | 400 | 150 | New | 1066 | 1736 | Bulgaria - Turkey | 400kV OHL, Maritsa East 2 (BG) – Vize Havza (TR) | New interconnection line BG-TR by a 150km single circuit 400kV OHL. | 1 | New Investment |  | 11-2035 | 2035 | 1 | ESO |  | 1 | 1 | Maritsa East 2 (BG) | Vize Havza (TR) | ACTransmissionLine | AC | 0 | 400 | 150 | New | 1066 | 1736 | Bulgaria - Turkey | 400kV OHL, Maritsa East 2 (BG) – Vize Havza (TR) | New interconnection line BG-TR by a 150km single circuit 400kV OHL. | 1 |  | 11-2035 | 2035 | 1 | ESO | 1 | XX | XX | New | 2036 | 2035 | -1 | 15 | BGR;TUR | Maritsa East | Vize Havza | 42.1826 | 24.3565 | 41.5165 | 27.7593
436 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1738 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1067 | 1738 | New AC 400 kV interconnection line Greece - Turkey | New AC 400 kV interconnection line Greece - Turkey | New AC 400 kV Overhead line Greece - Turkey | 1 | New Investment |  | 2036 | 2036 | 1 | Admie |  | 1 | 1 | Nea Santa (GR) | Babaeski (TR) | ACTransmissionLine | AC | 130 | New | 1067 | 1738 | New AC 400 kV interconnection line Greece - Turkey | New AC 400 kV interconnection line Greece - Turkey | New AC 400 kV Overhead line Greece - Turkey | 1 | Investment on time |  | 06-2035 | 2035 | 1 | Admie |  | 1 | 1 | Nea Santa (GR) | Babaeski (TR) | ACTransmissionLine | AC | 0 | 400 | 130 | New | 1067 | 1738 | New AC 400 kV interconnection line Greece - Turkey | New AC 400 kV interconnection line Greece - Turkey | New AC 400 kV Overhead line Greece - Turkey | 2 | Ahead of time |  | 06-2031 | 2031 | 1 | Admie |  | 1 | 1 | Nea Santa (GR) | Babaeski (TR) | ACTransmissionLine | AC | 0 | 400 | 130 | New | 1067 | 1738 | New AC 400 kV interconnection line Greece - Turkey | New AC 400 kV interconnection line Greece - Turkey | New AC 400 kV Overhead line Greece - Turkey | 2 |  | 06-2031 | 2031 | 1 | Admie | 1 | XX | XX | New | 2036 | 2031 | -5 | 11 | GRC;TUR | Nea Santa | Babaeski | 40.8423 | 22.9204 | 41.4303 | 27.0918
437 | 2020 | 2024 | [2020, 2022, 2024] | 1740 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1068 | 1740 | LaSGo Link | LaSGo Link - Gotland to Latvia | New monopolar HVDC VSC monopole sub-sea cable running from a new substation in Gotland (TBC) to Grobina in Latvia (or Ventspils or a possible a new substation inbetween Grobina and Ventspils) (TBC). This investment consists of two VSC HVDC converter stations connected via two 320kV HVDC XLPE cables. | 1 | New Investment |  | 2036 | 2036 | 1 | Transmission Investment |  | 1 | 1 | New substation on Gotland (TBC) | Grobina (TBC) | OffshoreDCTransmissionCable | DC | 195 | New | 1068 | 1740 | LaSGo Link | LaSGo Link - Gotland to Latvia | New monopolar HVDC VSC monopole sub-sea cable running from a new substation in Gotland (TBC) to Grobina in Latvia (or Ventspils or a possible a new substation inbetween Grobina and Ventspils) (TBC). This investment consists of two VSC HVDC converter stations connected via two 320kV HVDC XLPE cables. | 1 | New Investment |  | 06-2031 | 2031 | 1 | Transmission Investment | 4.11 | 1 | 1 | New substation on Gotland (TBC) | Grobina (TBC) | OffshoreDCTransmissionCable | DC | 500 | 320 | 195 | New | 1068 | 1740 | LaSGo Link | LaSGo Link - Gotland to Latvia | New monopolar HVDC VSC monopole sub-sea cable running from a new substation in Gotland (TBC) to Grobina in Latvia (or Ventspils or a possible a new substation inbetween Grobina and Ventspils) (TBC). This investment consists of two VSC HVDC converter stations connected via two 320kV HVDC XLPE cables. | 1 | New Investment |  | 07-2037 | 2037 | 1 | Transmission Investment | 4.11 | 1 | 1 | New substation on Gotland (TBC) | Grobina (TBC) | OffshoreDCTransmissionCable | DC | 500 | 320 | 195 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2036 | 2037 | 1 | 17 | LVA;SWE | New On Gotland | Grobina
438 | 2020 | 2024 | [2020, 2022, 2024] | 1741 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1068 | 1741 | LaSGo Link | LaSGo Link - Sweden to Gotland | New monopolar HVDC VSC monopole sub-sea cable running from the vicinity of Oskarshamn in mainland Sweden (TBC) to a new substation in Gotland (TBC). This investment consists of one HVDC VSC converter station connected via two 320kV HVDC XLPE cables to a Converter Station being built as part of the LaSGo Link Gotland to Latvia investment. | 1 | New Investment |  | 2036 | 2036 | 1 | Transmission Investment |  | 0 | 1 | Oskarshamn (TBC) | New substation on Gotland (TBC) | OffshoreDCTransmissionCable | DC | 125 | New | 1068 | 1741 | LaSGo Link | LaSGo Link - Sweden to Gotland | New monopolar HVDC VSC monopole sub-sea cable running from the vicinity of Oskarshamn in mainland Sweden (TBC) to a new substation in Gotland (TBC). This investment consists of one HVDC VSC converter station connected via two 320kV HVDC XLPE cables to a Converter Station being built as part of the LaSGo Link Gotland to Latvia investment. | 1 | New Investment |  | 06-2031 | 2031 | 1 | Transmission Investment | 4.11 | 0 | 1 | Oskarshamn (TBC) | New substation on Gotland (TBC) | OffshoreDCTransmissionCable | DC | 700 | 320 | 125 | New | 1068 | 1741 | LaSGo Link | LaSGo Link - Sweden to Gotland | New monopolar HVDC VSC monopole sub-sea cable running from the vicinity of Oskarshamn in mainland Sweden (TBC) to a new substation in Gotland (TBC). This investment consists of one HVDC VSC converter station connected via two 320kV HVDC XLPE cables to a Converter Station being built as part of the LaSGo Link Gotland to Latvia investment. | 1 | New Investment |  | 07-2037 | 2037 | 1 | Transmission Investment | 4.11 | 0 | 1 | Oskarshamn (TBC) | New substation on Gotland (TBC) | OffshoreDCTransmissionCable | DC | 700 | 320 | 125 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2036 | 2037 | 1 | 17 | LVA;SWE | Oskarshamn | New On Gotland | 57.2633 | 16.4443
439 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1742 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1074 | 1742 | Pannonian Corridor | 400 kV OHL SS Subotica 3 – SS Sándorfalva | New 400 kV interconnection OHL between SS Subotica (RS) and SS Sándorfalva (HU). This is the main investment of the project and a part of the new North-South corridor for energy transmission. | 1 | New Investment | No delay on this investment yet. | 2036 | 2036 | 1 | EMS |  | 1 | 1 | SS Subotica 3 | SS Sándorfalva | ACTransmissionLine | AC | 50.6 | New | 1074 | 1742 | Pannonian Corridor | 400 kV OHL SS Subotica 3 – SS Sándorfalva | New 400 kV interconnection OHL between SS Subotica (RS) and SS Sándorfalva (HU). This is the main investment of the project and a part of the new North-South corridor for energy transmission. | 1 | Ahead of time | No delay on this investment yet. | 09-2033 | 2033 | 1 | EMS, MAVIR |  | 1 | 1 | SS Subotica 3 | SS Sándorfalva | ACTransmissionLine | AC | 0 | 400 | 50.6 | New | 1074 | 1742 | Pannonian Corridor | 400 kV OHL SS Subotica 3 – SS Sándorfalva | New 400 kV interconnection OHL between SS Subotica (RS) and SS Sándorfalva (HU). This is the main investment of the project and a part of the new North-South corridor for energy transmission. | 2 | Ahead of time | No delay on this investment yet. | 09-2028 | 2028 | 1 | EMS, MAVIR | 2.12 | 1 | 1 | SS Subotica 3 | SS Sándorfalva | ACTransmissionLine | AC | 0 | 400 | 50.6 | New | 1074 | 1742 | Pannonian Corridor | 400 kV OHL SS Subotica 3 – SS Sándorfalva | New 400 kV interconnection OHL between SS Subotica (RS) and SS Sándorfalva (HU). This is the main investment of the project and a part of the new North-South corridor for energy transmission. |  |  | 09-2028 | 2028 | 1 | EMS, MAVIR | 1 | XX | XX | New | 2036 | 2028 | -8 | 8 | HUN;SRB | Subotica | Sándorfalva | 46.1019 | 19.6685 | 46.3657 | 20.1042
440 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1743 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1074 | 1743 | Pannonian Corridor | 400 kV OHL SS Sombor 3 – SS Srbobran | New 400 kV OHL from existing substation Sombor 3 to existing substation Srbobran (both in Serbia). | 1 | New Investment | No delay on this investment yet. | 2036 | 2036 | 1 | EMS |  | 0 | 1 | SS Sombor 3 | SS Srbobran | ACTransmissionLine | AC | 80 | New | 1074 | 1743 | Pannonian Corridor | 400 kV OHL SS Sombor 3 – SS Srbobran | New 400 kV OHL from existing substation Sombor 3 to existing substation Srbobran (both in Serbia). | 1 | Ahead of time | No delay on this investment yet. | 09-2033 | 2033 | 1 | EMS, MAVIR |  | 0 | 1 | SS Sombor 3 | SS Srbobran | ACTransmissionLine | AC | 0 | 400 | 80 | New | 1074 | 1743 | Pannonian Corridor | 400 kV OHL SS Novi Sad 3 – SS Sombor 3 | New 400 kV OHL from existing substation Novi Sad 3 to existing substation Sombor 3 (both in Serbia). | 2 | Ahead of time | No delay on this investment yet. | 09-2030 | 2030 | 1 | EMS, MAVIR | 2.12 | 0 | 1 | SS Sombor 3 | SS Novi Sad 3 | ACTransmissionLine | AC | 0 | 400 | 80 | New | 1074 | 1743 | Pannonian Corridor | 400 kV OHL SS Novi Sad 3 – SS Sombor 3 | New 400 kV OHL from existing substation Novi Sad 3 to existing substation Sombor 3 (both in Serbia). |  |  | 09-2030 | 2030 | 1 | EMS, MAVIR | 1 | XX | XX | New | 2036 | 2030 | -6 | 10 | HUN;SRB | Sombor | Novi Sad | 45.7727 | 19.1147 | 45.2522 | 19.8491
441 | 2020 | 2026 | [2020, 2022, 2024, 2026] | 1744 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1074 | 1744 | Pannonian Corridor | 400 kV OHL SS Srbobran – SS Sremska Mitrovica 2 | New 400 kV OHL from existing substation Srbobran to existing substation Sremska Mitrovica 2 (both in Serbia). | 1 | New Investment | No delay on this investment yet. | 2036 | 2036 | 1 | EMS |  | 0 | 1 | SS Srbobran | SS Sremska Mitrovica 2 | ACTransmissionLine | AC | 90 | New | 1074 | 1744 | Pannonian Corridor | 400 kV OHL SS Srbobran – SS Sremska Mitrovica 2 | New 400 kV OHL from existing substation Srbobran to existing substation Sremska Mitrovica 2 (both in Serbia). | 1 | Ahead of time | No delay on this investment yet. | 09-2033 | 2033 | 1 | EMS, MAVIR |  | 0 | 1 | SS Srbobran | SS Sremska Mitrovica 2 | ACTransmissionLine | AC | 0 | 400 | 90 | New | 1074 | 1744 | Pannonian Corridor | 2x400 kV OHL SS Belgrade 50 – SS Sremska Mitrovica 2 | New 400 kV OHL from future substation Srbobran to existing substation Sremska Mitrovica 2 (both in Serbia). | 2 | Ahead of time | No delay on this investment yet. | 09-2030 | 2030 | 1 | EMS, MAVIR | 2.12 | 0 | 1 | SS Belgrade 50 | SS Sremska Mitrovica 2 | ACTransmissionLine | AC | 0 | 400 | 60 | New | 1074 | 1744 | Pannonian Corridor | 2x400 kV OHL SS Belgrade 50 – SS Sremska Mitrovica 2 | New 2x400 kV OHL from future substation Belgrade 50 to existing substation Sremska Mitrovica 2 (both in Serbia). |  |  | 09-2030 | 2030 | 1 | EMS, MAVIR | 1 | XX | XX | New | 2036 | 2030 | -6 | 10 | HUN;SRB | Belgrade | Sremska Mitrovica | 47.6689 | 19.0757 | 44.9686 | 19.6084
442 | 2020 | 2020 | [2020] | 1745 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1081 | 1745 | LAG Interconnector (LAG) | Libya Greece | The HVDC interconnector will link Libya to Greece with XLPE or MI submarine cables, and use VSC converters. | 1 | New Investment |  | 2036 | 2036 | 1 | GreenPower 2020 |  | 1 | 1 | Tobruk | Arachtos | OffshoreDCTransmissionCable | DC | 1070 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2036 | 2036 | 0 | 16 | ALB;GRC;LBY | Tobruk | Arachtos |  |  | 39.5242 | 21.0051
443 | 2020 | 2020 | [2020] | 1746 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1077 | 1746 | Crete-North Greece-North Macedonia-Bulgaria Interconnector | Crete-Northern Greece | The project will have a DC voltage of +/-525 kV. It will transmit 2000MW through bipolar HVDC cables. Converter technology is VSC. It will connect to LEG1 converter station of Linoperamata (Crete). | 1 |  |  | 2036 | 2036 | 1 | GreenPower 2020 |  | 1 | 1 | Linoperamata | Thessaloniki | OffshoreDCTransmissionCable | DC | 600 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2036 | 2036 | 0 | 16 | BGR;GRC;MKD | Linoperamata | Thessaloniki | 35.338 | 25.0504 | 41.3792 | 23.363
444 | 2020 | 2020 | [2020] | 1747 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1077 | 1747 | Crete-North Greece-North Macedonia-Bulgaria Interconnector | Northern Greece-North Macedonia | The project will have a DC voltage of +/-525 kV. It will transmit 2000MW through bipolar HVDC cables. Converter technology is VSC. | 1 |  |  | 2036 | 2036 | 1 | GreenPower 2020 |  | 0 | 1 | Thessaloniki | Dubrovo | DCTransmissionLine | DC | 110 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2036 | 2036 | 0 | 16 | BGR;GRC;MKD | Thessaloniki | Dubrovo | 41.3792 | 23.363 | 41.4704 | 22.1461
445 | 2020 | 2020 | [2020] | 1748 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1077 | 1748 | Crete-North Greece-North Macedonia-Bulgaria Interconnector | North Macedonia-Bulgaria | The project will have a DC voltage of +/-525 kV. It will transmit 2000MW through bipolar HVDC cables. Converter technology is VSC. | 1 |  |  | 2036 | 2036 | 1 | GreenPower 2020 |  | 0 | 1 | Dubrovo | Ch. Mogila | DCTransmissionLine | DC | 170 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2036 | 2036 | 0 | 16 | BGR;GRC;MKD | Dubrovo | Ch. Mogila | 41.4704 | 22.1461 | 42.5029 | 26.5961
446 | 2020 | 2020 | [2020] | 1749 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1081 | 1749 | LAG Interconnector (LAG) | Greece Albania | The HVDC interconnector will link Greece to Albania with XLPE underground cables or OHL, and use VSC converters. | 1 | New Investment |  | 2036 | 2036 | 1 | GreenPower 2020 |  | 0 | 1 | Arachtos | Elbasan | DCTransmissionLine | DC | 180 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2036 | 2036 | 0 | 16 | ALB;GRC;LBY | Arachtos | Elbasan | 39.5242 | 21.0051 | 41.1127 | 20.0821
447 | 2020 | 2022 | [2020, 2022] | 1750 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [6 empty] | 1082 | 1750 | Sea-Socket | Sea-Socket | Floating substation platform facilitating 700-MW multiple offshore wind connections and transmitted via 220kV subsea AC cables to onshore substation(s) located along the Shannon Estuary | 1 | New Investment |  | 2035 | 2035 | 1 | Siga Hydro Limited |  | 1 | 0 | New substation connection to 400kV/220kV lines in the Shannon Estuary | Not applicable - offshore connection point at Sea-Socket Platform | OffshoreSubstation | AC | 40 | New | 1082 | 1750 | Sea-Socket | Sea-Socket | Floating substation platform facilitating 700-MW multiple offshore wind connections and transmitted via 220kV subsea AC cables to onshore substation(s) located along the Shannon Estuary | 1 | New Investment |  | 01-2035 | 2035 | 1 | Siga Hydro Limited |  | 1 | 0 | New substation connection to 400kV/220kV lines in the Shannon Estuary | Not applicable - offshore connection point at Sea-Socket Platform | OffshoreSubstation | AC | 0 | 220 | 40 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2035 | 2035 | 0 | 15 | IRL | New Connection To Lines In The Shannon Estuary | Not Applicable - Connection Point At Sea-Socket Platform
448 | 2022 | 2026 | [2022, 2024, 2026] | 1751 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1085 | 1751 | Malta-Italy Cable Link No.2 | Malta-Italy Cable link No. 2 | 200MWe HVAC 2nd electrical cable link between Malta and Sicily | 1 | New Investment |  | 12-2025 | 2025 | 1 | Interconnect Malta Ltd |  | 1 | 1 | In Malta (MT): Maghtab Terminal Station (Maghtab TS) | In Italy (IT): Ragusa Terminal Station (Ragusa TS) | OffshoreACTransmissionCable | AC | 0 | 220 | 117.5 | New | 1085 | 1751 | Malta-Italy Cable Link No.2 | Malta-Italy Cable link No. 2 | 200MWe HVAC 2nd electrical cable link between Malta and Sicily | 3 | Delayed | The permitting process is taking longer than anticipated. | 12-2026 | 2026 | 1 | Interconnect Malta Ltd |  | 1 | 1 | In Malta (MT): Maghtab Terminal Station (Maghtab TS) | In Italy (IT): Ragusa Terminal Station (Ragusa TS) | OffshoreACTransmissionCable | AC | 0 | 220 | 122 | New | 1085 | 1751 | Malta-Italy Cable Link No.2 | Malta-Italy Cable link No. 2 | 225MWe HVAC 2nd electrical cable link between Malta and Sicily | 4 |  | 12-2026 | 2026 | 1 | Interconnect Malta Ltd | 1 | XX | XX | New | 2025 | 2026 | 1 | 4 | ITA;MLT | In Malta Mt Maghtab Terminal | In Italy It Ragusa Terminal
449 | 2022 | 2026 | [2022, 2024, 2026] | 1752 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1086 | 1752 | Estonia internal grid reinforcement to increase RES connection capability (RRF project) | L356 Mustvee-Paide 330 kV OHL reconstrucion (EE) | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. To reduce the environmental impact partially the parallel 110 kV lines will be place on the common towers with 330 kV reconstructed line. The thermal transmission capacity of the line is planned 1770 MW. | 2 | New Investment |  | 12-2025 | 2025 | 1 | Elering |  | 1 | 0 | Mustvee | Paide | ACTransmissionLine | AC | 0 | 330 | 87 | MostlyUpgrade | 1086 | 1752 | Estonia internal grid reinforcement to increase RES connection capability (RRF project) | L356 Mustvee-Paide 330 kV OHL reconstrucion (EE) | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. To reduce the environmental impact partially the parallel 110 kV lines will be place on the common towers with 330 kV reconstructed line. The thermal transmission capacity of the line is planned 1770 MW. | 4 | New Investment |  | 06-2026 | 2026 | 1 | Elering |  | 1 | 0 | Mustvee | Paide | ACTransmissionLine | AC | 0 | 330 | 87 | MostlyUpgrade | 1086 | 1752 | Internal grid reinforcements in Estonia to increase RES connection capability (RRF project) | L356 Mustvee-Paide 330 kV OHL reconstrucion (EE) | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. To reduce the environmental impact partially the parallel 110 kV lines will be place on the common towers with 330 kV reconstructed line. The thermal transmission capacity of the line is planned 1770 MW. | 4 |  | 06-2026 | 2026 | 1 | Elering | 0 | XX | XX | Mostly upgrade | 2025 | 2026 | 1 | 4 | EST | Mustvee | Paide | 58.8479 | 26.9301 | 58.8869 | 25.5699
450 | 2022 | 2026 | [2022, 2024, 2026] | 1753 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1086 | 1753 | Estonia internal grid reinforcement to increase RES connection capability (RRF project) | L357 Kiisa-Paide 330 kV OHL reconstruction (EE) | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. To reduce the environmental impact partially the parallel 110 kV lines will be place on the common towers with 330 kV reconstructed line. The thermal transmission capacity of the line is planned 1770 MW. | 2 | New Investment |  | 12-2026 | 2026 | 1 | Elering |  | 0 | 0 | Kiisa | Paide | ACTransmissionLine | AC | 0 | 330 | 70 | MostlyUpgrade | 1086 | 1753 | Estonia internal grid reinforcement to increase RES connection capability (RRF project) | L357 Kiisa-Paide 330 kV OHL reconstruction (EE) | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. To reduce the environmental impact partially the parallel 110 kV lines will be place on the common towers with 330 kV reconstructed line. The thermal transmission capacity of the line is planned 1770 MW. | 4 | New Investment |  | 06-2026 | 2026 | 1 | Elering |  | 0 | 0 | Kiisa | Paide | ACTransmissionLine | AC | 0 | 330 | 70 | MostlyUpgrade | 1086 | 1753 | Internal grid reinforcements in Estonia to increase RES connection capability (RRF project) | L357 Kiisa-Paide 330 kV OHL reconstruction (EE) | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. To reduce the environmental impact partially the parallel 110 kV lines will be place on the common towers with 330 kV reconstructed line. The thermal transmission capacity of the line is planned 1770 MW. | 4 |  | 06-2026 | 2026 | 1 | Elering | 0 | XX | XX | Mostly upgrade | 2026 | 2026 | 0 | 4 | EST | Kiisa | Paide | 59.2379 | 24.6875 | 58.8869 | 25.5699
451 | 2022 | 2026 | [2022, 2024, 2026] | 1754 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1086 | 1754 | Estonia internal grid reinforcement to increase RES connection capability (RRF project) | Lihula 330 KV substation (EE) and reinforcement of internal grid in western part of Estonia | New Lihula 330 kV substation will be connected to existing Harku-Sindi 330 kV OHL in Lihula. It consists of 2 330 kV duplex bays for 330 kV lines, and 3 simplex 330 kV bays of which 2 will be used for power transformers (200 MVA each) and one for reactive power compensator (125 Mvar). The investment also includes the reinforcement of internal 110 kV grid where are the potential RES connection points. | 2 | New Investment |  | 12-2025 | 2025 | 1 | Elering |  | 0 | 0 | Lihula | Lihula | OnshoreSubstation | AC | 0 | 330 | 0 | MostlyUpgrade | 1086 | 1754 | Estonia internal grid reinforcement to increase RES connection capability (RRF project) | Lihula 330 KV substation (EE) and reinforcement of internal grid in western part of Estonia | New Lihula 330 kV substation will be connected to existing Harku-Sindi 330 kV OHL in Lihula. It consists of 2 330 kV duplex bays for 330 kV lines, and 3 simplex 330 kV bays of which 2 will be used for power transformers (200 MVA each) and one for reactive power compensator (125 Mvar). The investment also includes the reinforcement of internal 110 kV grid where are the potential RES connection points. | 4 | New Investment |  | 06-2026 | 2026 | 1 | Elering |  | 0 | 0 | Lihula | Lihula | OnshoreSubstation | AC | 0 | 330 | 0 | MostlyUpgrade | 1086 | 1754 | Internal grid reinforcements in Estonia to increase RES connection capability (RRF project) | Lihula 330 KV substation (EE) and reinforcement of internal grid in western part of Estonia | New Lihula 330 kV substation will be connected to existing Harku-Sindi 330 kV OHL in Lihula. It consists of 2 330 kV duplex bays for 330 kV lines, and 3 simplex 330 kV bays of which 2 will be used for power transformers (200 MVA each) and one for reactive power compensator (125 Mvar). The investment also includes the reinforcement of internal 110 kV grid where are the potential RES connection points. | 4 |  | 06-2026 | 2026 | 1 | Elering | 0 | XX | XX | Mostly upgrade | 2025 | 2026 | 1 | 4 | EST | Lihula | Lihula | 58.6851 | 23.8288 | 58.6851 | 23.8288
452 | 2022 | 2026 | [2022, 2024, 2026] | 1755 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1088 | 1755 | Latvia and Estonia Hybrid Off-Shore interconnector | The interconnector between Latvia and Estonia with Off-shore wind connection hub in between | The planned subsea interconnection between Estonia and Latvia with off-shore connection hub in between. The connection of off-shore wind up to 1000 MW. | 1 | New Investment |  | 12-2030 | 2030 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING |  | 1 | 1 | Tume (LV) | Sindi (EE) | OffshoreDCTransmissionCable | DC | 1000 | 450 | 180 | New | 1088 | 1755 | Latvia and Estonia Hybrid Off-Shore interconnector | The interconnector between Latvia and Estonia with Off-shore wind connection hub in between | The planned subsea interconnection between Estonia and Latvia with off-shore connection hub in between. The connection of off-shore wind up to 1000 MW. | 1 | Investment on time |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 5.1 | 1 | 1 | Pavilosta (LV) | Saaremaa-Hub (EE) | OffshoreACTransmissionCable | AC | 1000 | 220 | 150 | New | 1088 | 1755 | Latvia and Estonia Hybrid Off-Shore interconnector | The interconnector between Latvia and Estonia with potential to connect off-shore RES | The planned subsea interconnection between Estonia and Latvia with potential to connect off-shore RES. The connection of off-shore wind up to 1000 MW. | 2 |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 1 | XX | XX | New | 2030 | 2035 | 5 | 13 | EST;LVA | Pavilosta | Saaremaa- | 56.8889 | 21.1825 | 58.2738 | 22.2771
453 | 2022 | 2022 | [2022] | 1756 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1088 | 1756 | Latvia and Estonia Hybrid Off-Shore interconnector | Cross-border network reinforcement Grobina (LV) - Derbenai (LT) | The reconstruction of the existing 330 kV OHL from substation Grobina in Latvia to substation Derbenai in Lithuania. The capacity increase on cross-border Latvia - Lithuania up to 300 MW. | 1 | New Investment |  | 12-2025 | 2025 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING |  | 0 | 1 | Grobina (LV) | Derbenai (LT) | ACTransmissionLine | AC | 0 | 330 | 85 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 3 | EST;LVA | Grobina | Derbenai
454 | 2022 | 2022 | [2022] | 1757 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1088 | 1757 | Latvia and Estonia Hybrid Off-Shore interconnector | Cross-border network reinforcement Broceni (LV) - Telsiai (LT) | 330 kV OHL | 1 | New Investment |  | 12-2030 | 2030 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING |  | 0 | 1 | Broceni (LV) | Telsiai (LT) | ACTransmissionLine | AC | 0 | 330 | 90 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 8 | EST;LVA | Broceni | Telsiai | 56.6845 | 22.5665
455 | 2022 | 2026 | [2022, 2024, 2026] | 1758 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1088 | 1758 | Latvia and Estonia Hybrid Off-Shore interconnector | Internal network reinforcement Ventspils (LV) - Broceni (LV) | 330 kV OHL | 1 | New Investment |  | 12-2030 | 2030 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING |  | 0 | 1 | Ventspils (LV) | Broceni (LV) | ACTransmissionLine | AC | 0 | 330 | 105 | New | 1088 | 1758 | Latvia and Estonia Hybrid Off-Shore interconnector | Internal network reinforcement Pavilosta (LV) - Broceni (LV) | New 330 kV OHL for internal network strengthening in Latvia | 1 | New Investment |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 5.1 | 0 | 1 | Pavilosta (LV) | Broceni (LV) | ACTransmissionLine | AC | 0 | 330 | 95 | New | 1088 | 1758 | Latvia and Estonia Hybrid Off-Shore interconnector | Internal network reinforcement Ventspils (LV) - Broceni (LV) | New 330 kV OHL for internal network strengthening in Latvia | 2 |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 1 | XX | XX | New | 2030 | 2035 | 5 | 13 | EST;LVA | Pavilosta | Broceni | 56.8889 | 21.1825 | 56.6845 | 22.5665
456 | 2022 | 2026 | [2022, 2024, 2026] | 1759 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1092 | 1759 | Triton Link: offshore hybrid HVDC interconnector Belgium – Denmark | Connection between Belgium and the Danish Energy Island | Hybrid HVDC interconnector | 1 | New Investment |  | 12-2031 | 2031 | 1 | Energinet and Elia Transmission Belgium |  | 1 | 1 | Mercator | Substation on Danish Energy Island | OffshoreDCTransmissionCable | DC | 2000 | 1050 | 773 | New | 1092 | 1759 | TritonLink: offshore hybrid HVDC interconnector Belgium – Denmark | Connection between Belgium and the Danish Energy Island | Hybrid HVDC interconnector | 2 | Rescheduled | Revision of Danish Energy Island concept | 12-2032 | 2032 | 1 | Energinet and Elia Transmission Belgium | 4.2 | 1 | 1 | Baekeland | Substation on Danish Energy Island | OffshoreDCTransmissionCable | DC | 2000 | 1050 | 773 | New | 1092 | 1759 | TritonLink: offshore hybrid HVDC interconnector Belgium – Denmark | Connection between Belgium and the Danish Energy Island | Hybrid HVDC interconnector | 2 |  | 12-2038 | 2038 | 1 | Energinet and Elia Transmission Belgium | 1 | XX | XX | New | 2031 | 2038 | 7 | 16 | BEL;DNK | Baekeland | On Danish Energy Island | 51.1296 | 3.7885
457 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 176 | Cancelled | [5 empty] | 0 |  |  | 44 | 44.90. 176 | Upgrade of transmission capacity of existing 380 kV line (120 km) | 1 | Progresses as planned | 2020 | 2020 | 1 | Daxlanden | Eichstetten | 44.90. 176 | 44.90. 176 | Upgrade of transmission capacity of existing 380 kV line Daxlanden Eichstetten (120 km) | 1 |  | 2020 | 2020 | 1 | Daxlanden (DE) | Eichstetten (DE) | 134 | 176 | N-S Western DE_section South | This AC project is necessary in order to evacuate the energy arriving from HVDC corridors towards southern Germany and reinforce the interconnection capacity with Switzerland | 1 | Investment on time | No significant change | 2020 | 2020 | 1 | Daxlanden (DE) | Eichstetten (DE) | 176 | This AC project is necessary in order to evacuate the energy arriving from HVDC corridors towards southern Germany and reinforce the interconnection capacity with Switzerland | 2 | Rescheduled | No significant change | 2021 | 2021 | 1 | Daxlanden (DE) | Eichstetten (DE) | 134 | 176 | Grid Reinforcements in South-West Germany | Daxlanden-Eichstetten | This AC project is necessary in order to evacuate the energy arriving from HVDC corridors towards southern Germany and reinforce the interconnection capacity with Switzerland | 2 | Rescheduled | No significant change | 1/ 1/ 2021 | 2021 | 1 |  | 0 | Daxlanden (DE) | Eichstetten (DE) | Overhead Line | AC | 754 | 380 | 120 | Upgrade | 134 | 176 | N-S Western DE_section South | Daxlanden-Eichstetten |  |  |  | 1/ 1/ 2021 | 2021 | 1 | AMPRION;TRANSNET-BW | Daxlanden (DE) | Eichstetten (DE) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2021 | 1 | 9 | DEU | Daxlanden | Eichstetten | 49.0014 | 8.3386 | 48.0938 | 7.7314
458 | 2022 | 2026 | [2022, 2024, 2026] | 1760 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1094 | 1760 | Estlink 3 | Estlink 3 | HVDC subsea connection between FI and EE | 1 | New Investment |  | 06-2040 | 2040 | 1 | Fingrid and Elering |  | 1 | 1 | FI | EE | OffshoreDCTransmissionCable | DC | 700 | 450 | 100 | New | 1094 | 1760 | Estlink 3 | Estlink 3 | HVDC subsea connection between FI and EE, including converter stations | 2 | New Investment |  | 06-2035 | 2035 | 1 | Fingrid and Elering | 3.6 | 1 | 1 | FI | EE | OffshoreDCTransmissionCable | DC | 700 | 450 | 120 | New | 1094 | 1760 | EstLink 3 | Estlink 3 | HVDC subsea connection between FI and EE, including converter stations | 2 |  | 06-2038 | 2038 | 1 | Fingrid and Elering | 1 | XX | XX | New | 2040 | 2038 | -2 | 16 | EST;FIN | Fi | Ee | 60.2166 | 19.9439 | 59.409 | 24.737
459 | 2022 | 2026 | [2022, 2024, 2026] | 1761 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1088 | 1761 | Latvia and Estonia Hybrid Off-Shore interconnector | Off-shore substation for off-shore wind park connection | The planned off-shore substation in Baltic Sea on cross-border between Estonia and Latvia. The amount and location of the substation(s) will be determined by studies. | 1 | New Investment |  | 12-2030 | 2030 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING |  | 1 | 1 | ELWIND off-shore substation | ELWIND off-shore substation | OffshoreSubstation | DC | 1000 | 450 | 0 | New | 1088 | 1761 | Latvia and Estonia Hybrid Off-Shore interconnector | Off-shore substation for off-shore wind park connection - Latvia | The planned off-shore substation in Baltic Sea near Western part of Latvia for offshore wind connection. The exact location of the substation will be determined by ongoing studies. | 1 | Investment on time |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 5.1 | 0 | 1 | ELWIND off-shore substation | ELWIND off-shore substation | OffshoreSubstation | AC | 1000 | 220 | 0 | New | 1088 | 1761 | Latvia and Estonia Hybrid Off-Shore interconnector | Off-shore substation for off-shore wind park connection - Latvia | The planned off-shore substation in Baltic Sea near Western part of Latvia for offshore wind connection. The exact location of the substation will be determined by ongoing studies. | 2 |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 1 | XX | XX | New | 2030 | 2035 | 5 | 13 | EST;LVA | Elwind Off-Shore | Elwind Off-Shore
460 | 2022 | 2026 | [2022, 2024, 2026] | 1762 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1095 | 1762 | Aurora line 2 (4th AC Finland-Sweden north) | 4th AC Finland-Sweden north | Fourth AC 400 kV overhead line interconnector between Finland north and Sweden SE1. | 1 | New Investment |  | 06-2035 | 2035 | 1 | Fingrid, Svenska Kraftnät |  | 1 | 1 | FI | SE1 | ACTransmissionLine | AC | 0 | 400 | 250 | New | 1095 | 1762 | Aurora line 2 (4th AC Finland-Sweden north) | 4th AC Finland-Sweden north | Fourth AC 400 kV overhead line interconnector between Finland north and Sweden SE1. | 2 | New Investment |  | 06-2032 | 2032 | 1 | Fingrid, Svenska Kraftnät | 3.5 | 1 | 1 | FI | SE1 | ACTransmissionLine | AC | 0 | 400 | 250 | New | 1095 | 1762 | Aurora line 2 (4th AC Finland-Sweden north) | 4th AC Finland-Sweden north | Fourth AC 400 kV overhead line interconnector between Finland north and Sweden SE1. | 2 |  | 06-2036 | 2036 | 1 | Fingrid, Svenska Kraftnät | 1 | XX | XX | New | 2035 | 2036 | 1 | 14 | FIN;SWE | Fi | Se | 60.2166 | 19.9439
461 | 2022 | 2026 | [2022, 2024, 2026] | 1763 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1096 | 1763 | Beznau - Mettlen | Beznau - Mettlen | line | 3 | Investment on time |  | 12-2028 | 2028 | 1 | Swissgrid |  | 1 | 0 | Beznau | Mettlen | ACTransmissionLine | AC | 0 | 380 | 1 | MostlyNew | 1096 | 1763 | Beznau - Mettlen | Beznau - Mettlen | line | 3 | Delayed | permitting procedure | 12-2031 | 2031 | 1 | Swissgrid |  | 1 | 0 | Beznau | Mettlen | ACTransmissionLine | AC | 0 | 380 | 1 | MostlyNew | 1096 | 1763 | Beznau - Mettlen | Beznau - Mettlen | line |  |  | 12-2033 | 2033 | 1 | Swissgrid | 0 | XX | XX | Mostly new | 2028 | 2033 | 5 | 11 | CHE | Beznau | Mettlen | 47.5542 | 8.2297 | 47.5311 | 9.1236
462 | 2022 | 2024 | [2022, 2024] | 1764 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1039 | 1764 | SE North-south long-term reinforcements | SE North-south Long-term reinforcements | The second investment has also the same description as the first one. | 1 | Investment on time |  | 01-2040 | 2040 | 1 | Svenska Kraftnät |  | 1 | 0 | SE2 | SE3 | ACTransmissionLine | AC | 0 | 400 | 475 | MostlyUpgrade | 1039 | 1764 | SE North-south long-term reinforcements | SE North-south Long-term reinforcements | The second investment has also the same description as the first one. | 1 | Investment on time |  | 01-2040 | 2040 | 1 | Svenska Kraftnät |  | 1 | 0 | SE2 | SE3 | ACTransmissionLine | AC | 0 | 400 | 475 | MostlyUpgrade | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2040 | 2040 | 0 | 18 | SWE | Se | Se
463 | 2022 | 2026 | [2022, 2024, 2026] | 1765 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1097 | 1765 | Upgrade to Konti-Skan | Upgrade to Konti-Skan | This project will increase the capacity on the existing HVDC connections Konti-Skan 1 and 2 connecting SE3 and DK1 by 700 MW, resulting in a total of 1400 MW capacity between SE3 and DK1. | 1 | New Investment |  | 01-2032 | 2032 | 1 | Svenska kraftnät, Energinet |  | 1 | 1 | SE4 (Substation is not decided yet) | DK1 (Substation is not decided yet) | OffshoreDCTransmissionCable | DC | 700 | 525 | 160 | MostlyNew | 1097 | 1765 | Upgrade to Konti-Skan | Upgrade to Konti-Skan | This project will increase the capacity on the existing HVDC connections Konti-Skan 1 and 2 connecting SE3 and DK1 by 700 MW, resulting in a total of 1400 MW capacity between SE3 and DK1. | 1 | New Investment |  | 01-2032 | 2032 | 1 | Svenska kraftnät, Energinet |  | 1 | 1 | SE4 (Substation is not decided yet) | DK1 (Substation is not decided yet) | OffshoreDCTransmissionCable | DC | 700 | 525 | 160 | MostlyNew | 1097 | 1765 | Konti-Skan Connect | Konti-Skan Connect | This project will repleace the existing HVDC connections Konti-Skan 1 and 2 connecting SE3 and DK1, resulting in a total of 1000 MW capacity between SE3 and DK1. | 2 |  | 06-2036 | 2036 | 1 | Svenska kraftnät, Energinet | 1 | XX | XX | Mostly new | 2032 | 2036 | 4 | 14 | DNK;SWE | Se | Dk |  |  | 55.3784 | 9.1318
464 | 2022 | 2026 | [2022, 2024, 2026] | 1766 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1100 | 1766 | Reinforcement of the existing CZ-DE interconnector (Hradec - Röhrsdorf) on the CZ side | Modernization of existing interconnector Hradec - Röhrsdorf | The project consists in the modernization of an existing 400 kV line between the Hradec and Röhrsdorf substations. | 3 | New Investment |  | 08-2028 | 2028 | 1 | CEPS |  | 1 | 1 | Hradec | Röhrsdorf | ACTransmissionLine | AC | 0 | 400 | 81.5 | Upgrade | 1100 | 1766 | Reinforcement of the existing CZ-DE interconnector (Hradec - Röhrsdorf) on the CZ side | Modernization of existing interconnector Hradec - Röhrsdorf | The project consists in the modernization of an existing 400 kV line between the Hradec and Röhrsdorf substations. | 3 | New Investment |  | 08-2028 | 2028 | 1 | CEPS |  | 1 | 1 | Hradec | Röhrsdorf | ACTransmissionLine | AC | 0 | 400 | 81.5 | Upgrade | 1100 | 1766 | Reinforcement of the existing CZ-DE interconnector (Hradec - Röhrsdorf) on the CZ side | Modernization of existing interconnector Hradec - Röhrsdorf | The project consists in the modernization of an existing 400 kV line between the Hradec and Röhrsdorf substations on the CZ side. |  |  | 09-2028 | 2028 | 1 | CEPS | 1 | XX | XX | Upgrade | 2028 | 2028 | 0 | 6 | CZE;DEU | Hradec | Röhrsdorf | 49.7119 | 15.2985 | 50.7919 | 14.5968
465 | 2022 | 2026 | [2022, 2024, 2026] | 1767 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1102 | 1767 | Mettlen - Ulrichen | Mettlen - Ulrichen | AC Line | 3 | Investment on time |  | 12-2035 | 2035 | 1 | Swissgrid |  | 1 | 0 | Mettlen | Ulrichen | ACTransmissionLine | AC | 0 | 380 | 1 | MostlyNew | 1102 | 1767 | Mettlen - Ulrichen | Mettlen - Ulrichen | AC Line | 3 | Ahead of time |  | 12-2034 | 2034 | 1 | Swissgrid |  | 1 | 0 | Mettlen | Ulrichen | ACTransmissionLine | AC | 0 | 220 | 1 | MostlyNew | 1102 | 1767 | Mettlen - Ulrichen | Mettlen - Ulrichen | AC Line |  |  | 12-2038 | 2038 | 1 | Swissgrid | 0 | XX | XX | Mostly new | 2035 | 2038 | 3 | 16 | CHE | Mettlen | Ulrichen | 47.5311 | 9.1236 | 46.5066 | 8.305
466 | 2022 | 2026 | [2022, 2024, 2026] | 1768 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1103 | 1768 | Bickigen - Chippis | Bickigen - Chippis | line | 3 | Investment on time |  | 12-2028 | 2028 | 1 | Swissgrid |  | 1 | 0 | Bickigen | Chippis | ACTransmissionLine | AC | 0 | 380 | 1 | MostlyUpgrade | 1103 | 1768 | Bickigen - Chippis | Bickigen - Chippis | line | 3 | Ahead of time |  | 12-2027 | 2027 | 1 | Swissgrid |  | 1 | 0 | Bickigen | Chippis | ACTransmissionLine | AC | 0 | 380 | 1 | MostlyUpgrade | 1103 | 1768 | Bickigen - Chippis | Bickigen - Chippis | line |  |  | 12-2031 | 2031 | 1 | Swissgrid | 0 | XX | XX | Mostly upgrade | 2028 | 2031 | 3 | 9 | CHE | Bickigen | Chippis | 47.0908 | 7.649 | 46.2805 | 7.5406
467 | 2022 | 2024 | [2022, 2024] | 1769 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1094 | 1769 | Estlink 3 | Estonian grid reinforcements: L346 Paide-Sopi 330 kV OHL reconstruction | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. The thermal transmission capacity of the line is planned 1772 MW. | 2 | New Investment |  | 12-2028 | 2028 | 1 | Fingrid and Elering |  | 0 | 1 | Paide | Sopi | ACTransmissionLine | AC | 0 | 330 | 66.3 | New | 1094 | 1769 | Estlink 3 | Estonian grid reinforcements: L346 Paide-Sopi 330 kV OHL reconstruction | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. The thermal transmission capacity of the line is planned 1772 MW. | 2 | New Investment |  | 12-2028 | 2028 | 1 | Fingrid and Elering | 3.6 | 0 | 1 | Paide | Sopi | ACTransmissionLine | AC | 0 | 330 | 66.3 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2028 | 2028 | 0 | 6 | EST;FIN | Paide | Sopi | 58.8869 | 25.5699 | 58.4651 | 26.3667
468 | 2012 | 2015 | [2012, 2013, 2014, 2015] | 177 | Cancelled | [5 empty] | 0 |  |  | 45 | 45. 90. 177 |  |  | 0 |  |  | 1 |  |  | 45. 90. 177 | 45. 90. 177 | A new 380kV OHL. Length: 45km. | 3 | Anticipation of design and permitting phase due to foreseen difficulties (protected area in the Swabian Alps) | 2020 | 2020 | 1 | Goldshöfe (DE) | Bünzwangen (DE) | 164 | 177 | N-S Eastern DE_central section | AC-extension of the "C corridor" at one ending point in Southern Germany towards the consumption areas allowing the existing grid to deal with the additionnal flows from DC-link | 3 | Investment on time | Anticipation of design and permitting phase due to foreseen difficulties (protected area in the Swabian Alps) | 2020 | 2020 | 1 | Goldshöfe (DE) | Bünzwangen (DE) | 177 | AC-extension of the "C corridor" at one ending point in Southern Germany towards the consumption areas allowing the existing grid to deal with the additionnal flows from DC- link | 6 | Cancelled | Cancelled due to the new project HVDC Area of Segeberg-Area of Wendlingen achieving the same goal. |  |  | 1 | Goldshöfe (DE) | Bünzwangen (DE) | [10 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [9 empty] | DEU | Goldshöfe | Bünzwangen | 48.8944 | 10.1283 | 48.7091 | 9.5461
469 | 2022 | 2024 | [2022, 2024] | 1770 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1094 | 1770 | Estlink 3 | Estonian grid reinforcements: L347 Sopi-Sindi 330 kV OHL reconstruction | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. The thermal transmission capacity of the line is planned 1772 MW. | 2 | New Investment |  | 12-2028 | 2028 | 1 | Fingrid and Elering |  | 0 | 1 | Sopi | Sindi | ACTransmissionLine | AC | 0 | 330 | 28.7 | New | 1094 | 1770 | Estlink 3 | Estonian grid reinforcements: L347 Sopi-Sindi 330 kV OHL reconstruction | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. The thermal transmission capacity of the line is planned 1772 MW. | 2 | New Investment |  | 12-2028 | 2028 | 1 | Fingrid and Elering | 3.6 | 0 | 1 | Sopi | Sindi | ACTransmissionLine | AC | 0 | 330 | 28.7 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2028 | 2028 | 0 | 6 | EST;FIN | Sopi | Sindi | 58.4651 | 26.3667 | 58.4075 | 24.6583
470 | 2022 | 2026 | [2022, 2024, 2026] | 1771 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1094 | 1771 | Estlink 3 | Estonian grid reinforcements: L506 Rakvere-Kiisa 330 kV OHL reconstruction | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. The thermal transmission capacity of the line is planned 1772 MW. | 2 | New Investment |  | 12-2029 | 2029 | 1 | Fingrid and Elering |  | 0 | 1 | Rakvere | Kiisa | ACTransmissionLine | AC | 0 | 330 | 107.8 | New | 1094 | 1771 | Estlink 3 | Estonian grid reinforcements: L506 Rakvere-Kiisa 330 kV OHL reconstruction | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. The thermal transmission capacity of the line is planned 1772 MW. | 2 | New Investment |  | 12-2029 | 2029 | 1 | Fingrid and Elering | 3.6 | 0 | 1 | Rakvere | Kiisa | ACTransmissionLine | AC | 0 | 330 | 107.8 | New | 1094 | 1771 | EstLink 3 | Estonian grid reinforcements: L506 Rakvere-Kiisa 330 kV OHL reconstruction | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. The thermal transmission capacity of the line is planned 1772 MW. | 2 |  | 12-2037 | 2037 | 1 | Fingrid and Elering | 1 | XX | XX | New | 2029 | 2037 | 8 | 15 | EST;FIN | Rakvere | Kiisa | 59.3482 | 26.3617 | 59.2379 | 24.6875
471 | 2022 | 2026 | [2022, 2024, 2026] | 1772 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1104 | 1772 | Niederstedem - Roost | Roost - Flebour - Bauler | Upgrade of existing transmission OHL between Roost and Bauler to increase the thermal cross-border capacity. | 2 | New Investment |  | 12-2027 | 2027 | 1 | Amprion, Creos |  | 1 | 1 | Bauler (DE) | Roost (LU) | ACTransmissionLine | AC | 0 | 220 | 27.8 | Upgrade | 1104 | 1772 | Bauler - Roost | Roost - Flebour - Border Luxemburg | Upgrade of existing transmission OHL between Roost and Border Luxembourg to increase the thermal cross-border capacity. | 5 | New Investment |  | 12-2022 | 2022 | 1 | Amprion, Creos |  | 1 | 1 | Bauler (DE) | Roost (LU) | ACTransmissionLine | AC | 0 | 220 | 27.8 | Upgrade | 1104 | 1772 | Bauler - Roost | Roost - Flebour - Border Luxemburg | Upgrade of existing transmission OHL between Roost and Border Luxembourg to increase the thermal cross-border capacity. | 5 | Commissioned | 12-2022 | 2022 | 1 | Amprion, Creos | 1 | XX | XX | Upgrade | 2027 | 2022 | -5 | 0 | DEU;LUX | Bauler | Roost | 49.9651 | 6.2069 | 51.7379 | 7.1838
472 | 2022 | 2026 | [2022, 2024, 2026] | 1773 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1104 | 1773 | Niederstedem - Roost | Bauler - Niederstedem | Upgrade of existing transmission OHL between Bauler and Niederstedem to increase the thermal capacity. To reach a higher capacity the options are High Temperature Low Sag (HTLS) conductors or a reconstruction of the tie-line in the existing route . | 2 | New Investment |  | 12-2030 | 2030 | 1 | Amprion, Creos |  | 0 | 1 | Niederstedem (DE) | Bauler (DE) | ACTransmissionLine | AC | 0 | 220 | 20.3 | Upgrade | 1104 | 1773 | Bauler - Roost | Bauler - German Border | Upgrade of existing transmission OHL between Station Bauler and Border to Luxembourg to increase the thermal capacity by using High Temperature Low Sag (HTLS) conductors | 2 | New Investment |  | 12-2025 | 2025 | 1 | Amprion, Creos |  | 0 | 1 | German Border | Bauler (DE) | ACTransmissionLine | AC | 0 | 220 | 20.3 | Upgrade | 1104 | 1773 | Bauler - Roost | Bauler - German Border | Upgrade of existing transmission OHL between Station Bauler and Border to Luxembourg to increase the thermal capacity by using High Temperature Low Sag (HTLS) conductors | 2 |  | 12-2027 | 2027 | 1 | Amprion, Creos | 1 | XX | XX | Upgrade | 2030 | 2027 | -3 | 5 | DEU;LUX | German Border | Bauler |  |  | 49.9651 | 6.2069
473 | 2022 | 2026 | [2022, 2024, 2026] | 1774 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1094 | 1774 | Estlink 3 | Estonian grid reinforcements: L360 Püssi-Rakvere 330 kV OHL reconstruction | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. The thermal transmission capacity of the line is planned 1772 MW. | 2 | New Investment |  | 12-2030 | 2030 | 1 | Fingrid and Elering |  | 0 | 1 | Püssi | Rakvere | ACTransmissionLine | AC | 0 | 330 | 57.7 | New | 1094 | 1774 | Estlink 3 | Estonian grid reinforcements: L360 Püssi-Rakvere 330 kV OHL reconstruction | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. The thermal transmission capacity of the line is planned 1772 MW. | 2 | New Investment |  | 12-2030 | 2030 | 1 | Fingrid and Elering | 3.6 | 0 | 1 | Püssi | Rakvere | ACTransmissionLine | AC | 0 | 330 | 57.7 | New | 1094 | 1774 | EstLink 3 | Estonian grid reinforcements: L360 Püssi-Rakvere 330 kV OHL reconstruction | The new reconstructed 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. The thermal transmission capacity of the line is planned 1772 MW. | 2 |  | 12-2035 | 2035 | 1 | Fingrid and Elering | 1 | XX | XX | New | 2030 | 2035 | 5 | 13 | EST;FIN | Püssi | Rakvere | 59.361 | 27.0445 | 59.3482 | 26.3617
474 | 2022 | 2026 | [2022, 2024, 2026] | 1775 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1094 | 1775 | Estlink 3 | Estonian grid reinforcements: L512 Aruküla-Kiisa 330 kV new OHL | The new 330 kV OHL will be wired with 3x402 mm2 in phase and with operating temperature of 80 degrees Celsius. The thermal transmission capacity of the line is planned 1772 MW. | 2 | New Investment |  | 12-2030 | 2030 | 1 | Fingrid and Elering |  | 0 | 1 | Aruküla | Kiisa | ACTransmissionLine | AC | 0 | 330 | 32.3 | New | 1094 | 1775 | Estlink 3 | Estonian grid reinforcements: Kiisa-Aruküla 330 kV new OHL | New 330 kV overhead powerline and new 330 kV substation between Kiisa and Aruküla 330 kV substations, | 2 | New Investment |  | 06-2035 | 2035 | 1 | Fingrid and Elering | 3.6 | 0 | 1 | Aruküla | Kiisa | ACTransmissionLine | AC | 0 | 330 | 41 | New | 1094 | 1775 | EstLink 3 | Estonian grid reinforcements: Tallinn area grid reinforcements | New 330 kV substation in Tallinn area and two new 330 kV OHLs to connect the new substation with existing Kiisa and Aruküla 330 kV substations | 2 |  | 06-2034 | 2034 | 1 | Fingrid and Elering | 1 | XX | XX | New | 2030 | 2034 | 4 | 12 | EST;FIN | Aruküla | Kiisa | 59.365 | 25.0736 | 59.2379 | 24.6875
475 | 2022 | 2026 | [2022, 2024, 2026] | 1777 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1092 | 1777 | Triton Link: offshore hybrid HVDC interconnector Belgium – Denmark | Connection between Denmark and the Danish Energy Island | Hybrid HVDC interconnector | 1 | New Investment |  | 12-2030 | 2030 | 1 | Energinet and Elia Transmission Belgium |  | 0 | 1 | Danish Energy Island | Revsing | OffshoreDCTransmissionCable | DC | 1400 | 1050 | 140 | New | 1092 | 1777 | TritonLink: offshore hybrid HVDC interconnector Belgium – Denmark | Connection between Denmark and the Danish Energy Island | Hybrid HVDC interconnector | 2 | Rescheduled | Revision of Danish Energy Island concept | 12-2032 | 2032 | 1 | Energinet and Elia Transmission Belgium | 4.2 | 0 | 1 | Danish Energy Island | Revsing | OffshoreDCTransmissionCable | DC | 2000 | 1050 | 215 | New | 1092 | 1777 | TritonLink: offshore hybrid HVDC interconnector Belgium – Denmark | Connection between Denmark and the Danish Energy Island | Hybrid HVDC interconnector | 2 |  | 12-2038 | 2038 | 1 | Energinet and Elia Transmission Belgium | 1 | XX | XX | New | 2030 | 2038 | 8 | 16 | BEL;DNK | Danish Energy Island | Revsing |  |  | 55.5073 | 9.1751
476 | 2022 | 2026 | [2022, 2024, 2026] | 1778 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1098 | 1778 | Offshore Wind LT 2 | Offshore Wind LT 2 | Offshore platform for connection of up to 700 MW offshore wind farms, 220 kV subsea cables to onshore substation, internal grid reinforcements in onshore network. | 1 | New Investment |  | 12-2030 | 2030 | 1 | LITGRID AB |  | 1 | 0 | Darbenai | offshore platform | OffshoreSubstation | AC | 0 | 220 | 70 | New | 1098 | 1778 | Offshore Wind LT 2 | Extension of Darbenai substation | Extension of Darbenai substation to connect offshore wind farm. | 2 | New Investment |  | 12-2030 | 2030 | 1 | LITGRID AB |  | 1 | 0 | Darbenai | - | OnshoreSubstation | AC | 0 | 330 | 0 | New | 1098 | 1778 | Offshore Wind LT 2 | Extension of Darbenai substation | Extension of 330 kV Darbenai substation to connect second stage of offshore wind farm (700 MW). | 2 |  | 12-2030 | 2030 | 1 | LITGRID AB | 0 | XX | XX | New | 2030 | 2030 | 0 | 8 | LTU | Darbenai | Platform | 56.0232 | 21.254
477 | 2022 | 2022 | [2022] | 1779 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1042 | 1779 | Offshore Wind LT 1 | Offshore Wind LT 1 | 'Connection of 700 MW offshore wind farms to onshore Darbenai substation. Offshore platform and cables planned to be build and owned not by TSO, therefore their costs are not added to this project investments. | 2 | New Investment |  | 12-2028 | 2028 | 1 | Litgrid AB |  | 1 | 0 | Darbenai | offshore platform | OnshoreSubstation | AC | 0 | 220 | 70 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2028 | 2028 | 0 | 6 | LTU | Darbenai | Platform | 56.0232 | 21.254
478 | 2022 | 2026 | [2022, 2024, 2026] | 1780 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1046 | 1780 | Finnish North-South reinforcement | Jylkkä-Alajärvi (2 x OHL) –Toivila (1 x OHL) | New 2 x 400 kV OHL built from Jylkkä substation (western Finland) to Alajärvi substation (central Finland) (+other required investments). The line continues as a single 400 kV OHL from Alajärvi to Toivila substation (Central Finland). Enables the integration of renewables and the utilization of full transfer capacity from North to South . | 2 | New Investment |  | 06-2028 | 2028 | 1 | Fingrid |  | 0 | 0 | Jylkkä | Toivila | ACTransmissionLine | AC | 0 | 400 | 300 | New | 1046 | 1780 | Finnish North-South reinforcement | Jylkkä-Alajärvi (2 x OHL) –Toivila (1 x OHL) | New 2 x 400 kV OHL built from Jylkkä substation (western Finland) to Alajärvi substation (central Finland) (+other required investments). The line continues as a single 400 kV OHL from Alajärvi to Toivila substation (Central Finland). Enables the integration of renewables and the utilization of full transfer capacity from North to South . | 3 | New Investment |  | 06-2028 | 2028 | 1 | Fingrid |  | 0 | 0 | Jylkkä | Toivila | ACTransmissionLine | AC | 0 | 400 | 300 | New | 1046 | 1780 | Finnish North-South reinforcement | Jylkkä-Alajärvi (2 x OHL) –Toivila (1 x OHL) | New 2 x 400 kV OHL built from Jylkkä substation (western Finland) to Alajärvi substation (central Finland) (+other required investments). The line continues as a single 400 kV OHL from Alajärvi to Toivila substation (Central Finland). Enables the integration of renewables and the utilization of full transfer capacity from North to South . |  |  | 06-2028 | 2028 | 1 | Fingrid | 0 | XX | XX | New | 2028 | 2028 | 0 | 6 | FIN | Jylkkä | Toivila | 64.2818 | 24.2054 | 60.4948 | 22.9735
479 | 2022 | 2026 | [2022, 2024, 2026] | 1781 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1046 | 1781 | Finnish North-South reinforcement | Nuojuankangas-Petäjävesi (Metsälinja 2) | New single circuit 400 kV OHL will be built to the central part of Finland. Enables the integration of renewables and the utilization of full transfer capacity from North to South . | 2 | New Investment |  | 06-2030 | 2030 | 1 | Fingrid |  | 0 | 0 | Nuojuankangas | Petäjävesi | ACTransmissionLine | AC | 0 | 400 | 290 | New | 1046 | 1781 | Finnish North-South reinforcement | Nuojuankangas-Vihtavuori (Metsälinja 2) | New single circuit 400 kV OHL will be built to the central part of Finland. Enables the integration of renewables and the utilization of full transfer capacity from North to South . | 3 | New Investment |  | 06-2030 | 2030 | 1 | Fingrid |  | 0 | 0 | Nuojuankangas | Petäjävesi | ACTransmissionLine | AC | 0 | 400 | 290 | New | 1046 | 1781 | Finnish North-South reinforcement | Nuojuankangas-Vihtavuori-Toivila (Metsälinja 2) | New single circuit 400 kV OHL will be built to the central part of Finland. Enables the integration of renewables and the utilization of full transfer capacity from North to South . |  |  | 06-2030 | 2030 | 1 | Fingrid | 0 | XX | XX | New | 2030 | 2030 | 0 | 8 | FIN | Nuojuankangas | Petäjävesi | 64.573 | 26.7217 | 62.2505 | 25.2005
480 | 2022 | 2026 | [2022, 2024, 2026] | 1782 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1105 | 1782 | Georgia-Romania Black Sea (submarine) interconnection cable project | Black Sea HVDC submarine interconnection project | Submarine cable Anaklia-Constanta Sud which will be placed under Black Sea DC 2-circuit ±500 kV cable, route distance – 1100KM | 1 | New Investment |  | 12-2029 | 2029 | 1 | JSC Georgian State Electrosystem (GSE) |  | 1 | 1 | SS Anaklia | SS Constanta Sud | OffshoreDCTransmissionCable | DC | 1000 | 500 | 1100 | New | 1105 | 1782 | Georgia-Romania Black Sea (submarine) interconnection cable project | Black Sea HVDC submarine interconnection project | Submarine cable Anaklia-Constanta Sud which will be placed under Black Sea DC 2-circuit ±500 kV cable, route distance – 1155KM | 1 | New Investment |  | 12-2031 | 2031 | 1 | JSC Georgian State Electrosystem (GSE) |  | 1 | 1 | SS Anaklia | SS Constanta Sud | OffshoreDCTransmissionCable | DC | 1000 | 500 | 1155 | New | 1105 | 1782 | Georgia-Romania Black Sea (submarine) interconnection cable project | Black Sea HVDC submarine interconnection project | Submarine cable Anaklia-Constanta Sud which will be placed under Black Sea DC 2-circuit ±525 kV cable, route distance – 1155KM | 1 |  | 12-2031 | 2031 | 1 | JSC Georgian State Electrosystem (GSE) and | 1 | XX | XX | New | 2029 | 2031 | 2 | 9 | GEO;ROU | Anaklia | Constanta Sud |  |  | 44.1363 | 28.62
481 | 2022 | 2024 | [2022, 2024] | 1783 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 124 | 1783 | NordBalt phase 2 | Nybro-Hemsjo | Second phase includes the internal network reinforcements in Sweden to be able to fully utilize the interconnector between Lithuania and Sweden. | 4 | Delayed | Permit recieved. | 12-2026 | 2026 | 1 | AST, Svenska Kraftnat, Litgrid AB | 4.4.2 | 1 | 1 | Nybro (SE) | Hemsjo (SE) | ACTransmissionLine | AC | 0 | 400 | 90 | New | 124 | 1783 | Ekhyddan-Nybro-Hemsjö | Nybro-Hemsjo | Second phase includes the internal network reinforcements in Sweden to be able to fully utilize the interconnector between Lithuania and Sweden. | 4 | Delayed | Permit recieved. | 12-2026 | 2026 | 1 | AST, Svenska Kraftnat, Litgrid AB | 4.4.2 | 1 | 1 | Nybro (SE) | Hemsjo (SE) | ACTransmissionLine | AC | 0 | 400 | 90 | New | [5 empty] | 5 | Commissioned |  |  | 0 | [5 empty] | 2026 | 2026 | 0 | 4 | LTU;LVA;SWE | Nybro | Hemsjo | 56.7445 | 15.9075 | 57.8445 | 12.4771
482 | 2022 | 2024 | [2022, 2024] | 1784 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 124 | 1784 | NordBalt phase 2 | Ekhyddan-Nybro | Second phase includes the internal network reinforcements in Sweden to be able to fully utilize the interconnector between Lithuania and Sweden. | 3 | Delayed | Permit denied. Appeal process ongoing | 12-2027 | 2027 | 1 | AST, Svenska Kraftnat, Litgrid AB | 4.4.2 | 0 | 1 | Ekhyddan (SE) | Nybro (SE) | ACTransmissionLine | AC | 0 | 400 | 98 | New | 124 | 1784 | Ekhyddan-Nybro-Hemsjö | Ekhyddan-Nybro | Second phase includes the internal network reinforcements in Sweden to be able to fully utilize the interconnector between Lithuania and Sweden. | 3 | Delayed | Permit denied. Appeal process ongoing | 12-2027 | 2027 | 1 | AST, Svenska Kraftnat, Litgrid AB | 4.4.2 | 0 | 1 | Ekhyddan (SE) | Nybro (SE) | ACTransmissionLine | AC | 0 | 400 | 98 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2027 | 2027 | 0 | 5 | LTU;LVA;SWE | Ekhyddan | Nybro | 59.3996 | 18.1538 | 56.7445 | 15.9075
483 | 2022 | 2026 | [2022, 2024, 2026] | 1785 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1094 | 1785 | Estlink 3 | Inkoo-Hikiä | Inkoo-Hikiä 400 kV single circuit OHL | 1 | New Investment |  | 06-2040 | 2040 | 1 | Fingrid and Elering |  | 0 | 1 | Inkoo (FI) | Hikiä (FI) | ACTransmissionLine | AC | 0 | 400 | 100 | New | 1094 | 1785 | Estlink 3 | Inkoo-Hikiä | Inkoo-Hikiä 400 kV single circuit OHL | 2 | New Investment |  | 06-2031 | 2031 | 1 | Fingrid and Elering | 3.6 | 0 | 1 | Inkoo (FI) | Hikiä (FI) | ACTransmissionLine | AC | 0 | 400 | 100 | New | 1094 | 1785 | EstLink 3 | Inkoo-Ulvila | Inkoo-Ulvila 400 kV single circuit OHL | 2 |  | 06-2034 | 2034 | 1 | Fingrid and Elering | 1 | XX | XX | New | 2040 | 2034 | -6 | 12 | EST;FIN | Inkoo | Hikiä | 60.0461 | 24.0042 | 60.7538 | 24.9233
484 | 2022 | 2026 | [2022, 2024, 2026] | 1787 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1067 | 1787 | New AC 400 kV interconnection line Greece - Turkey | New 400 kV OHL Nea Santa - Filippi | New AC 400 kV double circuit OHL Nea Santa - Filippi | 2 | New Investment |  | 12-2027 | 2027 | 1 | Admie |  | 0 | 1 | Nea Santa | Fillipi | ACTransmissionLine | AC | 0 | 400 | 140 | New | 1067 | 1787 | New AC 400 kV interconnection line Greece - Turkey | New 400 kV OHL Nea Santa - Filippi | New AC 400 kV double circuit OHL Nea Santa - Filippi | 2 | Rescheduled |  | 06-2028 | 2028 | 1 | Admie |  | 0 | 1 | Nea Santa | Fillipi | ACTransmissionLine | AC | 0 | 400 | 140 | New | 1067 | 1787 | New AC 400 kV interconnection line Greece - Turkey | New 400 kV OHL Nea Santa - Filippi | New AC 400 kV double circuit OHL Nea Santa - Filippi |  |  | 06-2028 | 2028 | 1 | Admie | 1 | XX | XX | New | 2027 | 2028 | 1 | 6 | GRC;TUR | Nea Santa | Fillipi | 40.8423 | 22.9204
485 | 2022 | 2022 | [2022] | 1788 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1098 | 1788 | Offshore Wind LT 2 | New 330 kV OHL Darbenai-Musa | New 330 kV OHL to strengthen internal network after connection of 700 MW offshore capacity. | 1 | New Investment |  | 12-2030 | 2030 | 1 | LITGRID AB |  | 0 | 0 | Darbenai | Musa | ACTransmissionLine | AC | 0 | 330 | 170 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 8 | LTU | Darbenai | Musa | 56.0232 | 21.254 | 54.9365 | 24.9126
486 | 2022 | 2022 | [2022] | 1789 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1098 | 1789 | Offshore Wind LT 2 | New 330 kV OHL Panevezys-Musa | New 330 kV OHL to strengthen internal network after connection of 700 MW offshore capacity. | 1 | New Investment |  | 12-2030 | 2030 | 1 | LITGRID AB |  | 0 | 0 | Panevezys | Musa | ACTransmissionLine | AC | 0 | 330 | 72 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 8 | LTU | Panevezys | Musa | 55.7345 | 24.3578 | 54.9365 | 24.9126
487 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 179 | Commissioned | 179 | New line, extension of existing and erection of substations, erection of 380/110kV-transformers. Total line length: 100km. | 4 | mid term |  | 1 | Rommerskirchen (DE) | Weißenthurm (DE) | 44 | 44. 179 | New line, extension of existing and erection of substations, erection of 380/110kV-transformers. Total line length: 100km. | 4 | Some parts are commissioned but the main elements of the investment are still in design and permitting due to delays in permitting process. | mid term |  | 1 | Rommerskirchen (DE) | Weißenthurm (DE) | 44. 179 | 44. 179 | New line, extension of existing and erection of substations, erection of 380/110kV-transformers. | 4 |  | 2015 | 2015 | 1 | Rommerskirchen (DE) | Weißenthurm (DE) | 134 | 179 | N-S Western DE_section South | New380 kV overhead line in existing route. Extension and erection of substations incl. erection of 380/110kV-transformers. | 4 | Delayed | The section Rommerskrichen to Sechtem is delayed because the permitting procedures take longer than planned. The 36 km section from Sechtem to Weißenturm is already commissioned. | 2017 | 2017 | 1 | Rommerskirchen (DE) | Weißenthurm (DE) | 179 | New380 kV overhead line in existing route. Extension and erection of substations incl. erection of 380/110kV- transformers. | 4 | Delayed | The section Rommerskrichen to Sechtem is delayed because the permitting procedures take longer than planned. The 36 km section from Sechtem to Weißenturm is already commissioned. | 2018 | 2018 | 1 | Rommerskirc hen (DE) | Weißenthur m (DE) | 135 | 179 | Grid Reinforcements in Western Germany | Rommerskirchen - Weißenthurm | New380 kV overhead line in existing route. Extension and erection of substations incl. erection of 380/110kV-transformers. | 4 | Delayed | The section Rommerskrichen to Sechtem is delayed because the permitting procedures take longer than planned. The 36 km section from Sechtem to Weißenturm is already commissioned. | 1/ 1/ 2019 | 2019 | 1 |  | 0 | Rommerskirchen (DE) | Weißenthurm (DE) | Overhead Line | AC | 900 | 400 | 94 | New | 135 | 179 | N-S Western DE_parallel lines | Rommerskirchen - Weißenthurm | 4 | Investment on time |  | 1/ 1/ 2019 | 2019 | 1 | AMPRION | Rommerskirchen (DE) | Weißenthurm (DE) | Overhead Line | AC | 400 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2019 |  | 9 | DEU | Rommerskirchen | Weißenthurm | 51.0634 | 6.6979 | 50.4145 | 7.4558
488 | 2022 | 2026 | [2022, 2024, 2026] | 1791 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 120 | 1791 | Belgian Modular Offshore Grid II (MOG II) | DC-part of Belgian Modular Offshore Grid II (MOG II) | One or more offshore substations centralize the production from these offshore wind farms, and then transport it via +/- 525 kV subsea DC cables to the Gezelle 380kV | 2 | New Investment |  | 12-2029 | 2029 | 1 | Elia |  | 0 | 0 | Offshore (TBD) | Onshore (TBD | OffshoreSubstation | DC | 1400 | 1050 | 60 | New | 120 | 1791 | Princess Elisabeth Island (MOG 2) | DC-part of Princess Elisabeth Island | Construction of an artificial island including AC & DC assets to connect +-3,5GW of offshore wind and connect it to the onshore grid | 3 | Rescheduled | Reevaluation of the project's schedule | 12-2030 | 2030 | 1 | Elia |  | 0 | 0 | Princess Elisabeth Island | Onshore (TBD) | OffshoreSubstation | DC | 1400 | 1050 | 60 | New | 120 | 1791 | Princess Elisabeth Island (MOG 2) | DC-part of Princess Elisabeth Island | Construction of an artificial island including AC & DC assets to connect +-3,5GW of offshore wind and connect it to the onshore grid |  |  | 01-2032 | 2032 | 1 | Elia | 0 | XX | XX | New | 2029 | 2032 | 3 | 10 | BEL | Princess Elisabeth Island | Onshore
489 | 2022 | 2022 | [2022] | 1792 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1107 | 1792 | EuroAfrica Interconnector | EuroAfrica Interconnector | The EuroAfrica Interconnector consists of a 500 kV DC underwater electric cable and any essential equipment and/or installation for interconnecting the Cypriot and the Egyptian transmission networks (offshore). The Interconnector will have a total capacity of 2000 MW and a total length of 498km and allow for reverse transmission of electricity. | 3 | New Investment |  | 12-2026 | 2026 | 1 | EuroAfrica Interconnector Ltd |  | 1 | 1 | Kofinou | Damietta (Egypt) | OffshoreDCTransmissionCable | DC | 1000 | 500 | 512 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2026 | 2026 | 0 | 4 | CYP;EGY | Kofinou | Damietta
490 | 2022 | 2026 | [2022, 2024, 2026] | 1793 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1106 | 1793 | Bornholm Energy Island (BEI) | Bornholm Energy Island: BEI-DKE | DC connection from mainland Zealand (Solhøjgård, DKE) to Bornholm including converters on Zealand and on Bornholm, as well as AC and MTDC components on the island of Bornholm | 1 | New Investment |  | 12-2029 | 2029 | 1 | Energinet, 50Hertz |  | 1 | 1 | Solhøjgård (DKE) | Bornholm Energy Island (BEI) | OffshoreDCTransmissionCable | DC | 1200 | 525 | 229 | New | 1106 | 1793 | Bornholm Energy Island (BEI) | Bornholm Energy Island: BEI-DKE | DC connection from mainland Zealand (Solhøjgård, DKE) to Bornholm including converters on Zealand and on Bornholm, as well as AC and MTDC components on the island of Bornholm | 1 | New Investment |  | 12-2029 | 2029 | 1 | Energinet, 50Hertz | 5.2 | 1 | 1 | Solhøjgård (DKE) | Bornholm Energy Island (BEI) | OffshoreDCTransmissionCable | DC | 1200 | 525 | 229 | New | 1106 | 1793 | Bornholm Energy Island (BEI) | Bornholm Energy Island: BEI-DKE | DC connection from mainland Zealand (Lindehøj, DKE) to Bornholm including converters on Zealand and on Bornholm, as well as AC and MTDC components on the island of Bornholm. | 2 |  | 12-2033 | 2033 | 1 | Energinet, 50Hertz | 1 | XX | XX | New | 2029 | 2033 | 4 | 11 | DEU;DNK | Solhøjgård | Bornholm Energy Island | 55.6137 | 11.1901
491 | 2022 | 2026 | [2022, 2024, 2026] | 1794 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1106 | 1794 | Bornholm Energy Island (BEI) | Bornholm Energy Island: BEI-DE | DC connection from mainland Germany (Stilow) to Bornholm including converters in Stilow and on Bornholm, as well as AC and MTDC components on the island of Bornholm | 1 | New Investment |  | 12-2029 | 2029 | 1 | Energinet, 50Hertz |  | 1 | 1 | Stilow (DE) | Bornholm Energy Island (BEI) | OffshoreDCTransmissionCable | DC | 2000 | 525 | 193 | New | 1106 | 1794 | Bornholm Energy Island (BEI) | Bornholm Energy Island: BEI-DE | DC connection from mainland Germany (area of Brünzow/Kemnitz) to Bornholm including converters in Stilow and on Bornholm, as well as AC and MTDC components on the island of Bornholm | 1 | New Investment |  | 12-2030 | 2030 | 1 | Energinet, 50Hertz | 5.2 | 1 | 1 | Stilow (DE) | Bornholm Energy Island (BEI) | OffshoreDCTransmissionCable | DC | 2000 | 525 | 193 | New | 1106 | 1794 | Bornholm Energy Island (BEI) | Bornholm Energy Island: BEI-DE | DC connection from mainland Germany (Rappenhagen) to Bornholm including converters in Rappenhagen and on Bornholm, as well as AC and MTDC components on the island of Bornholm. | 2 |  | 12-2030 | 2030 | 1 | Energinet, 50Hertz | 1 | XX | XX | New | 2029 | 2030 | 1 | 8 | DEU;DNK | Stilow | Bornholm Energy Island | 54.0888 | 13.5721
492 | 2022 | 2026 | [2022, 2024, 2026] | 1795 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 339 | 1795 | Tyrrhenian link | Tyrrhenian HVDC link - East | The project envisages a new HVDC interconnection between Campania (SE Montecorvino) and Sicily (SE Caracoli). The design solution envisages a bi-terminal plant configuration as it allows for greater reliability of the connection by increasing the safety and stability of the connection between Sicily and the continent as well as an increase of NTC between the two market areas equal to 1000 MW. | 3 | New Investment | - | 12-2028 | 2028 | 1 | Terna |  | 0 | 0 | Montecorvino | Caracoli | OffshoreDCTransmissionCable | DC | 1000 | 500 | 424 | New | 339 | 1795 | Tyrrhenian link | Tyrrhenian HVDC link - East | Tyrrhenian HVDC link - East | 4 | New Investment | - | 12-2028 | 2028 | 1 | Terna |  | 0 | 0 | Montecorvino | Caracoli | OffshoreDCTransmissionCable | DC | 1000 | 500 | 424 | New | 339 | 1795 | Tyrrhenian link | Tyrrhenian HVDC link - East | Tyrrhenian HVDC link - East | 4 |  | 12-2028 | 2028 | 1 | Terna | 0 | XX | XX | New | 2028 | 2028 | 0 | 6 | ITA | Montecorvino | Caracoli | 41.5172 | 15.15 | 37.9669 | 13.7255
493 | 2022 | 2026 | [2022, 2024, 2026] | 1796 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1109 | 1796 | Basilicata - Campania reinforcements | New 400 kV overhead line between Aliano and Montecorvino | New 400 kV overhead line between Aliano and Montecorvino | 2 | New Investment |  | 12-2032 | 2032 | 1 | Terna SpA |  | 1 | 0 | Aliano | Montecorvino | ACTransmissionLine | AC | 0 | 400 | 116 | New | 1109 | 1796 | Basilicata - Campania reinforcements | New 400 kV overhead line between Aliano and Montecorvino | New 400 kV overhead line between Aliano and Montecorvino | 2 | New Investment |  | 12-2032 | 2032 | 1 | Terna SpA |  | 1 | 0 | Aliano | Montecorvino | ACTransmissionLine | AC | 0 | 400 | 116 | New | 1109 | 1796 | Basilicata - Campania reinforcements | New 400 kV overhead line between Aliano and Montecorvino | New 400 kV overhead line between Aliano and Montecorvino | 2 |  | 12-2040 | 2040 | 1 | Terna SpA | 0 | XX | XX | New | 2032 | 2040 | 8 | 18 | ITA | Aliano | Montecorvino | 40.3114 | 16.232 | 41.5172 | 15.15
494 | 2022 | 2026 | [2022, 2024, 2026] | 1797 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1109 | 1797 | Basilicata - Campania reinforcements | New 400 kV overhead line in the northern area of Benevento | New 400 kV overhead line in the northern area of Benevento | 2 | New Investment |  | 12-2035 | 2035 | 1 | Terna SpA |  | 0 | 0 | Benevento | New Substation | ACTransmissionLine | AC | 0 | 400 | 42 | New | 1109 | 1797 | Basilicata - Campania reinforcements | New 400 kV overhead line in the northern area of Benevento | New 400 kV overhead line in the northern area of Benevento | 2 | New Investment |  | 12-2035 | 2035 | 1 | Terna SpA |  | 0 | 0 | Benevento | New Substation | ACTransmissionLine | AC | 0 | 400 | 42 | New | 1109 | 1797 | Basilicata - Campania reinforcements | New 400 kV overhead line in the northern area of Benevento | New 400 kV overhead line in the northern area of Benevento | 2 |  | 12-2035 | 2035 | 1 | Terna SpA | 0 | XX | XX | New | 2035 | 2035 | 0 | 13 | ITA | Benevento | New | 41.2476 | 14.7057
495 | 2022 | 2026 | [2022, 2024, 2026] | 1798 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1110 | 1798 | Sicily - Calabria | New 400 kV submarine cable Bolano-Annunziata | New 400 kV submarine cable Bolano-Annunziata | 2 | New Investment |  | 12-2026 | 2026 | 1 | Terna SpA |  | 1 | 0 | Bolano | Annunziata | ACTransmissionLine | AC | 0 | 400 | 9 | New | 1110 | 1798 | Sicily - Calabria | New 400 kV submarine cable Bolano-Annunziata | New 400 kV submarine cable Bolano-Annunziata | 3 | New Investment |  | 12-2026 | 2026 | 1 | Terna SpA |  | 1 | 0 | Bolano | Annunziata | ACTransmissionLine | AC | 0 | 400 | 9 | New | 1110 | 1798 | Sicily - Calabria | New 400 kV submarine cable Bolano-Annunziata | New 400 kV submarine cable Bolano-Annunziata |  |  | 12-2027 | 2027 | 1 | Terna SpA | 0 | XX | XX | New | 2026 | 2027 | 1 | 5 | ITA | Bolano | Annunziata | 44.1837 | 9.8893 | 44.6365 | 7.954
496 | 2022 | 2026 | [2022, 2024, 2026] | 1799 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1112 | 1799 | GRITA 2 | GRITA 2 | New HVDC link between Italy (Galatina) and Greece (Arachthos) with an NTC increase of 500 MW. | 1 | New Investment |  | 12-2031 | 2031 | 1 | TERNA;IPTO |  | 1 | 1 | Galatina (IT) | Arachthos (GR) | DCTransmissionLine | DC | 500 | 400 | 320 | New | 1112 | 1799 | GRITA 2 | GRITA 2 | New HVDC link between Italy (Galatina) and Greece (Thesprotia) with an NTC increase of 1000 MW | 2 | Investment on time |  | 12-2031 | 2031 | 1 | TERNA; IPTO |  | 1 | 1 | Galatina (IT) | Thesprotia (GR) | OffshoreDCTransmissionCable | DC | 1000 | 400 | 275 | New | 1112 | 1799 | GRITA 2 | GRITA 2 | New HVDC link between Italy (Galatina) and Greece (Thesprotia) with an NTC increase of 1000 MW | 2 |  | 12-2033 | 2033 | 1 | TERNA; IPTO | 1 | XX | XX | New | 2031 | 2033 | 2 | 11 | GRC;ITA | Galatina | Thesprotia | 40.1743 | 18.1678 | 39.544 | 20.3084
497 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 18 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 4 | 18 | Interconnection Portugal-Spain | New northern interconnection. New double circuit 400kV OHL between Beariz (ES) - Fontefria (ES). | 3 | Delayed | Delays in authorization process due to a change on the route and on the location of substations, induced by environmental concerns | 2016 | 2016 | 1 | Beariz (ES) | Fontefria (ES) | 18 | New northern interconnection. New double circuit 400kV OHL between Beariz (ES) - Fontefria (ES). | 3 | Delayed | The delay of this investment is affected by the explanation in the investment 496. Also, environmental problems lead to re-routing. | 2017 | 2017 | 1 | Beariz (ES) | Fontefria (ES) | 4 | 18 | Interconnection Portugal-Spain | Beariz (ES) - Fontefria (ES) | New northern interconnection. New double circuit 400kV OHL between Beariz (ES) - Fontefria (ES). | 3 | Delayed | The delay of this investment is affected by the explanation in the investment 496. Also, environmental problems lead to re-routing. | 1/ 1/ 2017 | 2017 | 1 |  | 0 | Beariz (ES) | Fontefria (ES) | Overhead Line | AC | 1000 | 400 | 32 | New | 4 | 18 | Interconnection Portugal-Spain | Beariz (ES) - Fontefria (ES) | 3 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 1/ 1/ 2021 | 2021 | 1 | REE;REN | Beariz (ES) | Fontefria (ES) | Overhead Line | AC | 400 | 4 | 18 | Interconnection Portugal-Spain | Beariz (ES) - Fontefria (ES) | New northern interconnection. New double circuit 400kV OHL between Beariz (ES) - Fontefria (ES). | 3 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 2022 | 2022 | 1 | Red Eléctrica de España Rede Elétrica Nacional | 2.17 | 1 | 1 | Beariz (ES) | Fontefria (ES) | ACTransmissionLine | AC | 30 | New | 4 | 18 | Interconnection Portugal-Spain | Beariz (ES) - Fontefria (ES) | New double circuit 400kV OHL between Beariz (ES) - Fontefria (ES). | 3 | Delayed | Delays in the Environmental Impact Assessment process | 06-2024 | 2024 | 1 | REN and Red Eléctrica | 2.17 | 1 | 1 | Beariz (ES) | Fontefria (ES) | ACTransmissionLine | AC | 0 | 400 | 30 | New | 4 | 18 | Interconnection Portugal-Spain | Beariz (ES) - Fontefria (ES) | New double circuit 400kV OHL between Beariz (ES) - Fontefria (ES). | 3 | Delayed | Delays in the Environmental Impact Assessment process | 06-2024 | 2024 | 1 | REN and Red Eléctrica | 1.1 | 1 | 1 | Beariz (ES) | Fontefria (ES) | ACTransmissionLine | AC | 0 | 400 | 30 | New | 4 | 18 | Interconnection Portugal-Spain | Beariz (ES) - Fontefria (ES) | New double circuit 400kV OHL between Beariz (ES) - Fontefria (ES). | 4 |  | 11-2025 | 2025 | 1 | REN and Red Eléctrica | 1 | XX | XX | New | 2016 | 2025 | 9 | 11 | ESP;PRT | Beariz | Fontefria | 42.4865 | -8.2876 | 42.387 | -7.9464
498 | 2022 | 2022 | [2022] | 1804 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1119 | 1804 | Bisamberg (AT) - Wien SO (AT) - Parndorf (AT) | Bisamberg (AT) - Wien SO (AT) - Parndorf (AT) | Reinforcement/Upgrade 220-kV Overhead Line | 1 | New Investment |  | 12-2031 | 2031 | 1 | Austrian Power Grid |  | 1 | 0 | Bisamberg (AT) | Parndorf (AT) | ACTransmissionLine | AC | 0 | 380 | 85 | Upgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2031 | 2031 | 0 | 9 | AUT | Bisamberg | Parndorf | 48.3317 | 16.3616 | 47.9974 | 16.8608
499 | 2022 | 2026 | [2022, 2024, 2026] | 1805 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1121 | 1805 | Hessenberg (AT) - Weißenbach (AT) | Hessenberg (AT) - Weißenbach (AT) | Reinforcement/Upgrade 220-kV Overheadline | 2 | New Investment |  | 12-2029 | 2029 | 1 | Austrian Power Grid |  | 1 | 0 | Hessenberg (AT) | Weißenbach (AT) | ACTransmissionLine | AC | 0 | 220 | 71 | Upgrade | 1121 | 1805 | 220-kV Hessenberg (AT) - Weißenbach (AT) | 220-kV Hessenberg (AT) - Weißenbach (AT) | Reinforcement/Upgrade 220-kV Overheadline | 2 | New Investment |  | 12-2030 | 2030 | 1 | Austrian Power Grid |  | 1 | 0 | Hessenberg (AT) | Weißenbach (AT) | ACTransmissionLine | AC | 0 | 220 | 71 | Upgrade | 1121 | 1805 | 220-kV Hessenberg (AT) - Weißenbach (AT) | 220-kV Hessenberg (AT) - Weißenbach (AT) | Reinforcement/Upgrade 220-kV Overheadline | 2 |  | 12-2031 | 2031 | 1 | Austrian Power Grid | 0 | XX | XX | Upgrade | 2029 | 2031 | 2 | 9 | AUT | Hessenberg | Weißenbach | 47.4 | 14.9992 | 47.7998 | 13.5361
500 | 2022 | 2022 | [2022] | 1806 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1120 | 1806 | Wien SO (AT) – Ternitz (AT) – Hessenberg (AT) | Wien SO (AT) – Ternitz (AT) – Hessenberg (AT) | Reinforcement/Upgrade 220-kV Overhead Line | 1 | New Investment |  | 12-2033 | 2033 | 1 | Austrian Power Grid |  | 1 | 0 | Wien SO (AT) | Hessenberg (AT) | ACTransmissionLine | AC | 0 | 220 | 156 | Upgrade | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2033 | 2033 | 0 | 11 | AUT | Wien So | Hessenberg | 48.2084 | 16.3725 | 47.4 | 14.9992
501 | 2022 | 2026 | [2022, 2024, 2026] | 1808 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1125 | 1808 | Offshore Wind Connection Occitanie | AO6 Occitanie | HVAC 225 kV offshore connection | 1 | New Investment |  | 09-2030 | 2030 | 1 | RTE |  | 1 | 0 | Tbd | Tbd | OffshoreACTransmissionCable | AC | 0 | 225 | 70 | New | 1125 | 1808 | Offshore Wind Connection Occitanie | AO6 Occitanie | HVAC 225 kV offshore platform + onshore and offshore cables + onshore substation | 2 | Investment on time |  | 03-2031 | 2031 | 1 | RTE | 6.1 | 1 | 0 | OSS TRAMONTANE | Liviere | OffshoreACTransmissionCable | AC | 0 | 225 | 60 | New | 1125 | 1808 | Offshore Wind Connection Occitanie (Narbonnaise) | AO6 Occitanie (Narbonnaise) | HVAC offshore platform + HVAC onshore and offshore cables + HVAC onshore substation | 2 |  | 12-2032 | 2032 | 1 | RTE | 0 | XX | XX | New | 2030 | 2032 | 2 | 10 | FRA | Oss Tramontane | Liviere |  |  | 43.7723 | 4.181
502 | 2022 | 2026 | [2022, 2024, 2026] | 1809 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1126 | 1809 | Offshore Wind Connection PACA | AO6 Occitanie | HVAC 225 kV offshore connection | 1 | New Investment |  | 09-2030 | 2030 | 1 | RTE |  | 1 | 0 | Tbd | Tbd | OffshoreACTransmissionCable | AC | 0 | 225 | 70 | New | 1126 | 1809 | Offshore Wind Connection PACA | AO6 Occitanie | HVAC 225 kV offshore platform + onshore and offshore cables + onshore substation | 2 | Investment on time |  | 12-2031 | 2031 | 1 | RTE | 6.2 | 1 | 0 | OSS MISTRAL | Lavera | OffshoreACTransmissionCable | AC | 0 | 225 | 60 | New | 1126 | 1809 | Offshore Wind Connection PACA (Golfe de Fos) | AO6 PACA (Golfe de Fos) | HVAC offshore platform + HVAC onshore and offshore cables + HVAC onshore substation | 2 |  | 12-2032 | 2032 | 1 | RTE | 0 | XX | XX | New | 2030 | 2032 | 2 | 10 | FRA | Oss Mistral | Lavera |  |  | 43.7893 | 7.2664
503 | 2022 | 2026 | [2022, 2024, 2026] | 1810 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1122 | 1810 | Offshore Wind connection Centre Manche 1 | HVDC converter stations and cables | HVDC offshore platform, onshore converter station, hvdc cables | 1 | New Investment |  | 09-2031 | 2031 | 1 | RTE |  | 1 | 0 | Centre Manche 1 | Menuel | OffshoreSubstation | DC | 1250 | 320 | 100 | New | 1122 | 1810 | Offshore Wind farm connection Centre Manche 1 | CM1 Offshore wind farm HVDC grid connection | HVDC offshore platform with converter station + onshore converter station + HVDC onshore & offshore cables+ onshore AC transmission cable | 2 | Investment on time |  | 03-2032 | 2032 | 1 | RTE | 4.3 | 1 | 0 | Centre Manche 1 | Menuel | DCTransmissionLine | DC | 1250 | 320 | 100 | New | 1122 | 1810 | Offshore Wind connection Centre Manche 1 | Offshore wind connection Centre Manche 1 | HVDC offshore platform with converter station + HVDC onshore converter station + HVDC onshore & offshore cables + onshore AC transmission cable |  |  | 12-2032 | 2032 | 1 | RTE | 0 | XX | XX | New | 2031 | 2032 | 1 | 10 | FRA | Manche | Menuel | 49.0919 | -1.2455 | 49.4974 | -1.6142
504 | 2022 | 2026 | [2022, 2024, 2026] | 1811 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1123 | 1811 | Offshore Wind Connection Centre Manche 2 | Offshore Wind Connection Centre Manche 2 | HVDC offshore platform + onshore station + HVDC onshore & offshore cables | 1 | New Investment |  | 09-2032 | 2032 | 1 | RTE |  | 1 | 0 | Centre Manche 2 | Tourbe | OffshoreSubstation | DC | 1250 | 320 | 100 | New | 1123 | 1811 | Offshore Wind farm connection Centre Manche 2 | Offshore Wind Connection Centre Manche 2 | HVDC offshore platform with converter station + onshore converter station + HVDC onshore & offshore cables+ offshore AC transmission cable | 2 | Investment on time |  | 09-2032 | 2032 | 1 | RTE | 4.4 | 1 | 0 | Centre Manche 2 | Tourbe | OffshoreSubstation | DC | 1250 | 320 | 100 | New | 1123 | 1811 | Offshore Wind connection Centre Manche 2 | Offshore Wind Connection Centre Manche 2 | HVDC offshore platform with converter station + HVDC onshore converter station + HVDC onshore & offshore cables + offshore AC transmission cable |  |  | 12-2033 | 2033 | 1 | RTE | 0 | XX | XX | New | 2032 | 2033 | 1 | 11 | FRA | Manche | Tourbe | 49.0919 | -1.2455 | 49.1021 | 4.67
505 | 2022 | 2026 | [2022, 2024, 2026] | 1812 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1124 | 1812 | Offshore Wind Connection South Britanny | Offshore Wind Connection South Britanny | HVAC offshore platform + onshore and offshore cables + onshore substation | 1 | New Investment |  | 11-2029 | 2029 | 1 | RTE |  | 1 | 0 | Bretagne Sud | tbd | OffshoreSubstation | AC | 0 | 225 | 70 | New | 1124 | 1812 | Offshore Wind Connection South Britanny | Offshore Wind Connection South Britanny | HVAC offshore platform + onshore and offshore cables + onshore substation | 2 | Investment on time |  | 09-2030 | 2030 | 1 | RTE | 8.1 | 1 | 0 | Bretagne Sud | Pluvigner | OffshoreACTransmissionCable | AC | 0 | 225 | 80 | New | 1124 | 1812 | Offshore Wind Connection South Brittany | Offshore Wind Connection South Brittany | HVAC offshore platform + HVAC onshore and offshore cables + HVAC onshore substation |  |  | 12-2032 | 2032 | 1 | RTE | 0 | XX | XX | New | 2029 | 2032 | 3 | 10 | FRA | Bretagne Sud | Pluvigner |  |  | 47.7771 | -3.0096
506 | 2022 | 2026 | [2022, 2024, 2026] | 1813 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 1127 | 1813 | Offshore Wind Connection South Atlantic | Offshore wind connection South Atlantic | High voltage wind farm connection between 500 MW and 2 GW, including ˜100 km of underground cables, 2 substations (offshore and inland) and reactive compensation substation or converting HVDC/HVAC substation. Ongoing public debate to define the location of the offshore wind farm and its production capacity. Therefore the characteristics of the electrical connection are not defined yet. | 1 | New Investment |  | 12-2030 | 2030 | 1 | RTE |  | 1 | 0 | TBD | TBD | OffshoreDCTransmissionCable | DC | 0 | 0 | 0 | New | 1127 | 1813 | Offshore Wind Connection South Atlantic Oléron 1 | HVDC converter stations and cables (substations) | HVDC offshore platform, onshore converter station, hvdc cables | 2 | Investment on time |  | 03-2032 | 2032 | 1 | RTE | 8.2 | 1 | 0 | Oléron 1 substation | Grandzay | OffshoreSubstation | DC | 0 | 320 | 140 | New | 1127 | 1813 | Offshore Wind Connection South Atlantic Oléron 1 | Offshore wind connection South Atlantic Oléron 1 | HVDC offshore platform with converter station + onshore converter station + HVDC onshore & offshore cables | 2 |  | 12-2033 | 2033 | 1 | RTE | 0 | XX | XX | New | 2030 | 2033 | 3 | 11 | FRA | Oléron | Grandzay | 45.9438 | -1.3061
507 | 2022 | 2024 | [2022, 2024] | 1815 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 335 | 1815 | North Sea Wind Power Hub | Dutch Hub | Hub installation suitable to connect 4GW of HVDC systems to Dutch shore and up to 4W of nearby offshore wind. Dutch hub is connected to the Danish and German hub with 2 GW HVDC systems each. | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 1.19 | 1 | 1 | 0 | 0 | OffshoreSubstation | AC | 0 | 0 | 0 | New | 335 | 1815 | North Sea Wind Power Hub | Dutch Hub | Hub installation suitable to connect 4GW of HVDC systems to Dutch shore and up to 4W of nearby offshore wind. Dutch hub is connected to the Danish and German hub with 2 GW HVDC systems each. | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 4.1 | 1 | 1 | 0 | 0 | OffshoreSubstation | AC | 0 | 0 | 0 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2035 | 2035 | 0 | 13 | DEU;DNK;NLD
508 | 2022 | 2024 | [2022, 2024] | 1816 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 335 | 1816 | North Sea Wind Power Hub | German Hub | Hub installation suitable to connect 6 GW of HVDC systems to German shore and up to 6 GW of nearby offshore wind. German hub is connected to the Danish and Dutch hub with 2 GW HVDC systems each. | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 1.19 | 1 | 1 | 0 | 0 | OffshoreSubstation | AC | 0 | 0 | 0 | New | 335 | 1816 | North Sea Wind Power Hub | German Hub | Hub installation suitable to connect 6 GW of HVDC systems to German shore and up to 6 GW of nearby offshore wind. German hub is connected to the Danish and Dutch hub with 2 GW HVDC systems each. | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 4.1 | 1 | 1 | 0 | 0 | OffshoreSubstation | AC | 0 | 0 | 0 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2035 | 2035 | 0 | 13 | DEU;DNK;NLD
509 | 2022 | 2024 | [2022, 2024] | 1817 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 335 | 1817 | North Sea Wind Power Hub | Interconnection Danish hub to Dutch hub | One of three HVDC connectors including substations interfacing 2 of the 3 hubs | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 1.19 | 0 | 1 | Danish hub | Dutch hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 351 | New | 335 | 1817 | North Sea Wind Power Hub | Interconnection Danish hub to Dutch hub | One of three HVDC connectors including substations interfacing 2 of the 3 hubs | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 4.1 | 0 | 1 | Danish hub | Dutch hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 351 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2035 | 2035 | 0 | 13 | DEU;DNK;NLD | Danish | Dutch
510 | 2022 | 2024 | [2022, 2024] | 1818 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 335 | 1818 | North Sea Wind Power Hub | Interconnection Danish hub to German hub | One of three HVDC connectors including substations interfacing 2 of the 3 hubs | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 1.19 | 0 | 1 | Danish hub | German hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 226 | New | 335 | 1818 | North Sea Wind Power Hub | Interconnection Danish hub to German hub | One of three HVDC connectors including substations interfacing 2 of the 3 hubs | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 4.1 | 0 | 1 | Danish hub | German hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 226 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2035 | 2035 | 0 | 13 | DEU;DNK;NLD | Danish | German
511 | 2022 | 2024 | [2022, 2024] | 1819 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 335 | 1819 | North Sea Wind Power Hub | Interconnection Dutch hub to German hub | One of three HVDC connectors including substations interfacing 2 of the 3 hubs | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 1.19 | 0 | 1 | Dutch hub | German hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 125 | New | 335 | 1819 | North Sea Wind Power Hub | Interconnection Dutch hub to German hub | One of three HVDC connectors including substations interfacing 2 of the 3 hubs | 1 | Investment on time |  | 01-2035 | 2035 | 1 | Energinet.dk, TenneT-NL, TenneT-DE | 4.1 | 0 | 1 | Dutch hub | German hub | OffshoreDCTransmissionCable | DC | 2000 | 525 | 125 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2035 | 2035 | 0 | 13 | DEU;DNK;NLD | Dutch | German
512 | 2022 | 2026 | [2022, 2024, 2026] | 1827 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 144 | 1827 | Mid Continental East corridor | Upgrade of the existing 220kV double circuit OHL Arad -Timisoara - Sacalaz to 400kV | Upgrade of the existing 220 kV AC double circuit line (OHL) Arad-Timisoara/Sacalaz to 400 kV on 67 km of which: 14 km of line will be build single circuit between Sacalaz-C.Aradului-""connection point"", 11 km single circuit from Timisoara to ""connection point"" and the rest 42 km of the line will be double circuit from ""connection point"" to Arad. The investment contains also the 400/110kV substation Sacalaz and the extension of substation 400kV Arad. | 3 | Rescheduled |  | 12-2029 | 2029 | 1 | EMS, Transelectrica | 3.22 | 0 | 1 | Arad(RO) | Timisoara-Sacalaz(RO) | ACTransmissionLine | AC | 0 | 400 | 109 | MostlyNew | 144 | 1827 | Mid Continental East corridor | Upgrade of the existing 220kV double circuit OHL Arad -Timisoara - Sacalaz to 400kV | Upgrade of the existing 220 kV AC double circuit line (OHL) Arad-Timisoara/Sacalaz to 400 kV on 67 km of which: 14 km of line will be build single circuit between Sacalaz-C.Aradului-""connection point"", 11 km single circuit from Timisoara to ""connection point"" and the rest 42 km of the line will be double circuit from ""connection point"" to Arad. The investment contains the extension of substation 400kV Arad. | 3 | Rescheduled |  | 12-2029 | 2029 | 1 | EMS, Transelectrica | 3.22 Cluster Romania-Serbia [currently known as "Mid Continental East corridor''] | 0 | 1 | Arad (RO) | Timisoara-Sacalaz(RO) | ACTransmissionLine | AC | 0 | 400 | 109 | MostlyNew | 144 | 1827 | Mid Continental East corridor | Upgrade of the existing 220kV double circuit OHL Arad -Timisoara - Sacalaz to 400kV | Upgrade of the existing 220 kV AC double circuit line (OHL) Arad-Timisoara/Sacalaz to 400 kV on 67 km of which: 14 km of line will be build single circuit between Sacalaz-C.Aradului-""connection point"", 11 km single circuit from Timisoara to ""connection point"" and the rest 42 km of the line will be double circuit from ""connection point"" to Arad. The investment contains the extension of substation 400kV Arad. | 4 |  | 12-2029 | 2029 | 1 | EMS, Transelectrica | 1 | XX | XX | Mostly new | 2029 | 2029 | 0 | 7 | ROU;SRB | Arad | Timisoara-Sacalaz
513 | 2022 | 2026 | [2022, 2024, 2026] | 1832 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 259 | 1832 | HU-RO | RO1 | New 400/220 kV transformer in substation Rosiori | 2 | Investment on time |  | 12-2027 | 2027 | 1 | MAVIR, Transelectrica |  | 0 | 1 | Rosiori (RO) | Rosiori (RO) | Transformer | AC | 0 | 0 | 0 | MostlyNew | 259 | 1832 | HU-RO | New 400/220 kV transformer in substation Rosiori (RO) | New 400/220 kV transformer in substation Rosiori | 2 | Investment on time |  | 12-2027 | 2027 | 1 | MAVIR, Transelectrica | 2.5.1, 2.5.2, 2.5.3, 2.5.4, 2.5.5 | 0 | 1 | Rosiori (RO) | Rosiori (RO) | Transformer | AC | 0 | 0 | 0 | MostlyNew | 259 | 1832 | HU-RO | New 400/220 kV transformer in substation Rosiori (RO) | New 400/220 kV transformer in substation Rosiori | 2 |  | 12-2028 | 2028 | 1 | MAVIR, Transelectrica | 1 | XX | XX | Mostly new | 2027 | 2028 | 1 | 6 | HUN;ROU | Rosiori | Rosiori | 47.2568 | 21.9521 | 47.2568 | 21.9521
514 | 2022 | 2026 | [2022, 2024, 2026] | 1833 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 259 | 1833 | HU-RO | RO2 | Reconductoring 220 kV OH line Urechesti-Tg. Jiu | 2 | Investment on time |  | 12-2028 | 2028 | 1 | MAVIR, Transelectrica |  | 0 | 1 | Urechesti (RO) | Targu Jiu (RO) | ACTransmissionLine | AC | 0 | 400 | 18 | MostlyNew | 259 | 1833 | HU-RO | Reconductoring of 220 kV OHL Urechesti (RO) -Targu Jiu Nord (RO) | Reconductoring 220 kV OH line Urechesti-Tg. Jiu Nord | 2 | Investment on time |  | 12-2028 | 2028 | 1 | MAVIR, Transelectrica | 2.5.1, 2.5.2, 2.5.3, 2.5.4, 2.5.5 | 0 | 1 | Urechesti (RO) | Targu Jiu Nord (RO) | ACTransmissionLine | AC | 0 | 220 | 22 | MostlyNew | 259 | 1833 | HU-RO | Reconductoring of 220 kV OHL Urechesti (RO) -Targu Jiu Nord (RO) | Reconductoring 220 kV OH line Urechesti-Tg. Jiu Nord | 2 |  | 12-2028 | 2028 | 1 | MAVIR, Transelectrica | 1 | XX | XX | Mostly new | 2028 | 2028 | 0 | 6 | HUN;ROU | Urechesti | Targu Jiu Nord | 45.6152 | 27.1107 | 44.3577 | 23.769
515 | 2022 | 2026 | [2022, 2024, 2026] | 1834 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 259 | 1834 | HU-RO | RO3 | Reconductoring 220 kV OH line Tg. Jiu-Paroseni | 2 | Investment on time |  | 12-2028 | 2028 | 1 | MAVIR, Transelectrica |  | 0 | 1 | Targu Jiu (RO) | Paroseni (RO) | ACTransmissionLine | AC | 0 | 400 | 38 | MostlyNew | 259 | 1834 | HU-RO | Reconductoring of 220 kV OHL Targu Jiu Nord (RO)- Paroseni (RO) | Reconductoring 220 kV OH line Tg. Jiu Nord - Paroseni | 2 | Investment on time |  | 12-2028 | 2028 | 1 | MAVIR, Transelectrica | 2.5.1, 2.5.2, 2.5.3, 2.5.4, 2.5.5 | 0 | 1 | Targu Jiu Nord (RO) | Paroseni (RO) | ACTransmissionLine | AC | 0 | 220 | 38 | MostlyNew | 259 | 1834 | HU-RO | Reconductoring of 220 kV OHL Targu Jiu Nord (RO)- Paroseni (RO) | Reconductoring 220 kV OH line Tg. Jiu Nord - Paroseni | 2 |  | 12-2028 | 2028 | 1 | MAVIR, Transelectrica | 1 | XX | XX | Mostly new | 2028 | 2028 | 0 | 6 | HUN;ROU | Targu Jiu Nord | Paroseni | 44.3577 | 23.769 | 45.3644 | 23.2612
516 | 2022 | 2026 | [2022, 2024, 2026] | 1835 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 259 | 1835 | HU-RO | RO4 | Reconductoring 220 kV OH line Paroseni- Baru Mare | 2 | Investment on time |  | 12-2028 | 2028 | 1 | MAVIR, Transelectrica |  | 0 | 1 | Paroseni (RO) | Baru Mare (RO) | ACTransmissionLine | AC | 0 | 400 | 20 | MostlyNew | 259 | 1835 | HU-RO | Reconductoring of 220 kV OHL Paroseni (RO)- Baru Mare (RO) | Reconductoring 220 kV OH line Paroseni- Baru Mare | 2 | Investment on time |  | 12-2028 | 2028 | 1 | MAVIR, Transelectrica | 2.5.1, 2.5.2, 2.5.3, 2.5.4, 2.5.5 | 0 | 1 | Paroseni (RO) | Baru Mare (RO) | ACTransmissionLine | AC | 0 | 220 | 20.2 | MostlyNew | 259 | 1835 | HU-RO | Reconductoring of 220 kV OHL Paroseni (RO)- Baru Mare (RO) | Reconductoring 220 kV OH line Paroseni- Baru Mare | 2 |  | 12-2028 | 2028 | 1 | MAVIR, Transelectrica | 1 | XX | XX | Mostly new | 2028 | 2028 | 0 | 6 | HUN;ROU | Paroseni | Baru Mare | 45.3644 | 23.2612 | 45.475 | 23.1449
517 | 2022 | 2026 | [2022, 2024, 2026] | 1836 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [10 empty] | 259 | 1836 | HU-RO | RO5 | Reconductoring 220 kV OH line Baru Mare-Hasdat | 2 | Investment on time |  | 12-2028 | 2028 | 1 | MAVIR, Transelectrica |  | 0 | 1 | Baru Mare (RO) | Hasdat (RO) | ACTransmissionLine | AC | 0 | 400 | 44 | MostlyNew | 259 | 1836 | HU-RO | Reconductoring of 220 kV OHL Baru Mare (RO) -Hasdat (RO) | Reconductoring 220 kV OH line Baru Mare-Hasdat | 2 | Investment on time |  | 12-2028 | 2028 | 1 | MAVIR, Transelectrica | 2.5.1, 2.5.2, 2.5.3, 2.5.4, 2.5.5 | 0 | 1 | Baru Mare (RO) | Hasdat (RO) | ACTransmissionLine | AC | 0 | 400 | 43.9 | MostlyNew | 259 | 1836 | HU-RO | Reconductoring of 220 kV OHL Baru Mare (RO) -Hasdat (RO) | Reconductoring 220 kV OH line Baru Mare-Hasdat | 2 |  | 12-2028 | 2028 | 1 | MAVIR, Transelectrica | 1 | XX | XX | Mostly new | 2028 | 2028 | 0 | 6 | HUN;ROU | Baru Mare | Hasdat | 45.475 | 23.1449 | 48.5291 | 21.348
518 | 2024 | 2026 | [2024, 2026] | 1838 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1134 | 1838 | GiLA | GiLA 1st circuit | 2 x 1200 MW HVDC 320 kV links including onshore and offshore cables +¨onshore converter stations | 1 | New Investment |  | 12-2033 | 2033 | 1 | RTE |  | 1 | 0 | Bordeaux area | Nantes area | DCTransmissionLine | DC | 1200 | 320 | 400 | New | 1134 | 1838 | GiLA | GiLA 1st circuit | 2 x 1200 MW HVDC 320 kV links including onshore and offshore cables + onshore converter stations | 1 |  | 04-2034 | 2034 | 1 | RTE | 0 | XX | XX | New | 2033 | 2034 | 1 | 10 | FRA | Bordeaux Area | Nantes Area
519 | 2024 | 2026 | [2024, 2026] | 1839 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 342 | 1839 | Central Balkan Corridor | New 400 kV SS Pozarevac 3 | New 400 kV SS Pozarevac 3 | 2 | New Investment | The need for this investment came after the detailed consideration of the need for connecting SS Jagodina 4 with the Kostolac and Banat regions. | 09-2030 | 2030 | 1 | JSC EMS, ESO EAD |  | 0 | 1 | SS Pozarevac 3 | SS Pozarevac 3 | OnshoreSubstation | AC | 0 | 400 | 0 | MostlyUpgrade | 342 | 1839 | Central Balkan Corridor | New 400 kV SS Požarevac 3 | New 400 kV SS Požarevac 3 | 2 |  | 09-2030 | 2030 | 1 | JSC EMS, ESO EAD | 1 | XX | XX | Mostly new | 2030 | 2030 | 0 | 6 | BGR;SRB | Pozarevac | Pozarevac | 44.62 | 21.1854 | 44.62 | 21.1854
520 | 2024 | 2026 | [2024, 2026] | 1840 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1074 | 1840 | Pannonian Corridor | Reconstruction of SS Subotica 3 | Reconstruction of SS Subotica 3 in the Serbian system. | 2 | New Investment | No delay yet. | 09-2030 | 2030 | 1 | EMS, MAVIR | 2.12 | 0 | 1 | SS Subotica 3 | SS Subotica 3 | OnshoreSubstation | AC | 0 | 400 | 0 | New | 1074 | 1840 | Pannonian Corridor | Reconstruction of SS Subotica 3 | Reconstruction of SS Subotica 3 in the Serbian system. |  |  | 09-2028 | 2028 | 1 | EMS, MAVIR | 1 | XX | XX | New | 2030 | 2028 | -2 | 4 | HUN;SRB | Subotica | Subotica | 46.1019 | 19.6685 | 46.1019 | 19.6685
521 | 2024 | 2026 | [2024, 2026] | 1844 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1145 | 1844 | 380-kV Obersielach (AT) - Hessenberg (AT) | 380-kV Obersielach (AT) - Hessenberg (AT) | Integration of large amounts of RES in the federted states of Styria and Carinthia. | 1 | New Investment |  | 12-2035 | 2035 | 1 | Austrian Power Grid |  | 1 | 0 | Obersielach (AT) | Hessenberg (AT) | ACTransmissionLine | AC | 0 | 380 | 119 | New | 1145 | 1844 | 380-kV Obersielach (AT) - Hessenberg (AT) | 380-kV Obersielach (AT) - Hessenberg (AT) | Integration of large amounts of RES in the federted states of Styria and Carinthia. | 1 |  | 12-2039 | 2039 | 1 | Austrian Power Grid | 0 | XX | XX | New | 2035 | 2039 | 4 | 15 | AUT | Obersielach | Hessenberg | 46.6631 | 14.684 | 47.4 | 14.9992
522 | 2024 | 2026 | [2024, 2026] | 1846 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 343 | 1846 | CSE1 New | New OHL 2x400 kV Lika - Tumbri | New OHL 2x400 kV Lika - Tumbri | 3 | New Investment |  | 12-2034 | 2034 | 1 | HOPS, NOS-BIH |  | 0 | 1 | SS Lika | SS Tumbri | ACTransmissionLine | AC | 0 | 400 | 111 | New | 343 | 1846 | CSE1 New | New OHL 2x400 kV Lika - Tumbri | New OHL 2x400 kV Lika - Tumbri |  |  | 12-2034 | 2034 | 1 | HOPS, NOS-BIH | 1 | XX | XX | New | 2034 | 2034 | 0 | 10 | BIH;HRV | Lika | Tumbri | 44.6259 | 15.3436 | 45.6745 | 15.8626
523 | 2024 | 2026 | [2024, 2026] | 1847 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1096 | 1847 | Beznau - Mettlen | Transformers Mettlen | Transformers | 4 | New Investment |  | 12-2026 | 2026 | 1 | Swissgrid |  | 0 | 0 | Mettlen 380 kV | Mettlen 220 kV | Transformer | AC | 0 | 380 | 1 | MostlyNew | 1096 | 1847 | Beznau - Mettlen | Transformer Mettlen | Transformer | 4 |  | 12-2026 | 2026 | 1 | Swissgrid | 0 | XX | XX | Mostly new | 2026 | 2026 | 0 | 2 | CHE | Mettlen | Mettlen | 47.5311 | 9.1236 | 47.5311 | 9.1236
524 | 2024 | 2026 | [2024, 2026] | 1854 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1139 | 1854 | 380-kV Westtirol (AT) – Zell/Ziller (AT) | 380-kV Westtirol (AT) – Zell/Ziller (AT) | 380-kV OHL | 1 | New Investment |  | 12-2037 | 2037 | 1 | Austrian Power Grid |  | 1 | 0 | Westtirol (AT) | Zell/Ziller (AT) | ACTransmissionLine | AC | 0 | 380 | 125 | New | 1139 | 1854 | 380-kV Westtirol (AT) – Zell/Ziller (AT) | 380-kV Westtirol (AT) – Zell/Ziller (AT) | 380-kV OHL | 1 |  | 12-2040 | 2040 | 1 | Austrian Power Grid | 0 | XX | XX | New | 2037 | 2040 | 3 | 16 | AUT | Westtirol | Zellziller | 47.2439 | 10.8743
525 | 2024 | 2026 | [2024, 2026] | 1855 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1140 | 1855 | 380-kV St. Peter (AT) - Dürnrohr (AT) | 380-kV St. Peter (AT) - Dürnrohr (AT) | 380-kV OHL | 1 | New Investment |  | 12-2037 | 2037 | 1 | Austrian Power Grid |  | 1 | 0 | St. Peter (AT) | Dürnrohr (AT) | ACTransmissionLine | AC | 0 | 380 | 276 | New | 1140 | 1855 | 380-kV St. Peter (AT) - Dürnrohr (AT) | 380-kV St. Peter (AT) - Dürnrohr (AT) | 380-kV OHL | 1 |  | 12-2039 | 2039 | 1 | Austrian Power Grid | 0 | XX | XX | New | 2037 | 2039 | 2 | 15 | AUT | St. Peter | Dürnrohr | 46.6202 | 14.335 | 48.3318 | 15.8991
526 | 2024 | 2026 | [2024, 2026] | 1856 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1153 | 1856 | PST romands | PST romands - Riddes (220 kV/220 kV) | PST on line Cornier - Riddes in the Riddes substation | 1 | New Investment |  | 12-2030 | 2030 | 1 | Swissgrid |  | 0 | 0 | Riddes 220 kV | Riddes 220 kV | PhaseShiftingTransformer | AC | 0 | 220 | 1 | New | 1153 | 1856 | PST romands | PST romands - Riddes (220 kV/220 kV) | PST on line Cornier - Riddes in the Riddes substation | 1 |  | 12-2031 | 2031 | 1 | Swissgrid | 0 | XX | XX | New | 2030 | 2031 | 1 | 7 | CHE | Riddes | Riddes | 46.1403 | 7.2375 | 46.1403 | 7.2375
527 | 2024 | 2026 | [2024, 2026] | 1857 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1153 | 1857 | PST romands | PST romands - Châtelard (380 kV/220 kV) | substituted PST transformer in the Châtelard substation | 1 | New Investment |  | 12-2030 | 2030 | 1 | Swissgrid |  | 0 | 0 | Châtelard 380 kV | Châtelard 220 kV | PhaseShiftingTransformer | AC | 0 | 380 | 1 | New | 1153 | 1857 | PST romands | PST romands - Châtelard (380 kV/220 kV) | substituted PST transformer in the Châtelard substation | 1 |  | 12-2033 | 2033 | 1 | Swissgrid | 0 | XX | XX | New | 2030 | 2033 | 3 | 9 | CHE | Châtelard | Châtelard | 46.4468 | 6.9011 | 46.4468 | 6.9011
528 | 2024 | 2026 | [2024, 2026] | 1858 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1153 | 1858 | PST romands | PST romands - St Triphon (220 kV/220 kV) | PST on line Cornier - St. Triphon in the St Triphon substation | 1 | New Investment |  | 12-2030 | 2030 | 1 | Swissgrid |  | 0 | 0 | St Triphon 220 kV | St Triphon 220 kV | PhaseShiftingTransformer | AC | 0 | 220 | 1 | New | 1153 | 1858 | PST romands | PST romands - St Triphon (220 kV/220 kV) | PST on line Cornier - St. Triphon in the St Triphon substation | 1 |  | 12-2031 | 2031 | 1 | Swissgrid | 0 | XX | XX | New | 2030 | 2031 | 1 | 7 | CHE | St Triphon | St Triphon | 46.2926 | 6.9785 | 46.2926 | 6.9785
529 | 2024 | 2026 | [2024, 2026] | 1859 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1153 | 1859 | PST romands | PST romands - Verbois (380 kV/220 kV) | new PST transformer in the Verbois substation | 1 | New Investment |  | 12-2030 | 2030 | 1 | Swissgrid |  | 1 | 0 | Verbois 380 kV | Verbois 220 kV | PhaseShiftingTransformer | AC | 0 | 380 | 1 | New | 1153 | 1859 | PST romands | PST romands - Verbois (380 kV/220 kV) | new PST transformer in the Verbois substation | 1 |  | 12-2032 | 2032 | 1 | Swissgrid | 0 | XX | XX | New | 2030 | 2032 | 2 | 8 | CHE | Verbois | Verbois | 46.193 | 6.0289 | 46.193 | 6.0289
530 | 2024 | 2026 | [2024, 2026] | 1860 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1138 | 1860 | 400 kV OHL Suceava (RO) - Balti (MD) | 400kV OHL Suceava-Balti | New 400kV interconnection OHL aims to enhance the transmission capacity along the East-West corridor in the South-Eastern and Central Europe, remove bottlenecks and integrate RES to the network. | 3 | New Investment |  | 12-2030 | 2030 | 1 | Transelectrica |  | 1 | 1 | Suceava | Balti | ACTransmissionLine | AC | 0 | 400 | 148 | New | 1138 | 1860 | 400 kV OHL Suceava (RO) - Balti (MD) | 400kV OHL Suceava-Balti | New 400kV interconnection OHL aims to enhance the transmission capacity along the East-West corridor in the South-Eastern and Central Europe, remove bottlenecks and integrate RES to the network. |  |  | 12-2030 | 2030 | 1 | Transelectrica | 1 | XX | XX | New | 2030 | 2030 | 0 | 6 | MDA;ROU | Suceava | Balti | 47.5327 | 25.8346
531 | 2024 | 2026 | [2024, 2026] | 1861 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1138 | 1861 | 400 kV OHL Suceava (RO) - Balti (MD) | 400/330 kV substation Balti | new transformer 400/330kV in Balti (Republic of Moldova) substation | 2 | New Investment |  | 12-2030 | 2030 | 1 | Transelectrica |  | 0 | 1 | Balti (RM) 400kV | Balti (RM) 330kV | OnshoreSubstation | AC | 0 | 0 | 0 | New | 1138 | 1861 | 400 kV OHL Suceava (RO) - Balti (MD) | 400/330 kV substation Balti | new transformer 400/330kV in Balti (Republic of Moldova) substation | 2 |  | 12-2030 | 2030 | 1 | Transelectrica | 1 | XX | XX | New | 2030 | 2030 | 0 | 6 | MDA;ROU | Balti | Balti
532 | 2024 | 2026 | [2024, 2026] | 1862 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1155 | 1862 | 380-kV Burgenland North (AT) - Sarasdorf (AT) - Greater Vienna (AT) | 380-kV Burgenland North (AT) - Sarasdorf (AT) - Greater Vienna (AT) | Integration of large amounts of industry and RES in the federal states of Lower Austria and Vienna. | 2 | New Investment |  | 12-2032 | 2032 | 1 | Austrian Power Grid |  | 1 | 0 | Burgenland North (AT) | Greater Vienna (AT) | ACTransmissionLine | AC | 0 | 380 | 62 | New | 1155 | 1862 | 380-kV Burgenland North (AT) - Sarasdorf (AT) - Greater Vienna (AT) | 380-kV Burgenland North (AT) - Sarasdorf (AT) - Greater Vienna (AT) | Integration of large amounts of industry and RES in the federal states of Lower Austria and Vienna. | 2 |  | 12-2033 | 2033 | 1 | Austrian Power Grid | 0 | XX | XX | New | 2032 | 2033 | 1 | 9 | AUT | Burgenland North | Greater Vienna
533 | 2024 | 2026 | [2024, 2026] | 1863 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1156 | 1863 | 380-kV Greater Vienna (AT) - Hessenberg (AT) | 380-kV Greater Vienna (AT) - Hessenberg (AT) | Integration of large amounts of industry and RES in the federal states of Styria, Lower Austria and Vienna. | 2 | New Investment |  | 12-2033 | 2033 | 1 | Austrian Power Grid |  | 1 | 0 | Hessenberg (AT) | Greater Vienna (AT | ACTransmissionLine | AC | 0 | 380 | 176 | New | 1156 | 1863 | 380-kV Greater Vienna (AT) - Hessenberg (AT) | 380-kV Greater Vienna (AT) - Hessenberg (AT) | Integration of large amounts of industry and RES in the federal states of Styria, Lower Austria and Vienna. | 2 |  | 12-2038 | 2038 | 1 | Austrian Power Grid | 0 | XX | XX | New | 2033 | 2038 | 5 | 14 | AUT | Hessenberg | Greater Vienna At | 47.4 | 14.9992
534 | 2024 | 2026 | [2024, 2026] | 1864 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 341 | 1864 | North CSE Corridor | Reconductoring of 220kV double circuit OHL Portile de Fier - Resita | Reconductoring of 220kV double circuit OHL Portile de Fier (Romania) - Resita (Romania) | 2 | New Investment |  | 12-2028 | 2028 | 1 | EMS, Transelectrica |  | 0 | 1 | Portile de Fier 220kV | Resita 220kV | ACTransmissionLine | AC | 0 | 220 | 116.55 | MostlyNew | 341 | 1864 | North CSE Corridor | Reconductoring of 220kV double circuit OHL Portile de Fier - Resita | Reconductoring of 220kV double circuit OHL Portile de Fier (Romania) - Resita (Romania) | 2 |  | 12-2028 | 2028 | 1 | EMS, Transelectrica | 1 | XX | XX | Mostly new | 2028 | 2028 | 0 | 4 | ROU;SRB | Portile De Fier | Resita | 46.6075 | 23.8328 | 45.289 | 21.8879
535 | 2024 | 2026 | [2024, 2026] | 1865 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 259 | 1865 | HU-RO | 2nd circuit of 400kV OHL Nadab (RO) - Bekescsaba (HU) | 2nd circuit of 400kV OHL Nadab (Romania) - Bekescsaba (Hungary) | 2 | New Investment |  | 12-2027 | 2027 | 1 | MAVIR, Transelectrica | 2.5.1, 2.5.2, 2.5.3, 2.5.4, 2.5.5 | 0 | 1 | Nadab | Bekescsaba | ACTransmissionLine | AC | 0 | 400 | 59.62 | MostlyNew | 259 | 1865 | HU-RO | 2nd circuit of 400kV OHL Nadab (RO) - Bekescsaba (HU) | 2nd circuit of 400kV OHL Nadab (Romania) - Bekescsaba (Hungary) | 2 |  | 01-2028 | 2028 | 1 | MAVIR, Transelectrica | 1 | XX | XX | Mostly new | 2027 | 2028 | 1 | 4 | HUN;ROU | Nadab | Bekescsaba | 46.4827 | 21.5111 | 46.6798 | 21.0985
536 | 2024 | 2026 | [2024, 2026] | 1868 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1159 | 1868 | 220-kV Bisamberg (AT) – Wien Südost (AT) | 220-kV Bisamberg (AT) – Wien Südost (AT) | RES Integration + 500 MW PV | 2 | New Investment |  | 12-2033 | 2033 | 1 | Austrian Power Grid |  | 1 | 0 | Bisamberg (AT) | Wien Südost (AT) | ACTransmissionLine | AC | 0 | 220 | 38 | MostlyUpgrade | 1159 | 1868 | 220-kV Bisamberg (AT) – Wien Südost (AT) | 220-kV Bisamberg (AT) – Wien Südost (AT) | RES Integration + 500 MW PV | 2 |  | 12-2027 | 2027 | 1 | Austrian Power Grid | 0 | XX | XX | Mostly upgrade | 2033 | 2027 | -6 | 3 | AUT | Bisamberg | Wien Südost | 48.3317 | 16.3616 | 48.1595 | 16.3956
537 | 2024 | 2026 | [2024, 2026] | 1869 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1158 | 1869 | 380-kV Bisamberg (AT) – Gaweinstal (AT) – Zaya (AT) | 380-kV Bisamberg (AT) – Gaweinstal (AT) – Zaya (AT) | RES Integration; 1.000 MW Wind + 1.000 MW PV | 1 | New Investment |  | 12-2037 | 2037 | 1 | Austrian Power Grid |  | 1 | 0 | Bisamberg (AT) | Zaya (AT) | ACTransmissionLine | AC | 0 | 380 | 48 | New | 1158 | 1869 | 380-kV Bisamberg (AT) – Gaweinstal (AT) – Zaya (AT) | 380-kV Bisamberg (AT) – Gaweinstal (AT) – Zaya (AT) | RES Integration; 1.000 MW Wind + 1.000 MW PV | 1 |  | 12-2035 | 2035 | 1 | Austrian Power Grid | 0 | XX | XX | New | 2037 | 2035 | -2 | 11 | AUT | Bisamberg | Zaya | 48.3317 | 16.3616 | 48.5724 | 16.6227
538 | 2026 | 2026 | [2026] | 1871 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1160 | 1871 | PST Riddes | PST on line Riddes – Pallazuit - Avise in the Riddes substation | PST on line Riddes – Pallazuit - Avise in the Riddes substation (220 kV/220 kV) | 4 |  | 12-2029 | 2029 | 1 | Swissgrid | 0 | XX | XX | New | 2029 | 2029 | 0 | 3 | CHE
539 | 2024 | 2026 | [2024, 2026] | 1878 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1161 | 1878 | Offshore Wind Connection South Atlantic Oléron 2 | HVDC converter stations Oléron2 | Connection of a 1.2 GW offshore wind farm to an offshore link | 1 | New Investment |  | 12-2035 | 2035 | 1 | RTE | 8.2 | 1 | 0 | Oléron 2 | Gironde Loire-Atlantique Link | OffshoreSubstation | DC | 1200 | 320 | 20 | New | 1161 | 1878 | Offshore Wind Connection South Atlantic Oléron 2 | Offshore wind connection Oléron 2 | HVDC offshore platform with converter station + HVDC offshore cables | 1 |  | 12-2035 | 2035 | 1 | RTE | 0 | XX | XX | New | 2035 | 2035 | 0 | 11 | FRA | Oléron | Gironde Loire-Atlantique Link | 45.9438 | -1.3061
540 | 2024 | 2026 | [2024, 2026] | 1879 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1162 | 1879 | Offshore Wind Connection Fécamp-Grand Large 1 | Offshore Wind Connection Fécamp-Grand Large 1 HVDC OSS + Onshore Converter Station + Cables | 525 kV Le Havre 1 HVDC terrestrial converter stations and OSS | 1 | New Investment |  | 12-2034 | 2034 | 1 | RTE |  | 1 | 0 | Le Havre 1 | Le Havre Port Jérôme area | OffshoreSubstation | DC | 2000 | 525 | 0 | New | 1162 | 1879 | Offshore Wind Connection Fécamp-Grand Large 1 | Offshore wind connection Fécamp - Grand Large 1 | HVDC offshore platform with converter station + onshore converter station + HVDC onshore & offshore cables | 1 |  | 12-2035 | 2035 | 1 | RTE | 0 | XX | XX | New | 2034 | 2035 | 1 | 11 | FRA | Le Havre | Le Havre Port Jérôme Area | 49.4939 | 0.10797
541 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 188 | Cancelled | 188 | New lines, extension of existing and erection of several 380/110kV-substations. Total line length: 130km. | 2 | long term |  | 1 | Kruckel (DE) | Dauersberg (DE) | 44 | 44. 188 | New lines, extension of existing and erection of several 380/110kV-substations. Total line length: 130km. | 2 | Progresses as planned | long term |  | 1 | Kruckel (DE) | Dauersberg (DE) | 44. 188 | 44. 188 | New lines, extension of existing and erection of several 380/110kV-substations. | 3 |  | 2020 | 2020 | 1 | Kruckel (DE) | Dauersberg (DE) | 135 | 188 | N-S Western DE_parallel lines | New 380 kV over head lines in existing rout. Extension of existing and erection of several 380/110kV-substations. | 3 | Investment on time | Progress as planned. | 2020 | 2020 | 1 | Kruckel (DE) | Dauersberg (DE) | 188 | New 380 kV over head lines in existing rout. Extension of existing and erection of several 380/110kV-substations. | 3 | Delayed | Delayed, due to public resistance and intricate construction planning. | 2021 | 2021 | 1 | Kruckel (DE) | Dauersberg (DE) | 135 | 188 | Grid Reinforcements in Western Germany | Kruckel - Dauersberg | New 380 kV over head lines in existing rout. Extension of existing and erection of several 380/110kV-substations. | 3 | Delayed | Delay due to long permitting process | 1/ 1/ 2021 | 2021 | 1 |  | 0 | Kruckel (DE) | Dauersberg (DE) | Overhead Line | AC | 774 | 380 | 110 | New | 135 | 188 | N-S Western DE_parallel lines | Kruckel - Dauersberg | 3 | Rescheduled | increased construction complexity | 1/ 1/ 2021 | 2021 | 1 |  | Kruckel (DE) | Dauersberg (DE) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2021 |  | 11 | DEU | Kruckel | Dauersberg | 51.4546 | 7.4154 | 50.7681 | 7.8427
542 | 2024 | 2026 | [2024, 2026] | 1881 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1163 | 1881 | Offshore Wind Connection Fécamp-Grand Large 2 | Offshore Wind Connection Fécamp-Grand Large 2 HVDC OSS + Onshore Converter Station + Cables | 525 kV Le Havre 2 HVDC terrestrial converter stations and OSS | 1 | New Investment |  | 12-2035 | 2035 | 1 | RTE |  | 1 | 0 | Le Havre 2 | Le Havre Port Jérôme area | OffshoreSubstation | DC | 2000 | 525 | 0 | New | 1163 | 1881 | Offshore Wind Connection Fécamp-Grand Large 2 | Offshore wind connection Fécamp - Grand Large 2 | HVDC offshore platform with converter station + onshore converter station + HVDC onshore & offshore cables | 1 |  | 12-2037 | 2037 | 1 | RTE | 0 | XX | XX | New | 2035 | 2037 | 2 | 13 | FRA | Le Havre | Le Havre Port Jérôme Area | 49.4939 | 0.10797
543 | 2024 | 2026 | [2024, 2026] | 1883 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1164 | 1883 | Offshore Wind Connection Golfe de Lion Centre | Offshore Wind Connection Golfe de Lion Centre HVDC OSS + Onshore Converter Station + Cables | 525 kV Fos HVDC terrestrial converter stations and OSS | 1 | New Investment |  | 12-2035 | 2035 | 1 | RTE |  | 1 | 0 | Fos | Fos sur Mer - Realtor area | OffshoreSubstation | DC | 2000 | 525 | 0 | New | 1164 | 1883 | Offshore Wind Connection Golfe du Lion Centre | Offshore Wind Connection Golfe du Lion Centre | HVDC offshore platform with converter station + onshore converter station + HVDC onshore & offshore cables | 1 |  | 12-2037 | 2037 | 1 | RTE | 0 | XX | XX | New | 2035 | 2037 | 2 | 13 | FRA | Fos | Fos Sur Mer - Realtor Area | 42.8722 | 0.73654
544 | 2024 | 2026 | [2024, 2026] | 1885 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1165 | 1885 | Offshore Wind Connection Golfe de Gascogne Sud | HVDC converter station Golfe de Gascogne Sud | Connection of a 1.2 GW offshore wind farm to an offshore link | 1 | New Investment |  | 12-2034 | 2034 | 1 | RTE |  | 1 | 0 | Charente-Maritime | Gironde Loire-Atlantique Link | OffshoreSubstation | DC | 1200 | 320 | 20 | New | 1165 | 1885 | Offshore Wind Connection Golfe de Gascogne Sud | Offshore wind connection Golfe de Gascogne Sud | HVDC offshore platform with converter station + HVDC offshore cables | 1 |  | 12-2037 | 2037 | 1 | RTE | 0 | XX | XX | New | 2034 | 2037 | 3 | 13 | FRA | Charente-Maritime | Gironde Loire-Atlantique Link | 45.7302 | -0.72129
545 | 2024 | 2026 | [2024, 2026] | 1886 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1088 | 1886 | Latvia and Estonia Hybrid Off-Shore interconnector | Internal new 330 kV connection between Lihula substation (EE) and Saaremaa hub (EE) | 330 kV OHLs and cable lines, new 330 kV substations | 1 | New Investment |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 5.1 | 0 | 1 | Lihula | western Saaremaa off-shore hub | ACTransmissionLine | AC | 0 | 330 | 160 | New | 1088 | 1886 | Latvia and Estonia Hybrid Off-Shore interconnector | Internal new 330 kV connection from Ranniku substation (EE) to Eastern Saaremaa (EE) | Two new 330 kV cable lines from new Ranniku 330 kV substation to new eastern Saaremaa 330 kV substation | 2 |  | 12-2033 | 2033 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 1 | XX | XX | New | 2035 | 2033 | -2 | 9 | EST;LVA | Lihula | Western Saaremaa Off-Shore | 58.6851 | 23.8288
546 | 2024 | 2026 | [2024, 2026] | 1887 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1088 | 1887 | Latvia and Estonia Hybrid Off-Shore interconnector | Internal new 330 kV OHL between Lihula (EE) and Paide (EE) | New overhead power line between Lihula and Paide 330 kV substations. | 1 | New Investment |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 5.1 | 0 | 1 | Lihula | Paide | ACTransmissionLine | AC | 0 | 330 | 90 | New | 1088 | 1887 | Latvia and Estonia Hybrid Off-Shore interconnector | Internal new 330 kV connection from Paide substation (EE) to Ranniku substation (EE) | New 330 kV OHL from existing Paide and Lihula 330 kV substations to new Ranniku 330 kV substation. Investment also includes construction of Paide and Lihula new 330 kV substations. | 2 |  | 12-2033 | 2033 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 1 | XX | XX | New | 2035 | 2033 | -2 | 9 | EST;LVA | Lihula | Paide | 58.6851 | 23.8288 | 58.8869 | 25.5699
547 | 2024 | 2024 | [2024] | 1888 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 227 | 1888 | Transbalkan Corridor | Equipping the 2nd circuit from SS Visegrad to SS Pljevlja | Equipping the 2nd circuit from SS Visegrad to SS Pljevlja | 3 | New Investment |  | 09-2030 | 2030 | 1 | EMS, NOS-BIH, CGES |  | 0 | 1 | SS Visegrad | SS Pljevlja | ACTransmissionLine | AC | 0 | 400 | 91 | MostlyNew | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2030 | 2030 | 0 | 6 | BIH;MNE;SRB | Visegrad | Pljevlja |  |  | 43.3562 | 19.3579
548 | 2024 | 2026 | [2024, 2026] | 1889 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1157 | 1889 | HG North Tyrrhenian Corridor | HVDC Milano-Montalto | HVDC Milano-Montalto | 2 | New Investment |  | 12-2030 | 2030 | 1 | Terna |  | 1 | 0 | Montalto | Avenza | DCTransmissionLine | DC | 2000 | 500 | 440 | New | 1157 | 1889 | HG North Tyrrhenian Corridor | HVDC Milano-Montalto | HVDC Milano-Montalto | 2 |  | 12-2034 | 2034 | 1 | Terna | 0 | XX | XX | New | 2030 | 2034 | 4 | 10 | ITA | Montalto | Avenza | 43.4985 | 11.6655 | 44.047 | 10.0622
549 | 2024 | 2026 | [2024, 2026] | 1913 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1166 | 1913 | HG Adriatic Corridor | HG Adriatic Corridor | HG Adriatic Corridor | 2 | New Investment |  | 12-2036 | 2036 | 1 | Terna |  | 1 | 0 | Foggia (IT) | Forlì (IT) | DCTransmissionLine | DC | 2000 | 500 | 500 | New | 1166 | 1913 | HG Adriatic Corridor | HG Adriatic Corridor | HG Adriatic Corridor | 2 |  | 12-2033 | 2033 | 1 | Terna | 0 | XX | XX | New | 2036 | 2033 | -3 | 9 | ITA | Foggia | Forlì | 41.5028 | 15.4529 | 44.2227 | 12.0413
550 | 2024 | 2026 | [2024, 2026] | 1917 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1167 | 1917 | HG Central link | HG Central link | HG Central link | 2 | New Investment |  | 12-2030 | 2030 | 1 | Terna |  | 1 | 0 | Villavalle (IT) | S. Barbara (IT) | DCTransmissionLine | AC | 0 | 220 | 150 | New | 1167 | 1917 | HG Central link | HG Central link | HG Central link | 2 |  | 12-2031 | 2031 | 1 | Terna | 0 | XX | XX | New | 2030 | 2031 | 1 | 7 | ITA | Villavalle | S. Barbara | 42.3432 | 14.1114 | 40.1806 | 15.2567
551 | 2024 | 2026 | [2024, 2026] | 1918 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1168 | 1918 | HG Ionian-Tyrrhenian Corridor | HG Ionian-Tyrrhenian Corridor:Ionian Link | HG Ionian-Tyrrhenian Corridor:Ionian Link | 2 | New Investment |  | 12-2035 | 2035 | 1 | Terna |  | 0 | 0 | Priolo (IT) | Rossano (IT) | DCTransmissionLine | DC | 1000 | 500 | 425 | New | 1168 | 1918 | HG Ionian-Tyrrhenian Corridor | HG Ionian-Tyrrhenian Corridor:Ionian Link | HG Ionian-Tyrrhenian Corridor:Ionian Link | 2 |  | 12-2039 | 2039 | 1 | Terna | 0 | XX | XX | New | 2035 | 2039 | 4 | 15 | ITA | Priolo | Rossano
552 | 2024 | 2026 | [2024, 2026] | 1919 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1168 | 1919 | HG Ionian-Tyrrhenian Corridor | HG Ionian-Tyrrhenian Corridor:Rossano-Montecorvino-Latina | HG Ionian-Tyrrhenian Corridor:Rossano-Montecorvino-Latina | 2 | New Investment |  | 12-2035 | 2035 | 1 | Terna |  | 1 | 0 | Rossano (IT) | Latina (IT) | DCTransmissionLine | DC | 2000 | 500 | 345 | New | 1168 | 1919 | HG Ionian-Tyrrhenian Corridor | HG Ionian-Tyrrhenian Corridor:Rossano-Latina | HG Ionian-Tyrrhenian Corridor:Rossano-Montecorvino-Latina | 2 |  | 12-2039 | 2039 | 1 | Terna | 0 | XX | XX | New | 2035 | 2039 | 4 | 15 | ITA | Rossano | Latina |  |  | 41.4595 | 13.0126
553 | 2024 | 2026 | [2024, 2026] | 1921 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1169 | 1921 | SAPEI 2 | SAPEI 2 | SAPEI 2 | 2 | New Investment |  | 12-2040 | 2040 | 1 | Terna |  | 1 | 0 | Selargius | Montalto di castro | OffshoreDCTransmissionCable | DC | 1000 | 500 | 500 | New | 1169 | 1921 | SAPEI 2 | SAPEI 2 | SAPEI 2 | 2 |  | 12-2040 | 2040 | 1 | Terna | 0 | XX | XX | New | 2040 | 2040 | 0 | 16 | ITA | Selargius | Montalto Di Castro | 39.257 | 9.1676 | 42.3515 | 11.6073
554 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 193 | Commissioned | 193 | New 380kV double-circuit OHL between the substations Lauchstädt-Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). | 4 | mid term |  | 1 | Halle/Saale (DE) | Schweinfurt (DE) | 45 | 45. 193 | New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see project 153). The Section Lauchstedt-Vieselbach has already been commissioned. Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is right downstream in the main load flow direction. The project will help to avoid loop flows through neighboring grids. | 3 | Investment partly completed, strong local public resistance- delay due to permitting process | mid term |  | 1 | Halle/Saale (DE) | Schweinfurt (DE) | 45. 193 | 45. 193 | New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see investment 153). The Section Lauchstedt-Vieselbach has already been commissioned. Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is right downstream in the main load flow direction. The project will help to avoid loop flows through neighboring grids. | 3 | Previously "mid term" is now updated to specific date. Partly under construction (section Vieselbach – Altenfeld). 3rd section (Altenfeld – Redwitz) in permitting process, long permitting process with strong public resistance. | 2015 | 2015 | 1 | Vieselbach (DE) | Redwitz (DE) | 205 | 193 | N-S transmission DE_par_line_1 | New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see investment 153). The Section Lauchstädt-Vieselbach has already been commissioned. Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is right downstream in the main load flow direction. The project will help to avoid loop flows through neighbouring grids. | 3 | Delayed | Previously "mid term" is now updated to specific date. Partly under construction (section Vieselbach – Altenfeld). 3rd section (Altenfeld – Redwitz) in permitting process, long permitting process with strong public resistance. | 2015 | 2015 | 1 | Vieselbach (DE) | Redwitz (DE) | 193 | New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see investment 153). The Section Lauchstädt-Vieselbach has already been commissioned. Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is right downstream in the main load flow direction. The project will help to avoid loop flows through neighboring grids. | 4 | Delayed | 3rd section (Altenfeld – Redwitz) is under construction now, long permitting process with strong public resistance. | 2016 | 2016 | 1 | Vieselbach (DE) | Redwitz (DE) | 205 | 193 | South-West Interconnector | Südwestkuppelleitung | New 380kV double-circuit OHL between the substations Vieselbach-Altenfeld-Redwitz with 215km length combined with upgrade between Redwitz and Grafenrheinfeld (see investment 153). The Sections Lauchstädt-Vieselbach and Vieselbach-Altenfeld has already been commissioned. Support of RES integration in Germany, annual redispatching cost reduction, maintaining of security of supply and support of the market development. The line crosses the former border between Eastern and Western Germany and is right downstream in the main load flow direction. The project will help to avoid loop flows through neighboring grids. | 4 | Delayed | 3rd section (Altenfeld – Redwitz) is under construction now, long permitting process with strong public resistance. | 1/ 1/ 2016 | 2016 | 1 |  | 0 | Vieselbach (DE) | Redwitz (DE) | Overhead Line | AC | 3583 | 380 | 92 | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2016 |  | 6 | DEU | Vieselbach | Redwitz | 50.9975 | 11.146 | 50.1692 | 11.2084
555 | 2024 | 2024 | [2024] | 1934 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1197 | 1934 | NU-Link Interconnector | NU-Link | Subsea HVDC Interconnector between GB and NL | 1 | New Investment |  | 12-2031 | 2031 | 1 | Frontier Power International Limited, Kansai Electric Power Company, TEPCO Power Grid Inc, Transnet BW |  | 1 | 1 | Mablethorpe | Moerdijk | OffshoreDCTransmissionCable | DC | 1200 | 525 | 330 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2031 | 2031 | 0 | 7 | GBR;NLD | Mablethorpe | Moerdijk | 53.3408 | 0.26068 | 51.6628 | 4.5256
556 | 2024 | 2026 | [2024, 2026] | 1935 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1185 | 1935 | South Coast Offshore Transmission Project | South Coast Offshore Transmission Project | While the project is at an early stage of development, to facilitate up to 900MW of new renewable generation, it is envisaged that the following infrastructure will be required: two new 220kV offshore platforms, two new 220kV onshore reactive compensation compounds / substations, two 220kV HVAC export transmission cables (consisting of both onshore and offshore elements comprising approximately 124km in total). | 1 | New Investment |  | 10-2030 | 2030 | 1 | EirGrid PLC |  | 1 | 0 | Two new offshore substation platforms located within the DMAP area (as identified in accompanying map). | Great Island substation and a new substation in Cork looping into the Aghada – Knockraha 220 kV 1 & 2 circuits (these are the leading onshore connection nodes at this time). | OffshoreSubstation | AC | 0 | 220 | 124 | New | 1185 | 1935 | Powering Up Offshore South Coast project | Powering Up Offshore South Coast project | While the project is at an early stage of development, to facilitate 900MW of new renewable generation, it is envisaged that the following infrastructure will be required: two new 220kV offshore platforms, two new 220kV onshore reactive compensation compounds, two 220kV HVAC export transmission cables (consisting of both onshore and offshore elements comprising approximately 148km in total). The use of the 220 kV voltage level is currently under assessment to ensure it can accommodate the required transmission capacity. However, the current cost estimates have been developed to reflect any potential adjustments to this specification. | 2 |  | 09-2033 | 2033 | 1 | EirGrid PLC | 0 | XX | XX | New | 2030 | 2033 | 3 | 9 | IRL | Two New Platforms Located Within The Dmap Area | Great Island And A New In Cork Looping Into The Aghada Knockraha Circuits
557 | 2024 | 2026 | [2024, 2026] | 1936 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1200 | 1936 | Hybrid interconnector Norway-Sørvest F Windfarm-Continent (DK, DE or BE) | Hybrid interconnector Norway-Sørvest F Windfarm (first leg) | One or more hybrid interconnectors connecting the Sørvest F windfarm area to Norway as well as to other countries around the North Sea. In the first phase we are planning for a 1400 MW hybrid interconnector, but a 2000 MW interconnector might as well be considered. At this stage the Danish, German and Belgian alternative are considered equal alternatives. Step 1 (1500 MW) of Sørvest F windfarm is planned awarded in Q4/2023 and radial connected. Step 2 is planned awarded in 2025 and will potential be hybrid connected. Further steps might be expected, as the potential of Sørvest F windfarms is in the range 6-12 GW. | 1 | New Investment |  | 12-2035 | 2035 | 1 | Statnett together with Energinet, TenneT Germany, Amprion and Elia |  | 1 | 1 | Kristiansand | Sørvest F windfarm | OffshoreDCTransmissionCable | DC | 1400 | 525 | 250 | New | 1200 | 1936 | Hybrid interconnector Norway-Sørvest F Windfarm-Continent (DK, DE, BE or NL) | Hybrid interconnector Norway-Sørvest F Windfarm (first leg) | One or more hybrid interconnectors connecting the Sørvest F windfarm area to Norway as well as to other countries around the North Sea. In the first phase we are planning for a 1400 MW hybrid interconnector, but a 2000 MW interconnector might as well be considered. At this stage the Danish, German and Belgian alternative are considered equal alternatives. Step 1 (1500 MW) of Sørvest F windfarm is planned awarded in Q4/2023 and radial connected. Step 2 is planned awarded in 2025 and will potential be hybrid connected. Further steps might be expected, as the potential of Sørvest F windfarms is in the range 6-12 GW. | 1 |  | 12-2035 | 2035 | 1 | Statnett together with Energinet, TenneT Germany, Amprion, TenneT Netherlands and Elia | 1 | XX | XX | New | 2035 | 2035 | 0 | 11 | BEL;DEU;DNK;NOR | Kristiansand | Sørvest F Windfarm | 58.0856 | 7.9319
558 | 2024 | 2026 | [2024, 2026] | 1937 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1200 | 1937 | Hybrid interconnector Norway-Sørvest F Windfarm-Continent (DK, DE or BE) | Hybrid interconnector Sørvest F Windfarm-Denmark (second leg, alt.1) | One or more hybrid interconnectors connecting the Sørvest F windfarm area to Norway as well as to other countries around the North Sea. In the first phase we are planning for a 1400 MW hybrid interconnector, but a 2000 MW interconnector might as well be considered. In the CBA, only one of the Continental countries might be CBA-assessed (for ENTSO-E to decide). At this stage the Danish, German and Belgian alternative are considered equal alternatives. Step 1 (1500 MW) of Sørvest F windfarm is planned awarded in Q4/2023 and radial connected. Step 2 is planned awarded in 2025 and will potential be hybrid connected. Further steps might be expected, as the potential of Sørvest F windfarms is in the range 6-12 GW. | 1 | New Investment |  | 12-2035 | 2035 | 1 | Statnett together with Energinet, TenneT Germany, Amprion and Elia |  | 0 | 1 | Sørvest F windfarm | Danish offshore island (to be decided) | OffshoreDCTransmissionCable | DC | 1400 | 525 | 200 | New | 1200 | 1937 | Hybrid interconnector Norway-Sørvest F Windfarm-Continent (DK, DE, BE or NL) | Hybrid interconnector Sørvest F Windfarm-Denmark (second leg, alt.1) | One or more hybrid interconnectors connecting the Sørvest F windfarm area to Norway as well as to other countries around the North Sea. In the first phase we are planning for a 1400 MW hybrid interconnector, but a 2000 MW interconnector might as well be considered. In the CBA, only one of the Continental countries might be CBA-assessed (for ENTSO-E to decide). At this stage the Danish, German and Belgian alternative are considered equal alternatives. Step 1 (1500 MW) of Sørvest F windfarm is planned awarded in Q4/2023 and radial connected. Step 2 is planned awarded in 2025 and will potential be hybrid connected. Further steps might be expected, as the potential of Sørvest F windfarms is in the range 6-12 GW. | 1 |  | 12-2035 | 2035 | 1 | Statnett together with Energinet, TenneT Germany, Amprion, TenneT Netherlands and Elia | 1 | XX | XX | New | 2035 | 2035 | 0 | 11 | BEL;DEU;DNK;NOR | Sørvest F Windfarm | Danish Island
559 | 2024 | 2026 | [2024, 2026] | 1938 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1200 | 1938 | Hybrid interconnector Norway-Sørvest F Windfarm-Continent (DK, DE or BE) | Hybrid interconnector Sørvest F Windfarm-Germany (second leg, alt.2) | Statnett is by the Norwegian Ministry given the task to plan for one or more hybrid interconnectors connecting the Sørvest F windfarm area to Norway as well as to other countries around the North Sea. MoUs are about to be signed between Statnett and TSOs of Denmark, Germany and Belgium aiming to develop one or more hybrid interconnectors. In the first phase we are planning for a 1400 MW hybrid interconnector, but a 2000 MW interconnector will also be evaluated. This is the alternative to Germany. Statnett, Amprion GmbH and TenneT TSO GmbH are currently investigating several options for the design of a possible hybrid interconnector between Norway and Germany. It is currently still open whether this is an offshore - offshore or offshore - onshore connection. Also several connection points are under consideration. | 1 | New Investment |  | 12-2035 | 2035 | 1 | Statnett together with Energinet, TenneT Germany, Amprion and Elia |  | 0 | 1 | Sørvest F windfarm | Germany (connection point to be decided) | OffshoreDCTransmissionCable | DC | 1400 | 525 | 350 | New | 1200 | 1938 | Hybrid interconnector Norway-Sørvest F Windfarm-Continent (DK, DE, BE or NL) | Hybrid interconnector Sørvest F Windfarm-Germany (second leg, alt.2) | Statnett is by the Norwegian Ministry given the task to plan for one or more hybrid interconnectors connecting the Sørvest F windfarm area to Norway as well as to other countries around the North Sea. MoUs are about to be signed between Statnett and TSOs of Denmark, Germany and Belgium aiming to develop one or more hybrid interconnectors. In the first phase we are planning for a 1400 MW hybrid interconnector, but a 2000 MW interconnector will also be evaluated. This is the alternative to Germany. Statnett, Amprion GmbH and TenneT TSO GmbH are currently investigating several options for the design of a possible hybrid interconnector between Norway and Germany. It is currently still open whether this is an offshore - offshore or offshore - onshore connection. Also several connection points are under consideration. | 1 |  | 12-2035 | 2035 | 1 | Statnett together with Energinet, TenneT Germany, Amprion, TenneT Netherlands and Elia | 1 | XX | XX | New | 2035 | 2035 | 0 | 11 | BEL;DEU;DNK;NOR | Sørvest F Windfarm | Germany
560 | 2024 | 2026 | [2024, 2026] | 1939 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1200 | 1939 | Hybrid interconnector Norway-Sørvest F Windfarm-Continent (DK, DE or BE) | Hybrid interconnector Sørvest F Windfarm-Belgium (second leg, alt.3) | One or more hybrid interconnectors connecting the Sørvest F windfarm area to Norway as well as to other countries around the North Sea. In the first phase we are planning for a 1400 MW hybrid interconnector, but a 2000 MW interconnector might as well be considered. In the CBA, only one of the Continental countries might be CBA-assessed (for ENTSO-E to decide). At this stage the Danish, German and Belgian alternative are considered equal alternatives. Step 1 (1500 MW) of Sørvest F windfarm is planned awarded in Q4/2023 and radial connected. Step 2 is planned awarded in 2025 and will potential be hybrid connected. Further steps might be expected, as the potential of Sørvest F windfarms is in the range 6-12 GW. | 1 | New Investment |  | 12-2035 | 2035 | 1 | Statnett together with Energinet, TenneT Germany, Amprion and Elia |  | 0 | 1 | Sørvest F windfarm | Belgium (connection point to be decided, Mercator as reference) | OffshoreDCTransmissionCable | DC | 1400 | 525 | 780 | New | 1200 | 1939 | Hybrid interconnector Norway-Sørvest F Windfarm-Continent (DK, DE, BE or NL) | Hybrid interconnector Sørvest F Windfarm-Belgium (second leg, alt.3) | One or more hybrid interconnectors connecting the Sørvest F windfarm area to Norway as well as to other countries around the North Sea. In the first phase we are planning for a 1400 MW hybrid interconnector, but a 2000 MW interconnector might as well be considered. In the CBA, only one of the Continental countries might be CBA-assessed (for ENTSO-E to decide). At this stage the Danish, German and Belgian alternative are considered equal alternatives. Step 1 (1500 MW) of Sørvest F windfarm is planned awarded in Q4/2023 and radial connected. Step 2 is planned awarded in 2025 and will potential be hybrid connected. Further steps might be expected, as the potential of Sørvest F windfarms is in the range 6-12 GW. | 1 |  | 12-2035 | 2035 | 1 | Statnett together with Energinet, TenneT Germany, Amprion, TenneT Netherlands and Elia | 1 | XX | XX | New | 2035 | 2035 | 0 | 11 | BEL;DEU;DNK;NOR | Sørvest F Windfarm | Belgium
561 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 194 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 46 | 194 | Offshore Wind Baltic Sea | Grid Connection of offshore wind farms ( using AC-technology). According to German law, the grid connection has to be constructed and operated by the TSO (50Hertz Transmission). | 3 | Investment on time | The investment is split into different stages with different commissioning dates (starting in 2017) depending on the predicted installed capacity of offshore wind. For further information see the national "Offshore Grid Development Plan" | 2031 | 2031 | 1 | OWF Cluster Baltic Sea East (DE) | Lüdershagen/Lubmin (DE) | 194 | Grid Connection of offshore wind farms ( using AC- technology). According to german law, the grid connection has to be constructed and operated by the TSO (50Hertz Transmission). | 4 | Investment on time | The investment is split into different stages with different commissioning dates (starting in 2017) depending on the predicted installed capacity of offshore wind. For further information see the national "Offshore Grid Development Plan" | 2031 | 2031 | 1 | OWF Cluster Baltic Sea East (DE) | Lüdershagen/ Lubmin (DE) | 242 | 194 | Offshore Wind Baltic Sea (I) | Offshore Wind Baltic Sea (I) | ​AC grid connections connecting Offshore Wind Farms in Cluster 1 of the Baltic Sea (see German Offshore Grid Development Plan). Cluster 1 is located north east of Rügen in the German Exclusive Economic Zone. According to german law, the grid connection has to be constructed and operated by the TSO (50Hertz Transmission). | 4 | Investment on time | The investment is split into different stages with different commissioning dates (starting in 2017) depending on the predicted installed capacity of offshore wind. For further informations see the national "Offshore Grid Development Plan" | 2018 | 2018 | 1 |  | 0 | OWF Cluster Baltic Sea East (DE) | Lubmin (DE) | Subsea Cable | AC | 750 | 220 | 115 | New | 242 | 194 | Offshore Wind Baltic Sea (I) | Offshore Connection Cluster 1 | 4 | Investment on time |  | 2019 | 2019 | 1 | 50Hertz Transmission | OWF Cluster Baltic Sea East (DE) | Lubmin (DE) | Subsea Cable | AC | 220 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2031 | 2019 | -12 | 5 | DEU | Owf Cluster Baltic Sea East | Lubmin |  |  | 54.1322 | 13.6138
562 | 2024 | 2026 | [2024, 2026] | 1940 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1201 | 1940 | Reinvestment of Skagerrak 1 and 2 | Interconnector Norway-Denmark | The existing interconnectors Skagerrak 1 and 2 (500 MW in total) were commissioned in 1976 and 1977 and are at the end of their technical life. The cables are expected to be in operation until 2026 with normal maintenance. The risk of failures is increasing and major repairs are not considered to be rational. The Norwegian TSO (Statnett) and the Danish TSO (Energinet) are considering to build a new 700 MW interconnector as a replacement of the ones that soon are expected to be decommissioned. MoU has been signed between the Statnett and Energinet. | 2 | New Investment |  | 12-2035 | 2035 | 1 | Statnett and Energinet |  | 1 | 1 | Kristiansand | Tjele | OffshoreDCTransmissionCable | DC | 700 | 525 | 249 | New | 1201 | 1940 | Reinvestment of Skagerrak 1 and 2 | Interconnector Norway-Denmark | The existing interconnectors Skagerrak 1 and 2 (500 MW in total) were commissioned in 1976 and 1977 and are at the end of their technical life. The cables are expected to be in operation until 2032. The risk of failures is increasing and major repairs are not considered to be rational. The Norwegian TSO (Statnett) and the Danish TSO (Energinet) are considering to build a new 700 MW interconnector as a replacement of the ones that soon are expected to be decommissioned. MoU has been signed between Statnett and Energinet. | 2 |  | 12-2039 | 2039 | 1 | Statnett and Energinet | 1 | XX | XX | New | 2035 | 2039 | 4 | 15 | DNK;NOR | Kristiansand | Tjele | 58.0856 | 7.9319 | 56.512 | 9.61
563 | 2024 | 2026 | [2024, 2026] | 1941 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1202 | 1941 | Increased capacity Norway-Finland, Back-to-Back | Back-to-Back converter Seidafjellet | Back-to-Back converter in the new Seidafjellet station (planned to replace the current Varangerbotn station) on the 220 kV line between Norway and Finland, the power flow will be better controlled and by this the cross-border capacity on existing 220 kV line Varangerbotn-Ivalo will be better utilised. | 2 | New Investment |  | 12-2030 | 2030 | 1 | Statnett and Fingrid |  | 1 | 1 | Seidafjellet | Seidafjellet | BackToBackSubstation | DC | 150 | 420 | 0 | New | 1202 | 1941 | Increased capacity Norway-Finland | Back-to-Back converter Seidafjellet (alt.1) | Back-to-Back converter in the new Seidafjellet station (planned to replace the current Varangerbotn station) on the 220 kV line between Norway and Finland, the power flow will be better controlled and by this the cross-border capacity on existing 220 kV line Varangerbotn-Ivalo will be better utilised. | 1 |  | 12-2033 | 2033 | 1 | Statnett and Fingrid | 1 | XX | XX | New | 2030 | 2033 | 3 | 9 | FIN;NOR | Seidafjellet | Seidafjellet | 70.2104 | 28.3503 | 70.2104 | 28.3503
564 | 2024 | 2026 | [2024, 2026] | 1942 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1096 | 1942 | Beznau - Mettlen | Transformer Lachmatt | Transformer | 4 | New Investment |  | 12-2026 | 2026 | 1 | Swissgrid |  | 0 | 0 | Lachmatt 380 kV | Lachmatt 220 kV | Transformer | AC | 0 | 380 | 1 | MostlyNew | 1096 | 1942 | Beznau - Mettlen | Transformer Lachmatt | Transformer | 4 |  | 12-2027 | 2027 | 1 | Swissgrid | 0 | XX | XX | Mostly new | 2026 | 2027 | 1 | 3 | CHE | Lachmatt | Lachmatt | 47.521 | 7.6699 | 47.521 | 7.6699
565 | 2024 | 2026 | [2024, 2026] | 1943 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1192 | 1943 | HansaLink - Phase 1 | Germany-UK Hybrid Interconnector - Phase1 | 2GW hybrid interconnector | 1 | New Investment |  | 10-2033 | 2033 | 1 | WindGrid |  | 1 | 1 | Fiddes | TBC | OffshoreDCTransmissionCable | DC | 2000 | 525 | 810 | New | 1192 | 1943 | HansaLink - Phase 1 | Germany-UK Hybrid Interconnector - Phase1 | 2GW hybrid interconnector | 1 |  | 10-2033 | 2033 | 1 | WindGrid | 1 | XX | XX | New | 2033 | 2033 | 0 | 9 | DEU;GBR | Fiddes | Tbc | 53.4559 | -2.2165
566 | 2024 | 2026 | [2024, 2026] | 1944 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1207 | 1944 | 380kV Niederstedem-Bertrange/Bofferdange | 380kV overhead Line Niederstedem-Bertrange | This projects helps to increase the cross border capacity between Germany and Luxemburg by upgrading an existing line from 220 kV to 380 kV. The additional capacity is needed to ensure security of supply in Luxemburg. | 2 | Investment on time |  | 12-2037 | 2037 | 1 | Amprion, Creos |  | 1 | 1 | Niederstedem | Bertrange | ACTransmissionLine | AC | 0 | 380 | 72.4 | Upgrade | 1207 | 1944 | 380kV Niederstedem-Bertrange/Bofferdange | 380kV overhead Line Niederstedem-Bertrange | This projects helps to increase the cross border capacity between Germany and Luxemburg by upgrading an existing line from 220 kV to 380 kV. The additional capacity is needed to ensure security of supply in Luxemburg. | 2 |  | 12-2037 | 2037 | 1 | Amprion, Creos | 1 | XX | XX | Upgrade | 2037 | 2037 | 0 | 13 | DEU;LUX | Niederstedem | Bertrange | 49.9303 | 6.4986 | 49.6106 | 6.0502
567 | 2024 | 2026 | [2024, 2026] | 1945 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1208 | 1945 | Medlink | Medlink (Algeria - Italy) - DC Link 1 | Medlink is a 4000 MW system composed of two links of 2000MW each, connecting Italy to North Africa. The link hereby described refers to the La Specia s/s (Italy) – Annaba (Algeria) and will be built in HVDC-VSC technology with an operating voltage of 525 kVdc. The link consists of a double bipole of 1 GW each equipped with sea electrodes, so to be able to operate at half power (500 MW) in case of fault of one pole. This is also favorable for the receiving system (Italy) where the application of the N-1 security criterion entails the loss of only 500 MW, which is fully compatible with the current reserve of the system. Design of the system can be subject to modification and revision during the detailed engineering phase. | 1 | New Investment |  | 06-2030 | 2030 | 1 | Zhero Europe B.V |  | 1 | 1 | Annaba (Algeria) - new | La Spezia (Italy) - existing | OffshoreDCTransmissionCable | DC | 2000 | 525 | 940 | New | 1208 | 1945 | Medlink | Medlink (Algeria - Italy) - DC Link 1 | Medlink is a 4000 MW system composed of two links of 2000MW each, connecting Italy to North Africa. The link hereby described refers to the La Specia s/s (Italy) – Annaba (Algeria) and will be built in HVDC-VSC technology with an operating voltage of 525 kVdc. The link consists of a double bipole of 1 GW each equipped with sea electrodes, so to be able to operate at half power (500 MW) in case of fault of one pole. This is also favorable for the receiving system (Italy) where the application of the N-1 security criterion entails the loss of only 500 MW, which is fully compatible with the current reserve of the system. Design of the system can be subject to modification and revision during the following phases of the development of the project. | 2 |  | 06-2030 | 2030 | 1 | Zhero Europe B.V | 1 | XX | XX | New | 2030 | 2030 | 0 | 6 | DZA;ITA;TUN | Annaba | La Spezia | 36.8982 | 7.7549 | 44.2384 | 9.6912
568 | 2024 | 2026 | [2024, 2026] | 1946 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1208 | 1946 | Medlink | Medlink (Tunisia - Italy) - DC Link 2 | Medlink is a 4000 MW system composed of two links of 2000MW each, connecting Italy to North Africa. The link hereby described refers to the Suvereto s/s (Italy) – Marsa Dhib (Tunisia) and will be built in HVDC-VSC technology with an operating voltage of 525 kVdc. The link consists of a double bipole of 1 GW each equipped with sea electrodes, so to be able to operate at half power (500 MW) in case of fault of one pole. This is also favorable for the receiving system (Italy) where the application of the N-1 security criterion entails the loss of only 500 MW, which is fully compatible with the current reserve of the system. Design of the system can be subject to modification and revision during the detailed engineering phase | 1 | New Investment |  | 06-2030 | 2030 | 1 | Zhero Europe B.V |  | 1 | 1 | Marsa Dhib (Tunisia) - New | Suvereto (Italy) - Existing | OffshoreDCTransmissionCable | DC | 2000 | 525 | 590 | New | 1208 | 1946 | Medlink | Medlink (Tunisia - Italy) - DC Link 2 | Medlink is a 4000 MW system composed of two links of 2000MW each, connecting Italy to North Africa. The link hereby described refers to the Suvereto s/s (Italy) – Marsa Dhib (Tunisia) and will be built in HVDC-VSC technology with an operating voltage of 525 kVdc. The link consists of a double bipole of 1 GW each equipped with sea electrodes, so to be able to operate at half power (500 MW) in case of fault of one pole. This is also favorable for the receiving system (Italy) where the application of the N-1 security criterion entails the loss of only 500 MW, which is fully compatible with the current reserve of the system. Design of the system can be subject to modification and revision during the following phases of the development of the project | 2 |  | 06-2030 | 2030 | 1 | Zhero Europe B.V | 1 | XX | XX | New | 2030 | 2030 | 0 | 6 | DZA;ITA;TUN | Marsa Dhib | Suvereto |  |  | 43.079 | 10.6787
569 | 2024 | 2026 | [2024, 2026] | 1947 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1208 | 1947 | Medlink | Medlink (Algeria - AC) | The RES generation site currently located in Touggourt region (Algeria) will be connected to the 2 GW HVDC link converter station in Annaba through 2 x 400kV double three-phase circuit AC lines and relate sub-stations. Data provided below refer to each single circuit. | 1 | New Investment |  | 06-2030 | 2030 | 1 | Zhero Europe B.V |  | 0 | 1 | Annaba | Tougourt | ACTransmissionLine | AC | 0 | 400 | 600 | New | 1208 | 1947 | Medlink | Medlink (Algeria - AC) | The RES generation site currently located in Langhouat region (Algeria) will be connected to the 2 GW HVDC link converter station in Annaba through 2 x 400kV double three-phase circuit AC lines and relate sub-stations. Data provided below refer to each single circuit. | 2 |  | 06-2030 | 2030 | 1 | Zhero Europe B.V | 1 | XX | XX | New | 2030 | 2030 | 0 | 6 | DZA;ITA;TUN | Annaba | Tougourt | 36.8982 | 7.7549 | 33.1054 | 6.0686
570 | 2024 | 2026 | [2024, 2026] | 1948 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1208 | 1948 | Medlink | Medlink (Tunisia - AC) | The RES generation site currently located in De Jebil area (Tunisia) will be connected to the 2 GW HVDC link converter station in Marsa Dhib through 2 x 400kV double three-phase circuit AC lines and relate sub-stations | 1 | New Investment |  | 06-2030 | 2030 | 1 | Zhero Europe B.V |  | 0 | 1 | De Jebil (Tunisia) | Marsa Dhib (Tunisia) | ACTransmissionLine | AC | 0 | 400 | 500 | New | 1208 | 1948 | Medlink | Medlink (Tunisia - AC) | The RES generation site currently located in De Jebil area (Tunisia) will be connected to the 2 GW HVDC link converter station in Marsa Dhib through 2 x 400kV double three-phase circuit AC lines and relate sub-stations | 2 |  | 06-2030 | 2030 | 1 | Zhero Europe B.V | 1 | XX | XX | New | 2030 | 2030 | 0 | 6 | DZA;ITA;TUN | De Jebil | Marsa Dhib | 33.0727 | 9.0814
571 | 2014 | 2015 | [2014, 2015] | 195 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 46 | 195 | Offshore Wind Baltic Sea | Grid Connection of offshore wind farms ( using AC-technology). According to German law, the grid connection has to be constructed and operated by the TSO (50Hertz Transmission). | 3 | Investment on time | The investment is split into different stages with different commissioning dates (starting in 2026) depending on the predicted installed capacity of offshore wind. For further information see the national "Offshore Grid Development Plan" | 2032 | 2032 | 1 | wind farm cluster Baltic Sea West (DE) | Bentwisch/Lüdershagen (DE) | 195 | Grid Connection of offshore wind farms ( using AC- technology). According to german law, the grid connection has to be constructed and operated by the TSO (50Hertz Transmission). | 3 | Investment on time | The investment is split into different stages with different commissioning dates (starting in 2026) depending on the predicted installed capacity of offshore wind. For further information see the national "Offshore Grid Development Plan" | 2032 | 2032 | 1 | wind farm cluster Baltic Sea West (DE) | Bentwisch/Lü dershagen (DE) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2032 | 2032 | 0 | 18 | DEU | Wind Farm Cluster Baltic Sea West | Bentwischlü Dershagen
572 | 2024 | 2026 | [2024, 2026] | 1953 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1209 | 1953 | Latvia and Lithuania cross-border strengthening project | Broceni - Varduva new cross-border line between Latvia and Lithuania | The new cross-border network interconnection between Broceni (LV) - Varduva (LT) | 1 | New Investment |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls and Litgrid AB |  | 1 | 1 | Broceni (LV) | Varduva (LT) | ACTransmissionLine | AC | 0 | 330 | 50 | New | 1209 | 1953 | Latvia and Lithuania cross-border strengthening project | New 330 kV cross-border line Broceni (LV)-Varduva (LT) | Construction of new 330 kV cross-border network interconnection between Broceni (LV) - Varduva (LT) | 2 |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls and Litgrid AB | 1 | XX | XX | Mostly new | 2035 | 2035 | 0 | 11 | LTU;LVA | Broceni | Varduva | 56.6845 | 22.5665 | 56.388 | 22.205
573 | 2024 | 2026 | [2024, 2026] | 1954 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1209 | 1954 | Latvia and Lithuania cross-border strengthening project | Cross-border network reinforcement Grobina (LV) - Derbenai (LT) | The reconstruction of the existing 330 kV OHL from substation Grobina in Latvia to substation Derbenai in Lithuania. The capacity increase on cross-border Latvia - Lithuania up to 300 MW. | 1 | New Investment |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls and Litgrid AB |  | 0 | 1 | Grobina (LV) | Derbenai (LT) | ACTransmissionLine | AC | 0 | 330 | 65 | New | 1209 | 1954 | Latvia and Lithuania cross-border strengthening project | Reinforcement of 330 kV cross-border line Grobina (LV)-Darbenai (LT) | The reconstruction of the existing 330 kV OHL from substation Grobina in Latvia to substation Darbenai in Lithuania. | 2 |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls and Litgrid AB | 1 | XX | XX | Mostly new | 2035 | 2035 | 0 | 11 | LTU;LVA | Grobina | Derbenai
574 | 2024 | 2026 | [2024, 2026] | 1955 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1153 | 1955 | PST romands | PST romands - Verbois (220 kV/220 kV #1) | PST on line Génissiat - Verbois #1 in the Verbois substation | 1 | New Investment |  | 12-2030 | 2030 | 1 | Swissgrid |  | 0 | 0 | Verbois 220 kV | Verbois 220 kV | PhaseShiftingTransformer | AC | 0 | 220 | 1 | New | 1153 | 1955 | PST romands | PST romands - Verbois (220 kV/220 kV #1) | PST on line Génissiat - Verbois #1 in the Verbois substation | 1 |  | 12-2032 | 2032 | 1 | Swissgrid | 0 | XX | XX | New | 2030 | 2032 | 2 | 8 | CHE | Verbois | Verbois | 46.193 | 6.0289 | 46.193 | 6.0289
575 | 2024 | 2026 | [2024, 2026] | 1956 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1153 | 1956 | PST romands | PST romands - Verbois (220 kV/220 kV #2) | PST on line Génissiat - Verbois #2 in the Verbois substation | 1 | New Investment |  | 12-2030 | 2030 | 1 | Swissgrid |  | 0 | 0 | Verbois 220 kV | Verbois 220 kV | PhaseShiftingTransformer | AC | 0 | 220 | 1 | New | 1153 | 1956 | PST romands | PST romands - Verbois (220 kV/220 kV #2) | PST on line Génissiat - Verbois #2 in the Verbois substation | 1 |  | 12-2032 | 2032 | 1 | Swissgrid | 0 | XX | XX | New | 2030 | 2032 | 2 | 8 | CHE | Verbois | Verbois | 46.193 | 6.0289 | 46.193 | 6.0289
576 | 2024 | 2026 | [2024, 2026] | 1957 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1210 | 1957 | APOLLO-LINK | APOLLO-LINK | The project is a 2GW HVDC Interconnection with two converters operating a VSC technology at 525 kV. It consists of approx. 660 km of subsea and 40km of onshore transmission cable. The investment is a new green field project with 2,091MW thermal capacity. | 1 | New Investment |  | 01-2032 | 2032 | 1 | OMNIA GmbH |  | 1 | 1 | La Spezia (Italy) | Ramis (Spain) | DCTransmissionLine | DC | 2091 | 525 | 700 | New | 1210 | 1957 | APOLLO-LINK | APOLLO-LINK | The project is a 2GW HVDC Interconnection with two converters operating a VSC technology at 525 kV. It consists of approx. 660 km of subsea and 40km of onshore transmission cable. The investment is a new green field project with 2,091MW thermal capacity. | 1 |  | 12-2032 | 2032 | 1 | APOLLO-LINK DEVELOPMENT & OPERATIONS SRL | 1 | XX | XX | New | 2032 | 2032 | 0 | 8 | ESP;ITA | La Spezia | Ramis | 44.2384 | 9.6912 | 41.4317 | 1.3456
577 | 2024 | 2026 | [2024, 2026] | 1958 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1211 | 1958 | Baltic WindConnector (BWC) | Baltic WindConnector (BWC) | HVDC interconnector including converters and sea cables | 1 | New Investment |  | 12-2037 | 2037 | 1 | 50Hertz, Elering, AST |  | 1 | 1 | Saaremaa-Hub (EE) | Area of Brünzow/Kemnitz (DE) | OffshoreDCTransmissionCable | DC | 2000 | 525 | 800 | New | 1211 | 1958 | Baltic WindConnector (BWC) | Baltic WindConnector (BWC) | HVDC interconnector including converters and sea cables | 1 |  | 12-2039 | 2039 | 1 | 50Hertz, Elering, AST | 1 | XX | XX | New | 2037 | 2039 | 2 | 15 | DEU;EST;LVA | Saaremaa- | Brünzowkemnitz | 58.2738 | 22.2771
578 | 2024 | 2026 | [2024, 2026] | 1960 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1213 | 1960 | Offshore hybrid Interconnector (DE-NL) | HVDC line | Hybrid offshore Interconnector between Germany and the Netherlands | 1 | New Investment |  | 12-2035 | 2035 | 1 | TenneT TSO GmbH, TenneT TSO BV |  | 1 | 1 | Search area 6/7 | NOR-14-x | DCTransmissionLine | DC | 2000 | 525 | 30 | New | 1213 | 1960 | Offshore hybrid Interconnector (DE-NL) | HVDC line | Hybrid offshore Interconnector between Germany and the Netherlands | 1 |  | 12-2037 | 2037 | 1 | TenneT TSO GmbH, TenneT TSO BV | 1 | XX | XX | New | 2035 | 2037 | 2 | 13 | DEU;NLD | Search Area | Nor--X |  |  | 52.488 | 13.4135
579 | 2024 | 2026 | [2024, 2026] | 1962 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1171 | 1962 | Interconnection IT-CH | 400kV Interconnection IT-CH | 380 kV interconnection projects between Italian and Swiss transmission system | 2 | New Investment |  | 01-2038 | 2038 | 1 | Terna; Swissgrid |  | 1 | 1 | Regoledo | Swiss node | ACTransmissionLine | AC | 0 | 400 | 80 | New | 1171 | 1962 | Interconnection IT-CH | 400kV Interconnection IT-CH | 380 kV interconnection projects between Italian and Swiss transmission system | 2 |  | 01-2042 | 2042 | 1 | Terna; Swissgrid | 1 | XX | XX | New | 2038 | 2042 | 4 | 18 | CHE;ITA | Regoledo | Swiss Node | 46.1299 | 9.5518
580 | 2024 | 2026 | [2024, 2026] | 1963 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1193 | 1963 | HansaLink - Phase 2 | Germany-UK Hybrid Interconnector - Phase2 | 2GW hybrid interconnector | 1 | New Investment |  | 10-2035 | 2035 | 1 | WindGrid |  | 1 | 1 | Fiddes | TBC | OffshoreDCTransmissionCable | DC | 2000 | 525 | 100 | New | 1193 | 1963 | HansaLink - Phase 2 | Germany-UK Hybrid Interconnector - Phase2 | 2GW hybrid interconnector | 1 |  | 10-2035 | 2035 | 1 | WindGrid | 1 | XX | XX | New | 2035 | 2035 | 0 | 11 | DEU;GBR | Fiddes | Tbc | 53.4559 | -2.2165
581 | 2024 | 2026 | [2024, 2026] | 1964 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1214 | 1964 | Hybrid Interconnector Denmark-Germany | Hybrid Interconnector Denmark-Germany | The project aims to integrate 2 GW of additional Danish offshore wind capacity to onshore markets as part of the Danish Energy Island. To integrate the additional capacity an increase of transfer capacity across the DE-DK EEZ corridor is envisioned towards 2036. | 1 | New Investment |  | 12-2036 | 2036 | 1 | Amprion, Energinet |  | 1 | 1 | Danish Energy Island | German offshore grid connection | OffshoreDCTransmissionCable |  | 0 | 525 | 1000 | New | 1214 | 1964 | Hybrid Interconnector Denmark-Germany | DK-DE Hybrid Interconnector: Danish Energy Hub - Germany | Hybrid HVDC interconnector | 1 |  | 12-2040 | 2040 | 1 | Amprion, Energinet | 1 | XX | XX | New | 2036 | 2040 | 4 | 16 | DEU;DNK | Danish Energy Island | German Grid Connection
582 | 2024 | 2026 | [2024, 2026] | 1965 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 85 | 1965 | Integration of RES in Alentejo | Substation Panóias | New 400/150 kV Substation | 4 | New Investment |  | 03-2025 | 2025 | 1 | Rede Elétrica Nacional |  | 1 | 0 | Panóias | - | OnshoreSubstation | AC | 0 | 400 | 0 | MostlyUpgrade | 85 | 1965 | Integration of RES in Alentejo | Substation Panóias | New 400/150 kV Substation | 5 | Commissioned | 12-2024 | 2024 | 1 | Rede Elétrica Nacional | 0 | XX | XX | Mostly upgrade | 2025 | 2024 | -1 | 0 | PRT | Panóias |  | 37.7607 | -8.3035
583 | 2024 | 2024 | [2024] | 1966 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1088 | 1966 | Latvia and Estonia Hybrid Off-Shore interconnector | Offshore platform with reactive power compensation equipment | The 4th Latvia and Estonia interconnection is a long subsea cable which request additional reactive power compensation equipment in between. It is planned to install additional offshore platform with shunt reactors for reactive power compensation. | 1 | New Investment |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 5.1 | 0 | 1 | Platform with equipment for reactive power compensation | Platform with equipment for reactive power compensation | ReactiveCompensationDevice | AC | 0 | 220 | 0 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2035 | 2035 | 0 | 11 | EST;LVA | Platform With Equipment For Reactive Power Compensation | Platform With Equipment For Reactive Power Compensation
584 | 2024 | 2026 | [2024, 2026] | 1967 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1209 | 1967 | Latvia and Lithuania cross-border strengthening project | New 330 kV OHL Darbenai-Varduva-Musa | New 330 kV OHL Darbenai-Varduva-Musa | 1 | New Investment |  | 12-2034 | 2034 | 1 | AS Augstsprieguma tikls and Litgrid AB |  | 0 | 1 | Derbenai | Musa | ACTransmissionLine | AC | 0 | 330 | 170 | New | 1209 | 1967 | Latvia and Lithuania cross-border strengthening project | New 330 kV OHL Darbenai-Varduva-Musa | Construction of new 330 kV OHL Darbenai-Varduva-Musa | 2 |  | 12-2034 | 2034 | 1 | AS Augstsprieguma tikls and Litgrid AB | 1 | XX | XX | Mostly new | 2034 | 2034 | 0 | 10 | LTU;LVA | Derbenai | Musa |  |  | 54.9365 | 24.9126
585 | 2024 | 2026 | [2024, 2026] | 1968 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1209 | 1968 | Latvia and Lithuania cross-border strengthening project | New 330 kV OHL Panevezys-Musa | New 330 kV OHL Panevezys-Musa | 1 | New Investment |  | 12-2033 | 2033 | 1 | AS Augstsprieguma tikls and Litgrid AB |  | 0 | 1 | Panevezys | Musa | ACTransmissionLine | AC | 0 | 330 | 72 | New | 1209 | 1968 | Latvia and Lithuania cross-border strengthening project | New 330 kV OHL Panevezys-Musa | Construction of new 330 kV OHL Panevezys-Musa | 2 |  | 12-2033 | 2033 | 1 | AS Augstsprieguma tikls and Litgrid AB | 1 | XX | XX | Mostly new | 2033 | 2033 | 0 | 9 | LTU;LVA | Panevezys | Musa | 55.7345 | 24.3578 | 54.9365 | 24.9126
586 | 2024 | 2026 | [2024, 2026] | 1969 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1209 | 1969 | Latvia and Lithuania cross-border strengthening project | New 330 kV Varduva substation | New 330 kV Varduva substation | 1 | New Investment |  | 12-2032 | 2032 | 1 | AS Augstsprieguma tikls and Litgrid AB |  | 0 | 1 | Varduva | Varduva | OnshoreSubstation | AC | 0 | 330 | 0 | New | 1209 | 1969 | Latvia and Lithuania cross-border strengthening project | New 330 kV Varduva substation | Construction of new 330 kV Varduva substation | 2 |  | 12-2032 | 2032 | 1 | AS Augstsprieguma tikls and Litgrid AB | 1 | XX | XX | Mostly new | 2032 | 2032 | 0 | 8 | LTU;LVA | Varduva | Varduva | 56.388 | 22.205 | 56.388 | 22.205
587 | 2024 | 2024 | [2024] | 1970 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1209 | 1970 | Latvia and Lithuania cross-border strengthening project | New reactive compensation device in Darbenai substation | New reactive compensation device in Darbenai substation, for compensation of reactive power generated by new 330 kV lines. | 1 | New Investment |  | 12-2028 | 2028 | 1 | AS Augstsprieguma tikls and Litgrid AB |  | 0 | 1 | Darbenai | Darbenai | ReactiveCompensationDevice | AC | 0 | 330 | 0 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2028 | 2028 | 0 | 4 | LTU;LVA | Darbenai | Darbenai | 56.0232 | 21.254 | 56.0232 | 21.254
588 | 2024 | 2026 | [2024, 2026] | 1971 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1209 | 1971 | Latvia and Lithuania cross-border strengthening project | New reactive compensation device in Musa substation | New reactive compensation device in Musa substation, for compensation of reactive power generated by new 330 kV lines. | 1 | New Investment |  | 12-2028 | 2028 | 1 | AS Augstsprieguma tikls and Litgrid AB |  | 0 | 1 | Musa | Musa | ReactiveCompensationDevice | AC | 0 | 330 | 0 | New | 1209 | 1971 | Latvia and Lithuania cross-border strengthening project | New reactive compensation device in Musa substation | New reactive compensation device in Musa substation, for compensation of reactive power generated by new 330 kV lines. | 2 |  | 12-2030 | 2030 | 1 | AS Augstsprieguma tikls and Litgrid AB | 1 | XX | XX | Mostly new | 2028 | 2030 | 2 | 6 | LTU;LVA | Musa | Musa | 54.9365 | 24.9126 | 54.9365 | 24.9126
589 | 2024 | 2026 | [2024, 2026] | 1972 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1217 | 1972 | Further Development of Offshore Renewables (MOG 3) | MOG 3 | 2000MW radial connection | 1 | New Investment |  | 12-2040 | 2040 | 1 | Elia |  | 1 | 0 | MOG 3 | Van Eyck | OffshoreDCTransmissionCable | DC | 2000 | 1050 | 310 | New | 1217 | 1972 | Further Development of Offshore Renewables (MOG 3) | MOG 3 | 2000MW radial connection | 1 |  | 12-2040 | 2040 | 1 | Elia | 0 | XX | XX | New | 2040 | 2040 | 0 | 16 | BEL | Mog | Van Eyck | 50.6426 | 5.5718 | 51.2108 | 4.4116
590 | 2024 | 2026 | [2024, 2026] | 1973 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1218 | 1973 | Hybrid HVDC Interconnector BE-NL | Hybrid IC BE-NL | Link between Belgium and a already radially connected offshore wind farms in the Netherlands. | 1 | New Investment |  | 12-2040 | 2040 | 1 | Elia and TenneT-NL |  | 1 | 1 | Offshore wind farm | Doel | OffshoreDCTransmissionCable | DC | 2000 | 1050 | 503 | New | 1218 | 1973 | Hybrid HVDC Interconnector BE-NL | Hybrid IC BE-NL | Link between Belgium and an already radially connected offshore wind farm in the Netherlands. | 1 |  | 12-2038 | 2038 | 1 | Elia and TenneT-NL | 1 | XX | XX | New | 2040 | 2038 | -2 | 14 | BEL;NLD | Wind Farm | Doel |  |  | 51.3111 | 4.2643
591 | 2024 | 2026 | [2024, 2026] | 1974 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1219 | 1974 | Bofferdange- Bertrange | 380kV Overhead line Bofferdange – Bertrange | The projected 380kV overhead line in subsection Bofferdange – Bertrange; length: 20km; Pylons: 2 x 380 kV AC circuits (1 circuit per side) | 2 | New Investment |  | 12-2030 | 2030 | 1 | Creos Luxembourg |  | 1 | 0 | Bofferdange | Bertrange | ACTransmissionLine | AC | 0 | 380 | 20 | Upgrade | 1219 | 1974 | Bofferdange- Bertrange | 380kV Overhead line Bofferdange – Bertrange | The projected 380kV overhead line in subsection Bofferdange – Bertrange; length: 20km; Pylons: 2 x 380 kV AC circuits (1 circuit per side) | 2 |  | 12-2035 | 2035 | 1 | Creos Luxembourg | 0 | XX | XX | Upgrade | 2030 | 2035 | 5 | 11 | DEU;LUX | Bofferdange | Bertrange | 49.6886 | 6.1408 | 49.6106 | 6.0502
592 | 2024 | 2026 | [2024, 2026] | 1975 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1219 | 1975 | Bofferdange- Bertrange | 380/220/110-65kV substation Bertrange | Upgrade of existing 220/65/20kV substation Bertrange to connect the 380kV transmission grid to the 220kV grid infrastructure, connection e.a. of 2 circuits of the 380kV overhead line Bofferdange – Bertrange | 2 | New Investment |  | 12-2035 | 2035 | 1 | Creos Luxembourg |  | 0 | 0 | Bertrange | Bertrange | OnshoreSubstation | AC | 0 | 380 | 0 | Upgrade | 1219 | 1975 | Bofferdange- Bertrange | 380/220/110-65kV substation Bertrange | Upgrade of existing 220/65/20kV substation Bertrange to connect the 380kV transmission grid to the 220kV grid infrastructure, connection e.a. of 2 circuits of the 380kV overhead line Bofferdange – Bertrange | 2 |  | 12-2035 | 2035 | 1 | Creos Luxembourg | 0 | XX | XX | Upgrade | 2035 | 2035 | 0 | 11 | DEU;LUX | Bertrange | Bertrange | 49.6106 | 6.0502 | 49.6106 | 6.0502
593 | 2024 | 2026 | [2024, 2026] | 1976 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1088 | 1976 | Latvia and Estonia Hybrid Off-Shore interconnector | Construction of new substation in Pavilosta (LV) | The construction of new 330 kV substation in Pavilosta to connect Estonia and Latvia 4th interconnector | 1 | New Investment |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 5.1 | 0 | 1 | Pavilosta (LV) | Pavilosta (LV) | OnshoreSubstation | AC | 0 | 330 | 0 | New | 1088 | 1976 | Latvia and Estonia Hybrid Off-Shore interconnector | Construction of new substation in Ventspils (LV) | The construction of new 330 kV substation in Ventspils to connect Estonia and Latvia 4th interconnector | 2 |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 1 | XX | XX | New | 2035 | 2035 | 0 | 11 | EST;LVA | Pavilosta | Pavilosta | 56.8889 | 21.1825 | 56.8889 | 21.1825
594 | 2024 | 2026 | [2024, 2026] | 1977 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1209 | 1977 | Latvia and Lithuania cross-border strengthening project | Reconstruction of Broceni substation (LV) | The reconstruction of Broceni substation in Latvia | 1 | New Investment |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls and Litgrid AB |  | 0 | 1 | Broceni (LV) | Broceni (LV) | OnshoreSubstation | AC | 0 | 330 | 0 | New | 1209 | 1977 | Latvia and Lithuania cross-border strengthening project | Reconstruction of Broceni substation (LV) | The reconstruction of Broceni substation in Latvia | 2 |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls and Litgrid AB | 1 | XX | XX | Mostly new | 2035 | 2035 | 0 | 11 | LTU;LVA | Broceni | Broceni | 56.6845 | 22.5665 | 56.6845 | 22.5665
595 | 2024 | 2026 | [2024, 2026] | 1978 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1088 | 1978 | Latvia and Estonia Hybrid Off-Shore interconnector | Reconstruction of OHL Pavilosta (LV) - Grobina (LV) | The reconstruction of existing OHL to increase the capacity for cross-border exchange and offshore wind production between Estonia and Latvia | 1 | New Investment |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 5.1 | 0 | 1 | Pavilosta (LV) | Grobina (LV) | ACTransmissionLine | AC | 0 | 330 | 40 | New | 1088 | 1978 | Latvia and Estonia Hybrid Off-Shore interconnector | Reconstruction of OHL Ventspils (LV) - Grobina (LV) | The reconstruction of existing OHL to increase the capacity for cross-border exchange and offshore wind production between Estonia and Latvia | 2 |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 1 | XX | XX | New | 2035 | 2035 | 0 | 11 | EST;LVA | Pavilosta | Grobina | 56.8889 | 21.1825
596 | 2024 | 2026 | [2024, 2026] | 1979 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1094 | 1979 | Estlink 3 | Estonian grid reinforcements: New 330 kV substation for converter station connection | New 330 kV substation and two 330kV overhead powerlines to connect Estlink 3 to Estonian transmission grid. | 2 | New Investment |  | 06-2035 | 2035 | 1 | Fingrid and Elering | 3.6 | 0 | 1 | Aulepa | Aulepa | OnshoreSubstation | AC | 0 | 330 | 0 | New | 1094 | 1979 | EstLink 3 | Estonian grid reinforcements: Aulepa-Rehemäe 330 kV new OHL | New Aulepa-Rehemäe 330 kV overhead powerline to connect Estlink 3 to Estonian transmission grid. | 2 |  | 06-2038 | 2038 | 1 | Fingrid and Elering | 1 | XX | XX | New | 2035 | 2038 | 3 | 14 | EST;FIN | Aulepa | Aulepa | 59.0812 | 23.5864 | 59.0812 | 23.5864
597 | 2024 | 2026 | [2024, 2026] | 1980 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1220 | 1980 | Offshore Wind Connection Viana do Castelo | Offshore Wind Connection Viana do Castelo | Offshore Wind Connection (to be confirmed technical details\type of element) | 1 | New Investment |  | 12-2030 | 2030 | 1 | REN |  | 1 | 0 | tbc | tbc | OffshoreDCTransmissionCable | AC | 0 | 0 | 0 | New | 1220 | 1980 | Offshore Wind Connection Viana do Castelo | Offshore Wind Connection Viana do Castelo | Offshore Wind Connection (to be confirmed technical details\type of element) | 1 |  | 12-2030 | 2030 | 1 | REN | 0 | XX | XX | New | 2030 | 2030 | 0 | 6 | PRT | Tbc | Tbc
598 | 2024 | 2026 | [2024, 2026] | 1981 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1203 | 1981 | Offshore Wind Connection Bretagne Nord-Ouest | Offshore Wind Connection Bretagne Nord-Ouest HVDC OSS + Onshore Converter Station + Cables | 320 kV North Atlantic HVDC terrestrial converter stations and OSS | 1 | New Investment |  | 12-2036 | 2036 | 1 | RTE |  | 1 | 0 | North Atlantic OSS | Cordemais | OnshoreSubstation | DC | 1200 | 320 | 0 | New | 1203 | 1981 | Offshore Wind Connection Bretagne Nord-Ouest | Offshore Wind Connection Bretagne Nord-Ouest | HVDC offshore platform with converter station + onshore converter station + HVDC onshore & offshore cables | 1 |  | 12-2038 | 2038 | 1 | RTE | 0 | XX | XX | New | 2036 | 2038 | 2 | 14 | FRA | North Atlantic Oss | Cordemais |  |  | 47.2909 | -1.8763
599 | 2024 | 2026 | [2024, 2026] | 1983 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1138 | 1983 | 400 kV OHL Suceava (RO) - Balti (MD) | 400kV OHL Suceava (RO) - Gadalin (RO) | A new 400kV OHL that helps the transit of electricity in the east-west direction in Romania up to the border of the Republic of Moldova | 2 | New Investment |  | 12-2030 | 2030 | 1 | Transelectrica |  | 0 | 1 | 400kV Suceava (RO) | 400kV Gadalin (RO) | ACTransmissionLine | AC | 0 | 400 | 258.8 | New | 1138 | 1983 | 400 kV OHL Suceava (RO) - Balti (MD) | 400kV OHL Suceava (RO) - Gadalin (RO) | A new 400kV OHL that helps the transit of electricity in the east-west direction in Romania up to the border of the Republic of Moldova | 2 |  | 12-2030 | 2030 | 1 | Transelectrica | 1 | XX | XX | New | 2030 | 2030 | 0 | 6 | MDA;ROU | Suceava | Gadalin | 47.5327 | 25.8346 | 46.8402 | 23.8485
600 | 2024 | 2026 | [2024, 2026] | 1984 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1229 | 1984 | Rhine-Main-Link | HVDC from Ovelgönne/Rastede/Wiefelstede/Westerstede to Bürstadt | New HVDC-line from Ovelgönne/Rastede/Wiefelstede/Westerstede to Bürstadt to integrate new wind generation especially from North Sea towards Central Germany for consumption and storage. | 2 | New Investment |  | 03-2033 | 2033 | 1 | Amprion |  | 1 | 0 | Ovelgönne/Rastede/Wiefelstede/Westerstede (DE) | Bürstadt (DE) | DCTransmissionLine | DC | 2000 | 525 | 523 | New | 1229 | 1984 | Rhein-Main-Link | HVDC from Ovelgönne/Rastede/Wiefelstede/Westerstede to Bürstadt | New HVDC-line from Ovelgönne/Rastede/Wiefelstede/Westerstede to Bürstadt to integrate new wind generation especially from North Sea towards Central Germany for consumption and storage. | 2 |  | 03-2033 | 2033 | 1 | Amprion | 0 | XX | XX | New | 2033 | 2033 | 0 | 9 | DEU | Ovelgönnerastedewiefelstedewesterstede | Bürstadt |  |  | 49.6532 | 8.4747
601 | 2024 | 2026 | [2024, 2026] | 1985 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1229 | 1985 | Rhine-Main-Link | HVDC from Ovelgönne/Rastede/Wiefelstede/Westerstede to Marxheim | New HVDC-line from Ovelgönne/Rastede/Wiefelstede/Westerstede to Marxheim to integrate new wind generation especially from North Sea towards Central Germany for consumption and storage. | 2 | New Investment |  | 03-2035 | 2035 | 1 | Amprion |  | 0 | 0 | Ovelgönne/Rastede/Wiefelstede/Westerstede (DE) | Marxheim (DE) | DCTransmissionLine | DC | 2000 | 525 | 461 | New | 1229 | 1985 | Rhein-Main-Link | HVDC from Ovelgönne/Rastede/Wiefelstede/Westerstede to Marxheim | New HVDC-line from Ovelgönne/Rastede/Wiefelstede/Westerstede to Marxheim to integrate new wind generation especially from North Sea towards Central Germany for consumption and storage. | 2 |  | 03-2035 | 2035 | 1 | Amprion | 0 | XX | XX | New | 2035 | 2035 | 0 | 11 | DEU | Ovelgönnerastedewiefelstedewesterstede | Marxheim |  |  | 48.7405 | 10.9444
602 | 2024 | 2026 | [2024, 2026] | 1986 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1216 | 1986 | High-Voltage Direct Current Interconnector Project Romania-Hungary | HVDC Arad-Albertirsa | HVDC cable 2500MW 238km between Romania and Hungary | 1 | New Investment |  | 12-2030 | 2030 | 1 | Transelectrica; MAVIR |  | 1 | 1 | Arad | Albertirsa | DCTransmissionLine | DC | 2500 | 525 | 238 | New | 1216 | 1986 | High-Voltage Direct Current Interconnector Project Romania-Hungary | HVDC Arad-Albertirsa | HVDC cable 2500MW 238km between Romania and Hungary | 1 |  | 12-2032 | 2032 | 1 | Transelectrica; MAVIR; | 1 | XX | XX | New | 2030 | 2032 | 2 | 8 | HUN;ROU | Arad | Albertirsa |  |  | 47.2457 | 19.6128
603 | 2024 | 2026 | [2024, 2026] | 1987 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1216 | 1987 | High-Voltage Direct Current Interconnector Project Romania-Hungary | HVDC Arad-Constanta South | HVDC cable 2500MW between Arad (RO) and Constanta South (RO) | 1 | New Investment |  | 12-2030 | 2030 | 1 | Transelectrica; MAVIR |  | 0 | 1 | Arad | Constanta South | DCTransmissionLine | DC | 2500 | 525 | 830 | New | 1216 | 1987 | High-Voltage Direct Current Interconnector Project Romania-Hungary | HVDC Arad-Constanta South | HVDC cable 2500MW between Arad (RO) and Constanta South (RO) | 1 |  | 12-2030 | 2030 | 1 | Transelectrica; MAVIR; | 1 | XX | XX | New | 2030 | 2030 | 0 | 6 | HUN;ROU | Arad | Constanta South |  |  | 44.1002 | 28.6622
604 | 2024 | 2026 | [2024, 2026] | 1988 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1183 | 1988 | New interconnection line 400 kV Greece - Albania | New single circuit OHL 400 kV Thesprotia - Fier | New single circuit OHL 400 kV Thesprotia - Fier | 2 | New Investment |  | 10-2030 | 2030 | 1 | IPTO, OST |  | 1 | 1 | Fier | Thesprotia | ACTransmissionLine | AC | 0 | 400 | 170 | New | 1183 | 1988 | New interconnection line 400 kV Greece - Albania | New single circuit OHL 400 kV Thesprotia - Fier | New single circuit OHL 400 kV Thesprotia - Fier | 2 |  | 06-2031 | 2031 | 1 | IPTO, OST | 1 | XX | XX | New | 2030 | 2031 | 1 | 7 | ALB;GRC | Fier | Thesprotia | 40.7251 | 19.5582 | 39.544 | 20.3084
605 | 2024 | 2026 | [2024, 2026] | 1989 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1221 | 1989 | Offshore Wind Connection Leixões | Offshore Wind Connection Leixões | Offshore Wind Connection (to be confirmed technical details\type of element) | 1 | New Investment |  | 12-2030 | 2030 | 1 | REN |  | 1 | 0 | tbc | tbc | OffshoreDCTransmissionCable | AC | 0 | 0 | 0 |  | 1221 | 1989 | Offshore Wind Connection Leixões | Offshore Wind Connection Leixões | Offshore Wind Connection (to be confirmed technical details\type of element) | 1 |  | 12-2030 | 2030 | 1 | REN | 0 | XX | XX | New | 2030 | 2030 | 0 | 6 | PRT | Tbc | Tbc
606 | 2024 | 2026 | [2024, 2026] | 1991 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1215 | 1991 | Xlinks Morocco - Germany | Xlinks DC | The HVDC transmission architecture is based on two 1,800 MW (receiving end) bipolar 525 kV DC lines. Each cable system will be connected to a HVDC converter at the landing site based on VSC (Voltage Source Converter) technology, providing high reliability and efficiency of the transmission system. Each bipolar system will be an XLPE rigid bipole, using an aluminum conductor with a cross section of 3,500mm2. The cable systems will have two layers of steel armoring and will be buried 1m below the seabed. The entire cable system will be operated in an average water depth of 120-150m, with very limited sections of the cable crossing the seabed at water depths of 600-700m. | 1 | New Investment |  | 10-2032 | 2032 | 1 | Xlinks Ltd and Xlinks Germany GmbH |  | 1 | 1 | [Tan Tan] (MOR) VSC HVDC - 525 kV DC – 2x 1.8GW | (GER) VSC HVDC - 525 kV DC - 2x 1.8GW | OffshoreDCTransmissionCable | DC | 3600 | 525 | 4800 | New | 1215 | 1991 | Sila Atlantik | Sila - TenneT | The HVDC transmission architecture is based on two 1,800 MW (receiving end) bipolar 525 kV DC lines. Each cable system will be connected to a HVDC converter at the landing site based on VSC (Voltage Source Converter) technology, providing high reliability and efficiency of the transmission system. Each bipolar system will be an XLPE rigid bipole, using an aluminum conductor with a cross section of 3,500mm2. The cable systems will have two layers of steel armoring and will be buried 1m below the seabed. The entire cable system will be operated in an average water depth of 120-150m, with very limited sections of the cable crossing the seabed at water depths of 600-700m. | 1 |  | 09-2032 | 2032 | 1 | Xlinks Germany GmbH | 1 | XX | XX | New | 2032 | 2032 | 0 | 8 | DEU;MAR | Tan Tan |  | 28.5889 | 77.1884
607 | 2024 | 2026 | [2024, 2026] | 1992 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1230 | 1992 | TuNur Malta | TuNur DC | The HVDC transmission architecture is based on a single symmetrical monopole +/-320 kV system of 500MW. The HVDC converter is based on VSC (Voltage Source Converter) technology, providing high reliability and efficiency of the transmission system. TuNur DC will consist of a single symmetrical monopole +/-320 kV HVDC system with 500MW, including the overhead transmission line in Tunisia spanning from the power plant to the first converter station located in the gulf of Gabès in Tunisia, the submarine cable from the Tunisian coast to the landing point in Malta, and the HVDC converter station on the Maltese side. | 1 | New Investment |  | 02-2032 | 2032 | 1 | TuNur Ltd |  | 1 | 1 | Rejim Maatoug (TUN) VSC HVDC - +/- 320 kV DC, 500MW | Converter station in Malta (MLT) VSC HVDC - +/- 320 kV DC – 220kV AC, 500MW | OffshoreDCTransmissionCable | DC | 500 | 320 | 654 | New | 1230 | 1992 | TuNur Malta | TuNur DC | The HVDC transmission architecture is based on a single symmetrical monopole +/-320 kV system of 500MW. The HVDC converter is based on VSC (Voltage Source Converter) technology, providing high reliability and efficiency of the transmission system. TuNur DC will consist of a single symmetrical monopole +/-320 kV HVDC system with 500MW, including the overhead transmission line in Tunisia spanning from the power plant to the first converter station located in Maloulech in Tunisia, the submarine cable from the Tunisian coast to the landing point in Malta, and the HVDC converter station on the Maltese side. | 1 |  | 02-2032 | 2032 | 1 | TuNur Ltd | 1 | XX | XX | New | 2032 | 2032 | 0 | 8 | MLT;TUN | Rejim Maatoug | Converter In Malta | 33.32 | 8.033
608 | 2024 | 2026 | [2024, 2026] | 1993 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1230 | 1993 | TuNur Malta | TuNur AC | 220 kV AC underground cables from the HVDC converter station in Malta to the point of injection in the Maltese network (identification of the final point of injection is ongoing and will be finalized through a network impact study in coordination with Enemalta). CAPEX includes also bays extension in the existing substation in the Maltese network. | 1 | New Investment |  | 02-2032 | 2032 | 1 | TuNur Ltd |  | 0 | 1 | Converter station in Malta (MLT) VSC HVDC - +/- 320 kV DC – 220kV AC, 500MW | Malta (MLT) Enemalta substation 220 kV AC | OnshoreACTransmissionCable | AC | 0 | 220 | 4 | New | 1230 | 1993 | TuNur Malta | TuNur AC | 132 kV AC underground cables from the HVDC converter station in Malta to the point of injection in the Maltese network (identification of the final point of injection is ongoing and will be finalized through a network impact study in coordination with Enemalta). CAPEX includes also bays extension in the existing substation in the Maltese network. | 1 |  | 02-2032 | 2032 | 1 | TuNur Ltd | 1 | XX | XX | New | 2032 | 2032 | 0 | 8 | MLT;TUN | Converter In Malta | Malta |  |  | 35.9311 | 14.3952
609 | 2024 | 2026 | [2024, 2026] | 1994 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1231 | 1994 | Green Aegean Interconnector | New HVDC link between Germany and Greece | New HVDC link between Germany and Greece with an NTC increase of 3000 MW. | 1 | New Investment |  | 12-2035 | 2035 | 1 | IPTO |  | 1 | 1 | Thesprotia | Ottenhofen | DCTransmissionLine | DC | 3000 | 525 | 1400 | New | 1231 | 1994 | Green Aegean Interconnector | New HVDC link between Germany and Greece | New HVDC link between Germany and Greece with an NTC increase of 3000 MW. | 1 |  | 01-2036 | 2036 | 1 | IPTO | 1 | XX | XX | New | 2035 | 2036 | 1 | 12 | DEU;GRC | Thesprotia | Ottenhofen | 39.544 | 20.3084 | 48.2157 | 11.88
610 | 2024 | 2026 | [2024, 2026] | 1996 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1182 | 1996 | EHV S/S Thesprotias and its connection to the 400 kV System | New EHV SS Thesprotia | New SS 400/150 kV Thesprotia | 2 | New Investment |  | 10-2030 | 2030 | 1 | IPTO |  | 1 | 0 | Aracthos | Thesprotia | OnshoreSubstation | AC | 0 | 400 | 0 | New | 1182 | 1996 | EHV S/S Thesprotias and its connection to the 400 kV System | New EHV SS Thesprotia | New SS 400/150 kV Thesprotia | 2 |  | 06-2031 | 2031 | 1 | IPTO | 0 | XX | XX | New | 2030 | 2031 | 1 | 7 | GRC | Aracthos | Thesprotia |  |  | 39.544 | 20.3084
611 | 2024 | 2026 | [2024, 2026] | 1997 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1182 | 1997 | EHV S/S Thesprotias and its connection to the 400 kV System | New double circuit OHL 400 kV Aracthos - Thesprotia | New double circuit OHL 400 kV Aracthos - Thesprotia | 2 | New Investment |  | 10-2030 | 2030 | 1 | IPTO |  | 0 | 0 | Aracthos | Thesprotia | ACTransmissionLine | AC | 0 | 400 | 65 | New | 1182 | 1997 | EHV S/S Thesprotias and its connection to the 400 kV System | New double circuit OHL 400 kV Aracthos - Thesprotia | New double circuit OHL 400 kV Aracthos - Thesprotia | 2 |  | 06-2031 | 2031 | 1 | IPTO | 0 | XX | XX | New | 2030 | 2031 | 1 | 7 | GRC | Aracthos | Thesprotia |  |  | 39.544 | 20.3084
612 | 2024 | 2026 | [2024, 2026] | 1998 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1222 | 1998 | Offshore Wind Connection Figueira da Foz (North) | Offshore Wind Connection Figueira da Foz (North) | Offshore Wind Connection (to be confirmed technical details\type of element) | 1 | New Investment |  | 12-2030 | 2030 | 1 | REN |  | 1 | 0 | tbc | tbc | OffshoreDCTransmissionCable | AC | 0 | 0 | 0 | New | 1222 | 1998 | Offshore Wind Connection Figueira da Foz (North) | Offshore Wind Connection Figueira da Foz (North) | Offshore Wind Connection (to be confirmed technical details\type of element) | 1 |  | 12-2030 | 2030 | 1 | REN | 0 | XX | XX | New | 2030 | 2030 | 0 | 6 | PRT | Tbc | Tbc
613 | 2024 | 2026 | [2024, 2026] | 1999 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1223 | 1999 | Offshore Wind Connection Figueira da Foz (South) | Offshore Wind Connection Figueira da Foz | Offshore Wind Connection (to be confirmed technical details\type of element) | 1 | New Investment |  | 12-2030 | 2030 | 1 | REN |  | 1 | 0 | tbc | tbc | OffshoreDCTransmissionCable | AC | 0 | 0 | 0 | New | 1223 | 1999 | Offshore Wind Connection Figueira da Foz (South) | Offshore Wind Connection Figueira da Foz | Offshore Wind Connection (to be confirmed technical details\type of element) | 1 |  | 12-2030 | 2030 | 1 | REN | 0 | XX | XX | New | 2030 | 2030 | 0 | 6 | PRT | Tbc | Tbc
614 | 2010 | 2022 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022] | 2 | Cancelled | 2 | New 50km double circuit Pedralva (PT) - Alfena (PT) 400kV OHL (only one circuit installed in a first step). | 2 | 2016 | 2016 | 1 | Pedralva (PT) | Alfena (PT) | 1 | 1. 2 | New 50km double circuit Pedralva (PT) - Alfena (PT) 400kV OHL, (only one circuit installed in a first step). This line is going to use partially a corridor of a existing single 150 OHL. | 2 | Adjustment resulting from the new date of the hydro power plant. | 2017 | 2017 | 1 | Pedralva (PT) | Alfena (PT) | 1. 2 | 1. 2 | New 47km double circuit Pedralva (PT) - Sobrado (PT) 400kV OHL, (only one circuit installed in a first step). | 2 | Due to the expected delay of the connection of new RES generation in North of Portugal, the commissioning date of this investment is postponed accordingly | 2020 | 2020 | 1 | Pedralva (PT) | Sobrado (PT) | 1 | 2 | RES in north of Portugal | New 47km double circuit Pedralva (PT) - Sobrado (PT) 400kV OHL, (only one circuit installed in a first step). | 2 | Delayed | Due to the expected delay of the connection of new RES generation in North of Portugal, the commissioning date of this investment item is delayed | 2020 | 2020 | 1 | Pedralva (PT) | Sobrado (PT) | 2 | New 47km double circuit Pedralva (PT) - Sobrado (PT) 400kV OHL, (only one circuit installed in a first step). | 2 | Rescheduled | Due to the expected delay of the connection of new RES generation in North of Portugal, the commissioning date of this investment item was rescheduled | 2022 | 2022 | 1 | Pedralva (PT) | Sobrado (PT) | 1 | 2 | RES in north of Portugal | Pedralva-Sobrado | New 67km double circuit Pedralva (PT) - Sobrado (PT) 400kV OHL, (only one circuit installed in a first step). | 3 | Rescheduled | Due to the expected delay of the connection of new RES generation in North of Portugal, the commissioning date of this investment item was rescheduled | 31/ 12/ 2022 | 2022 | 1 |  | 0 | Pedralva (PT) | Sobrado (PT) | Overhead Line | AC | 830 | 400 | 66.5 | New | 1 | 2 | RES in north of Portugal | Pedralva-Sobrado | 2 | Rescheduled | Due to the expected delay of the connection of new RES generation, the commissioning date of this investment item was rescheduled | 2022-2023 | 2023 | 1 | REN | Pedralva (PT) | Sobrado (PT) | Overhead Line | AC | 400 | 1 | 2 | RES in north of Portugal | Pedralva-Sobrado | New double circuit Pedralva (PT) - Sobrado (PT) 400kV OHL, (only one circuit installed in a first step). | 2 | Rescheduled | Due to the expected delay of the connection of new RES generation, the commissioning date of this investment item was rescheduled | 2024 | 2024 | 1 | Rede Elétrica Nacional | 2.16.1 and 2.16.3 | 0 | 0 | Pedralva (PT) | Sobrado (PT) | ACTransmissionLine | AC | 67 | New | 1129 | 2 | New RES at Minho region | Pedralva-Sobrado | New double circuit Pedralva (PT) - Sobrado (PT) 400kV OHL, (only one circuit installed in a first step). | 2 | Rescheduled | Due to increasing difficulties in the identification of feasible corridors with acceptable environmental and social impact, it was decided to reassess the project and its configuration considering the new network developments in the region and the update on the expected generation and demand evolution. | 12-2029 | 2029 | 1 | Rede Elétrica Nacional | 2.16.1 | 1 | 0 | Pedralva (PT) | Sobrado (PT) | ACTransmissionLine | AC | 0 | 400 | 67 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2029 | 13 | 19 | PRT | Pedralva | Sobrado | 41.5599 | -8.3209 | 41.2115 | -8.4653
615 | 2016 | 2016 | [2016] | 200 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 240 | 200 | 380-kV-grid enhancement between Area Güstrow/Bentwisch and Wolmirstedt | Güstrow - Wolmirstedt | 380-kV-grid enhancement and structuralchange Magdeburg/Wolmirstedt, incl. 380-kV-lineGustrow-Wolmirstedt (195 km). | 3 | Investment on time | Investment on time | 2020 | 2020 | 1 |  | 0 | Güstrow (DE) | Wolmirstedt (DE) | Overhead Line | AC | 0 | 380 | 195 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 4 | DEU | Güstrow | Wolmirstedt | 53.7936 | 12.1765 | 52.2485 | 11.6267
616 | 2024 | 2024 | [2024] | 2000 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1224 | 2000 | Offshore Wind Connection Ericeira | Offshore Wind Connection Ericeira | Offshore Wind Connection (to be confirmed technical details\type of element) | 1 | New Investment |  | 12-2030 | 2030 | 1 | REN |  | 1 | 0 | tbc | tbc | OffshoreACTransmissionCable | AC | 0 | 0 | 0 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2030 | 2030 | 0 | 6 | PRT | Tbc | Tbc
617 | 2024 | 2026 | [2024, 2026] | 2001 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1233 | 2001 | Laufenburg - Beznau - Breite | Beznau - Laufenburg | line | 1 | New Investment |  | 12-2035 | 2035 | 1 | Swissgrid |  | 0 | 0 | Beznau 380 kV | Laufenburg 380 kV | ACTransmissionLine | AC | 0 | 380 | 16 | New | 1233 | 2001 | Laufenburg - Beznau - Breite | Beznau - Laufenburg | line | 1 |  | 12-2035 | 2035 | 1 | Swissgrid | 0 | XX | XX | New | 2035 | 2035 | 0 | 11 | CHE | Beznau | Laufenburg | 47.5542 | 8.2297 | 47.5123 | 8.0527
618 | 2024 | 2026 | [2024, 2026] | 2002 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1233 | 2002 | Laufenburg - Beznau - Breite | Beznau - Breite | line | 1 | New Investment |  | 12-2035 | 2035 | 1 | Swissgrid |  | 1 | 0 | Beznau 380 kV | Breite 380 kV | ACTransmissionLine | AC | 0 | 380 | 42 | New | 1233 | 2002 | Laufenburg - Beznau - Breite | Beznau - Breite | line | 1 |  | 12-2035 | 2035 | 1 | Swissgrid | 0 | XX | XX | New | 2035 | 2035 | 0 | 11 | CHE | Beznau | Breite | 47.5542 | 8.2297 | 47.5518 | 7.6179
619 | 2024 | 2026 | [2024, 2026] | 2003 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1216 | 2003 | High-Voltage Direct Current Interconnector Project Romania-Hungary | HVDC Arad-Bucharest | HVDC cable between Arad and Bucharest South | 1 | New Investment |  | 12-2030 | 2030 | 1 | Transelectrica; MAVIR |  | 0 | 1 | Arad | Bucharest South | DCTransmissionLine | DC | 2500 | 525 | 586 | New | 1216 | 2003 | High-Voltage Direct Current Interconnector Project Romania-Hungary | HVDC Arad-Bucharest | HVDC cable between Arad and Bucharest South | 1 |  | 12-2030 | 2030 | 1 | Transelectrica; MAVIR; | 1 | XX | XX | New | 2030 | 2030 | 0 | 6 | HUN;ROU | Arad | Bucharest South |  |  | 44.4056 | 26.156
620 | 2024 | 2026 | [2024, 2026] | 2004 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1234 | 2004 | 220-kV Reitdorf (AT) - Weißenbach (AT) | 220-kV Reitdorf (AT) - Weißenbach (AT) | Reinforcement/Upgrade 220-kV Overheadline | 3 | New Investment |  | 12-2028 | 2028 | 1 | Austrian Power Grid |  | 1 | 0 | Reitdorf (AT) | Weißenbach (AT) | ACTransmissionLine | AC | 0 | 220 | 73 | Upgrade | 1234 | 2004 | 220-kV Reitdorf (AT) - Weißenbach (AT) | 220-kV Reitdorf (AT) - Weißenbach (AT) | Reinforcement/Upgrade 220-kV Overheadline |  |  | 12-2027 | 2027 | 1 | Austrian Power Grid | 0 | XX | XX | Upgrade | 2028 | 2027 | -1 | 3 | AUT | Reitdorf | Weißenbach | 47.3723 | 13.3858 | 47.7998 | 13.5361
621 | 2024 | 2026 | [2024, 2026] | 2006 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1225 | 2006 | Offshore Wind Connection Sines | Offshore Wind Connection Sines | Offshore Wind Connection (to be confirmed technical details\type of element) | 1 | New Investment |  | 12-2030 | 2030 | 1 | REN |  | 1 | 0 | tbc | tbc | OffshoreDCTransmissionCable | AC | 0 | 0 | 0 | New | 1225 | 2006 | Offshore Wind Connection Sines | Offshore Wind Connection Sines | Offshore Wind Connection (to be confirmed technical details\type of element) | 1 |  | 12-2030 | 2030 | 1 | REN | 0 | XX | XX | New | 2030 | 2030 | 0 | 6 | PRT | Tbc | Tbc
622 | 2024 | 2026 | [2024, 2026] | 2007 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1235 | 2007 | Second circuit of the 400 kV OHL Sajóivánka (HU) – Rimavská Sobota (SK) | Second circuit of the 400 kV OHL Sajóivánka (HU) – Rimavská Sobota (SK) | nstallation of the second circuit on existing 400 kV OHL Sajóivánka (HU) – Rimavská Sobota (SK) | 1 | New Investment |  | 12-2027 | 2027 | 1 | MAVIR, SEPS |  | 1 | 1 | Sajóivánka (HU) | Rimavska Sobotá (SK) | ACTransmissionLine | AC | 0 | 400 | 51.057 | Upgrade | 1235 | 2007 | Second circuit of the 400 kV OHL Sajóivánka (HU) – Rimavská Sobota (SK) | Second circuit of the 400 kV OHL Sajóivánka (HU) – Rimavská Sobota (SK) | nstallation of the second circuit on existing 400 kV OHL Sajóivánka (HU) – Rimavská Sobota (SK) | 1 |  | 12-2030 | 2030 | 1 | MAVIR, SEPS | 1 | XX | XX | Upgrade | 2027 | 2030 | 3 | 6 | HUN;SVK | Sajóivánka | Rimavska Sobotá | 48.2661 | 20.5794 | 48.3834 | 20.0181
623 | 2024 | 2026 | [2024, 2026] | 2008 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1216 | 2008 | High-Voltage Direct Current Interconnector Project Romania-Hungary | HVDC Bucharest - Constanta South | HVDC cable between Bucharest and Constanta South | 1 | New Investment |  | 12-2030 | 2030 | 1 | Transelectrica; MAVIR |  | 0 | 1 | Bucharest South | Constanta South | DCTransmissionLine | DC | 2500 | 525 | 344 | New | 1216 | 2008 | High-Voltage Direct Current Interconnector Project Romania-Hungary | HVDC Bucharest - Constanta South | HVDC cable between Bucharest and Constanta South | 1 |  | 12-2030 | 2030 | 1 | Transelectrica; MAVIR; | 1 | XX | XX | New | 2030 | 2030 | 0 | 6 | HUN;ROU | Bucharest South | Constanta South | 44.4056 | 26.156 | 44.1002 | 28.6622
624 | 2024 | 2024 | [2024] | 2011 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1226 | 2011 | North-South Electricity Corridor in Eastern Europe | 400kV OHL, Maritsa East (BG) - Nea Santa (GR) | Third interconnection line on the border between Bulgaria and Greece. It is in parallel to the existing one. | 1 | New Investment |  | 07-2036 | 2036 | 1 | ESO, IPTO, MEPSO, TEL, PSA, MAVIR, SEPS, CEPS |  | 1 | 1 | SS Maritsa East (BG) | SS Nea Santa (GR) | ACTransmissionLine | AC | 0 | 400 | 153 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2036 | 2036 | 0 | 12 | BGR;CZE;GRC;HUN;MKD;POL;ROU;SVK | Maritsa East | Nea Santa | 42.1826 | 24.3565 | 40.8423 | 22.9204
625 | 2024 | 2024 | [2024] | 2013 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1226 | 2013 | North-South Electricity Corridor in Eastern Europe | 400kV OHL, Blagoevgrad (BG) - Lagadas (GR) | Fourth interconnection line on the border between Bulgaria and Greece | 1 | New Investment |  | 07-2036 | 2036 | 1 | ESO, IPTO, MEPSO, TEL, PSA, MAVIR, SEPS, CEPS |  | 0 | 1 | SS Blagoevgrad (BG) | SS Lagadas (GR) | ACTransmissionLine | AC | 0 | 400 | 161 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2036 | 2036 | 0 | 12 | BGR;CZE;GRC;HUN;MKD;POL;ROU;SVK | Blagoevgrad | Lagadas | 41.7503 | 23.4873 | 40.7435 | 23.0106
626 | 2024 | 2024 | [2024] | 2014 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1226 | 2014 | North-South Electricity Corridor in Eastern Europe | 400kV OHL, Tsarevets (BG) - Draganesti Olt (RO) | Fifth interconnection line on the border between Bulgaria and Romania | 1 | New Investment |  | 07-2036 | 2036 | 1 | ESO, IPTO, MEPSO, TEL, PSA, MAVIR, SEPS, CEPS |  | 0 | 1 | SS Tsarevets (BG) | SS Draganesti Olt (RO) | ACTransmissionLine | AC | 0 | 400 | 153 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2036 | 2036 | 0 | 12 | BGR;CZE;GRC;HUN;MKD;POL;ROU;SVK | Tsarevets | Draganesti Olt | 41.671 | 25.3517 | 44.1685 | 24.522
627 | 2024 | 2024 | [2024] | 2015 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1226 | 2015 | North-South Electricity Corridor in Eastern Europe | 400kV OHL, Svoboda (BG) - Bucuresti Sud (RO) | Sixth interconnection line on the border between Bulgaria and Romania | 1 | New Investment |  | 07-2036 | 2036 | 1 | ESO, IPTO, MEPSO, TEL, PSA, MAVIR, SEPS, CEPS |  | 0 | 1 | SS Svoboda (BG) | SS Bucuresti Sud (RO) | ACTransmissionLine | AC | 0 | 400 | 147 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2036 | 2036 | 0 | 12 | BGR;CZE;GRC;HUN;MKD;POL;ROU;SVK | Svoboda | Bucuresti Sud | 43.7493 | 27.8178 | 44.4263 | 26.0885
628 | 2024 | 2024 | [2024] | 2016 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1226 | 2016 | North-South Electricity Corridor in Eastern Europe | 400kV OHL, Tsarevets (BG) - Zlatitsa (BG) | New internal km single circuit 400kV OHL | 1 | New Investment |  | 07-2036 | 2036 | 1 | ESO, IPTO, MEPSO, TEL, PSA, MAVIR, SEPS, CEPS |  | 0 | 1 | SS Tsarevets (BG) | SS Zlatitsa (BG) | ACTransmissionLine | AC | 0 | 400 | 0 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2036 | 2036 | 0 | 12 | BGR;CZE;GRC;HUN;MKD;POL;ROU;SVK | Tsarevets | Zlatitsa | 41.671 | 25.3517 | 42.7117 | 24.139
629 | 2024 | 2026 | [2024, 2026] | 2017 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1239 | 2017 | Interconnection Ukraine-Slovak Republic | 400 kV cross-border interconnection between Mukacheve (UA) - Velké Kapušany (SK) | Upgrade of the line 400 kV Mukacheve (UA) - Velké Kapušany (SK) | 3 | Investment on time |  | 12-2026 | 2026 | 1 | NPC Ukrenergo, SEPS |  | 1 | 1 | Mukacheve (UA) | Velké Kapušany (SK) | ACTransmissionLine | AC | 0 | 400 | 52 | Upgrade | 1239 | 2017 | Interconnection Ukraine-Slovak Republic | 400 kV cross-border interconnection between Mukacheve (UA) - Velké Kapušany (SK) | Upgrade of the line 400 kV Mukacheve (UA) - Velké Kapušany (SK) |  |  | 12-2026 | 2026 | 1 | NPC Ukrenergo, SEPS | 1 | XX | XX | Upgrade | 2026 | 2026 | 0 | 2 | SVK;UKR | Mukacheve | Velké Kapuany
630 | 2024 | 2026 | [2024, 2026] | 2018 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1239 | 2018 | Interconnection Ukraine-Slovak Republic | Reconstruction of substation Velké Kapušany (SK) | Reconstruction of substation Velké Kapušany (SK) | 2 | New Investment |  | 12-2030 | 2030 | 1 | NPC Ukrenergo, SEPS |  | 0 | 1 | Substation | Substation | OnshoreSubstation | AC | 0 | 400 | 0 | Upgrade | 1239 | 2018 | Interconnection Ukraine-Slovak Republic | Reconstruction of substation Velké Kapušany (SK) | Reconstruction of substation Velké Kapušany (SK) | 2 |  | 12-2030 | 2030 | 1 | NPC Ukrenergo, SEPS | 1 | XX | XX | Upgrade | 2030 | 2030 | 0 | 6 | SVK;UKR
631 | 2024 | 2026 | [2024, 2026] | 2019 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1239 | 2019 | Interconnection Ukraine-Slovak Republic | Extension of substation Lemešany (SK) | Extension of 400 kV substation Lemešany (SK) by one bay + W2 busbar | 2 | New Investment |  | 12-2031 | 2031 | 1 | NPC Ukrenergo, SEPS |  | 0 | 1 | Substation | Substation | OnshoreSubstation | AC | 0 | 400 | 1 | Upgrade | 1239 | 2019 | Interconnection Ukraine-Slovak Republic | Extension of substation Lemešany (SK) | Extension of 400 kV substation Lemešany (SK) by one bay + W2 busbar | 2 |  | 12-2031 | 2031 | 1 | NPC Ukrenergo, SEPS | 1 | XX | XX | Upgrade | 2031 | 2031 | 0 | 7 | SVK;UKR
632 | 2024 | 2026 | [2024, 2026] | 2020 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1239 | 2020 | Interconnection Ukraine-Slovak Republic | Upgrade of 400 kV line Lemešany (SK) - Vola (SK) | New double-circuit 400kV OHL Lemešany (SK) - Vola (SK) and Lemešany (SK) - Velké Kapušany (SK). | 2 | New Investment |  | 08-2032 | 2032 | 1 | NPC Ukrenergo, SEPS |  | 0 | 1 | Lemešany (SK) | Vola (SK) | ACTransmissionLine | AC | 0 | 400 | 47 | Upgrade | 1239 | 2020 | Interconnection Ukraine-Slovak Republic | Upgrade of 400 kV line Lemešany (SK) - Vola (SK) | New double-circuit 400kV OHL Lemešany (SK) - Vola (SK) and Lemešany (SK) - Velké Kapušany (SK). | 2 |  | 08-2032 | 2032 | 1 | NPC Ukrenergo, SEPS | 1 | XX | XX | Upgrade | 2032 | 2032 | 0 | 8 | SVK;UKR | Lemeany | Vola |  |  | 48.841 | 21.8439
633 | 2024 | 2026 | [2024, 2026] | 2021 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1239 | 2021 | Interconnection Ukraine-Slovak Republic | Upgrade of 400 kV line Vola (SK) - Velké Kapušany (SK) | New double-circuit 400kV OHL Lemešany (SK) - Velké Kapušany (SK) and Vola (SK) - Mukacheve (UA) | 2 | New Investment |  | 08-2032 | 2032 | 1 | NPC Ukrenergo, SEPS |  | 0 | 1 | Vola (SK) | Velké Kapušany (SK) | ACTransmissionLine | AC | 0 | 400 | 23 | Upgrade | 1239 | 2021 | Interconnection Ukraine-Slovak Republic | Upgrade of 400 kV line Vola (SK) - Velké Kapušany (SK) | New double-circuit 400kV OHL Lemešany (SK) - Velké Kapušany (SK) and Vola (SK) - Mukacheve (UA) | 2 |  | 08-2032 | 2032 | 1 | NPC Ukrenergo, SEPS | 1 | XX | XX | Upgrade | 2032 | 2032 | 0 | 8 | SVK;UKR | Vola | Velké Kapuany | 48.841 | 21.8439
634 | 2024 | 2026 | [2024, 2026] | 2022 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1240 | 2022 | Interconnection Ukraine-Romania | 400 kV cross-border interconnection between Artsyz (UA) - Isaccea (RO) | New double-circuit 400kV OHL Artsyz (UA) - Isaccea (RO). | 2 | New Investment |  | 12-2028 | 2028 | 1 | Transelectica and NPC Ukrenergo |  | 1 | 1 | Artsyz (UA) | Isaccea (RO) | ACTransmissionLine | AC | 0 | 400 | 130 | New | 1240 | 2022 | Interconnection Ukraine-Romania | 400 kV cross-border interconnection between Artsyz (UA) - Isaccea (RO) | New double-circuit 400kV OHL Artsyz (UA) - Isaccea (RO). | 2 |  | 12-2028 | 2028 | 1 | Transelectica and NPC Ukrenergo | 1 | XX | XX | New | 2028 | 2028 | 0 | 4 | ROU;UKR | Artsyz | Isaccea |  |  | 45.2722 | 28.4571
635 | 2024 | 2026 | [2024, 2026] | 2023 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 1134 | 2023 | GiLA | GiLA 2nd circuit | One 1200 MW HVDC 320 kV link including onshore and offshore cables +¨onshore converter stations | 1 | New Investment |  | 12-2034 | 2034 | 1 | RTE |  | 0 | 0 | Bordeaux area | Nantes area | DCTransmissionLine | DC | 1200 | 320 | 1 | New | 1134 | 2023 | GiLA | GiLA 2nd circuit | One 1200 MW HVDC 320 kV link including onshore and offshore cables +¨onshore converter stations | 1 |  | 06-2036 | 2036 | 1 | RTE | 0 | XX | XX | New | 2034 | 2036 | 2 | 12 | FRA | Bordeaux Area | Nantes Area
636 | 2024 | 2024 | [2024] | 2024 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [12 empty] | 270 | 2024 | FR-ES project -Aragón-Atlantic Pyrenees | Upgrade Cantegrit-Marsillon | Upgrade of existing 2*225kV line Cantegrit-Marsillon to 1* 400kV | 1 | Rescheduled |  | 00-0000 |  | 1 | Red Eléctrica, Rte | 1.7.2 | 0 | 1 | Cantegrit | Marsillon | ACTransmissionLine | AC | 0 | 400 | 80 | New | [9 empty] | 0 | [9 empty] | ESP;FRA | Cantegrit | Marsillon | 44.2482 | -0.80087 | 43.3908 | -0.59997
637 | 2026 | 2026 | [2026] | 2025 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1242 | 2025 | Baltic Hub | Baltic Hub | HVDC interconnector including converters, sea cables and internal grid reinforcements | 1 |  | 12-2037 | 2037 | 1 | 50Hertz, AST, Litgrid | 1 | XX | XX | New | 2037 | 2037 | 0 | 11 | EST;LVA;LTU
638 | 2026 | 2026 | [2026] | 2026 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1186 | 2026 | Malta-Italy Cable Interconnector No.3 | Malta-Italy Cable Interconnector No.3 | The project consists of a new 200MW HVDC electrical cable interconnection through a submarine cable operating at 320 kV between Malta and Sicily. The project will also include the commissioning of two new HVDC converter/terminal stations, one at each end. | 1 |  | 12-2032 | 2032 | 1 | Interconnect Malta Ltd | 1 | XX | XX | New | 2032 | 2032 | 0 | 6 | AUT;ITA;MLT;NOR
639 | 2026 | 2026 | [2026] | 2027 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1241 | 2027 | Malta Offshore Grid Connection System | Malta Offshore Grid Connection System | A Grid Connection System, consisting of an offshore substation; export cables; an onshore intermediate 132kV Substation housing electrical equipment and reactors; and the subsequent cables up to the circuit breakers of the Distribution System Operator at the grid connection point. | 1 |  | 12-2032 | 2032 | 1 | Interconnect Malta Ltd | 0 | XX | XX | New | 2032 | 2032 | 0 | 6 | AUT;MLT
640 | 2026 | 2026 | [2026] | 2028 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1243 | 2028 | Ostwind 4 Plus DK (OW4+DK) | Ostwind 4 Plus DK | Facilitation of connection of 1 GW offshore wind capacity from Danish waters to existing 2 GW converter in German waters. Offshore AC transmission cable category is used as a proxy for actual connection costs. | 1 |  | 12-2033 | 2033 | 1 | 50Hertz | 1 | XX | XX | New | 2033 | 2033 | 0 | 7 | DNK;ISL
641 | 2026 | 2026 | [2026] | 2029 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1202 | 2029 | Increased capacity Norway-Finland | Phase Shifting Transformer (alt.2) | Phase Shifting Transformer in the new Seidafjellet station (planned to replace the current Varangerbotn station) on the 220 kV line between Norway and Finland, the power flow will be better controlled and by this the cross-border capacity on existing 220 kV line Varangerbotn-Ivalo will be better utilised. | 1 |  | 12-2033 | 2033 | 1 | Statnett and Fingrid | 1 | XX | XX | New | 2033 | 2033 | 0 | 7 | BEL;FIN;NOR
642 | 2026 | 2026 | [2026] | 2030 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1202 | 2030 | Increased capacity Norway-Finland | Re-routing cross border line NO-FI | The Seidafjellet station is planned to replace the current Varangerbotn station on the 220 kV line between Norway and Finland. Due to this a rerouting of the existing cross-border line is recommended. As details of such re-routing are not yet planned, the cost has yet not been estimated. | 1 |  | 12-2035 | 2035 | 1 | Statnett and Fingrid | 1 | XX | XX | New | 2035 | 2035 | 0 | 9 | FIN;ISL;NOR
643 | 2026 | 2026 | [2026] | 2031 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1200 | 2031 | Hybrid interconnector Norway-Sørvest F Windfarm-Continent (DK, DE, BE or NL) | Hybrid interconnector Sørvest F Windfarm-Netherlands (second leg, alt.4) | One or more hybrid interconnectors connecting the Sørvest F windfarm area to Norway as well as to other countries around the North Sea. In the first phase we are planning for a 1400 MW hybrid interconnector, but a 2000 MW interconnector might as well be considered. In the CBA, only one of the Continental countries might be CBA-assessed (for ENTSO-E to decide). At this stage all alternatives are considered equal. | 1 |  | 12-2035 | 2035 | 1 | Statnett together with Energinet, TenneT Germany, Amprion, TenneT Netherlands and Elia | 1 | XX | XX | New | 2035 | 2035 | 0 | 9 | AUT;BEL;DEU;DNK;NLD;NOR
644 | 2026 | 2026 | [2026] | 2035 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1209 | 2035 | Latvia and Lithuania cross-border strengthening project | Static Synchronous Series Compensation (SSSC) equipment | Installation of Static Synchronous Series Compensation (SSSC) equipment for grid operation optimisation and higher reliability. Concrete connection points for the equipment will be decided after in-depth studies implementation. Equipment is intended to be installed in Lithuania and Latvia (common investment). | 2 |  | 12-2035 | 2035 | 1 | AS Augstsprieguma tikls and Litgrid AB | 1 | XX | XX | Mostly new | 2035 | 2035 | 0 | 9 | BEL;ISL;LTU;LVA
645 | 2026 | 2026 | [2026] | 2046 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1249 | 2046 | Central Western Italy | Central Western Italy | New 380 kV station near the intersection of the existing Marginone-Calenzano and Calenzano-Suvereto power lines, with specific operations to remove limitations on 380 kV lines in the area | 2 |  | 12-2036 | 2036 | 1 | Terna | 0 | XX | XX | New | 2036 | 2036 | 0 | 10 | ITA
646 | 2026 | 2026 | [2026] | 2047 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1244 | 2047 | Green Energy Corridor - Phase 2 | GEC Phase 2 - DC Tskaltubo (GE) - Constanta Sud (RO) Link 3 | HVDC Submarine cable 525kV Tskaltubo (GE) to Constanta Sud (RO) as part of the Link 3 of the GEC phase 2 | 1 |  | 01-2040 | 2040 | 1 | Transelectrica | 1 | XX | XX | New | 2040 | 2040 | 0 | 14 | AZE;GEO;HUN;ROU
647 | 2026 | 2026 | [2026] | 2048 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1244 | 2048 | Green Energy Corridor - Phase 2 | GEC Phase 2 - DC Baku (AZ) - Tskaltubo (GE) Link 3 | HVDC 525kV Baku (AZ) to Tskaltubo (GE) as part of the Link 3 of the GEC phase 2 | 1 |  | 01-2040 | 2040 | 1 | Transelectrica | 1 | XX | XX | New | 2040 | 2040 | 0 | 14 | AZE;GEO;HUN;ROU
648 | 2026 | 2026 | [2026] | 2049 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1248 | 2049 | Green Energy Corridor - Phase 1 | GEC Phase 1 - DC Constanta Sud (RO) - Albertirsa (HU) Link 1 | HVDC 525kV Constanta Sud (RO) to Albertirsa (HU) as part of the Link 1of the GEC Phase 1 | 1 |  | 01-2032 | 2032 | 1 | Transelectrica | 1 | XX | XX | New | 2032 | 2032 | 0 | 6 | AZE;GEO;HUN;ROU
649 | 2026 | 2026 | [2026] | 2050 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1248 | 2050 | Green Energy Corridor - Phase 1 | GEC Phase 1 - DC Ksani (GE) - Constanta Sud (RO) Link 1 | HVDC Submarine cable 525kV Ksani (GE) to Constanta Sud (RO) as part of the Link 1of the GEC Phase 1 | 1 |  | 01-2032 | 2032 | 1 | Transelectrica | 1 | XX | XX | New | 2032 | 2032 | 0 | 6 | AZE;GEO;HUN;ROU
650 | 2026 | 2026 | [2026] | 2051 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1248 | 2051 | Green Energy Corridor - Phase 1 | GEC Phase 1 - DC Baku (AZ) - Ksani (GE) Link 1 | HVDC 525kV Baku (AZ) to Ksani (GE) as part of the Link 1of the GEC Phase 1 | 1 |  | 01-2032 | 2032 | 1 | Transelectrica | 1 | XX | XX | New | 2032 | 2032 | 0 | 6 | AZE;GEO;HUN;ROU
651 | 2026 | 2026 | [2026] | 2052 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1248 | 2052 | Green Energy Corridor - Phase 1 | GEC Phase 1 - DC Tskaltubo (GE) - Domnesti (RO) Link 2 | HVDC Submarine cable 525kV Tskaltubo (GE) to Domnesti (RO) as part of the Link 2 of the GEC Phase 1 | 1 |  | 01-2036 | 2036 | 1 | Transelectrica | 1 | XX | XX | New | 2036 | 2036 | 0 | 10 | AZE;GEO;HUN;ROU
652 | 2026 | 2026 | [2026] | 2053 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1248 | 2053 | Green Energy Corridor - Phase 1 | GEC Phase 1 - DC Baku (AZ) - Tskaltubo (GE) Link 2 | HVDC 525kV Baku (AZ) to Tskaltubo (GE) as part of the Link 2 of the GEC Phase 1 | 1 |  | 01-2036 | 2036 | 1 | Transelectrica | 1 | XX | XX | New | 2036 | 2036 | 0 | 10 | AZE;GEO;HUN;ROU
653 | 2026 | 2026 | [2026] | 2054 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1250 | 2054 | New 400kV interconnection BA-ME | New SS 400/220 kV Crkvicko Polje | Construction of the new 400/220 kV substation Crkvicko Polje with 2x400 MVA 400/220 kV power transformers. | 2 |  | 12-2031 | 2031 | 1 | CGES, NOS BiH | 1 | XX | XX | New | 2031 | 2031 | 0 | 5 | BIH;MNE
654 | 2026 | 2026 | [2026] | 2055 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1250 | 2055 | New 400kV interconnection BA-ME | New 400 kV OHL Crkvicko Polje – Sarajevo 20 | A new 400 kV interconnection between the systems of Montenegro and Bosnia and Herzegovina will connect new substation 400/220 kV Crkvicko Polje (ME) with the existing 400/220 kV substation Sarajevo 20 (BA). The 400kV OHL from S/S Sarajevo 20 to BA-ME border exist (73.8 km), built as 400kV OHL but currently operating under 220kV, 12.7 km need to be reconstructed and upgraded. | 2 |  | 12-2030 | 2030 | 1 | CGES, NOS BiH | 1 | XX | XX | New | 2030 | 2030 | 0 | 4 | BEL;BIH;MNE
655 | 2026 | 2026 | [2026] | 2056 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1250 | 2056 | New 400kV interconnection BA-ME | New 400 kV OHL Brezna - Crkvicko Polje | The new 400kV internal line in Montenegro connecting new 400/110kV S/S Brezna with the new 400/220 kV S/S Crkvicko Polje. | 2 |  | 12-2032 | 2032 | 1 | CGES, NOS BiH | 1 | XX | XX | New | 2032 | 2032 | 0 | 6 | BIH;MNE
656 | 2026 | 2026 | [2026] | 2058 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1252 | 2058 | IberiaLink | IberiaLink (Spain-Italy) - DC | IberiaLink is a 1200 MW system, connecting Italy to Spain. The link hereby described refers to the La Spezia s/s (Italy) – Castellon (Spain) and will be built in HVDC-VSC technology with an operating voltage of 525 kVdc. The link consists of a bipole of 1200 MW equipped with sea electrodes, so to be able to operate at half power (600 MW) in case of fault of one pole. Design of the system can be subject to modification and revision during the following phases of the development of the project. | 1 |  | 03-2032 | 2032 | 1 | IberialLink Srl | 1 | XX | XX | New | 2032 | 2032 | 0 | 6 | ESP;PRT
657 | 2026 | 2026 | [2026] | 2059 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1253 | 2059 | GulfLink | GulfLink (Saudi Arabia -Italy) - DC Offshore | GulfLink is a 3000 MW HVDC transmission project between Italy and Saudi Arabia with integrated RES generation. The primary objective of the GulfLink is to establish a new interconnector between Saudi Arabia and Italy through a mixed OHTL and submarine cable HVDC link. The project consists for two links each one connecting Italy to the same generation area in Saudi Arabia with two separate 400 kV AC substation in Italy, notably: Forli 400 kV Substation and Ravenna 400 kV Substation. Each link will have a size of 1,5 GW and will be built in HVDC-VSC technology with an operating voltage of 525 kVdc. More specifically, each link will consist of a double bipole of 1,5 GW each equipped with sea electrodes, so to be able to operate at half power (750 MW) in case of fault of one pole. This is also favourable for the receiving system (Italy) where the application of the N-1 security criterion entails the loss of only 750 MW, which is fully compatible with the current reserve | 1 |  | 05-2033 | 2033 | 1 | GulfLink Srl | 1 | XX | XX | New | 2033 | 2033 | 0 | 7 | AUT;BEL;ISL;ITA
658 | 2026 | 2026 | [2026] | 2062 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1254 | 2062 | High-Voltage Direct Current Interconnector Project - Phase 2 (Romania-Serbia) | Constanta South - Arad | 525 kV HVDC link with 3000 mm2 copper with XLPE insulation cable between Constanta South and Arad 400 kV converter stations. | 1 |  | 12-2039 | 2039 | 1 | Meridiam Europe IV C SAS, TAQA Transmission and E-INFRA | 1 | XX | XX | New | 2039 | 2039 | 0 | 13 | ROU;SRB
659 | 2026 | 2026 | [2026] | 2063 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1254 | 2063 | High-Voltage Direct Current Interconnector Project - Phase 2 (Romania-Serbia) | Arad - Novi Sad 3 (Serbia) | 525 kV HVDC link with 3000 mm2 copper with XLPE insulation cable between Arad and Novi Sad 3 400 kV converter stations. | 1 |  | 12-2039 | 2039 | 1 | Meridiam Europe IV C SAS, TAQA Transmission and E-INFRA | 1 | XX | XX | New | 2039 | 2039 | 0 | 13 | ROU;SRB
660 | 2026 | 2026 | [2026] | 2064 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1253 | 2064 | GulfLink | GulfLink (Saudi Arabia -Italy) - DC Onshore | GulfLink is a 3000 MW HVDC transmission project between Italy and Saudi Arabia with integrated RES generation. The primary objective of the GulfLink is to establish a new interconnector between Saudi Arabia and Italy through a mixed OHTL and submarine cable HVDC link. The project consists for two links each one connecting Italy to the same generation area in Saudi Arabia with two separate 400 kV AC substation in Italy, notably: Forli 400 kV Substation and Ravenna 400 kV Substation. Each link will have a size of 1,5 GW and will be built in HVDC-VSC technology with an operating voltage of 525 kVdc. More specifically, each link will consist of a double bipole of 1,5 GW each equipped with sea electrodes, so to be able to operate at half power (750 MW) in case of fault of one pole. This is also favourable for the receiving system (Italy) where the application of the N-1 security criterion entails the loss of only 750 MW, which is fully compatible with the current reserve. | 1 |  | 12-2033 | 2033 | 1 | GulfLink Srl | 1 | XX | XX | New | 2033 | 2033 | 0 | 7 | AUT;BEL;ISL;ITA
661 | 2026 | 2026 | [2026] | 2066 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1255 | 2066 | High-Voltage Direct Current Interconnector Project - Phase 1 (Romania-Hungary) | Constanta South - Bucharest | 525 kV HVDC link with 3000 mm2 copper with XLPE insulation cable between Constanta South and Bucharest 400 kV converter stations. | 1 |  | 12-2031 | 2031 | 1 | Meridiam Europe IV C SAS, TAQA Transmission and E-INFRA. | 1 | XX | XX | New | 2031 | 2031 | 0 | 5 | HUN;ROU
662 | 2026 | 2026 | [2026] | 2067 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1255 | 2067 | High-Voltage Direct Current Interconnector Project - Phase 1 (Romania-Hungary) | Bucharest - Albertirsa (Hungary) | 525 kV HVDC link with 3000 mm2 copper with XLPE insulation cable between Bucharest and Albertirsa 400 kV converter stations. | 1 |  | 12-2034 | 2034 | 1 | Meridiam Europe IV C SAS, TAQA Transmission and E-INFRA. | 1 | XX | XX | New | 2034 | 2034 | 0 | 8 | HUN;ROU
663 | 2026 | 2026 | [2026] | 2068 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1214 | 2068 | Hybrid Interconnector Denmark-Germany | DK-DE Hybrid Interconnector: Danish Energy Hub - Denmark | Hybrid HVDC interconnector | 1 |  | 12-2040 | 2040 | 1 | Amprion, Energinet | 1 | XX | XX | New | 2040 | 2040 | 0 | 14 | DEU;DNK
664 | 2026 | 2026 | [2026] | 2069 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1247 | 2069 | NeuLink: hybrid interconnector Germany - UK | NeuLink: hybrid interconnector Germany - UK | NeuLink is a hybrid offshore interconnector of 2 GW in the North Sea. It links a German offshore wind farm with a British offshore wind farm and will thus contribute to integrating offshore wind and strengthening the cross-border trade between Germany and the UK. | 1 |  | 12-2040 | 2040 | 1 | 50Hertz, Amprion, TenneT DE | 1 | XX | XX | New | 2040 | 2040 | 0 | 14 | DEU;GBR;ISL;ITA
665 | 2026 | 2026 | [2026] | 2070 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1046 | 2070 | Finnish North-South reinforcement | Höyttikangas/Pysäysperä-Koria (Harjulinja, 2 x OHL) | New double 400 kV OHL will be built from Höyttikangas and Pysäysperä substations (central Finland) via Pyhäjärvi to Koria substation (south-eastern Finland). Enables integration of renewables especially in the north-eastern parts of the country and reinforces transmission between North and South of Finland. Includes the construction of possible new substation as seen necessary. |  |  | 06-2032 | 2032 | 1 | Fingrid | 0 | XX | XX | New | 2032 | 2032 | 0 | 6 | FIN
666 | 2026 | 2026 | [2026] | 2071 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1088 | 2071 | Latvia and Estonia Hybrid Off-Shore interconnector | Internal new 330 kV connection from Eastern Saaremaa (EE) to Western Saaremaa (EE) | New 330 kV OHL from Eastern Saaremaa new 330 kV substation to Western Saaremaa new 330 kV substation. Investment also includes construction of two new 330 kV substations at eastern and western part of Saaremaa. | 2 |  | 12-2033 | 2033 | 1 | AS Augstsprieguma tikls (AST) and AS ELERING | 1 | XX | XX | New | 2033 | 2033 | 0 | 7 | AUT;EST;LVA
667 | 2026 | 2026 | [2026] | 2072 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1256 | 2072 | Limitations removal on the Italian - Slovenian border | Limitations removal on the existing grid interconnected to Slovenia | Limitations removal on the 400 kV and 220 kV grid interconnected to Slovenia | 2 |  | 12-2030 | 2030 | 1 | Terna; ELES | 1 | XX | XX | Mostly upgrade | 2030 | 2030 | 0 | 4 | ITA;SVN
668 | 2026 | 2026 | [2026] | 2073 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1160 | 2073 | PST Riddes | PST on line Riddes – Valpelline in the Riddes substation | PST on line Riddes – Valpelline in the Riddes substation (220 kV/220 kV) | 4 |  | 12-2029 | 2029 | 1 | Swissgrid | 0 | XX | XX | New | 2029 | 2029 | 0 | 3 | CHE
669 | 2026 | 2026 | [2026] | 2074 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1257 | 2074 | Qantara Med | Qantara Med DC | The HVDC transmission architecture is based on two 1,000 MW (receiving end) double symmetrical monopoles 525 kV DC. Each cable system will be connected to a HVDC converter at the landing site based on VSC (Voltage Source Converter) technology, providing high reliability and efficiency of the transmission system. Each monopole system will be using MI insulation and an aluminum conductor with a cross section of 1,400mm2. The cable systems will have two layers of steel armoring and will be buried 1m below the seabed when needed. The entire cable system will be operated in a maximum water depth of 2800m. | 1 |  | 12-2033 | 2033 | 1 | Xlinks Limited and Elemental Power SAS | 1 | XX | XX | New | 2033 | 2033 | 0 | 7 | FRA;TUN
670 | 2026 | 2026 | [2026] | 2075 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1215 | 2075 | Sila Atlantik | Sila - Amprion | The HVDC transmission architecture is based on two 1,800 MW (receiving end) bipolar 525 kV DC lines. Each cable system will be connected to a HVDC converter at the landing site based on VSC (Voltage Source Converter) technology, providing high reliability and efficiency of the transmission system. Each bipolar system will be an XLPE rigid bipole, using an aluminum conductor with a cross section of 3,500mm2. The cable systems will have two layers of steel armoring and will be buried 1m below the seabed. The entire cable system will be operated in an average water depth of 120-150m, with very limited sections of the cable crossing the seabed at water depths of 600-700m. | 1 |  | 12-2035 | 2035 | 1 | Xlinks Germany GmbH | 1 | XX | XX | New | 2035 | 2035 | 0 | 9 | AUT;BEL;ISL
671 | 2026 | 2026 | [2026] | 2076 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1258 | 2076 | HTLS in Lyonnais | Step 1 - HTLS conductors upgrade in North Lyonnais | AC transmission line low expansion conductors upgrade between two main substation that are critical for all European exchanges in this region. | 1 |  | 12-2035 | 2035 | 1 | RTE | 0 | XX | XX | Upgrade | 2035 | 2035 | 0 | 9 | FRA
672 | 2026 | 2026 | [2026] | 2077 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1258 | 2077 | HTLS in Lyonnais | Step 2 - HTLS conductors upgrade in South Lyonnais | AC transmission line low expansion conductors upgrade between two main substation that are critical for all European exchanges in this region. | 1 |  | 01-2038 | 2038 | 1 | RTE | 0 | XX | XX | Upgrade | 2038 | 2038 | 0 | 12 | FRA
673 | 2026 | 2026 | [2026] | 2078 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1258 | 2078 | HTLS in Lyonnais | Step 3 - HTLS conductors upgrade in Center Lyonnais | AC transmission line low expansion conductors upgrade due to a potential new nuclear EPR2 on the Bugey site. | 1 |  | 01-2040 | 2040 | 1 | RTE | 0 | XX | XX | Upgrade | 2040 | 2040 | 0 | 14 | FRA
674 | 2026 | 2026 | [2026] | 2079 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1259 | 2079 | AC transmission line in Occitania | Step 1 - New HVAC transmission line in center Occitania | HVAC reinforcement required for any new interconnectors with Spain. | 1 |  | 12-2035 | 2035 | 1 | RTE | 0 | XX | XX | New | 2035 | 2035 | 0 | 9 | FRA
675 | 2012 | 2015 | [2012, 2013, 2014, 2015] | 208 | Cancelled | [5 empty] | 0 |  |  | 45 | 45. 208 | Construction of new 380kV double-circuit OHL in existing corridor Pulgar-Vieselbach (103 km) Support of RES and conventional generation integration, maintaining of security of supply and support of market development. | 2 | Progresses as planned | 2015/2020 | 2020 | 1 | Lines and Substations in South-Western part of 5 Hertz Transmission control area (DE) |  | 45. 208 | 45. 208 | Construction of new 380kV double-circuit OHL in existing corridor Pulgar-Vieselbach (103 km) Support of RES and conventional generation integration, maintaining of security of supply and support of market development. | 2 | No change. | 2020 | 2020 | 1 | Pulgar (DE) | Vieselbach (DE) | 130 | 208 | N-S Eastern DE_section East | Construction of new 380kV double-circuit OHL in existing corridor Pulgar-Vieselbach (103 km). Support of RES and conventional generation integration, maintaining of security of supply and support of market development. | 2 | Investment on time | The project is part of the results of the national grid development plan and included in the list of national interest (Bundesbedarfsplan). With in this process the commissioning dates of the included projects have been aligned with the current situation. | 2024 | 2024 | 1 | Pulgar (DE) | Vieselbach (DE) | 208 | Construction of new 380kV double-circuit OHL in existing corridor Pulgar-Vieselbach (103 km). Support of RES and conventional generation integration, maintaining of security of supply and support of market development. | 2 | Investment on time | The project is part of the results of the national grid development plan and included in the list of national interest (Bundesbedarfsplan). Within this process the commissioning dates of the included projects have been aligned with the current situation. | 2024 | 2024 | 1 | Pulgar (DE) | Vieselbach (DE) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2024 | 4 | 12 | DEU | Pulgar | Vieselbach | 51.1886 | 12.3517 | 50.9975 | 11.146
676 | 2026 | 2026 | [2026] | 2080 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1259 | 2080 | AC transmission line in Occitania | Step 2 - New HVAC transmission line in Occitania East | HVAC reinforcement required for any new interconnectors with Spain. | 1 |  | 12-2040 | 2040 | 1 | RTE | 0 | XX | XX | New | 2040 | 2040 | 0 | 14 | FRA
677 | 2026 | 2026 | [2026] | 2081 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1259 | 2081 | AC transmission line in Occitania | Step 3 - New HVAC transmission line in Occitania West | HVAC reinforcement required for any new interconnectors with Spain. | 1 |  | 12-2040 | 2040 | 1 | RTE | 0 | XX | XX | New | 2040 | 2040 | 0 | 14 | FRA
678 | 2026 | 2026 | [2026] | 2082 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1260 | 2082 | AC transmission line in Grand Est region | Step 1 - HTLS conductors upgrade | Rebuild with double circuit the AC transmission line in this region. | 1 |  | 12-2032 | 2032 | 1 | RTE | 0 | XX | XX | Upgrade | 2032 | 2032 | 0 | 6 | FRA
679 | 2026 | 2026 | [2026] | 2083 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1260 | 2083 | AC transmission line in Grand Est region | Step 2 - HVAC transmission line | Rebuild the AC line between Muhlbach and Scheer substation to increase the transit capacity. | 1 |  | 12-2035 | 2035 | 1 | RTE | 0 | XX | XX | Upgrade | 2035 | 2035 | 0 | 9 | FRA
680 | 2026 | 2026 | [2026] | 2084 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1261 | 2084 | AC transmission line between Bordeaux and Loire Valley | Step 1 - New AC transmission line between Bordeaux and Loire Valley | HVAC reinforcement required for any new interconnectors with Spain. | 1 |  | 12-2040 | 2040 | 1 | RTE | 0 | XX | XX | Upgrade | 2040 | 2040 | 0 | 14 | FRA
681 | 2026 | 2026 | [2026] | 2085 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [12 empty] | 1261 | 2085 | AC transmission line between Bordeaux and Loire Valley | Step 2 - AC transmission line FA | HVAC reinforcement required for any new interconnectors with Spain. | 1 |  | 12-2040 | 2040 | 1 | RTE | 0 | XX | XX | Upgrade | 2040 | 2040 | 0 | 14 | FRA
682 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 211 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 191 | 211 | OWP TenneT Northsea Part 2 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 190km. Line capacity: 900 MW | 1 | Investment on time | on time | 2020 | 2020 | 1 | Cluster DolWin 4 (NOR 3-2) | Unterweser | 211 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 190km. Line capacity: 900 MW | 1 | Delayed | Delayed due to the long permitting process | 2023 | 2023 | 1 | Cluster DolWin 4 (NOR 3-2) | Cloppenburg | 192 | 211 | OWP Northsea TenneT Part 3 | DolWin 4 (NOR-3-2) | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 190km. Line capacity&#58; 900 MW | 1 | Delayed | delayed due to the project | 1/ 1/ 2028 | 2028 | 1 |  | 0 | Cluster DolWin 4 (NOR 3-2) | area of Cloppenburg | Subsea Cable | DC | 900 | 400 | 190 | New | 381 | 211 | OWP Northsea Part 4 | DolWin 4 (NOR-3-2) | 2 | Investment on time |  | 2028 | 2028 | 1 | Amprion | Cluster DolWin 4 (NOR 3-2) | Hanekenfähr | Subsea Cable | DC | 320 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2028 | 8 | 14 |  | Cluster Dolwin | Hanekenfähr
683 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 212 | Cancelled | [5 empty] | 0 |  |  | 47 | 47. 212 | New 400kV double circuit OHL Isar - St. Peter including new 400kV switchgears Altheim, Simbach and St. Peter, and one new 400/230kV transformer in substation Altheim and fourth circuit on line Isar - Ottenhofen. Line length: 90km. | 3 | Progresses as planned | 2017 | 2017 | 1 | Isar / Ottenhofen (DE) | St. Peter (AT) | 47. 212 | 47. 212 | New 400kV double circuit OHL Isar - St. Peter including new 400kV switchgears Altheim, Pirach, Simbach and St. Peter. Also including 4. circuit on line Ottenhofen - Isar. | 3 |  | 2017 | 2017 | 1 | Isar (DE) | St. Peter (AT) | 47 | 212 | AT - DE | New 400kV double circuit OHL Isar - St. Peter including new 400kV switchgears Altheim, Pirach, Simbach and St. Peter. Also including 4. circuit on line Ottenhofen - Isar. | 3 | Delayed | delayed due to long permitting process | 2018 | 2018 | 1 | Isar (DE) | St. Peter (AT) | 212 | New 400kV double circuit OHL Isar - St. Peter including new 400kV switchgears Altheim, Pirach, Simbach and St. Peter. | 3 | Delayed | Delay due to long permitting process | 2020 | 2020 | 1 | Isar/Altheim/ Ottenhofen | St. Peter (AT) | 47 | 212 | Austria - Germany | 212 Isar/Altheim/Ottenhofen - St. Peter | New 380kV double circuit OHL Isar/Altheim - St. Peter including new 380kV switchgears Altheim, Pirach, Simbach and St. Peter. | 3 | Delayed | Delayed due to long permitting process | 1/ 1/ 2020 | 2020 | 1 |  | 1 | Isar (DE) | St. Peter (AT) | Overhead Line | AC | 2320 | 400 | 90 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2020 | 3 | 8 | AUT;DEU | Isar | St. Peter | 48.2511 | 11.684 | 46.6202 | 14.335
684 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 214 | Cancelled | [5 empty] | 0 |  |  | 48 | 48. 214 | New interconnection (new 2x400 kV tie-line) between SK and HU starting from Gabčíkovo substation (SK) to the Gőnyü substation on Hungarian side ( preliminary decision). Project also includes the erection of new switching station Gabčíkovo next to the existing one. | 1 | The commissioning date has been moved to earlier term due to earlier erection of new 400 kV line Veľký Ďur - Gabčíkovo that help to evacuate power from new NPP. | 2016 | 2016 | 1 | Gabcikovo (SK) | Gőnyü area (HU) | 48. 214 | 48. 214 | New interconnection (new 2x400 kV tie-line) between SK and HU starting from Gabčíkovo substation (SK) to the Gőnyü substation on Hungarian side ( preliminary decision). Project also includes the erection of new switching station Gabčíkovo next to the existing one. | 1 | No change. Negotiations between SEPS and MAVIR are still ongoing. | 2016 | 2016 | 1 | Gabcikovo (SK) | Gonyü area (HU) | 48 | 214 | New SK-HU intercon. - phase 1 | New interconnection (new 2x400 kV tie-line) between SK and HU starting from Gabčíkovo substation (SK) to the Gőnyü substation on Hungarian side ( preliminary decision). Project also includes the erection of new switching station Gabčíkovo next to the existing one. | 2 | Delayed | Expected commission date postponed on 2018 by reason of difficulties associated with finding the common national border crossing point. | 2018 | 2018 | 1 | Gabcikovo (SK) | Gonyü area (HU) | 214 | New interconnection (new 2x400 kV tie-line) between SK and HU starting from Gabčíkovo substation (SK) to the Gőnyü substation on Hungarian side ( preliminary decision). Project also includes the erection of new switching station Gabčíkovo next to the existing one. | 6 | Cancelled | In TYNDP16 this investment will be merged with the SK investment "2x400kV OHL Gabcikovo-Velky Dur" as a new investment. This technical solution change is caused by the environmental restrictions of the SK-HU cross-border line original technical solution. |  |  | 1 | Gabcikovo (SK) | Gőnyü area (HU) | 48 | 214 | New SK-HU intercon. - phase 1 | 1. SK-HU interconnection | New interconnection (new 2x400 kV tie-line) between SK and HU starting from Gabčíkovo substation (SK) to the Gőnyü substation (HU), with one circuit connected to Veľký Ďur substation (SK). Project does not include the erection of new switching station Gabčíkovo next to the existing one. It includes extension of the new Gabčíkovo substation by the two 400 kV bays where the new double line will be connected. | 2 | Delayed | The approval of the Contract of Construction for each PCI in the project between the two promoters has been in delay compared to the original schedule. The project promoters agreed jointly in November 2015 to set a new feasible commissioning date, which will also figure in the Contract. | 31/12/2019 | 2019 | 1 |  | 1 | Gabčíkovo (SK) | Gőnyü (HU) | Overhead Line | AC | 1000 | 400 | 110 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2019 | 3 | 7 | HUN;SVK | Gabíkovo | Gnyü
685 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 216 | Cancelled | [5 empty] | 0 |  |  | 26 | 26. 47. 216 |  |  | 0 |  |  | 1 |  |  | 26. 47. 216 | 26. 47. 216 | New internal double circuit 380kV-line connecting the substations Salzburg and Tauern (replacement of existing 220kV-lines on optimized routes). | 3 | In Sept. 2012 the application for granting the permission (EIA) was submitted to the relevant authorities. According to the experience of similar investments the commissioning is expected for 2019. | 2019 | 2019 | 1 | St. Peter (AT) | Tauern (AT) | 47 | 216 | AT - DE | Completion of the 380kV-line St. Peter - Tauern. This contains an upgrade of the existing 380kV-line St. Peter - Salzburg from 220kV-operation to 380kV-operation and the erection of a new internal double circuit 380kV-line connecting the substations Salzburg and Tauern (replacement of existing 220kV-lines on optimized routes). Moreover the erection of the new substations Wagenham and Pongau and the integration of the substations Salzburg and Kaprun is planned. | 3 | Investment on time | In Sept. 2012 the application for granting the permission (EIA) was submitted to the relevant authorities. According to the experience of similar projects the commissioning is expected for 2020. | 2020 | 2020 | 1 | St. Peter (AT) | Tauern (AT) | 216 | Completion of the 380kV-line St. Peter - Tauern. This contains an upgrade of the existing 380kV-line St. Peter - Salzburg from 220kV-operation to 380kV-operation and the erection of a new internal double circuit 380kV-line connecting the substations Salzburg and Tauern (replacement of existing 220kV-lines on optimized routes). Moreover the erection of the new substations Wagenham and Pongau and the integration of the substations Salzburg and Kaprun is planned. | 3 | Delayed | Significant delays in the authorisation process (EIA). | 2021 | 2021 | 1 | St. Peter (AT) | Tauern (AT) | 47 | 216 | Austria - Germany | 216 | Completion of the 380kV-line St. Peter - Tauern. This contains an upgrade of the existing 380kV-line St. Peter - Salzburg from 220kV-operation to 380kV-operation and the erection of a new internal double circuit 380kV-line connecting the substations Salzburg and Tauern (replacement of existing 220kV-lines on optimized routes). Moreover the erection of the new substations Wagenham and Pongau and the integration of the substations Salzburg and Kaprun is planned. | 3 | Delayed | Significant delays in the authorisation process (EIA). | 1/ 1/ 2021 | 2021 | 1 |  | 0 | St. Peter (AT) | Tauern (AT) | Overhead Line | AC | 1740 | 400 | 128 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2021 |  | 9 | AUT | St. Peter | Tauern | 46.6202 | 14.335 | 47.4678 | 10.7622
686 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 218 | Cancelled | 218 | The project is concerning new 380kV-lines connecting the substations Lienz (AT) and Obersielach (AT) to close the Austrian 380kV-Ring in the southern grid area. Line length: 190km. | 1 | 2020/2025 | 2025 | 1 | Obersielach (AT) | Lienz (AT) | 26 | 26. 47. 218 | New 190km 380kV OHL connecting the substations Lienz (AT) and Obersielach (AT) to close the Austrian 380kV-Ring in the southern grid area. Line length: 190km. | 1 | Progresses as planned | long term |  | 1 | Obersielach (AT) | Lienz (AT) | 26. 47. 218 | 26. 47. 218 | New 380kV OHL connecting the substations Lienz (AT) and Obersielach (AT) to close the Austrian 380kV-Ring in the southern grid area. Line length: 190km. | 1 |  | 2023 | 2023 | 1 | Obersielach (AT) | Lienz (AT) | 26 | 218 | Austria - Italy | New 380kV OHL connecting the substations Lienz (AT) and Obersielach (AT) to close the Austrian 380kV-Security Ring in the southern grid area. Line length: 190km. | 1 | Investment on time | Progress as planned. | 2023 | 2023 | 1 | Obersielach (AT) | Lienz (AT) | 218 | New 380kV OHL connecting the substations Lienz (AT) and Obersielach (AT) to close the Austrian 380kV-Security Ring in the southern grid area. Line length: 190km. | 2 | Investment on time | Progressed as planned. As the project is part of the national development plan, the status is set to "planning". | 2023 | 2023 | 1 | Obersielach (AT) | Lienz (AT) | 26 | 218 | Austria - Italy | 218 | New 380kV OHL connecting the substations Lienz (AT) and Obersielach (AT) to close the Austrian 380kV-Security Ring in the southern grid area. Line length&#58; 190km. | 2 | Rescheduled | Tests and gaining of experience for novel technical solution in progress. | 1/ 1/ 2024 | 2024 | 1 |  | 0 | Obersielach (AT) | Lienz (AT) | Overhead Line | AC | 320 | 400 | 190 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2024 | -1 | 14 | AUT | Obersielach | Lienz | 46.6631 | 14.684 | 46.8299 | 12.7681
687 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 219 | Cancelled | 219 | Upgrade of the existing 220kV-line Westtirol - Zell-Ziller and erection of additional 220/380kV-Transformers. Line length: 105km. | 1 | 2012/2020 | 2020 | 1 | Westtirol (AT) | Zell-Ziller (AT) | 47 | 47. 219 | Upgrade of the existing 220kV-line Westtirol - Zell-Ziller and erection of additional 220/380kV-Transformers. Line length: 105km. | 4 | Project consists of several measures and is on schedule | 2013-2020 | 2020 | 1 | Westtirol (AT) | Zell-Ziller (AT) | 47. 219 | 47. 219 | Upgrade of the existing 220kV-line Westtirol - Zell-Ziller and erection of additional 220/380kV-Transformers. Line length: 105km. | 2 | The upgrade of the line and substation Westtirol is currently in the planning process, the transformer in Zell/Ziller is already under construction. | 2020 | 2020 | 1 | Westtirol (AT) | Zell-Ziller (AT) | 47 | 219 | AT - DE | Upgrade of the existing 220kV-line Westtirol - Zell-Ziller and erection of an additional 220/380kV-Transformer. Line length: 105km. | 2 | Investment on time | The upgrade of the line and substation Westtirol is currently in the planning process. | 2021 | 2021 | 1 | Westtirol (AT) | Zell-Ziller (AT) | 219 | Upgrade of the existing 220kV-line Westtirol - Zell-Ziller and erection of an additional 220/380kV-Transformer. Line length: 105km. | 2 | Investment on time | Progressed as planned | 2021 | 2021 | 1 | Westtirol (AT) | Zell-Ziller (AT) | 47 | 219 | Austria - Germany | 219 | Upgrade of the existing 220kV-line Westtirol - Zell-Ziller and erection of an additional 220/380kV-Transformer. Line length 105km. | 2 | Rescheduled | Tests and gaining of experience for novel technical solution in progress | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Westtirol (AT) | Zell-Ziller (AT) | Overhead Line | AC | 470 | 400 | 105 | New | 47 | 219 | Westtirol - Vöhringen | 219: Westtirol - Zell/Ziller (AT internal) | 2 | Rescheduled | Tests and gaining of experience for novel technical solution in progress. | 2024 | 2024 | 1 | AMPRION; APG | Westtirol (AT) | Zell-Ziller (AT) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2024 | 4 | 14 | AUT | Westtirol | Zell-Ziller | 47.2439 | 10.8743 | 47.2336 | 11.882
688 | 2014 | 2016 | [2014, 2015, 2016] | 223 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 141 | 223 | CSE3 | The existing substation of Cirkovce(SI) will be connected to one circuit of the existing Heviz(HU) -Zerjavinec(HR) double circuit 400kV OHL by erecting a new 80km double circuit 400kV OHL in Slovenia. The project will result in two new cross-border circuits: Heviz(HU)-Cirkovce(SI) and Cirkovce (SI)-Žerjavenec (HR). | 3 | Investment on time | Progresses as planned. | 2016 | 2016 | 1 | Cirkovce (SI) | Heviz (HU) Zerjavenec (HR) | 223 | The existing substation of Cirkovce(SI) will be connected to one circuit of the existing Heviz(HU) -Zerjavinec(HR) double circuit 400kV OHL by erecting a new 80km double circuit 400kV OHL in Slovenia. The project will result in two new cross-border circuits: Heviz(HU)-Cirkovce(SI) and Cirkovce (SI)-Žerjavenec (HR). | 3 | Delayed | The investment is delayed due to environmental problems (including re-routing) and problems with cultural heritage authorities | 2018 | 2018 | 1 | Cirkovce (SI) | Heviz (HU) Zerjavenec (HR) | 141 | 223 | Slovenia-Hungary corridor | 223 | A new 400 kV substation of Cirkovce(SI) will be connected to one circuit of the existing Heviz(HU) -Zerjavinec(HR) double circuit 400kV OHL by erecting a new 80km double circuit 400kV OHL in Slovenia. The project will result in two new cross-border circuits&#58; Heviz(HU)-Cirkovce(SI) and Cirkovce (SI)-Žerjavenec (HR). | 3 | Delayed | ELES is currently in the process of gaining easment from the land owners. | 1/ 1/ 2019 | 2019 | 1 |  | 1 | Cirkovce (SI) | Heviz (HU) Zerjavenec (HR) | Overhead Line | AC | 1085 | 400 | 80 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2019 | 3 | 5 | HRV;SVN | Cirkovce | Heviz Hu Zerjavenec | 46.3949 | 15.7274
689 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 225 | Cancelled | 225 | Upgrading 220kV lines to 400kV in corridor Divaca-Klece-Bericevo-Podlog-Cirkovce. Line length: 193km. | 2 | long term |  | 1 | Divaca (SI) | Cirkovce (SI) | 27 | 27. 225 | Upgrading 220kV lines to 400kV in corridor Divaca-Klece-Bericevo-Podlog-Cirkovce. Line length: 193km. | 2 | Progresses as planned | long term |  | 1 | Divaca (SI) | Cirkovce (SI) | 27. 225 | 27. 225 | Upgrading 220kV lines to 400kV in corridor Divaca-Klece-Bericevo-Podlog-Cirkovce. | 3 |  | 2020 | 2020 | 1 | Divaca (SI) | Cirkovce (SI) | 141 | 225 | CSE3 | Upgrading 220kV lines to 400kV in corridor Divaca-Klece-Bericevo-Podlog-Cirkovce. | 3 | Investment on time | Progresses as planed. | 2020 | 2020 | 1 | Divaca (SI) | Cirkovce (SI) | 225 | Upgrading 220kV lines to 400kV in corridor Divaca-Klece- Bericevo-Podlog-Cirkovce. | 3 | Investment on time | The project is splitted in three phases: 1st phase corridor Divača-Kleče-Beričevo (2020) 2nd phase corridor Beričevo-Podlog (2025 under consideration) 3rd phase corridor Podlog-Cirkovce (2025 under consideration). | 2020 | 2020 | 1 | Divaca (SI) | Cirkovce (SI) | 141 | 225 | Slovenia-Hungary corridor | 225 | Upgrading 220kV lines to 400kV in corridor Divaca-Klece-Bericevo-Podlog-Cirkovce. | 3 | Investment on time | The project is splitted in three phases: - 1st phase corridor Divača-Kleče-Beričevo (2020 - in permitting) - 2nd phase corridor Beričevo-Podlog (2025 - under consideration) - 3rd phase corridor Podlog-Cirkovce (2025 - under consideration). | 1/ 1/ 2025 | 2025 | 1 |  | 0 | Divaca (SI) | Cirkovce (SI) | Overhead Line | AC | 800 | 400 | 193 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2025 |  | 15 | SVN | Divaca | Cirkovce | 45.6869 | 14.0125 | 46.3949 | 15.7274
690 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 227 | Cancelled | [5 empty] | 0 |  |  | 27 | 27. 227 | New 400kV interconnection line between BA and HR | 1 | End points of OHL and commissioning date defined after bilateral HR-BA agreement | 2020 | 2020 | 1 | Banja Luka (BA) | Lika (HR) | 27. 227 | 27. 227 | New 400kV interconnection line between BA and HR | 1 | Feasibility study is expected to be launched. | 2020 | 2020 | 1 | Banja Luka (BA) | Lika (HR) | 136 | 227 | CSE1 | New 400kV interconnection line between BA and HR | 1 | Rescheduled | Feasibility study is expected to be launched. | 2021 | 2021 | 1 | Banja Luka (BA) | Lika (HR) | 227 | New 400kV interconnection line between BA and HR | 1 | Rescheduled | Feasibility study is expected to be launched. | 2022 | 2022 | 1 | Banja Luka (BA) | Lika (HR) | 136 | 227 | CSE1 | OHL 400 kV Banja Luka - Lika | New 400kV interconnection line between BA and HR | 1 | Rescheduled | Feasibility study is expected to be launched. | 1/ 1/ 2030 | 2030 | 1 |  | 1 | Banja Luka (BA) | Lika (HR) | Overhead Line | AC | 504 | 400 | 155 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2030 | 10 | 18 | BIH;HRV | Banja Luka | Lika | 44.7721 | 17.1918 | 44.6259 | 15.3436
691 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 235 | Commissioned | [5 empty] | 0 |  |  | 49 | 49. 235 | New 238km 400kV OHL; on 78km the circuit will be installed on the same towers as the Tirana-Podgorica OHL currently in construction (see project 233); the rest will be built as single circuit line. | 3 | Line in Albania is already constructed. The rest of the lines develops according to the schedule. | 2013 | 2013 | 1 | Tirana(AL) | Pristina (RS) | 49. 235 | 49. 235 | New 238km 400kV OHL; on 78km the circuit will be installed on the same towers as the Tirana-Podgorica OHL currently in construction ; the rest will be built as single circuit line. | 3 | Slight delay, due to procedural reasons. In particular the previous tender has been cancelled and a new one is on going. | 2015 | 2015 | 1 | Tirana(AL) | Pristina (RS) | 147 | 235 | CSE9 | New 238km 400kV OHL; on 78km the circuit will be installed on the same towers as the Tirana-Podgorica OHL currently in construction ; the rest will be built as single circuit line. | 4 | Delayed | slight delay, due to procedural reasons. In particular the previous tender has been cancelled and a new one was launched. Currently the project is under construction | 2016 | 2016 | 1 | Tirana(AL) | Pristina (RS) | 235 | New 242km 400kV OHL; on 78km the circuit will be installed on the same towers as the Tirana-Podgorica OHL currently in construction ; the rest will be built as single circuit line. | 4 | Investment on time | Currently the project is under construction | 2016 | 2016 | 1 | Tirana(AL) | Pristina (RS) | 147 | 235 | South Balkan (CSE9) | New_400kVinterconnection_RS_AL | New 242km 400kV OHL; on 78km the circuit will be installed on the same towers as the Tirana-Podgorica OHL currently in construction ; the rest will be built as single circuit line. | 5 | Commissioned | The project has been commissioned | 1/ 1/ 2016 | 2016 | 1 |  | 1 | Tirana(AL) | Pristina (RS) | Overhead Line | AC | 160 | 400 | 242 | New | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2013 | 2016 | 3 | 4 | ALB;SRB | Tirana | Pristina | 41.3281 | 19.8184 | 42.7462 | 21.1196
692 | 2014 | 2016 | [2014, 2015, 2016] | 236 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 147 | 236 | CSE9 | New 170km 400kV single circuit overhead interconnection between Serbia and FYR of Macedonia. | 4 | Delayed | land acquisition | 2014 | 2014 | 1 | Leskovac(RS) | Shtip (MK) | 236 | New 170km 400kV single circuit overhead interconnection between Serbia and FYR of Macedonia. | 4 | Delayed | land acquisition | 2015 | 2015 | 1 | Leskovac(RS) | Shtip (MK) | 147 | 236 | South Balkan (CSE9) | 236 | New 170km 400kV single circuit overhead interconnection between Serbia and FYR of Macedonia. | 5 | Commissioned | Project has been commissioned | 1/ 1/ 2015 | 2015 | 1 |  | 1 | Leskovac(RS) | Shtip (MK) | Overhead Line | AC | 620 | 400 | 170 | New | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2014 | 2015 | 1 | 1 | MKD;SRB | Leskovac | Shtip | 42.9951 | 21.9464 | 41.7375 | 22.1936
693 | 2010 | 2026 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 238 | Commissioned | 238 | New 150km double circuit (single wired at the beginning) 400kV OHL between existing substations. | 3 | 2015 | 2015 | 1 | Pancevo (RS) | Resita (RO) | 50 | 50. 238 | New 131 km double circuit 400kV OHL between existing substations in Romania and Serbia (63 km on Romanian side and 68 km on Serbian side). | 3 | Due to financing gap, the commissioning deadline was postponed to 2019. RO intends to apply for funding through the Operational Programme 'Increase of Economic Competitiveness' - Priority Axis 4. This would ensure realization of the project and allow for faster finalization (2015 instead of estimated 2019). Constructive characteristics were updated as a result of progress of feasibility and design studies. | 2015 (2019?) | 2019 | 1 | Pancevo (RS) | Resita (RO) | 50. 238 | 50. 238 | New 131 km double circuit 400kV OHL between existing substation in Romania and Serbia (63 km on Romanian side and 68 km on Serbian side)2x1380 MVA. | 3 | Activities are mostly synchronized on both sides. The main problem is right of land along the line path. | 2015 | 2015 | 1 | Pancevo (RS) | Resita (RO) | 144 | 238 | Mid Continental East corridor | New 131 km double circuit 400kV OHL between existing substation in Romania and Serbia (63 km on Romanian side and 68 km on Serbian side)2x1380 MVA. | 3 | Investment on time | Activities are mostly synchronized on both sides. The main problem is right of land along the line path. | 2017 | 2017 | 1 | Pancevo (RS) | Resita (RO) | 238 | New 131 km double circuit 400kV OHL between existing substation in Romania and Serbia (63 km on Romanian side and 68 km on Serbian side)2x1380 MVA. | 4 | Investment on time | On Romanian side the line is under construction and the status on Serbian territory is also under construction | 2017 | 2017 | 1 | Pancevo (RS) | Resita (RO) | 144 | 238 | Mid Continental East corridor | New_400 kV OHL RO-RS | New 131 km double circuit 400kV OHL between existing substation in Romania and Serbia (63 km on Romanian side and 68 km on Serbian side) 2x1380 MVA. | 4 | Investment on time | On Romanian side the line is under construction and the status on Serbian territory is also under construction | 31/03/ 2017 | 2017 | 1 |  | 1 | Resita (RO) | Pancevo (RS) | Overhead Line | AC | 350 | 400 | 131 | New | 144 | 238 | Mid Continental East corridor | New_400 kV OHL RO-RS | 4 | Delayed | National law changes affecting permitting, including complexities with the implementation of the new legislation implementing Regulation (EU) 347/2013 for permitting.Delays in construction works. | 31/03/2018 | 2018 | 1 | TRANSELECTRICA; EMS | Resita (RO) | Pancevo (RS) | Overhead Line | AC | 400 | 144 | 238 | Mid Continental East corridor | New_400 kV OHL RO-RS | New 131 km double circuit 400kV OHL between Romania and Serbia (63 km on Romanian (thermal limit 2513 A) side and 68 km on Serbian (thermal limit 1920 A) side). | 4 | Delayed | Due to some delays related to investments 701 and 269 the line is not operated | 2024 | 2024 | 1 | EMS TRANSELECTRICA | 3.22 | 1 | 1 | Resita (RO) | Pancevo (RS) | ACTransmissionLine | AC | 131 | MostlyNew | 144 | 238 | Mid Continental East corridor | New_400 kV OHL RO-RS | New 131 km double circuit 400kV OHL between Romania and Serbia (63 km on Romanian (thermal limit 2513 A) side and 68 km on Serbian (thermal limit 1920 A) side). | 5 | Delayed | Due to some delays related to investments 701 and 269 the line is not operated | 12-2025 | 2025 | 1 | EMS, Transelectrica | 3.22 | 1 | 1 | Resita (RO) | Pancevo (RS) | ACTransmissionLine | AC | 0 | 400 | 131 | MostlyNew | 144 | 238 | Mid Continental East corridor | New_400 kV OHL RO-RS | New 131 km double circuit 400kV OHL between Romania and Serbia (63 km on Romanian (thermal limit 2513 A) side and 68 km on Serbian (thermal limit 1920 A) side). | 4 | Delayed | Due to some delays related to investments 701 and 269 the line is not operated | 12-2025 | 2025 | 1 | EMS, Transelectrica | 3.22 Cluster Romania-Serbia [currently known as "Mid Continental East corridor''] | 1 | 1 | Resita (RO) | Pancevo (RS) | ACTransmissionLine | AC | 0 | 400 | 131 | MostlyNew | 144 | 238 | Mid Continental East corridor | New_400 kV OHL RO-RS | New 131 km double circuit 400kV OHL between Romania and Serbia (63 km on Romanian (thermal limit 2513 A) side and 68 km on Serbian (thermal limit 1920 A) side). | 5 | Commissioned | 11-2024 | 2024 | 1 | EMS, Transelectrica | 1 | XX | XX | Mostly new | 2015 | 2024 | 9 | 14 | ROU;SRB | Resita | Pancevo | 45.289 | 21.8879 | 44.8706 | 20.64
694 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 239 | Cancelled | 239 | New 200km cross-border single circuit 400kV OHL between existing substations. | 1 | long term |  | 1 | Bitola (MK) | Elbasan (AL) | 51 | 51. 239 | New 200km cross-border single circuit 400kV OHL between existing substations. New 400/110 kV substation in Ohrid area connected in/out to the new 400 kV line Bitola-Elbasan. | 2 | Change of date of commissioning due to : resolving the problems in the 110KV in S-W Macedonia; facilitate the market integration; increased interest of potential investors. | 2015 | 2015 | 1 | Bitola (MK) | Elbasan (AL) | 51. 239 | 51. 239 | New 150km cross-border single circuit 400kV OHL between existing substation Bitola and Elbasan | 3 | Additional investigation of feasibility is being performed | 2017 | 2017 | 1 | Bitola (MK) | Elbasan (AL) | 147 | 239 | CSE9 | New 150km cross-border single circuit 400kV OHL between existing substation Bitola and Elbasan | 3 | Delayed | additional investigation of feasibility | 2017 | 2017 | 1 | Bitola (MK) | Elbasan (AL) | 239 | New 150km cross-border single circuit 400kV OHL between existing substation Bitola and Elbasan | 3 | Rescheduled | additional investigation of feasibility | 2021 | 2021 | 1 | Bitola (MK) | Elbasan (AL) | 147 | 239 | South Balkan (CSE9) | 239 | New 150km cross-border single circuit 400kV OHL between existing substation Bitola and Elbasan | 3 | Rescheduled | additional investigation of feasibility | 1/ 1/ 2020 | 2020 | 1 |  | 0 | Bitola (MK) | Elbasan (AL) | Overhead Line | AC | 160 | 400 | 151 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2020 |  | 10 | ALB;MKD | Bitola | Elbasan | 41.0316 | 21.3303 | 41.1127 | 20.0821
695 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 244 | Commissioned | 244 | New 400kV substation in Lagadas in Thessaloniki area and connection to the existing substation of Filippi via a new 110km double circuit 400kV OHL. | 3 | 2012 | 2012 | 1 | Filippi(GR) | Lagadas (GR) | 51 | 51. 244 | New 400kV substation in Lagadas in Thessaloniki area and connection to the existing substation of Filippi via a new 110km double circuit 400kV OHL. | 4 | Initial delays due to authorization process.The project is now under construction | 2013 | 2013 | 1 | Filippi(GR) | Lagadas (GR) | 51. 244 | 51. 244 | Connection of the new 400kV substation in Lagadas in Thessaloniki area to the existing substation of Filippi via a new 110km double circuit 400kV OHL. | 3 | Delays due to difficulties in financing the investment. Investment status adapted considering the new breakdown of the investment description. | 2016 | 2016 | 1 | Filippi(GR) | Lagadas (GR) | 147 | 244 | CSE9 | Connection of the new 400kV substation in Lagadas in Thessaloniki area to the existing substation of Filippi via a new 110km double circuit 400kV OHL. | 3 | Delayed | Delays in the expropriation and permission process. These issues have been resolved. | 2016 | 2016 | 1 | Filippi(GR) | Lagadas (GR) | 244 | Connection of the new 400kV substation in Lagadas in Thessaloniki area to the existing substation of Filippi via a new 110km double circuit 400kV OHL. | 3 | Delayed | Delays in the expropriation and permission process. These issues have been resolved. | 2017 | 2017 | 1 | Filippi(GR) | Lagadas (GR) | 147 | 244 | South Balkan (CSE9) | 244 | Connection of the new 400kV substation in Lagadas in Thessaloniki area to the existing substation of Filippi via a new 110km double circuit 400kV OHL. | 4 | Delayed | Delayd due to dificulties with the acquisition of the land. This issue has been resolved. | 1/ 6/ 2017 | 2017 | 1 |  | 0 | Filippi(GR) | Lagadas (GR) | Overhead Line | AC | 301 | 400 | 110 | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2012 | 2017 | 5 | 7 | GRC | Filippi | Lagadas |  |  | 40.7435 | 23.0106
696 | 2012 | 2022 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022] | 256 | Commissioned | [5 empty] | 0 |  |  | 51 | 51. 256 | New interconnection line BG-GR by a 130km single circuit 400kV OHL. | 3 | After the interconnection with Turkey, the project can be delayed to LT as it is mainly connected to further RES development. The final commissioning date is subject to change depending of the evolution in the area. | long term |  | 1 | Maritsa East 1 (BG) | N.Santa (GR) | 51. 256 | 51. 256 | New interconnection line BG-GR by a 130km single circuit 400kV OHL. | 3 | Delayed due to lack of funding. | 2021 | 2021 | 1 | Maritsa East 1 (BG) | N.Santa (GR) | 142 | 256 | CSE4 | New interconnection line BG-GR by a 130km single circuit 400kV OHL. | 3 | Delayed | Delayed due to lack of funding. | 2021 | 2021 | 1 | Maritsa East 1 (BG) | N.Santa (GR) | 256 | New interconnection line BG-GR by a 130km single circuit 400kV OHL. | 3 | Delayed | Delayed due to lack of funding. | 2021 | 2021 | 1 | Maritsa East 1 (BG) | N.Santa (GR) | 142 | 256 | CSE 4 (2nd BG-GR interconnector and South BG corridor) | 256 | New interconnection line BG-GR by a 130km single circuit 400kV OHL. | 3 | Delayed | Delayed due to lack of funding. | 30/06/ 2021 | 2021 | 1 |  | 1 | Maritsa East 1 (BG) | N.Santa (GR) | Overhead Line | AC | 648 | 400 | 130 | New | 142 | 256 | CSE4 | 256 | 3 | Rescheduled | Having dificulities with acquiring the land | 30/01/ 2023 | 2023 | 1 | ESO,IPTO-SA | Maritsa East 1 (BG) | N.Santa (GR) | Overhead Line | AC | 400 | 142 | 256 | CSE4 | 256 | New interconnection line BG-GR by a 151km single circuit 400kV OHL. | 3 | Investment on time |  | 2023 | 2023 | 1 | ESO Admie | 3.7.1, 3.7.2, 3.7.3 and 3.7.4 | 1 | 1 | Maritsa East 1 (BG) | N.Santa (GR) | ACTransmissionLine | AC | 151 | New | 142 | 256 | CSE4 | 256 | New interconnection line BG-GR by a 153km single circuit 400kV OHL. | 4 | Ahead of time |  | 06-2022 | 2022 | 1 | ESO, Admie |  | 1 | 1 | Maritsa East 1 (BG) | N.Santa (GR) | ACTransmissionLine | AC | 0 | 400 | 153 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [6 empty] | 2022 |  | 10 | BGR;GRC | Maritsa East | N.Santa | 42.1826 | 24.3565
697 | 2012 | 2022 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022] | 257 | Commissioned | [5 empty] | 0 |  |  | 51 | 51. 257 | New 100km single circuit 400kV OHL in parallel to the existing one. | 3 | Investments 257,258 and 262 are postponed because the permitting procedures (environmental requirements) with the land owners induced delays . | 2014 | 2014 | 1 | Maritsa East 1 (BG) | Plovdiv (BG) | 51. 257 | 51. 257 | New 100km single circuit 400kV OHL in parallel to the existing one. | 3 | Delayed due to difficulties with the acquisition of the land | 2016 | 2016 | 1 | Maritsa East 1 (BG) | Plovdiv (BG) | 142 | 257 | CSE4 | New 100km single circuit 400kV OHL in parallel to the existing one. | 3 | Delayed | Delayed due to difficulties with the acquisition of the land | 2016 | 2016 | 1 | Maritsa East 1 (BG) | Plovdiv (BG) | 257 | New 100km single circuit 400kV OHL in parallel to the existing one. | 3 | Delayed | Delayed due to difficulties with the acquisition of the land | 2019 | 2019 | 1 | Maritsa East 1 (BG) | Plovdiv (BG) | 142 | 257 | CSE 4 (2nd BG-GR interconnector and South BG corridor) | 257 | New 100km single circuit 400kV OHL in parallel to the existing one. | 3 | Delayed | Delayed due to difficulties with the acquisition of the land | 1/ 1/ 2019 | 2019 | 1 |  | 0 | Maritsa East 1 (BG) | Plovdiv (BG) | Overhead Line | AC | 648 | 400 | 100 | New | 142 | 257 | CSE4 | 257 | 3 | Rescheduled | Having dificulities with acquiring the land | 30/ 12/ 2020 | 2020 | 1 |  | Maritsa East 1 (BG) | Plovdiv (BG) | Overhead Line | AC | 400 | 142 | 257 | CSE4 | 257 | New 94km single circuit 400kV OHL in parallel to the existing one. | 3 | Rescheduled | Having dificulities with acquiring the land | 2022 | 2022 | 1 | ESO Admie | 3.7.1, 3.7.2, 3.7.3 and 3.7.4 | 0 | 1 | Maritsa East 1 (BG) | Plovdiv (BG) | ACTransmissionLine | AC | 94 | New | 142 | 257 | CSE4 | 257 | New 94km single circuit 400kV OHL in parallel to the existing one. | 5 | Commissioned |  | 06-2022 | 2022 | 1 | ESO, Admie |  | 0 | 1 | Maritsa East 1 (BG) | Plovdiv (BG) | ACTransmissionLine | AC | 0 | 400 | 94 | New | [10 empty] | 0 | [21 empty] | 0 | [5 empty] | 2014 | 2022 | 8 | 10 | BGR;GRC | Maritsa East | Plovdiv | 42.1826 | 24.3565 | 42.1419 | 24.7499
698 | 2012 | 2022 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022] | 258 | Commissioned | [5 empty] | 0 |  |  | 51 | 51. 258 | New 13km single circuit 400kV OHL in parallel to the existing one. | 3 |  | 2014 | 2014 | 1 | Maritsa East 1 (BG) | Maritsa East 3 (BG) | 51. 258 | 51. 258 | New 13km single circuit 400kV OHL in parallel to the existing one. | 3 | Delayed due to difficulties with the acquisition of the land | 2016 | 2016 | 1 | Maritsa East 1 (BG) | Maritsa East 3 (BG) | 142 | 258 | CSE4 | New 13km single circuit 400kV OHL in parallel to the existing one. | 3 | Delayed | Delayed due to difficulties with the acquisition of the land | 2016 | 2016 | 1 | Maritsa East 1 (BG) | Maritsa East 3 (BG) | 258 | New 13km single circuit 400kV OHL in parallel to the existing one. | 3 | Delayed | Delayed due to difficulties with the acquisition of the land | 2017 | 2017 | 1 | Maritsa East 1 (BG) | Maritsa East 3 (BG) | 142 | 258 | CSE 4 (2nd BG-GR interconnector and South BG corridor) | 258 | New 13km single circuit 400kV OHL in parallel to the existing one. | 3 | Delayed | Delayed due to difficulties with the acquisition of the land | 1/ 1/ 2017 | 2017 | 1 |  | 0 | Maritsa East 1 (BG) | Maritsa East 3 (BG) | Overhead Line | AC | 648 | 400 | 13 | New | 142 | 258 | CSE4 | 258 | 3 | Rescheduled | Having dificulities with acquiring the land | 30/ 06/ 2019 | 2019 | 1 |  | Maritsa East 1 (BG) | Maritsa East 3 (BG) | Overhead Line | AC | 400 | 142 | 258 | CSE4 | 258 | New 13km single circuit 400kV OHL in parallel to the existing one. | 4 | Rescheduled | Having dificulities with acquiring the land | 2021 | 2021 | 1 | ESO Admie | 3.7.1, 3.7.2, 3.7.3 and 3.7.4 | 0 | 1 | Maritsa East 1 (BG) | Maritsa East 3 (BG) | ACTransmissionLine | AC | 13 | New | 142 | 258 | CSE4 | 258 | New 13km single circuit 400kV OHL in parallel to the existing one. | 5 | Commissioned |  | 03-2021 | 2021 | 1 | ESO, Admie |  | 0 | 1 | Maritsa East 1 (BG) | Maritsa East 3 (BG) | ACTransmissionLine | AC | 0 | 400 | 13 | New | [10 empty] | 0 | [21 empty] | 0 | [5 empty] | 2014 | 2021 | 7 | 9 | BGR;GRC | Maritsa East | Maritsa East | 42.1826 | 24.3565 | 42.1826 | 24.3565
699 | 2012 | 2022 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022] | 262 | Commissioned | [5 empty] | 0 |  |  | 51 | 51. 262 | New 400kV OHL. Line length: 150km. | 3 |  | 2014 | 2014 | 1 | Maritsa East 1 (BG) | Burgas (BG) | 51. 262 | 51. 262 | New 400kV OHL. Line length: 150km. | 3 | Delayed due to difficulties with the acquisition of the land | 2016 | 2016 | 1 | Maritsa East 1 (BG) | Burgas (BG) | 142 | 262 | CSE4 | New 400kV OHL. Line length: 150km. | 3 | Delayed | Delayed due to difficulties with the acquisition of the land | 2016 | 2016 | 1 | Maritsa East 1 (BG) | Burgas (BG) | 262 | New 400kV OHL. Line length: 150km. | 3 | Delayed | Delayed due to difficulties with the acquisition of the land | 2021 | 2021 | 1 | Maritsa East 1 (BG) | Burgas (BG) | 142 | 262 | CSE 4 (2nd BG-GR interconnector and South BG corridor) | 262 | New 400kV OHL. Line length&#58; 150km. | 3 | Delayed | Delayed due to difficulties with the acquisition of the land | 1/ 1/ 2021 | 2021 | 1 |  | 0 | Maritsa East 1 (BG) | Burgas (BG) | Overhead Line | AC | 648 | 400 | 150 | New | 142 | 262 | CSE4 | 262 | 3 | Investment on time |  | 01/ 06/ 2021 | 2021 | 1 |  | Maritsa East 1 (BG) | Burgas (BG) | Overhead Line | AC | 400 | 142 | 262 | CSE4 | 262 | New 400kV OHL. Line lengt 150km. | 4 | Investment on time |  | 2021 | 2021 | 1 | ESO Admie | 3.7.1, 3.7.2, 3.7.3 and 3.7.4 | 0 | 1 | Maritsa East 1 (BG) | Burgas (BG) | ACTransmissionLine | AC | 150 | New | 142 | 262 | CSE4 | 262 | New 400kV OHL. Line lengt 145km. | 5 | Commissioned |  | 03-2021 | 2021 | 1 | ESO, Admie |  | 0 | 1 | Maritsa East 1 (BG) | Burgas (BG) | ACTransmissionLine | AC | 0 | 400 | 145 | New | [10 empty] | 0 | [21 empty] | 0 | [5 empty] | 2014 | 2021 | 7 | 9 | BGR;GRC | Maritsa East | Burgas | 42.1826 | 24.3565 | 42.4937 | 27.4721
700 | 2012 | 2015 | [2012, 2013, 2014, 2015] | 265 | Cancelled | [5 empty] | 0 |  |  | 95 | 95. 265 | New 400kV double circuit OHL to accommodate 2000 MW RES generation in N-E Bulgaria (Dobruja region). Line length: 2x70km. | 2 | Moved from LT(TYNDP 2010) to MT due to high interest for very fast implementation of about 2000MW RES generation in Dobrudja region | 2015 | 2015 | 1 | Vidno (BG) | Svoboda (BG) | 95. 265 | 95. 265 | New 400kV double circuit OHL to accommodate 2000 MW RES generation in N-E Bulgaria (Dobruja region). Line length: 2x70km. | 2 | Delayed due to lack of funding. | 2019 | 2019 | 1 | Vidno (BG) | Svoboda (BG) | 138 | 265 | Black Sea Corridor | New 400kV double circuit OHL to accommodate 2000 MW RES generation in N-E Bulgaria (Dobruja region). Line length: 2x70km. | 2 | Delayed | Delayed due to lack of funding. | 2019 | 2019 | 1 | Vidno (BG) | Svoboda (BG) | 265 | New 400kV double circuit OHL to accommodate 2000 MW RES generation in N-E Bulgaria (Dobruja region). Line length: 2x70km. | 6 | Cancelled | Delayed due to lack of funding. |  |  | 1 | Vidno (BG) | Svoboda (BG) | [10 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 |  |  |  | BGR | Vidno | Svoboda | 43.5666 | 28.3838 | 43.7493 | 27.8178
701 | 2010 | 2026 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 269 | Commissioned | 269 | New 400kV OHL between existing stations. Line length: 121km. | 3 | 2015 | 2015 | 1 | Portile de Fier (RO) | Resita (RO) | 50 | 50. 269 | New 400kV OHL between existing substation 400 kV Portile de Fier and new 400 kV substation Resita. Line length: 116km. New 400 kV substation Resita, with 400/220 kV and 400/110 kV transformers, as development of the existing 220/110 kV substation. | 3 | Constructive characteristics were updated as a result of progress of feasibility and design studies. Commissioning date has been slightly shifted. | 2016 | 2016 | 1 | Portile de Fier (RO) | Resita (RO) | 50. 269 | 50. 269 | New 116 km 400kV OHL between existing substation 400 kV Portile de Fier and new 400 kV substation Resita; 1380 MVA. | 3 | The main problems are right of land along the line path and long permitting. | 2016 | 2016 | 1 | Portile de Fier (RO) | Resita (RO) | 144 | 269 | Mid Continental East corridor | New 116 km 400kV OHL between existing substation 400 kV Portile de Fier and new 400 kV substation Resita; 1380 MVA. | 3 | Delayed | The investment was coordinated with investment 50.238. The main problems are right of land along the line path and permitting. | 2017 | 2017 | 1 | Portile de Fier (RO) | Resita (RO) | 269 | New 116 km 400kV OHL between existing substation 400 kV Portile de Fier and new 400 kV substation Resita; 1380 MVA. | 3 | Investment on time | No change of status | 2017 | 2017 | 1 | Portile de Fier (RO) | Resita (RO) | 144 | 269 | Mid Continental East corridor | 400 kV OHL Portile de Fier-Resita | New 116 km 400kV OHL single circuit between existing substation 400 kV Portile de Fier and new 400 kV substation Resita; 1380 MVA. | 4 | Delayed | The investment was coordinated with investment no 238. The main problems are right of land along the line path and permitting. | 01/03/ 2018 | 2018 | 1 |  | 0 | Portile de Fier (RO) | Resita (RO) | Overhead Line | AC | 287 | 400 | 116 | New | 144 | 269 | Mid Continental East corridor | 400 kV OHL Portile de Fier-Resita | 4 | Delayed | National law changes affecting permitting, including complexities with the implementation of the new legislation implementing Regulation (EU) 347/2013 for permitting.Delays related to acquisition of and access to land. | 2019 | 2019 | 1 |  | Portile de Fier (RO) | Resita (RO) | Overhead Line | AC | 400 | 144 | 269 | Mid Continental East corridor | 400 kV OHL Portile de Fier-Resita | New 116 km 400kV OHL single circuit between existing substation 400 kV Portile de Fier and new 400 kV substation Resita. | 4 | Delayed | Delays in issuing the normative acts necessary for the realization of the OHL which led to very long delays in the execution of works. The execution contract was suspended for a period of 6 months. | 2024 | 2024 | 1 | EMS TRANSELECTRICA | 3.22 | 0 | 1 | Portile de Fier (RO) | Resita (RO) | ACTransmissionLine | AC | 116 | MostlyNew | 144 | 269 | Mid Continental East corridor | 400 kV OHL Portile de Fier-Resita | New 116 km 400kV OHL single circuit between existing substation 400 kV Portile de Fier and new 400 kV substation Resita. | 4 | Investment on time |  | 12-2024 | 2024 | 1 | EMS, Transelectrica | 3.22 | 0 | 1 | Portile de Fier (RO) | Resita (RO) | ACTransmissionLine | AC | 0 | 400 | 116 | MostlyNew | 144 | 269 | Mid Continental East corridor | 400 kV OHL Portile de Fier-Resita | New 116 km 400kV OHL single circuit between existing substation 400 kV Portile de Fier and new 400 kV substation Resita. | 4 | Investment on time |  | 12-2024 | 2024 | 1 | EMS, Transelectrica | 3.22 Cluster Romania-Serbia [currently known as "Mid Continental East corridor''] | 0 | 1 | Portile de Fier (RO) | Resita (RO) | ACTransmissionLine | AC | 0 | 400 | 116 | MostlyNew | 144 | 269 | Mid Continental East corridor | 400 kV OHL Portile de Fier-Resita | New 116 km 400kV OHL single circuit between existing substation 400 kV Portile de Fier and new 400 kV substation Resita. | 5 | Commissioned | 12-2024 | 2024 | 1 | EMS, Transelectrica | 1 | XX | XX | Mostly new | 2015 | 2024 | 9 | 14 | ROU;SRB | Portile De Fier | Resita | 46.6075 | 23.8328 | 45.289 | 21.8879
702 | 2010 | 2026 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 270 |  | 270 | Upgrade of an existing 220kV single circuit line to 400kV. Line length: 128km. | 3 | 2019 | 2019 | 1 | Resita( RO) | Timisoara-Sacalaz-Arad (RO) | 50 | 50. 270 | Upgrade of an existing 220kV double circuit line to 400kV double circuit line and replacement of 220 kV substations Timisoara and Sacalaz with 400 kV substations. Line length: 156km. | 3 | Due to financing gap, the commissioning deadline was postponed to 2022. Constructive characteristics were updated as a result of progress of feasibility and design studies. | 2022 | 2022 | 1 | Resita( RO) | Timisoara-Sacalaz-Arad (RO) | 50. 270 | 50. 270 | Upgrade of existing 220kV double circuit line Resita-Timisoara-Sacalaz-Arad to 400kV double circuit. Line length: aprox. 100 km d.c. + 74,6 km s.c.;2x1380 MVA; 1204 MVA the circuit between Sacalaz and C. Aradului | 3 |  | 2022 | 2022 | 1 | Resita (RO) | Timisoara-Sacalaz-Arad (RO) | 144 | 270 | Mid Continental East corridor | Upgrade of existing 220kV double circuit line Resita-Timisoara-Sacalaz-Arad to 400kV double circuit. Line length: approx.. 100 km d.c. + 74,6 km s.c.;2x1380 MVA; 1204 MVA the circuit between Sacalaz and C. Aradului | 3 | Investment on time | Planned to start after investment 269 is finalized. | 2022 | 2022 | 1 | Resita (RO) | Timisoara-Sacalaz-Arad (RO) | 270 | Upgrade of existing 220kV double circuit line Resita- Timisoara-Sacalaz-Arad to 400kV double circuit. Line length: aprox. 100 km d.c. + 74,6 km s.c.;2x1380 MVA; 1204 MVA the circuit between Sacalaz and C. Aradului | 3 | Investment on time | Planned to start after investment 269 is finalized. | 2022 | 2022 | 1 | Resita (RO) | Timisoara- Sacalaz-Arad (RO) | 144 | 270 | Mid Continental East corridor | Upgrade of the existing 220kV double circuit OHL Resita –Timisoara – Sacalaz – Arad to 400kV double circuit line | Upgrade of an existing 220 kV AC double circuit line (OHL) between Resita – Timisoara (RO) to 400 kV double circuit line Resita-Timisoara/Sacalaz of which: 74 km from Resita to Timisoara with a capacity of 1380 MVA and 92 km from Resita to Sacalaz with a capacity of 1380 MVA, both overhead lines will be built on common towers up to Icloda on 58 km. Upgrade of the existing 220 kV AC double circuit line (OHL) Timisoara/Sacalaz-Arad to 400 kV on 67 km of which: 14 km of line will be build single circuit between Sacalaz-C.Aradului-“connection point”, 11 km single circuit from Timisoara to “connection point” and the rest 42 km of the line will be double circuit from “connection point” to Arad. Current status of the project is devided as follows: Permitting for OHL 400 kV Resita- Timisoara/Sacalaz and Design for OHL 400 kV Timisoara/Sacalaz - Arad. | 3 | Delayed | Planned to start after investment 269 is finalized. | 31/12/ 2023 | 2023 | 1 |  | 0 | Resita (RO) | Arad (RO) | Overhead Line | AC | 180 | 400 | 175 | Upgrade | 144 | 270 | Mid Continental East corridor | Upgrade of the existing 220kV double circuit OHL Resita -Timisoara - Sacalaz - Arad to 400kV double circuit line | 3 | Delayed | National law changes affecting permitting, including complexities with the implementation of the new legislation implementing Regulation (EU) 347/2013 for permitting.Delays due to correlation with other delayed infrastructure investment. | 2023 | 2023 | 1 |  | Resita (RO) | Timisoara-Sacalaz-Arad (RO) | Overhead Line | AC | 400 | 144 | 270 | Mid Continental East corridor | Upgrade of the existing 220kV double circuit OHL Resita -Timisoara - Sacalaz - Arad to 400kV double circuit line | Upgrade of an existing 220 kV AC double circuit line (OHL) between Resita - Timisoara (RO) to 400 kV double circuit line Resita-Timisoara/Sacalaz of which: 74 km from Resita to Timisoara and 92 km from Resita to Sacalaz , both overhead lines will be built on common towers up to Icloda on 58 km. Upgrade of the existing 220 kV AC double circuit line (OHL) Timisoara/Sacalaz-Arad to 400 kV on 67 km of which: 14 km of line will be build single circuit between Sacalaz-C.Aradului-""connection point"", 11 km single circuit from Timisoara to ""connection point"" and the rest 42 km of the line will be double circuit from ""connection point"" to Arad. | 3 | Investment on time |  | 2025 | 2025 | 1 | EMS TRANSELECTRICA | 3.22 | 0 | 1 | Resita (RO) | Timisoara-Sacalaz-Arad (RO) | ACTransmissionLine | AC | 274 | MostlyNew | 144 | 270 | Mid Continental East corridor | Upgrade of the existing 220kV double circuit OHL Resita -Timisoara - Sacalaz to 400kV | Upgrade of an existing 220 kV AC double circuit line (OHL) between Resita - Timisoara (RO) to 400 kV double circuit line Resita-Timisoara/Sacalaz of which: 74 km from Resita to Timisoara and 92 km from Resita to Sacalaz , both overhead lines will be built on common towers up to Icloda on 58 km. | 3 | Rescheduled |  | 12-2026 | 2026 | 1 | EMS, Transelectrica | 3.22 | 0 | 1 | Resita (RO) | Timisoara-Sacalaz (RO) | ACTransmissionLine | AC | 0 | 400 | 166 | MostlyNew | 144 | 270 | Mid Continental East corridor | Upgrade of the existing 220kV double circuit OHL Resita -Timisoara - Sacalaz to 400kV | Upgrade of an existing 220 kV AC double circuit line (OHL) between Resita - Timisoara (RO) to 400 kV double circuit line Resita-Timisoara/Sacalaz of which: 74 km from Resita to Timisoara and 92 km from Resita to Sacalaz , both overhead lines will be built on common towers up to Icloda on 58 km. | 3 | Rescheduled |  | 12-2029 | 2029 | 1 | EMS, Transelectrica | 3.22 Cluster Romania-Serbia [currently known as "Mid Continental East corridor''] | 0 | 1 | Resita (RO) | Timisoara-Sacalaz (RO) | ACTransmissionLine | AC | 0 | 400 | 166 | MostlyNew | 144 | 270 | Mid Continental East corridor | Upgrade of the existing 220kV double circuit OHL Resita -Timisoara - Sacalaz to 400kV | Upgrade of an existing 220 kV AC double circuit line (OHL) between Resita - Timisoara (RO) to 400 kV double circuit line Resita-Timisoara/Sacalaz of which: 74 km from Resita to Timisoara and 92 km from Resita to Sacalaz , both overhead lines will be built on common towers up to Icloda on 58 km. | 4 |  | 12-2028 | 2028 | 1 | EMS, Transelectrica | 1 | XX | XX | Mostly new | 2019 | 2028 | 9 | 18 | ROU;SRB | Resita | Timisoara-Sacalaz | 45.289 | 21.8879
703 | 2012 | 2026 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 273 | Commissioned | [5 empty] | 0 |  |  | 53 | 53. 273 | New 400kV double circuit OHL between existing stations. Line length:145km. | 2 | Constructive characteristics were updated as a result of progress of feasibility and design studies. | 2017 | 2017 | 1 | Cernavoda (RO) | Stalpu | 53. 273 | 53. 273 | Reinforcement of the cross-section between the Western coast of the Black Sea (Eastern Romania and Bulgaria) and the rest of the system. New 400kV double circuit OHL between existing substations Cernavoda and Stalpu, with 1 circuit derivation in/out in 400 kV substation Gura Ialomitei,situated in the vicinity of the new line. Line length:159km.2x1380 MVA | 3 | Longer than expected delay regarding clarification of legal framework for right of land acquirement and regarding environmental permitting procedure. | 2019 | 2019 | 1 | Cernavoda (RO) | Stalpu (RO) and Gura Ialomitei (RO) | 138 | 273 | Black Sea Corridor | Reinforcement of the cross-section between the Western coast of the Black Sea (Eastern Romania) and the rest of the system. New 400kV double circuit OHL between existing substations Cernavoda and Stalpu, with 1 circuit derivation in/out in 400 kV substation Gura Ialomitei,situated in the vicinity of the new line. Line length:159km.2x1380 MVA | 3 | Delayed | Longer than expected delay regarding clarification of legal framework for right of land acquirement and regarding environment permitting procedure. | 2019 | 2019 | 1 | Cernavoda (RO) | Stalpu (RO) and Gura Ialomitei (RO) | 273 | Reinforcement of the cross-section between the Western coast of the Black Sea (Eastern Romania) and the rest of the system. New 400kV double circuit OHL between existing substations Cernavoda and Stalpu, with 1 circuit derivation in/out in 400 kV substation Gura Ialomitei,situated in the vicinity of the new line. Line length:159km.2x1380 MVA | 3 | Investment on time | No change of status | 2019 | 2019 | 1 | Cernavoda (RO) | Stalpu (RO) and Gura Ialomitei (RO) | 138 | 273 | Black Sea Corridor | 400kV OHL Cernavoda-Stalpu | Reinforcement of the cross-section between the Western coast of the Black Sea (Eastern Romania) and the rest of the system. New 400kV double circuit OHL between existing substations Cernavoda and Stalpu, with 1 circuit derivation in/out in 400 kV substation Gura Ialomitei,situated in the vicinity of the new line. Line length 159km,2x1380 MVA. | 3 | Delayed | Longer than expected delay regarding clarification of legal framework for right of land acquirement and regarding environmental permitting procedure. | 31/ 12/ 2020 | 2020 | 1 |  | 0 | Cernavoda (RO) | Stalpu (RO) | Overhead Line | AC | 808 | 400 | 159 | New | 138 | 273 | Black Sea Corridor | 400kV OHL Cernavoda-Stalpu | 3 | Delayed | National law changes affecting permitting, including complexities with the implementation of the new legislation implementing Regulation (EU) 347/2013 for permitting.Delays related to acquisition of and access to land. | 2020 | 2020 | 1 | "TRANSELECTRICA, ESO-EAD" | Cernavoda (RO) | Stalpu (RO) | Overhead Line | AC | 400 | 138 | 273 | Black Sea Corridor | 400kV OHL Cernavoda-Stalpu | Reinforcement of the cross-section between the Western coast of the Black Sea (Eastern Romania) and the rest of the system. A new 400 kV AC OHL double circuit of 159 km shall be built between the 400 kV substation Cernavoda and the existing 220/110 kV Stalpu substation, which shall be replaced with a 400/110 kV substation (onshore). One of the two circuits shall be connected in-out to the 400 kV substation Gura Ialomitei, situated in the vicinity of the new line. | 4 | Delayed | Delays related to land acquisition, obtaining approvals and modificatons to the public procurement legislation. | 2023 | 2023 | 1 | ESO TRANSELECTRICA | 3.8 | 0 | 0 | Cernavoda (RO) | Stalpu (RO) | ACTransmissionLine | AC | 159 | MostlyNew | 138 | 273 | Black Sea Corridor | 400kV OHL Cernavoda-Stalpu | Reinforcement of the cross-section between the Western coast of the Black Sea (Eastern Romania) and the rest of the system. A new 400 kV AC OHL double circuit of 159 km shall be built between the 400 kV substation Cernavoda and the existing 220/110 kV Stalpu substation, which shall be replaced with a 400/110 kV substation (onshore). One of the two circuits shall be connected in-out to the 400 kV substation Gura Ialomitei, situated in the vicinity of the new line. | 4 | Investment on time |  | 12-2022 | 2022 | 1 | ESO, Transelectrica |  | 0 | 0 | Cernavoda (RO) | Stalpu (RO) | ACTransmissionLine | AC | 0 | 400 | 159 | MostlyNew | 138 | 273 | Black Sea Corridor | 400kV OHL Cernavoda-Stalpu | Reinforcement of the cross-section between the Western coast of the Black Sea (Eastern Romania) and the rest of the system. A new 400 kV AC OHL double circuit of 159 km shall be built between the 400 kV substation Cernavoda and the existing 220/110 kV Stalpu substation, which shall be replaced with a 400/110 kV substation (onshore). One of the two circuits shall be connected in-out to the 400 kV substation Gura Ialomitei, situated in the vicinity of the new line. | 5 | Investment on time |  | 12-2022 | 2022 | 1 | ESO, Transelectrica |  | 0 | 0 | Cernavoda (RO) | Stalpu (RO) | ACTransmissionLine | AC | 0 | 400 | 159 | MostlyNew | 138 | 273 | Black Sea Corridor | 400kV OHL Cernavoda-Stalpu | Reinforcement of the cross-section between the Western coast of the Black Sea (Eastern Romania) and the rest of the system. A new 400 kV AC OHL double circuit of 159 km shall be built between the 400 kV substation Cernavoda and the existing 220/110 kV Stalpu substation, which shall be replaced with a 400/110 kV substation (onshore). One of the two circuits shall be connected in-out to the 400 kV substation Gura Ialomitei, situated in the vicinity of the new line. | 5 | Commissioned | 12-2022 | 2022 | 1 | ESO, Transelectrica | 0 | XX | XX | Mostly new | 2017 | 2022 | 5 | 10 | BGR;ROU | Cernavoda | Stalpu | 44.3416 | 28.0316 | 45.0852 | 26.7084
704 | 2010 | 2026 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 275 |  | 275 | New 400kV double circuit OHL between existing stations. Line length:140km. | 3 | 2016 | 2016 | 1 | Smardan(RO) | Gutinas(RO) | 53 | 53. 275 | New 400kV double circuit OHL between existing stations. Line length:140km. | 2 | As for other investments, the commissioning date was postponed due to financing gap. Constructive characteristics were updated as a result of progress of feasibility and design studies. | 2020 | 2020 | 1 | Smardan(RO) | Gutinas(RO) | 53. 275 | 53. 275 | Reinforcement of the cross-section between the Western coast of the Black Sea (Dobrogea area) and the rest of the system. New 400kV double circuit OHL (one circuit wired)between existing substations. Line length:140km; 1380 MVA | 3 | Rapid increase of wind generation connected in the area. Efforts to be made to speed construction. | 2020 | 2020 | 1 | Smardan(RO) | Gutinas(RO) | 138 | 275 | Black Sea Corridor | Reinforcement of the cross-section between the Western coast of the Black Sea (Dobrogea area) and the rest of the system. New 400kV double circuit OHL (one circuit wired)between existing substations. Line length:140km; 1380 MVA | 3 | Investment on time | Rapid increase of wind generation connected in the area. Efforts to be made to speed construction. | 2020 | 2020 | 1 | Smardan(RO) | Gutinas(RO) | 275 | Reinforcement of the cross-section between the Western coast of the Black Sea (Dobrogea area) and the rest of the system. New 400kV double circuit OHL (one circuit wired)between existing substations. Line length:140km; 1380 MVA | 3 | Investment on time | Rapid increase of wind generation connected in the area. Efforts to be made to speed construction. | 2020 | 2020 | 1 | Smardan(RO) | Gutinas(RO) | 138 | 275 | Black Sea Corridor | 400 kV OHL Smardan-Gutinas | Reinforcement of the cross-section between the Western coast of the Black Sea (Dobrogea area) and the rest of the system. New 400kV double circuit OHL (one circuit wired) between existing substations. Line length 140km; 1380 MVA. | 3 | Investment on time | Rapid increase of wind generation connected in the area. Efforts to be made to speed construction. | 28/ 02/ 2020 | 2020 | 1 |  | 0 | Smardan (RO) | Gutinas (RO) | Overhead Line | AC | 560 | 400 | 140 | New | 138 | 275 | Black Sea Corridor | 400 kV OHL Smardan-Gutinas | 3 | Delayed | National law changes affecting permitting, including complexities with the implementation of the new legislation implementing Regulation (EU) 347/2013 for permitting.Delays related to acquisition of and access to land. | 2020 | 2020 | 1 |  | Smardan (RO) | Gutinas (RO) | Overhead Line | AC | 400 | 138 | 275 | Black Sea Corridor | 400 kV OHL Smardan-Gutinas | Reinforcement of the cross-section between the Western coast of the Black Sea (Dobrogea area) and the rest of the system. New 400kV double circuit OHL (one circuit wired) between existing substations. Line length 140km. | 3 | Delayed | Delay in issuing the government decision for expropriation. | 2024 | 2024 | 1 | ESO TRANSELECTRICA | 3.8 | 1 | 0 | Smardan (RO) | Gutinas (RO) | ACTransmissionLine | AC | 140 | MostlyNew | 138 | 275 | Black Sea Corridor | 400 kV OHL Smardan-Gutinas | Reinforcement of the cross-section between the Western coast of the Black Sea (Dobrogea area) and the rest of the system. New 400kV double circuit OHL (one circuit wired) between existing substations. Line length 140km. | 4 | Investment on time |  | 12-2024 | 2024 | 1 | ESO, Transelectrica |  | 1 | 0 | Smardan (RO) | Gutinas (RO) | ACTransmissionLine | AC | 0 | 400 | 140 | MostlyNew | 138 | 275 | Black Sea Corridor | 400 kV OHL Smardan-Gutinas | Reinforcement of the cross-section between the Western coast of the Black Sea (Dobrogea area) and the rest of the system. New 400kV double circuit OHL (one circuit wired) between existing substations. Line length 140km. | 4 | Investment on time |  | 12-2024 | 2024 | 1 | ESO, Transelectrica |  | 1 | 0 | Smardan (RO) | Gutinas (RO) | ACTransmissionLine | AC | 0 | 400 | 140 | MostlyNew | 138 | 275 | Black Sea Corridor | 400 kV OHL Smardan-Gutinas | Reinforcement of the cross-section between the Western coast of the Black Sea (Dobrogea area) and the rest of the system. New 400kV double circuit OHL (one circuit wired) between existing substations. Line length 140km. | 4 |  | 12-2025 | 2025 | 1 | ESO, Transelectrica | 0 | XX | XX | Mostly new | 2016 | 2025 | 9 | 15 | BGR;ROU | Smardan | Gutinas |  |  | 46.2067 | 26.8205
705 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 276 | Cancelled | 276 | New 400kV OHL between existing stations. Line length: 260km. | 2 | 2019 | 2019 | 1 | Suceava(RO) | Gadalin(RO) | 53 | 53. 276 | New 400kV OHL between existing stations. Line length: 260km. | 2 | Constructive design characteristics and time schedule were updated as a result of progress of feasibility and design studies. | 2021 | 2021 | 1 | Suceava(RO) | Gadalin(RO) | 53. 276 | 53. 276 | Reinforcement of the cross-section between developing wind generation hub in Eastern Romania and the rest of the system. New 400kV simple circuit OHL between existing substations. Line length: 260km. 1204 MVA | 3 | Difficulties in simultaneous financing of unprecedented level of investment needs. Longer than expected delay regarding clarification of legal framework for right of land acquirement. | 2023 | 2023 | 1 | Suceava(RO) | Gadalin(RO) | 138 | 276 | Black Sea Corridor | Reinforcement of the cross-section between developing wind generation hub in Eastern Romania and the rest of the system. New 400kV simple circuit OHL between existing substations. Line length: 260km. 1204 MVA | 3 | Investment on time | No change of status. | 2021 | 2021 | 1 | Suceava(RO) | Gadalin(RO) | 276 | Reinforcement of the cross-section between developing wind generation hub in Eastern Romania and the rest of the system. New 400kV simple circuit OHL between existing substations. Line length: 260km. 1204 MVA | 3 | Investment on time | No change of status. | 2021 | 2021 | 1 | Suceava(RO) | Gadalin(RO) | 138 | 276 | Black Sea Corridor | 400 kV OHL Gadalin - Suceava | Reinforcement of the cross-section between developing wind generation hub in Eastern Romania and the rest of the system. New 400kV simple circuit OHL between existing substations. Line length 260km, 1204 MVA. | 3 | Delayed | Longer than expected delay regarding clarification of legal framework for right of land acquirement and regarding environmental permitting procedure. | 31/ 12/ 2023 | 2023 | 1 |  | 0 | Gadalin (RO) | Suceava (RO) | Overhead Line | AC | 165 | 400 | 260 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2023 | 4 | 13 | ROU | Gadalin | Suceava | 46.8402 | 23.8485 | 47.5327 | 25.8346
706 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 3 | Commissioned | 3 | New 55km double circuit Pedralva - Vila Fria 400kV OHL (one circuit installed), with needed extension of existing Vila Fria substation to include 400kV facilities. | 3 | 2013 | 2013 | 1 | Pedralva (PT) | Vila Fria (PT) | 1 | 1. 3 | New 55km double circuit Pedralva - Vila Fria 400kV OHL (one circuit installed), with needed extension of existing Vila Fria substation to include 400kV facilities. | 3 | Delays due to authorization process. | 2014/2015 | 2015 | 1 | Pedralva (PT) | Vila Fria (PT) | 1. 3 | 1. 3 | New 57,5km double circuit Pedralva - V. Castelo 400kV OHL (one circuit installed). | 3 |  | 2015 | 2015 | 1 | Pedralva (PT) | V. Castelo (PT) | 1 | 3 | RES in north of Portugal | New 57,5km double circuit Pedralva - V. Castelo 400kV OHL (one circuit installed). | 3 | Investment on time | Investment on time | 2015 | 2015 | 1 | Pedralva (PT) | V. Castelo (PT) | 3 | New 57,5km double circuit Pedralva - V. Castelo 400kV OHL (one circuit installed). | 4 | Investment on time | In the first stage the line will be connected between Pedralva and Vila Nova de Famalicão (previously Vila do Conde). New substation of Ponte de Lima (previously Viana do Castelo) will be commissioned in 2018 | 2015 | 2015 | 1 | Pedralva (PT) | V. Castelo (PT) | 1 | 3 | RES in north of Portugal | Pedralva - Ponte de Lima | New 37,6 km double circuit Pedralva - Ponte de Lima 400kV OHL (one circuit installed). | 4 | Delayed | In the first stage the line will be conected between Pedralva and Vila Nova de Famalicão (previously Vila do Conde). New substation of Ponte de Lima (previously Viana do Castelo) will be commissioned in 2018 | 31/ 12/ 2016 | 2016 | 1 |  | 0 | Pedralva (PT) | Ponte de Lima (PT) | Overhead Line | AC | 680 | 400 | 37.6 | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2013 | 2016 | 3 | 6 | PRT | Pedralva | Ponte De Lima | 41.5599 | -8.3209 | 41.7675 | -8.5831
707 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 302 | Commissioned | 302 | New second circuit 400kV OHL; 1385 MVA. | 2 | 2015 | 2015 | 1 | Vyskov (CZ) | Cechy stred (CZ) | 55 | 55. 302 | New second circuit 400kV OHL; 1385 MVA. | 3 | Progresses as planned | 2015 | 2015 | 1 | Vyskov (CZ) | Cechy stred (CZ) | 55. 302 | 55. 302 | New second circuit 400kV OHL; Target capacity 2x1730 MVA. | 3 | Delayed due to permitting procedure difficulty | 2016 | 2016 | 1 | Vyskov (CZ) | Cechy stred (CZ) | 55 | 302 | CZ West-east corridor (West) | New second circuit 400kV OHL; Target capacity 2x1730 MVA. | 3 | Delayed | Delayed due to permitting procedure difficulty | 2016 | 2016 | 1 | Vyskov (CZ) | Cechy stred (CZ) | 302 | New second circuit 400kV OHL; Target capacity 2x1730 MVA. | 4 | Investment on time | Progress as indicated in TYNDP 2014 | 2016 | 2016 | 1 | Vyskov (CZ) | Cechy stred (CZ) | 55 | 302 | CZ West-East corridor | Vyskov-Cechy Stred | New second circuit 400kV OHL; Target capacity 2x1730 MVA. | 4 | Investment on time | Progress as indicated in TYNDP 2014 | 1/ 1/ 2016 | 2016 | 1 |  | 0 | Vyskov (CZ) | Cechy Stred (CZ) | Overhead Line | AC | 1000 | 400 | 98 | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2016 | 1 | 6 | CZE | Vyskov | Cechy Stred | 49.2778 | 16.9994 | 50.1431 | 14.7682
708 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 303 | Commissioned | 303 | New second circuit 400kV OHL; 1385 MVA. | 2 | 2016 | 2016 | 1 | Babylon (CZ) | Bezdecin (CZ) | 55 | 55. 303 | New second circuit 400kV OHL; 1385 MVA. | 2 | Progresses as planned | 2016 | 2016 | 1 | Babylon (CZ) | Bezdecin (CZ) | 55. 303 | 55. 303 | New second circuit 400kV OHL; 1385 MVA. | 3 | Delay caused by permitting process difficulty | 2018 | 2018 | 1 | Babylon (CZ) | Bezdecin (CZ) | 55 | 303 | CZ West-east corridor (West) | New second circuit 400kV OHL; 1385 MVA. | 3 | Delayed | Delay caused by permitting process difficulty | 2018 | 2018 | 1 | Babylon (CZ) | Bezdecin (CZ) | 303 | New second circuit 400kV OHL; 1700 MVA. | 3 | Investment on time | Progress as indicated in TYNDP 2014 | 2018 | 2018 | 1 | Babylon (CZ) | Bezdecin (CZ) | 55 | 303 | CZ West-East corridor | Babylon-Bezdecin | New second circuit 400kV OHL; 1700 MVA. | 3 | Investment on time | Progress as indicated in TYNDP 2014 | 1/ 1/ 2018 | 2018 | 1 |  | 0 | Babylon (CZ) | Bezdecin (CZ) | Overhead Line | AC | 350 | 400 | 54 | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2018 | 2 | 8 | CZE | Babylon | Bezdecin | 49.3975 | 12.8617 | 50.3857 | 14.8985
709 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 304 | Cancelled | 304 | New second circuit 400kV OHL; 1385 MVA. | 2 | 2018 | 2018 | 1 | Babylon (CZ) | Vyskov (CZ) | 55 | 55. 304 | New second circuit 400kV OHL; 1385 MVA. | 2 | Progresses as planned | 2018 | 2018 | 1 | Babylon (CZ) | Vyskov (CZ) | 55. 304 | 55. 304 | New second circuit 400kV OHL; 1385 MVA. | 3 |  | 2018 | 2018 | 1 | Babylon (CZ) | Vyskov (CZ) | 55 | 304 | CZ West-east corridor (West) | New second circuit 400kV OHL; 1385 MVA. | 3 | Delayed | Delayed due to permitting procedure difficulty | 2021 | 2021 | 1 | Babylon (CZ) | Vyskov (CZ) | 304 | New second circuit 400kV OHL; 1700 MVA. | 3 | Ahead of time | Rescheduling due to construction phases harmonization of several investments | 2019 | 2019 | 1 | Babylon (CZ) | Vyskov (CZ) | 55 | 304 | CZ West-East corridor | Babylon-Vyskov | New second circuit 400kV OHL; 1700 MVA. | 3 | Ahead of time | Rescheduling due to construction phases harmonization of several investments | 1/ 1/ 2019 | 2019 | 1 |  | 0 | Babylon (CZ) | Vyskov (CZ) | Overhead Line | AC | 750 | 400 | 73 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2019 | 1 | 9 | CZE | Babylon | Vyskov | 49.3975 | 12.8617 | 49.2778 | 16.9994
710 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 306 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 200 | 306 | North-South corridor | New 400/110kV substation equipped with transformers 2x350MVA. | 3 | Delayed | Complication of permitting procedure | 2020 | 2020 | 1 | Vitkov (CZ) |  | 306 | New 400/110kV substation equipped with transformers 2x350MVA. | 3 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Vitkov (CZ) |  | 200 | 306 | CZ Northwest-South corridor | R Vitkov | New 400/110kV substation equipped with transformers 2x350MVA. | 3 | Investment on time | Progress as planned | 1/ 1/ 2020 | 2020 | 1 |  | 0 | Vitkov (CZ) |  | Substation |  | 500 | 400 |  | New | 200 | 306 | CZ Northwest-South corridor | R Vitkov | 3 | Rescheduled | Due to the delay of the needed connection line Vitkov-Vernerov or Vitkov-Prestice, the timeschedule has to be aligned with the timeschedule of the line Vitkov-Prestice | 30/ 11/ 2022 | 2022 | 1 | CEPS | Vitkov (CZ) |  | Substation | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2022 | 2 | 8 | CZE | Vitkov |  | 49.7758 | 17.7518
711 | 2014 | 2016 | [2014, 2015, 2016] | 307 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 200 | 307 | North-South corridor | New 400/110kV substation equipped with transformers 2x350MVA. | 3 | Delayed | Complication with permitting procedure. | 2017 | 2017 | 1 | Vernerov (CZ) |  | 307 | New 400/110kV substation equipped with transformers 2x350MVA. | 4 | Investment on time | Progressed as planned | 2017 | 2017 | 1 | Vernerov (CZ) |  | 200 | 307 | CZ Northwest-South corridor | R Vernerov | New 400/110kV substation equipped with transformers 2x350MVA. | 4 | Investment on time | Progress as planned | 1/ 1/ 2017 | 2017 | 1 |  | 0 | Vernerov (CZ) |  | Substation |  | 500 | 400 |  | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2017 | 0 | 3 | CZE | Vernerov |  | 50.4051 | 13.2245
712 | 2010 | 2024 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024] | 308 | Commissioned | 308 | New 400kV double circuit OHL, 1385 MVA. | 1 | >2015 | 2015 | 1 | Vernerov (CZ) | Vitkov (CZ) | 35 | 35. 308 | New 400kV double circuit OHL, 1385 MVA. | 2 | Permitting procedure complications are foreseen (line crosses protected area) | long term |  | 1 | Vernerov (CZ) | Vitkov (CZ) | 35. 308 | 35. 308 | New 400kV double circuit OHL, 1385 MVA. | 3 |  | 2019 | 2019 | 1 | Vernerov (CZ) | Vitkov (CZ) | 200 | 308 | North-South corridor | New 400kV double circuit OHL, 1385 MVA. | 3 | Investment on time | As planned | 2019 | 2019 | 1 | Vernerov (CZ) | Vitkov (CZ) | 308 | New 400kV double circuit OHL, 1385 MVA. | 3 | Delayed | Based on CEPS request the competent authority is still in the process to change the status of the project to "public-interest project". | 2023 | 2023 | 1 | Vernerov (CZ) | Vitkov (CZ) | 200 | 308 | CZ Northwest-South corridor | Vernerov-Vitkov | New 400kV double circuit OHL, 1385 MVA. | 3 | Delayed | Based onCEPS request the competent authority is still in the process to changethe status of the project to "public-interest project". | 1/ 1/ 2023 | 2023 | 1 |  | 0 | Vernerov (CZ) | Vitkov (CZ) | Overhead Line | AC | 500 | 400 | 71 | New | 200 | 308 | CZ Northwest-South corridor | Vernerov-Vitkov | 3 | Delayed | Delay due to the permit grant procedure and amendment of the respective legal framework | 30/ 07/ 2025 | 2025 | 1 |  | Vernerov (CZ) | Vitkov (CZ) | Overhead Line | AC | 400 | 200 | 308 | CZ Northwest-South corridor | Vernerov-Vitkov | New 400 kV double circuit OHL with a transmission capacity of 2x1713 MVA and 83 km length. | 3 | Ahead of time |  | 2023 | 2023 | 1 | CEPS | 3.11.1, 3.11.2, 3.11.4 | 1 | 0 | Vernerov (CZ) | Vitkov (CZ) | ACTransmissionLine | AC | 83 | MostlyNew | 200 | 308 | CZ Northwest-South corridor | Vernerov-Vitkov | New 400 kV double circuit OHL with a transmission capacity of 2 x 2445 A and 83 km length. | 3 | Investment on time |  | 06-2024 | 2024 | 1 | CEPS | 3.11.1 and 3.11.2 | 1 | 0 | Vernerov (CZ) | Vitkov (CZ) | ACTransmissionLine | AC | 0 | 400 | 83 | MostlyNew | 200 | 308 | CZ Northwest-South corridor | Vernerov-Vitkov | New 400 kV double circuit OHL with a transmission capacity of 2 x 2445 A and 83 km length. | 4 | Investment on time |  | 06-2024 | 2024 | 1 | CEPS | 2.3.1 | 1 | 0 | Vernerov (CZ) | Vitkov (CZ) | ACTransmissionLine | AC | 0 | 400 | 83 | MostlyNew | [5 empty] | 5 | Commissioned |  |  | 0 | [5 empty] | 2015 | 2024 | 9 | 14 | CZE | Vernerov | Vitkov | 50.4051 | 13.2245 | 49.7758 | 17.7518
713 | 2010 | 2020 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020] | 309 | Commissioned | 309 | New 400kV double circuit OHL, 1385 MVA. | 2 | 2020 | 2020 | 1 | Vitkov (CZ) | Prestice (CZ) | 35 | 35. 309 | New 400kV double circuit OHL, 1385 MVA. | 1 | Permitting procedure complications are foreseen (line crosses protected area) | long term |  | 1 | Vitkov (CZ) | Prestice (CZ) | 35. 309 | 35. 309 | New 400kV double circuit OHL, 2x1730 MVA. | 3 |  | 2021 | 2021 | 1 | Vitkov (CZ) | Prestice (CZ) | 200 | 309 | North-South corridor | New 400kV double circuit OHL, 2x1730 MVA. | 3 | Investment on time | As planned | 2021 | 2021 | 1 | Vitkov (CZ) | Prestice (CZ) | 309 | New 400kV double circuit OHL, 2x1730 MVA. | 3 | Ahead of time | Changes due to the delay of other investment connecting substation Vitkov | 2020 | 2020 | 1 | Vitkov (CZ) | Prestice (CZ) | 200 | 309 | CZ Northwest-South corridor | Vitkov-Prestice | New 400kV double circuit OHL, 2x1730 MVA. | 3 | Ahead of time | Changes due to the delay of other investment connecting substation Vitkov | 1/ 1/ 2020 | 2020 | 1 |  | 0 | Vitkov (CZ) | Prestice (CZ) | Overhead Line | AC | 500 | 400 | 86 | New | 200 | 309 | CZ Northwest-South corridor | Vitkov-Prestice | 3 | Delayed | Delay due to the permit grant procedure and amendment of the respective legal framework | 30/ 11/ 2022 | 2022 | 1 |  | Vitkov (CZ) | Prestice (CZ) | Overhead Line | AC | 400 | 200 | 309 | CZ Northwest-South corridor | Vitkov-Prestice | New 400 kV double circuit OHL with transmission capacity of 2x1713 MVA and 87 km length. | 4 | Ahead of time |  | 2021 | 2021 | 1 | CEPS | 3.11.1, 3.11.2, 3.11.4 | 1 | 0 | Vitkov (CZ) | Prestice (CZ) | ACTransmissionLine | AC | 87 | MostlyNew | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2021 | 1 | 11 | CZE | Vitkov | Prestice | 49.7758 | 17.7518 | 49.5726 | 13.3296
714 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 31 | Cancelled | 31 | New 177km double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to existing El Palmar-Litoral 400kV line ). In addition, the existing 173km single circuit Litoral-Tabernas-Hueneja-Caparacena 400kV line will be upgraded (uprated) in order to increase its capacity from 1310 to 1590 MVA. | 3 | 2012/2013 | 2013 | 1 | Caparacena (ES) | La Ribina (ES) | 13 | 13. 31 | New double circuit Caparacena-Baza-La Ribina 400kV OHL, with two new 400kV substations in Baza and La Ribina (these substations will be also connected to Carril-Litoral 400kV line ). | 3 | Delays due to authorization process. | 2016 | 2016 | 1 | Caparacena (ES) | La Ribina (ES) | 13. 31 | 13. 31 | New double circuit Caparacena-Baza-La Ribina 400kV OHL. | 3 | National law RDL 13/2012 has frozen the permitting process until publication of the next NDP. | 2018 | 2018 | 1 | Caparacena (ES) | La Ribina (ES) | 13 | 31 | Baza project | New double circuit Caparacena-Baza-La Ribina 400kV OHL. | 1 | Rescheduled | Investment rescheduled due to, and in accordance with, delayed development of new power plant, as considered in the Master Plan 2020 in progress | 2025 | 2025 | 1 | Caparacena (ES) | La Ribina (ES) | 31 | New double circuit Caparacena-Baza-La Ribina 400kV OHL. | 1 | Investment on time | Investment rescheduled due to, and in accordance with, delayed development of new power plant, as considered in the Master Plan 2020 in progress | 2025 | 2025 | 1 | Caparacena (ES) | La Ribina (ES) | 13 | 31 | Baza project | Axis Caparacena-Baza-La Ribina | New double circuit Caparacena-Baza-La Ribina 400kV OHL. | 1 | Investment on time | Investment rescheduled due to, and in accordance with, delayed development of new power plant, as considered in the Master Plan 2020 in progress | 1/ 1/ 2025 | 2025 | 1 |  | 0 | Caparacena (ES) | La Ribina (ES) | Overhead Line | AC | 2060 | 400 | 177 | New | 13 | 31 | Baza project | Axis Caparacena-Baza-La Ribina | 1 | Investment on time |  | 2025 | 2025 | 1 | REE | Caparacena (ES) | La Ribina (ES) | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2013 | 2025 | 12 | 15 | ESP | Caparacena | La Ribina | 37.2651 | -3.7143 | 37.2472 | -1.8585
715 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 311 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 35 | 311 | North-South corridor | Upgrade of the existing substation 400/110kV; upgrade transformers 2x350MVA. | 3 | Delayed | Project commissioning date postponed due to rescheduling of transmission projects together with commission rescheduled on the generation investor's side | 2024 | 2024 | 1 | Kocin (CZ) |  | 311 | Upgrade of the existing substation 400/110kV; upgrade transformers 2x350MVA. | 3 | Investment on time | Investment evolution as indicated in previous TYNDP. | 2024 | 2024 | 1 | Kocin (CZ) |  | 35 | 311 | CZ Southwest-east corridor | R Kocin | Upgrade of the existing substation 400/110kV; upgrade transformers 2x350MVA. | 3 | Investment on time | Investment evolution as indicated in previous TYNDP. | 1/ 1/ 2024 | 2024 | 1 |  | 0 | Kocin (CZ) |  | Substation |  | 500 | 400 |  | New | 35 | 311 | CZ Southwest-east corridor | R Kocin | 4 | Investment on time | The construction of the substation is underway | 1/ 1/ 2024 | 2024 | 1 | CEPS | Kocin (CZ) |  | Substation | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2024 | 2024 | 0 | 10 | CZE | Kocin |  | 49.9304 | 13.4761
716 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 312 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 200 | 312 | North-South corridor | Upgrade of the existing substation 400/110kV with two transformers 2x350MVA. | 3 | Delayed | Project delayed due to rescheduling of transmission projects together with commission rescheduled on the generation investor's side | 2020 | 2020 | 1 | Mirovka (CZ) |  | 312 | Upgrade of the existing substation 400/110kV with two transformers 2x350MVA. | 3 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Mirovka (CZ) |  | 200 | 312 | CZ Northwest-South corridor | R Mirovka | Upgrade of the existing substation 400/110kV with two transformers 2x350MVA. | 3 | Investment on time | Progress as planned | 1/ 1/ 2020 | 2020 | 1 |  | 0 | Mirovka (CZ) |  | Substation |  | 300 | 400 |  | New | 200 | 312 | CZ Northwest-South corridor | R Mirovka | 3 | Rescheduled | The construction of phase one is completed. The second phase of construction (extention for the purpose of connection of new line) has to be aligned with the timeschedule of line Kocin-Mirovka | 30/ 09/ 2025 | 2025 | 1 |  | Mirovka (CZ) |  | Substation | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2025 | 5 | 11 | CZE | Mirovka |  | 49.5796 | 15.6137
717 | 2010 | 2026 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 313 |  | 313 | Connection of 2 existing 400kV substations with double circuit OHL having 120.5km length: and a capacity of 2X1385 MVA. | 2 | 2017/2018 | 2018 | 1 | Kocin (CZ) | Mirovka (CZ) | 35 | 35. 313 | Connection of 2 existing 400kV substations with double circuit OHL having 120.5km length: and a capacity of 2X1385 MVA. | 2 | Schedule harmonization decided with market participants | long term |  | 1 | Kocin (CZ) | Mirovka (CZ) | 35. 313 | 35. 313 | Connection of 2 existing 400kV substations with double circuit OHL having 120.5km length: and a capacity of 2X1385 MVA. | 3 |  | 2020 | 2020 | 1 | Kocin (CZ) | Mirovka (CZ) | 35 | 313 | North-South corridor | Connection of 2 existing 400kV substations with double circuit OHL having 120.5km length: and a capacity of 2X1700 MVA. | 3 | Delayed | Project commissioning date postponed due to rescheduling of transmission projects together with commission rescheduled on the generation investor's side. Permitting procedure issues and wiring change. | 2024 | 2024 | 1 | Kocin (CZ) | Mirovka (CZ) | 313 | Connection of 2 existing 400kV substations with double circuit OHL having 120.5km length: and a capacity of 2X1700 MVA. | 3 | Investment on time | Investment evolution as indicated in previous TYNDP | 2024 | 2024 | 1 | Kocin (CZ) | Mirovka (CZ) | 35 | 313 | CZ Southwest-east corridor | Kocin-Mirovka | Connection of 2 existing 400kV substations with double circuit OHL having 120.5km length and a capacity of 2X1700 MVA. | 3 | Investment on time | Investment evolution as indicated in previous TYNDP | 1/ 1/ 2024 | 2024 | 1 |  | 0 | Kocin (CZ) | Mirovka (CZ) | Overhead Line | AC | 500 | 400 | 121 | New | 35 | 313 | CZ Southwest-east corridor | Kocin-Mirovka | 3 | Delayed | Delay due to the permit grant procedure and amendment of the respective legal framework | 1/ 1/ 2024 | 2024 | 1 |  | Kocin (CZ) | Mirovka (CZ) | Overhead Line | AC | 400 | 35 | 313 | CZ Southwest-east corridor | Kocin-Mirovka | Connection of 2 existing 400 kV substations with new double circuit OHL having 120.5 km length and a transmission capacity of 2X1713 MVA. | 3 | Delayed | Delay due to the permit grant procedure and amendment of the respective legal framework | 2026 | 2026 | 1 | CEPS | 3.11.3, 3.11.4 | 1 | 0 | Kocin (CZ) | Mirovka (CZ) | ACTransmissionLine | AC | 120.5 | New | 35 | 313 | CZ Southwest-east corridor | Kocin-Mirovka | Connection of 2 existing 400 kV substations with new double circuit OHL having 120.5 km length and a transmission capacity of 2 x 2445 A. | 3 | Delayed | Delays due to other permit granting reasons | 10-2028 | 2028 | 1 | CEPS | 3.11.3 and 3.11.4 | 1 | 0 | Kocin (CZ) | Mirovka (CZ) | ACTransmissionLine | AC | 0 | 400 | 120.5 | MostlyNew | 35 | 313 | CZ Southwest-east corridor | Kocin-Mirovka | Connection of 2 existing 400 kV substations with new double circuit OHL having 120.5 km length and a transmission capacity of 2 x 2445 A. | 3 | Delayed | Delays due to other permit granting reasons | 10-2029 | 2029 | 1 | CEPS | 2.3.2 and 2.3.3 | 1 | 0 | Kocin (CZ) | Mirovka (CZ) | ACTransmissionLine | AC | 0 | 400 | 120.5 | MostlyNew | 35 | 313 | CZ Southwest-east corridor | Kocin-Mirovka | Connection of 2 existing 400 kV substations with new double circuit OHL having 120.5 km length and a transmission capacity of 2 x 2445 A. |  |  | 10-2029 | 2029 | 1 | CEPS | 0 | XX | XX | Mostly new | 2018 | 2029 | 11 | 19 | CZE | Kocin | Mirovka | 49.9304 | 13.4761 | 49.5796 | 15.6137
718 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 314 | Commissioned | 314 | New double circuit OHL with a capacity of 2x1385 MVA and 26.5km length. | 2 | 2018/2019 | 2019 | 1 | Mirovka (CZ) | V413 (CZ) | 35 | 35. 314 | New double circuit OHL with a capacity of 2x1385 MVA and 26.5km length. | 2 | Schedule harmonization decided with market participants | long term |  | 1 | Mirovka (CZ) | V413 (CZ) | 35. 314 | 35. 314 | New double circuit OHL with a capacity of 2x1385 MVA and 26.5km length. | 3 |  | 2017 | 2017 | 1 | Mirovka (CZ) | V413 (CZ) | 200 | 314 | North-South corridor | New double circuit OHL with a capacity of 2x1385 MVA and 26.5km length. | 3 | Delayed | Project delayed due to rescheduling of transmission projects together with commission rescheduled on the generation investor's side | 2020 | 2020 | 1 | Mirovka (CZ) | V413 (CZ) | 314 | New double circuit OHL with a capacity of 2x1385 MVA and 26.5km length. | 3 | Ahead of time | Project rescheduled due to changes of transmission projects to harmonize construction phases. | 2018 | 2018 | 1 | Mirovka (CZ) | V413 (CZ) | 200 | 314 | CZ Northwest-South corridor | Mirkovka-V413 | New double circuit OHL with a capacity of 2x1385 MVA and 26.5km length. | 3 | Ahead of time | Project rescheduled due to changes of transmission projects to harmonize construction phases. | 1/ 1/ 2018 | 2018 | 1 |  | 0 | Mirovka (CZ) | V413 (CZ) | Overhead Line | AC | 200 | 400 | 27 | New | 200 | 314 | CZ Northwest-South corridor | Mirkovka-V413 | 3 | Delayed | Delay due to the permit grant procedure and amendment of the respective legal framework | 30/ 05/ 2019 | 2019 | 1 |  | Mirovka (CZ) | V413 (CZ) | Overhead Line | AC | 400 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2019 | 0 | 9 | CZE | Mirovka | V | 49.5796 | 15.6137 | 49.6777 | 18.3674
719 | 2010 | 2026 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 315 |  | 315 | Adding second circuit to existing single circuit line OHL upgrade in length of 115.8km. Target capacity 2x1385 MVA. | 2 | 2019/2021 | 2021 | 1 | Kocin (CZ) | Prestice (CZ) | 35 | 35. 315 | Adding second circuit to existing single circuit line OHL upgrade in length of 115.8km. Target capacity 2x1385 MVA. | 2 | Schedule harmonization decided with market participants | long term |  | 1 | Kocin (CZ) | Prestice (CZ) | 35. 315 | 35. 315 | Adding second circuit to existing single circuit line OHL upgrade in length of 115.8km. Target capacity 2x1385 MVA. | 3 |  | 2024 | 2024 | 1 | Kocin (CZ) | Prestice (CZ) | 35 | 315 | North-South corridor | Adding second circuit to existing single circuit line OHL upgrade in length of 115.8km. Target capacity 2x1700 MVA. | 3 | Delayed | Project commissioning date postponed due to rescheduling of transmission projects together with commission rescheduled on the generation investor's side. Wiring change to higher capacity. | 2028 | 2028 | 1 | Kocin (CZ) | Prestice (CZ) | 315 | Adding second circuit to existing single circuit line OHL upgrade in length of 115.8km. Target capacity 2x1700 MVA. | 3 | Investment on time | Investment evolution as indicated in previous TYNDP. | 2028 | 2028 | 1 | Kocin (CZ) | Prestice (CZ) | 35 | 315 | CZ Southwest-east corridor | Kocin-Prestice | Adding second circuit to existing single circuit line OHL upgrade in length of 115.8km. Target capacity 2x1700 MVA. | 3 | Investment on time | Investment evolution as indicated in previous TYNDP. | 1/ 1/ 2028 | 2028 | 1 |  | 0 | Kocin (CZ) | Prestice (CZ) | Overhead Line | AC | 500 | 400 | 116 | New | 35 | 315 | CZ Southwest-east corridor | Kocin-Prestice | 3 | Investment on time | The project is udergoing permit grant process | 1/ 1/ 2028 | 2028 | 1 |  | Kocin (CZ) | Prestice (CZ) | Overhead Line | AC | 400 | 35 | 315 | CZ Southwest-east corridor | Kocin-Prestice | Adding second circuit to the existing single circuit OHL with a total transmission capacity of 2x1730 MVA and 117 km length | 3 | Investment on time |  | 2028 | 2028 | 1 | CEPS | 3.11.3, 3.11.4 | 1 | 0 | Kocin (CZ) | Prestice (CZ) | ACTransmissionLine | AC | 117 | New | 35 | 315 | CZ Southwest-east corridor | Kocin-Prestice | Adding second circuit to the existing single circuit OHL with a total transmission capacity of 2 x 2445 A and 117 km length | 3 | Investment on time |  | 12-2028 | 2028 | 1 | CEPS | 3.11.3 and 3.11.4 | 1 | 0 | Kocin (CZ) | Prestice (CZ) | ACTransmissionLine | AC | 0 | 400 | 117 | MostlyNew | 35 | 315 | CZ Southwest-east corridor | Kocin-Prestice | Adding second circuit to the existing single circuit OHL with a total transmission capacity of 2 x 2445 A and 117 km length | 3 | Investment on time |  | 12-2028 | 2028 | 1 | CEPS | 2.3.2 and 2.3.3 | 1 | 0 | Kocin (CZ) | Prestice (CZ) | ACTransmissionLine | AC | 0 | 400 | 117 | MostlyNew | 35 | 315 | CZ Southwest-east corridor | Kocin-Prestice | Adding second circuit to the existing single circuit OHL with a total transmission capacity of 2 x 2445 A and 117 km length |  |  | 12-2028 | 2028 | 1 | CEPS | 0 | XX | XX | Mostly new | 2021 | 2028 | 7 | 18 | CZE | Kocin | Prestice | 49.9304 | 13.4761 | 49.5726 | 13.3296
720 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 316 | Cancelled | 316 | Adding second circuit to existing single circuit line (88.5km, 2x1385 MVA). | 2 | 2019/2021 | 2021 | 1 | Mirovka (CZ) | Cebin (CZ) | 35 | 35. 316 | Adding second circuit to existing single circuit line (88.5km, 2x1385 MVA). | 1 | Schedule harmonization decided with market participants | long term |  | 1 | Mirovka (CZ) | Cebin (CZ) | 35. 316 | 35. 316 | Adding second circuit to existing single circuit line (88.5km, 2x1385 MVA). | 3 |  | 2024 | 2024 | 1 | Mirovka (CZ) | Cebin (CZ) | 35 | 316 | North-South corridor | Adding second circuit to existing single circuit line (88.5km, 2x1700 MVA). | 3 | Delayed | Project is dependent on other investments which are delayed. | 2028 | 2028 | 1 | Mirovka (CZ) | Cebin (CZ) | 316 | Adding second circuit to existing single circuit line (88.5km, 2x1700 MVA). | 3 | Rescheduled | Changes on the generation side (in relation to other types of generation) | 2029 | 2029 | 1 | Mirovka (CZ) | Cebin (CZ) | 35 | 316 | CZ Southwest-east corridor | Mirovka-Cebin | Adding second circuit to existing single circuit line (88.5km, 2x1700 MVA). | 3 | Rescheduled | Changes on the generation side (in relation to other types of generation) | 1/ 1/ 2029 | 2029 | 1 |  | 0 | Mirovka (CZ) | Cebin (CZ) | Overhead Line | AC | 100 | 400 | 89 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2029 | 8 | 19 | CZE | Mirovka | Cebin | 49.5796 | 15.6137 | 49.3083 | 16.4798
721 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 335 | Commissioned | 335 | New 138km 400kV 2x1870 MVA double circuit OHL line Ostrołęka - Olsztyn Mątki after dismantling of 220kV line Ostrołęka - Olsztyn with one circuit from Ostrołęka to Olsztyn temporarily on 220kV. | 3 | 2015 | 2015 | 1 | Ostrołęka (PL) | Olsztyn Mątki (PL) | 100 | 100. 335 | New 138km 400kV 2x1870 MVA double circuit OHL line Ostrołęka - Olsztyn Mątki after dismantling of 220kV line Ostrołęka - Olsztyn with one circuit from Ostrołęka to Olsztyn temporarily on 220kV. | 3 | The time schedule of the project was shifted to meet the schedule of the generation connection. | 2017 | 2017 | 1 | Ostrołęka (PL) | Olsztyn Mątki (PL) | 100. 335 | 100. 335 | New 138 km 400 kV 2x1870 MVA double circuit OHL line Ostrołęka - Olsztyn Mątki after dismantling of 220kV line Ostrołęka - Olsztyn with one circuit from Ostrołęka to Olsztyn temporarily on 220 kV. | 3 | The commissioning date of the investment has been adopted to meet the schedule of generation connection in the region of north-east Poland. | 2019 | 2019 | 1 | Ostroleka (PL) | Olsztyn Matki (PL) | 123 | 335 | LitPol Link Stage 2 | Construction of new 400 kV line Ostrołęka - Olsztyn Mątki after dismantling of 220kV line Ostrołęka - Olsztyn with one circuit from Ostrołęka to Olsztyn temporarily on 220 kV. | 3 | Investment on time | The investment in on time. | 2017 | 2017 | 1 | Ostroleka (PL) | Olsztyn Matki (PL) | 335 | Construction of new 400 kV line Ostrołęka - Olsztyn Mątki after dismantling of 220kV line Ostrołęka - Olsztyn with one circuit from Ostrołęka to Olsztyn temporarily on 220 kV. | 3 | Delayed | Delay due to lingering permit granting process (land acquisition, right of way-local municipalities zoning plans). | 2018 | 2018 | 1 | Ostrołęka (PL) | Olsztyn Mątki (PL) | 123 | 335 | LitPol Link Stage 2 | Ostrołęka-Olsztyn Mątki | Existing 220 kV single circuit line of 139 km between Ostrołęka and Olsztyn Mątki will be upgraded to 400 kV AC double circuit OHL with capacity of 2x1870 MVA. After dismantling of 220 kV line Ostrołęka - Olsztyn the one circuit Ostrołęka - Olsztyn Mątki will be temporarily switched on 220kV and connected to Olsztyn substation. | 3 | Delayed | Delay due to lingering permit granting process and other formal aspects. | 1/ 1/ 2018 | 2018 | 1 |  | 0 | Ostrołęka (PL) | Olsztyn Mątki (PL) | Overhead Line | AC | 500 | 400 | 138 | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2018 | 3 | 8 | POL | Ostroka | Olsztyn Mtki
722 | 2010 | 2022 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022] | 353 | Commissioned | 353 | Construction of a new double circuit 400kV OHL Krajnik - Baczyna (2x1870 MVA, 91km); single circuit temporarily working at 220kV on Krajnik - Gorzów part + New substation 400kV Baczyna will be connected by splitting and extending existing line Krajnik-Plewiska + Upgrading of limitations line Krajnik - Plewiska. | 2 | 2020 | 2020 | 1 | Krajnik (PL) | Baczyna (PL) | 58 | 58. 353 | Construction of a new double circuit 400kV OHL Krajnik - Baczyna (2x1870 MVA, 91km); single circuit temporarily working at 220kV on Krajnik - Gorzów part + New substation 400kV Baczyna will be connected by splitting and extending existing line Krajnik-Plewiska + Upgrading of limitations line Krajnik - Plewiska. | 2 | Progresses as planned | 2020 | 2020 | 1 | Krajnik (PL) | Baczyna (PL) | 58. 353 | 58. 353 | Construction of a new double circuit 400 kV OHL Krajnik - Baczyna (2x1870 MVA, 91km); single circuit temporarily working at 220kV on Krajnik - Gorzów part | 2 | The currently provided commissioning dates were set in the detailed investment plan introduced in 2013. Previous dates in TYNDP 2012 were synchronized with a general national development plan which provided only time horizons for the investments (2015, 2020). | 2019 | 2019 | 1 | Krajnik (PL) | Baczyna (PL) | 58 | 353 | GerPol Power Bridge | Construction of new 400 kV double circuit line Krajnik – Baczyna. | 2 | Investment on time | Investment is in the tendering procedure. | 2020 | 2020 | 1 | Krajnik (PL) | Baczyna (PL) | 353 | Construction of new 400 kV double circuit line Krajnik – Baczyna. | 2 | Investment on time | Investment is in the tendering procedure. | 2020 | 2020 | 1 | Krajnik (PL) | Baczyna (PL) | 230 | 353 | GerPol Power Bridge I | Krajnik-Baczyna | Construction of new 400 kV double circuit line Krajnik – Baczyna. | 2 | Investment on time | The investment will enter the tendering procedure in 2016 and will be realized in design and build scheme. The line is planned to be operational in 2020. | 31/12/2021 | 2021 | 1 |  | 0 | Krajnik (PL) | Baczyna (PL) | Overhead Line | AC | 750 | 400 | 70 | New | 230 | 353 | GerPol Power Bridge I | Krajnik-Baczyna | 3 | Investment on time |  | 2021 | 2021 | 1 | PSE | Krajnik (PL) | Baczyna (PL) | Overhead Line | AC | 400 | 230 | 353 | GerPol Power Bridge I | Krajnik-Baczyna | Construction of new 400 kV double circuit line Krajnik - Baczyna. One circuit will be operating temporarily on 220 kV between stations Krajnik and Gorzów with winter thermal limit 1290 A, summer thermal limit 990 A. | 3 | Investment on time |  | 2021 | 2021 | 1 | Polskie Sieci Elektroenergetyczne S.A. | 3.14 (including 3.14.2, 3.14.3, 3.14.4) | 0 | 0 | Krajnik (PL) | Baczyna (PL) | ACTransmissionLine | AC | 70 | New | 230 | 353 | GerPol Power Bridge I | Krajnik-Baczyna | Construction of new 400 kV double circuit line Krajnik - Baczyna. | 4 | Rescheduled |  | 03-2023 | 2023 | 1 | Polskie Sieci Elektroenergetyczne S.A. | 3.14 Internal reinforcements in Poland (including 3.14.2, 3.14.3, 3.14.4) | 0 | 0 | Krajnik (PL) | Baczyna (PL) | ACTransmissionLine | AC | 0 | 400 | 70 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2023 | 3 | 13 | POL | Krajnik | Baczyna | 53.1974 | 14.4697
723 | 2010 | 2022 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022] | 355 | Commissioned | 355 | Double circuit line 220kV Mikułowa-Świebodzice will be upgraded to 400kV - single circuit temporarily working at 220kV (2x1870 MVA). | 2 | 2020 | 2020 | 1 | Mikułowa (PL) | Świebodzice (PL) | 58 | 58. 355 | Double circuit line 220kV Mikułowa-Świebodzice will be upgraded to 400kV - single circuit temporarily working at 220kV. | 2 | Progresses as planned | 2020 | 2020 | 1 | Mikułowa (PL) | Świebodzice (PL) | 58. 355 | 58. 355 | Double circuit line 220kV Mikułowa-Świebodzice will be upgraded to 400kV - single circuit temporarily working at 220kV. | 2 | The change in the commissioning date due to detailed rescheduling introduced in the latest investment plan. Adjustments were introduced after analysis of land acquisition problems and local opposition issues. | 2021 | 2021 | 1 | Mikulowa (PL) | Swiebodzice (PL) | 58 | 355 | GerPol Power Bridge | Construction of new 400 kV double circuit line Mikułowa-Świebodzice in place of existing 220 kV line. | 2 | Investment on time | Investment on time. | 2020 | 2020 | 1 | Mikulowa (PL) | Swiebodzice (PL) | 355 | Construction of new 400 kV double circuit line Mikułowa- Świebodzice in place of existing 220 kV line. | 2 | Investment on time | The investment will enter the tendering procedure as of beginning of 2016 and will be realized in design and build scheme. | 2020 | 2020 | 1 | Mikułowa (PL) | Świebodzice (PL) | 230 | 355 | GerPol Power Bridge I | Mikułowa - Świebodzice | Construction of new 400 kV double circuit line Mikułowa-Świebodzice in place of existing 220 kV line. | 2 | Investment on time | The investment will enter the tendering procedure in 2016 and will be realized in design and build scheme. The line is planned to be operational in 2020. | 31/12/2021 | 2021 | 1 |  | 0 | Mikułowa (PL) | Świebodzice (PL) | Overhead Line | AC | 750 | 400 | 100 | New | 230 | 355 | GerPol Power Bridge I | Mikułowa - Świebodzice | 2 | Rescheduled |  | 2023 | 2023 | 1 |  | Mikułowa (PL) | Świebodzice (PL) | Overhead Line | AC | 400 | 230 | 355 | GerPol Power Bridge I | Mikulowa - Swiebodzice | Construction of new 400 kV double circuit line Mikulowa-Swiebodzice in place of existing 220 kV line. One circuit will be operating temporarily on 220 kV between stations Mikulowa and Swiebodzice with winter thermal limit 1290 A, summer thermal limit 990 A. | 3 | Rescheduled |  | 2024 | 2024 | 1 | Polskie Sieci Elektroenergetyczne S.A. | 3.14 (including 3.14.2, 3.14.3, 3.14.4) | 0 | 0 | Mikulowa (PL) | Swiebodzice (PL) | ACTransmissionLine | AC | 100 | New | 230 | 355 | GerPol Power Bridge I | Mikulowa - Swiebodzice | Construction of new 400 kV double circuit line Mikulowa-Swiebodzice in place of existing 220 kV line together with expansion of 400/220/110kV Swiebodzice substation and 400/220/110kV Mikulowa substation. One circuit will be operating temporarily on 220 kV between stations Mikulowa and Swiebodzice with winter thermal limit 1290 A, summer thermal limit 990 A. | 3 | Rescheduled |  | 12-2024 | 2024 | 1 | Polskie Sieci Elektroenergetyczne S.A. | 3.14 Internal reinforcements in Poland (including 3.14.2, 3.14.3, 3.14.4) | 0 | 0 | Mikulowa (PL) | Swiebodzice (PL) | ACTransmissionLine | AC | 0 | 400 | 108 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2024 | 4 | 14 | POL | Mikulowa | Swiebodzice | 51.0808 | 15.1087 | 50.8596 | 16.3196
724 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 36 | Commissioned | 36 | New HVDC (VSC) bipolar interconnection in the Eastern part of the border, via 320kV DC underground cable using existing infrastructures corridors and converters in both ending points. The thermal capacity is expected in the range 2x825-2x1000MW. Total line length: 60km | 3 | 2014 | 2014 | 1 | Sta.Llogaia (ES) | Baixas (FR) | 5 | 5. 36 | New HVDC (VSC) bipolar interconnection in the Eastern part of the border, via 320kV DC underground cable using existing infrastructures corridors and converters in both ending points. | 4 | Progresses as planned. | 2014 | 2014 | 1 | Sta.Llogaia (ES) | Baixas (FR) | 5. 36 | 5. 36 | New HVDC (VSC) bipolar interconnection in the Eastern part of the border, via 320kV DC underground cable using existing infrastructures corridors and converters in both ending points. | 3 |  | 2014 | 2014 | 1 | Sta.Llogaia (ES) | Baixas (FR) | 5 | 36 | Eastern interconnection ES-FR | New HVDC (VSC) bipolar interconnection in the Eastern part of the border, via 320kV DC underground cable using existing infrastructures corridors and converters in both ending points. | 4 | Delayed | Answering all concerns expressed during the authorization process in Spain and environmental issues in France led to postponing the investment. Both issues are solved by now. | 2015 | 2015 | 1 | Sta.Llogaia (ES) | Baixas (FR) | 36 | New HVDC (VSC) bipolar interconnection in the Eastern part of the border, via 320kV DC underground cable using existing infrastructures corridors and converters in both ending points. | 5 | Commissioned | Construction finalized in December 2014. Commissioned for commercial operation in June 2015 | 2015 | 2015 | 1 | Sta.Llogaia (ES) | Baixas (FR) | [10 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2014 | 2015 | 1 | 5 | ESP;FRA | Sta.Llogaia | Baixas | 42.5767 | 1.0887 | 41.3976 | 2.1446
725 | 2014 | 2015 | [2014, 2015] | 368 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 59 | 368 | LitPol Link Stage 1 | Construction of a new 400 kV interconnector line from Ełk to PL-LT border. | 4 | Investment on time | Investment is under construction. | 2015 | 2015 | 1 | Elk (PL) | PL-LT border | 368 | Construction of a new 400 kV interconnector line from Ełk to PL-LT border. |  | Investment on time | Investment is under construction. | 2015 | 2015 | 1 | Ełk (PL) | PL-LT border | [5 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 1 | POL | Ek | Pl-Lt Border | 49.6888 | 21.7763
726 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 369 | Commissioned | 369 | Construction of a new 400kV OHL Siedlce Ujrzanów - Miłosna (1870 MVA, 84km) + A new AC 400kV switchgear in existing substation Siedlce Ujrzanow with transformation 400/110kV 400 MVA. | 3 | 2015 | 2015 | 1 | Siedlce Ujrzanów (PL) | Miłosna (PL) | 59 | 59. 369 | Construction of a new 400kV OHL Siedlce Ujrzanów - Miłosna (1870 MVA, 84km) + A new AC 400kV switchgear in existing substation Siedlce Ujrzanow with transformation 400/110kV 400 MVA. | 3 | Progresses as planned | 2015 | 2015 | 1 | Siedlce Ujrzanów (PL) | Miłosna (PL) | 59. 369 | 59. 369 | Construction of a new 400kV OHL Siedlce Ujrzanów - Miłosna (1870 MVA, 84km) + A new AC 400kV switchgear in existing substation Siedlce Ujrzanow with transformation 400/110kV 400 MVA. | 4 |  | 2015 | 2015 | 1 | Siedlce Ujrzanów (PL) | Milosna (PL) | 59 | 369 | LitPol Link Stage 1 | Construction of new 400 kV line Siedlce Ujrzanów - Miłosna. | 4 | Investment on time | The project is in the construction phase. | 2015 | 2015 | 1 | Siedlce Ujrzanów (PL) | Milosna (PL) | 369 | Construction of new 400 kV line Siedlce Ujrzanów - Miłosna. | 4 | Investment on time | The project is in the construction phase. | 2015 | 2015 | 1 | Siedlce Ujrzanów (PL) | Miłosna (PL) | [5 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 5 | POL | Siedlce Ujrzanów | Miosna | 52.1339 | 22.3146
727 | 2012 | 2015 | [2012, 2013, 2014, 2015] | 370 | Commissioned | [5 empty] | 0 |  |  | 59 | 59. 370 | Construction of a new 400kV double circuit OHL Ełk - Łomża (2x1870 MVA, 95km) + A new AC 400kV switchgear in existing substation Elk + A new 400 kV AC substation Łomża | 3 | Łomża has been elected as end substation for the project and the technical description is adapted accordingly. Progresses as planned otherwise. | 2015 | 2015 | 1 | Ełk (PL) | Łomża (PL) | 59. 370 | 59. 370 | Construction of a new 400kV double circuit OHL Ełk - Łomża (2x1870 MVA, 95km) + A new AC 400kV switchgear in existing substation Elk | 3 |  | 2015 | 2015 | 1 | Elk (PL) | Lomza (PL) | 59 | 370 | LitPol Link Stage 1 | Construction of new 400 kV line Ełk-Łomża. | 4 | Investment on time | The project is under construction. | 2015 | 2015 | 1 | Elk (PL) | Lomza (PL) | 370 | Construction of new 400 kV line Ełk-Łomża. | 4 | Investment on time | The project is under construction. | 2015 | 2015 | 1 | Ełk (PL) | Łomża (PL) | [5 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 3 | POL | Ek | Oma | 49.6888 | 21.7763 | 52.2408 | 21.0239
728 | 2014 | 2015 | [2014, 2015] | 371 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 59 | 371 | LitPol Link Stage 1 | Construction of new 400 kV line Ostroleka-Lomza-Narew + extension of substation Narew. | 4 | Investment on time | The project is under construction. | 2015 | 2015 | 1 | Ostroleka (PL) | Narew (PL) | 371 | Construction of new 400 kV line Ostrolęka-Łomża-Narew. | 5 | Commissioned | Commissioned. | 2015 | 2015 | 1 | Ostrołęka (PL) | Narew (PL) | [10 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 1 | POL | Ostroka | Narew |  |  | 53.1297 | 22.817
729 | 2010 | 2022 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022] | 373 | Commissioned | 373 | Single circuit line 220kV Ostrołęka-Miłosna will be partly upgraded to double circuit line 400kV (2x1870 MVA, 106km) with development of Ostrołęka 400kV substation + New substation 400kV Stanisławów will be connected by splitting and extending existing line Miłosna-Narew and Miłosna-Siedlce. | 3 | 2020 | 2020 | 1 | Ostrołęka (PL) | Stanisławów (PL) | 59 | 59. 373 | Single circuit line 220kV Ostrołęka-Miłosna will be partly upgraded to double circuit line 400kV (2x1870 MVA, 106km) with development of Ostrołęka 400kV substation + New substation 400kV Stanisławów will be connected by splitting and extending existing line Miłosna-Narew and Miłosna-Siedlce. | 3 | Progresses as planned | 2020 | 2020 | 1 | Ostrołęka (PL) | Stanisławów (PL) | 59. 373 | 59. 373 | Single circuit line 220kV Ostrołęka-Stanisławów will be upgraded to double circuit line 400kV (2x1870 MVA, 106km) with development of Ostrołęka 400kV substation. | 3 |  | 2020 | 2020 | 1 | Ostroleka (PL) | Stanislawów (PL) | 123 | 373 | LitPol Link Stage 2 | Construction of new 400 kV line Ostrołęka-Stanisławów. | 3 | Investment on time | The project is at the design stage. | 2020 | 2020 | 1 | Ostroleka (PL) | Stanislawów (PL) | 373 | Construction of new 400 kV line Ostrołęka-Stanisławów. | 3 | Investment on time | The investment is in tendering procedure, the contract (design and build scheme) will by signed by Q4 2015. | 2020 | 2020 | 1 | Ostrołęka (PL) | Stanisławów (PL) | 123 | 373 | LitPol Link Stage 2 | Ostrołęka-Stanisławów | Construction of new 400 kV AC double-circuit OHL line with a length of 108 km and capacity of 2x1870 MVA between Ostrołęka and Stanisławów will partly use route existing 220 kV single-circuit line between Ostrołęka and Miłosna. In one circuit of 400 kV line will be enabled substation Wyszków. After the construction of 400 kV line, the 220 kV line will be dismantled. Expansion of 400 kV Ostrołęka substation and construction of a new 400 kV substation Stanisławów, which will be connected by splitting and extending of 400 kV lines Miłosna - Narew and Miłosna - Siedlce. | 3 | Investment on time | The investment is in tendering procedure, the contract (design and build scheme) will by signed by Q4 2015. | 31/ 12/ 2021 | 2021 | 1 |  | 0 | Ostrołęka (PL) | Stanisławów (PL) | Overhead Line | AC | 500 | 400 | 106 | New | 123 | 373 | LitPol Link Stage 2 | Ostroleka-Stanislawow | 2 | Rescheduled |  | 31/ 12/ 2023 | 2023 | 1 | LITGRID,PSE | Ostroleka (PL) | Stanislawow (PL) | Overhead Line | AC | 400 | 123 | 373 | LitPol Link Stage 2 | Ostroleka-Stanislawow | Construction of new 400 kV AC double-circuit OHL line with a length of 108 km and capacity of 2x2450 MVA between Ostroleka and Stanislawow. | 4 | Investment on time |  | 2023 | 2023 | 1 | Polskie Sieci Elektroenergetyczne S.A. | 4.5.2 | 1 | 0 | Ostroleka (PL) | Stanislawow (PL) | ACTransmissionLine | AC | 108 | MostlyNew | 123 | 373 | LitPol Link Stage 2 | Ostroleka-Stanislawow | Construction of new 400 kV AC double-circuit OHL line with a length of 108 km and capacity of 2x2450 MVA between Ostroleka and Stanislawow. | 4 | Investment on time |  | 12-2023 | 2023 | 1 | Polskie Sieci Elektroenergetyczne S.A. | 4.5.2 | 1 | 0 | Ostroleka (PL) | Stanislawow (PL) | ACTransmissionLine | AC | 0 | 400 | 108 | MostlyNew | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2023 | 3 | 13 | LTU;POL | Ostroleka | Stanislawow | 53.0843 | 21.5669 | 52.2898 | 21.5472
730 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 374 | Cancelled | 374 | Existing single circuit line will be upgraded to 400kV line in the same direction (1870 MVA, 90km). | 3 | 2020 | 2020 | 1 | Kozienice (PL) | Siedlce Ujrzanów (PL) | 59 | 59. 374 | Existing single circuit line will be upgraded to 400kV line in the same direction (1870 MVA, 90km) + upgrade of Kozienice substation to connect the new line | 3 | Progressed as planned. The investment also foresee extension works in substation Kozienice | 2020 | 2020 | 1 | Kozienice (PL) | Siedlce Ujrzanów (PL) | 59. 374 | 59. 374 | Existing single circuit line 220kV will be upgraded to 400kV line in the same direction (1870 MVA, 90km) | 3 | The currently provided commissioning dates were set in the detailed investment plan introduced in 2013. Previous dates in TYNDP 2012 were synchronized with a general national development plan which provided only time horizons for the investments (2015, 2020). | 2018 | 2018 | 1 | Kozienice (PL) | Siedlce Ujrzanów (PL) | 123 | 374 | LitPol Link Stage 2 | Construction of new 400 kV line Kozienice-Siedlce Ujrzanów. | 3 | Expected earlier than planned previously | The commissioning date has been adjusted compared to the previous national plan and TYNDP. | 2019 | 2019 | 1 | Kozienice (PL) | Siedlce Ujrzanów (PL) | 374 | Construction of new 400 kV line Kozienice-Siedlce Ujrzanów. | 3 | Investment on time | Investment on time. | 2019 | 2019 | 1 | Kozienice (PL) | Siedlce Ujrzanów (PL) | 123 | 374 | LitPol Link Stage 2 | Kozienice-Siedlce Ujrzanów | Existing 220 kV single circuit OHL between Kozienice and Siedlce Ujrzanów will be upgraded to AC 400 kV double circuit line (OHL) with a length of 90 km and a capacity of 2x1870 MVA (onshore). The Kozienice substation will be upgraded to connect the new lines. | 3 | Investment on time | Investment on time. | 1/ 1/ 2019 | 2019 | 1 |  | 0 | Kozienice (PL) | Siedlce Ujrzanów (PL) | Overhead Line | AC | 300 | 400 | 90 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2019 | -1 | 9 | POL | Kozienice | Siedlce Ujrzanów | 51.585 | 21.5499 | 52.1339 | 22.3146
731 | 2014 | 2015 | [2014, 2015] | 376 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 59 | 376 | LitPol Link Stage 1 | Construction of 500 MW Back-to-Back convertor station near Alytus 330kV substation. Construction of double circuit 400kV OHL between Alytus and PL-LT border (51 km). | 4 | Investment on time | As planned. | 2015 | 2015 | 1 | Alytus (LT) | PL-LT border | 376 | Construction of 500 MW Back-to-Back convertor station near Alytus 330kV substation. Construction of double circuit 400kV OHL between Alytus and PL-LT border (51 km). | 4 | Investment on time | Progressed as planned | 2015 | 2015 | 1 | Alytus (LT) | PL-LT border | [5 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 1 | LTU | Alytus | Pl-Lt Border
732 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 377 | Commissioned | 377 | New single circuit 330kV OHL (943 MVA, 85km). | 3 | 2013 | 2013 | 1 | Klaipeda (LT) | Telsiai (LT) | 60 | 60. 377 | New single circuit 330kV OHL (943 MVA, 85km). | 4 | Project delayed because of land renting issues. | 2014 | 2014 | 1 | Klaipeda (LT) | Telsiai (LT) | 60. 377 | 60. 377 | New single circuit 330kV OHL (943 MVA, 85km). | 4 |  | 2014 | 2014 | 1 | Klaipeda (LT) | Telsiai (LT) | 60 | 377 | NordBalt phase 1 | New single circuit 330kV OHL (943 MVA, 85km). | 4 | Investment on time | - | 2014 | 2014 | 1 | Klaipeda (LT) | Telsiai (LT) | 377 | New single circuit 330kV OHL (943 MVA, 85km). | 4 | Investment on time | Progressed as planned | 2014 | 2014 | 1 | Klaipeda (LT) | Telsiai (LT) | [5 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2013 | 2014 | 1 | 4 | LTU | Klaipeda | Telsiai | 55.7128 | 21.135
733 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 378 | Cancelled | 378 | New single circuit 330kV OHL (1080 MVA, 80km). | 2 | 2016 | 2016 | 1 | Panevezys (LT) | Musa (LT) | 60 | 60. 378 | New single circuit 330kV OHL (1080 MVA, 80km). | 2 | Project postponed after investment portfolio optimization | 2018 | 2018 | 1 | Panevezys (LT) | Musa (LT) | 60. 378 | 60. 378 | New single circuit 330kV OHL (1080 MVA, 80km). | 2 | Construction of new NPPP, which has impact to the necessity of this investment is unclear, so priority was taken to the other internal investments needed. Investment 60. 378 is postponed accordingly in the new national transmission grid development plan. | 2022 | 2022 | 1 | Panevezys (LT) | Musa (LT) | 124 | 378 | NordBalt phase 2 | New single circuit 330kV OHL (1080 MVA, 80km). | 2 | Rescheduled | Investment 60 is postponed in the new national transmission grid development plan. Construction of new NPP, which has impact to the necessity of this investment is unclear, so priority was taken to the other internal investments needed. | 2022 | 2022 | 1 | Panevezys (LT) | Musa (LT) | 378 | New single circuit 330kV OHL (1080 MVA, 80km). | 2 | Investment on time | Progressed as planned | 2022 | 2022 | 1 | Panevezys (LT) | Musa (LT) | 124 | 378 | NordBalt phase 2 | 330 kV Panevezys-Musa | New single circuit 330kV OHL (1080 MVA, 80km). | 2 | Delayed | Project implementation depends on decisions about new nuclear power plant in Lithuania and project 170."Baltic synchronisation". | 31/12/ 2023 | 2023 | 1 |  | 0 | Panevezys (LT) | Musa (LT) | Overhead Line | AC | 150 | 330 | 80 | New | 124 | 378 | NordBalt phase 2 | 330 kV OHL Panevezys-Musa | 2 |  |  | 2023 | 2023 | 1 | AST;LITGRID;SVK | Panevezys | Musa | Overhead Line | AC | 330 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2023 | 7 | 13 | LTU | Panevezys | Musa | 55.7345 | 24.3578 | 54.9365 | 24.9126
734 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 379 | Commissioned | 379 | New double circuit 330kV OHL (2x1080 MVA, 53km). | 2 | 2020 | 2020 | 1 | Kruonis (LT) | Alytus (LT) | 59 | 59. 379 | New double circuit 330kV OHL (2x1080 MVA, 53km). | 2 | Progresses faster than intially planned to support the LitPol project | 2015 | 2015 | 1 | Kruonis (LT) | Alytus (LT) | 59. 379 | 59. 379 | New double circuit 330kV OHL Alytus–Kruonis(2x1080 MVA, 53km). | 3 |  | 2015 | 2015 | 1 | Kruonis (LT) | Alytus (LT) | 59 | 379 | LitPol Link Stage 1 | New double circuit 330kV OHL Alytus–Kruonis(2x1080 MVA, 53km). | 3 | Delayed | Several months delay due to difficulties with the acquisition of the land | 2016 | 2016 | 1 | Kruonis (LT) | Alytus (LT) | 379 | New double circuit 330kV OHL Alytus–Kruonis(2x1080 MVA, 53km). |  | Investment on time | Progressed as planned | 2016 | 2016 | 1 | Kruonis (LT) | Alytus (LT) | [5 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2016 | -4 | 6 | LTU | Kruonis | Alytus | 54.7577 | 24.2386
735 | 2012 | 2026 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 38 | [6 empty] | 0 |  |  | 16 | 16. 38 | New HVDC interconnection in the western part of the border via DC subsea cable in the Biscay Gulf. | 1 | New investment in TYNDP, defined since last release, aiming 4 GW capacity between France and Spain. | ca. 2020 | 2020 | 1 | Gatica (ES) | Aquitaine (FR) | 16. 38 | 16. 38 | New HVDC interconnection in the western part of the border via DC subsea cable in the Biscay Gulf. | 2 | The investment is expected to be commissioned around the year 2020. | 2020 | 2020 | 1 | Gatica (ES) | Aquitaine (FR) | 16 | 38 | Western interconnection FR-ES | New HVDC interconnection in the western part of the border via DC subsea cable in the Biscay Gulf. | 2 | Investment on time | The technical consistency of the project progresses and the commissioning date is now defined more accurately. | 2023 | 2023 | 1 | Gatica (ES) | Aquitaine (FR) | 38 | New HVDC interconnection in the western part of the border via DC subsea cable in the Biscay Gulf. | 2 | Rescheduled | The investment progressed as previously planned. Intergovernmental agreements ask for speed up implementation of this project | 2022 | 2022 | 1 | Gatica (ES) | Aquitaine (FR) | 16 | 38 | Biscay Gulf | HVDC Gatica-Cubnezais | New HVDC interconnection in the western part of the border via DC subsea cable in the Biscay Gulf. | 2 | Rescheduled | There is a common political will to speed up the project, but more detailed technical studies showed the need to reschedule the project till 2025 due to manufacturing and installation needs adjustment. Specifically there will be a partial operation of the link before 2025 as the first bipole will be in service in 2024. | 01/ 01/ 2025 | 2025 | 1 |  | 1 | Gatica (ES) | Cubnezais (FR) | Subsea Cable | DC | 2300 | 320 | 400 | New | 16 | 38 | Biscay Gulf | HVDC Gatica-Cubnezais | 3 | Investment on time |  | 01/ 01/ 2025 | 2025 | 1 | REE;RTE | Gatica (ES) | Cubnezais (FR) | Subsea Cable | DC | 320 | 16 | 38 | Biscay Gulf | HVDC Gatica-Cubnezais | New HVDC interconnection in the western part of the border via DC subsea cable in the Biscay Gulf (cable and converters at the end). | 3 | Investment on time |  | 2027 | 2027 | 1 | Red Eléctrica de España RTE | 2.7 | 1 | 1 | Gatica (ES) | Cubnezais (FR) | OffshoreDCTransmissionCable | DC | 370 | New | 16 | 38 | Biscay Gulf | HVDC Gatica-Cubnezais | New HVDC interconnection in the western part of the border via DC subsea cable in the Biscay Gulf (cable and converters at the end). | 3 | Investment on time |  | 12-2027 | 2027 | 1 | Red Eléctrica, Rte | 2.7 | 1 | 1 | Gatica (ES) | Cubnezais (FR) | OffshoreDCTransmissionCable | DC | 2000 | 400 | 394 | New | 16 | 38 | Biscay Gulf | HVDC Gatica-Cubnezais | New HVDC interconnection in the western part of the border via DC subsea cable in the Biscay Gulf (cable and converters at the end). | 4 | Investment on time |  | 12-2028 | 2028 | 1 | Red Eléctrica, Rte | 1.2 | 1 | 1 | Gatica (ES) | Cubnezais (FR) | OffshoreDCTransmissionCable | DC | 2000 | 400 | 394 | New | 16 | 38 | Biscay Gulf | HVDC Gatica-Cubnezais | New HVDC interconnection in the western part of the border via DC subsea cable in the Biscay Gulf (cable and converters at the end). | 4 |  | 12-2028 | 2028 | 1 | Red Eléctrica, Rte | 1 | XX | XX | New | 2020 | 2028 | 8 | 16 | ESP;FRA | Gatica | Cubnezais |  |  | 45.0738 | -0.40786
736 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 380 | Cancelled | 380 | New single circuit 330kV OHL (1080 MVA, 200km). | 2 | 2020 | 2020 | 1 | Visaginas (LT) | Kruonis (LT) | 61 | 61. 380 | New single circuit 330kV OHL (1080 MVA, 200km). | 2 | Progresses as planned | 2020 | 2020 | 1 | Visaginas (LT) | Kruonis (LT) | 61. 380 | 61. 380 | New single circuit 330kV OHL (1080 MVA, 200km). | 1 | Investment depending on Visaginas NPP construction time. | 2022 | 2022 | 1 | Visaginas (LT) | Kruonis (LT) | 170 | 380 | Baltics synchro with CE | New single circuit 330kV OHL (1080 MVA, 200km) for the internal grid reinforcement. | 1 | Rescheduled | Investment depending on Visaginas NPP construction time. | 2022 | 2022 | 1 | Visaginas (LT) | Kruonis (LT) | 380 | New single circuit 330kV OHL (1080 MVA, 200km) for the internal grid reinforcement. | 1 | Investment on time | Progressed as planned | 2022 | 2022 | 1 | Visaginas (LT) | Kruonis (LT) | 170 | 380 | Baltic synchronization | 330 kV line VAE-Kruonis | New single circuit 330kV OHL VAE-Kruonis for the internal grid reinforcement, to complement new Visaginas NPP and project 170. “Baltic synchronization” | 1 | Delayed | Investment implementation time depends from decisions about new Visaginas NPP and project 170. Baltic synchronization”. | 01/01/ 2024 | 2024 | 1 |  | 0 | Visaginas (LT) | Kruonis (LT) | Overhead Line | AC | 150 | 330 | 200 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2024 | 4 | 14 | LTU | Visaginas | Kruonis | 55.5997 | 26.437 | 54.7577 | 24.2386
737 | 2010 | 2026 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 382 |  | 382 | New single circuit 330kV OHL (943 MVA, 50km). | 2 | 2020 | 2020 | 1 | Vilnius (LT) | Neris (LT) | 61 | 61. 382 | New single circuit 330kV OHL (943 MVA, 50km). | 2 | Progresses as planned | 2020 | 2020 | 1 | Vilnius (LT) | Neris (LT) | 61. 382 | 61. 382 | New single circuit 330kV OHL (943 MVA, 50km). | 2 | Construction of new NPPP is unclear, so priority was taken to the other internal investments needed. Investment 61. 382 is postponed accordingly in the new national transmission grid development plan. | 2022 | 2022 | 1 | Vilnius (LT) | Neris (LT) | 170 | 382 | Baltics synchro with CE | New single circuit 330kV OHL (943 MVA, 50km). | 2 | Rescheduled | Investment 61 is postponed in the new national transmission grid development plan. Construction of new NPPP is unclear, so priority was taken to the other internal investments needed. | 2022 | 2022 | 1 | Vilnius (LT) | Neris (LT) | 382 | New single circuit 330kV OHL (943 MVA, 50km). | 2 | Investment on time | Investment 61 is postponed in the new national transmission grid development plan. Construction of new NPPP is unclear, so priority was taken to the other internal investments needed. | 2022 | 2022 | 1 | Vilnius (LT) | Neris (LT) | 170 | 382 | Baltic synchronization | 330 kV line Vilnius-Neris | New single circuit 330kV OHL (943 MVA, 50km). | 2 | Delayed | Investment implementation time depends from decisions about new Visaginas NPP and project 170. Baltic synchronization” | 1/ 1/ 2024 | 2024 | 1 |  | 0 | Vilnius (LT) | Neris (LT) | Overhead Line | AC | 150 | 330 | 50 | New | 170 | 382 | Baltics synchro with CE | New 330 kV OHL Vilnius-Neris | 2 | New Investment |  | 2024 | 2024 | 1 | AST;ELERING;LITGRID | Vilnius | Neris | Overhead Line | AC | 330 | 170 | 382 | Baltic States Synchronization with Continental Europe | New 330 kV OHL Vilnius-Neris | New 330 kV OHL Vilnius-Neris | 3 | Investment on time |  | 2025 | 2025 | 1 | AST ELERING Polskie Sieci Elektroenergetyczne S.A. LITGRID AB | 4.8 | 0 | 1 | Vilnius | Neris | ACTransmissionLine | AC | 80 | New | 170 | 382 | Baltic States Synchronization with Continental Europe | New 330 kV OHL Vilnius-Neris | New 330 kV OHL Vilnius-Neris. 57,9 km will be constructed as new line and 22,8 km will be used part of exicting 330 kV OHL Vilnius-Molodecno (Vilnius-Molodecno will be disconnected until end of 2025). | 3 | Investment on time |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 4.8 | 0 | 1 | Vilnius | Neris | ACTransmissionLine | AC | 0 | 330 | 80 | MostlyNew | 170 | 382 | Baltic States Synchronization with Continental Europe | New 330 kV OHL Vilnius-Neris | New 330 kV OHL Vilnius-Neris. 57,9 km will be constructed as new line and 22,8 km will be used part of exicting 330 kV OHL Vilnius-Molodecno (Vilnius-Molodecno will be disconnected until end of 2025). | 4 | Investment on time |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 3.3.1, 3.3.2, 3.3.3, 3.3.4, 3.3.5, 3.3.6, 3.3.7, 3.3.8, 3.3.9, 3.3.10, 3.3.11, 3.3.12, 3.3.13, 3.3.1 | 0 | 1 | Vilnius | Neris | ACTransmissionLine | AC | 0 | 330 | 80.7 | MostlyNew | 170 | 382 | Baltic States Synchronization with Continental Europe | New 330 kV OHL Vilnius-Neris | New 330 kV OHL Vilnius-Neris. 57,9 km will be constructed as new line and 22,8 km will be used part of exicting 330 kV OHL Vilnius-Molodecno (Vilnius-Molodecno will be disconnected until end of 2025). | 4 |  | 12-2025 | 2025 | 1 | AST, Elering, Litgrid AB, Polskie Sieci Elektroenergetyczne S.A. | 1 | XX | XX | Mostly new | 2020 | 2025 | 5 | 15 | EST;LTU;LVA;POL | Vilnius | Neris | 54.687 | 25.2829 | 54.7017 | 25.3091
738 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 383 | Commissioned | 383 | (NordBalt) A new 300kV HVDC VSC partly subsea and partly underground cable between Lithuania and Sweden. (440km). | 3 | 2015/2016 | 2016 | 1 | Klaipeda (LT) | Nybro (SE) | 60 | 60. 383 | (NordBalt) A new 300kV HVDC VSC partly subsea and partly underground cable between Lithuania and Sweden. (440km). | 3 | Progresses as planned | 2015 | 2015 | 1 | Klaipeda (LT) | Nybro (SE) | 60. 383 | 60. 383 | (NordBalt) A new 300kV HVDC VSC partly subsea and partly underground cable between Lithuania and Sweden | 4 |  | 2015 | 2015 | 1 | Klaipeda (LT) | Nybro (SE) | 60 | 383 | NordBalt phase 1 | (NordBalt) A new 300kV HVDC VSC partly subsea and partly underground cable between Lithuania and Sweden | 4 | Investment on time |  | 2015 | 2015 | 1 | Klaipeda (LT) | Nybro (SE) | 383 | (NordBalt) A new 300kV HVDC VSC partly subsea and partly underground cable between Lithuania and Sweden | 4 | Investment on time | Progressed as planned | 2015 | 2015 | 1 | Klaipeda (LT) | Nybro (SE) | [5 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2015 | -1 | 5 | LTU;SWE | Klaipeda | Nybro | 55.7128 | 21.135 | 56.7445 | 15.9075
739 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 385 | Commissioned | 385 | "Kurzeme Ring" is a Latvian grid reinforcement project with new 330kV OHL construction and connection to the Riga node. New 330kV OHL construction mainly instead of the existing 110kV double circuit line route, 110kV line will be renovated at the same time and both will be assembled on the same towers. Upgrade of double circuit 330kV double circuit OHL new 380 330. (Capacity 800MW). | 2 | 2016 | 2016 | 1 | Grobina (LV) | Imanta (LV) | 60 | 60. 62. 385 | Kurzeme roject a Latvian grid reinforcement roject with new 330kV OHL construction and connection to the Riga node. New 330kV OHL construction mainly instead of the existing 110kV double circuit line route, 110kV line will be renovated at the same time and both will be assembled on the same towers. Length 380km, Capacity 800MW | 3 | Investment delays due to authorization process and the extensive works. | 2018 | 2018 | 1 | Grobina (LV) | Imanta (LV) | 60. 62. 385 | 60. 62. 385 | The reinforcement for Latvian grid project with the new 330kV OHL construction and connection to the Riga node. New 330kV OHL construction mainly instead of the existing 110kV double circuit line route, 110kV line will be renovated at the same time and both will be assembled on the same towers. Length 380km, Capacity 800MW | 4 |  | 2018 | 2018 | 1 | Grobina (LV) | Imanta (LV) | 60 | 385 | NordBalt phase 1 | The reinforcement for Latvian grid project with the new 330kV OHL construction and connection to the Riga node. New 330kV OHL construction mainly instead of the existing 110kV double circuit line route, 110kV line will be renovated at the same time and both will be assembled on the same towers. Length 380km, Capacity 800MW | 4 | Investment on time | The part of reinforcement for Kurzemes ring | 2018 | 2018 | 1 | Grobina (LV) | Imanta (LV) | 385 | The reinforcement for Latvian grid project with the new 330kV OHL construction and connection to the Riga node. New 330kV OHL construction mainly instead of the existing 110kV double circuit line route, 110kV line will be renovated at the same time and both will be assembled on the same towers. Length 380km, Capacity 800MW | 4 | Investment on time | Progressed as planned | 2018 | 2018 | 1 | Grobina (LV) | Imanta (LV) | 124 | 385 | NordBalt phase 2 | Grobina (LV) - Imanta (LV) | The reinforcement for Latvian grid project with the new 330kV OHL construction and connection to the Riga node. New 330kV OHL construction mainly instead of the existing 110kV double circuit line route, 110kV line will be renovated at the same time and both will be assembled on the same towers. Length 380km, Capacity 800MW | 4 | Delayed | The last part of reinforcement for Kurzemes ring project | 2019 | 2019 | 1 |  | 0 | Grobina (LV) | Imanta (LV) | Overhead Line | AC | 150 | 330 | 380 | New | 124 | 385 | NordBalt phase 2 | Grobina (LV) - Imanta (LV) | 4 |  |  | 2019 | 2019 | 1 |  | Grobina (LV) | Imanta (LV) | Overhead Line | AC | 330 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2019 | 3 | 9 | LVA | Grobina | Imanta
740 | 2012 | 2020 | [2012, 2013, 2014, 2015, 2016, 2018, 2020] | 386 | Commissioned | [5 empty] | 0 |  |  | 62 | 62. 386 | Estonia-Latvia third interconnection will consist of 330 kV AC OHL Harku-Lihula-Sindi in Estonian part and OHL between Kilingi-Nõmme substation in Estonia and TEC2 substation in Latvia. The third interconnection allows to increase the NTC between Estonia and Latvia additionally in the range of 450 to 600 MW . | 2 | Progresses as planned | 2020 | 2020 | 1 | Kilingi-Nomme(EE) | RigaCHP2(LV) | 62. 386 | 62. 386 | Estonia-Latvia third interconnection will consist of 330 kV AC OHL Harku-Lihula-Sindi in Estonian part and OHL between Kilingi-Nõmme substation in Estonia and R-TEC2 substation in Latvia. The third interconnection allows to increase the NTC between Estonia and Latvia additionally in the range up to 600 MW . | 2 |  | 2020 | 2020 | 1 | Kilingi-Nomme (EE) | R-TEC2 (LV) | 62 | 386 | Estonia-Latvia 3rd IC | 330 kV AC OHL between Kilingi-Nõmme substation in Estonia and R-TEC2 substation in Latvia. New 330 kV power transmission line is planned to take route along already existing 110 kV power transmission lines, by constructing both 110 kV and 330 kV lines on the same towers. Under the framework of the project it is planned to reconstruct the open-air switchyard of the 330/110 kV substation „TEC-2” by constructing new open-air connection point for the 330 kV line „Kilingi Nomme-TEC-2”. | 2 | Investment on time | Progress as planned. | 2020 | 2020 | 1 | Kilingi-Nomme (EE) | R-TEC2 (LV) | 386 | 330 kV AC OHL between Kilingi-Nõmme substation in Estonia and R-TEC2 substation in Latvia. New 330 kV power transmission line is planned to take route along already existing 110 kV power transmission lines, by constructing both 110 kV and 330 kV lines on the same towers. Under the framework of the project it is planned to reconstruct the open-air switchyard of the 330/110 kV substation „TEC-2” by constructing new open-air connection point for the 330 kV line „Kilingi Nomme-TEC-2”. | 2 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Kilingi- Nomme (EE) | R-TEC2 (LV) | 62 | 386 | Estonia-Latvia 3rd IC | 3rd EE-LV | 330 kV AC OHL between Kilingi-Nõmme substation in Estonia and R-TEC2 substation in Latvia. New 330 kV power transmission line is planned to take route along already existing 110 kV power transmission lines, by constructing both 110 kV and 330 kV lines on the same towers. Under the framework of the project it is planned to reconstruct the open-air switchyard of the 330/110 kV substation „TEC-2” by constructing new open-air connection point for the 330 kV line „Kilingi Nomme-TEC-2”. | 3 | Investment on time | Electricty market integration, Security of Supply, RES connection to the transmission network. | 2020 | 2020 | 1 |  | 1 | Kilingi-Nomme (EE) | R-TEC2 (LV) | Overhead Line | AC | 500 | 330 | 205 | New | 62 | 386 | Estonia-Latvia 3rd IC | 3rd EE-LV interconnection | 4 |  |  | 2020 | 2020 | 1 | AST; ELERING | Kilingi-Nomme (EE) | Riga CHP2 (LV) | Overhead Line | AC | 330 | 62 | 386 | Estonia-Latvia 3rd IC | 3rd EE-LV interconnection | "330 kV AC OHL between Kilingi-Nomme substation in Estonia and Riga CHP2 substation in Latvia. New 330 kV power transmission line is planned to take route along already existing 110 kV power transmission lines, by constructing both 110 kV and 330 kV lines on the same towers. Under the framework of the project it is planned to reconstruct the open-air switchyard of the 330/110 kV substation Riga CHP2 by constructing new open-air connection point for the 330 kV line Kilingi Nomme - Riga CHP2. """ | 4 | Investment on time |  | 2020 | 2020 | 1 | AST ELERING | 4.2 | 1 | 1 | Kilingi-Nomme (EE) | Riga CHP2 (LV) | ACTransmissionLine | AC | 205 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 8 | EST;LVA | Kilingi-Nomme | Riga Chp | 58.153 | 24.9627
741 | 2012 | 2024 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024] | 396 | Commissioned | [5 empty] | 0 |  |  | 111 | 111. 396 | Third single circuit 400kV AC OHL between Sweden and Finland. Expected capacity: 1850 MVA. | 1 | The projects reinforcing the North-South transmission in the Scandinavia have been prioritized ahead of this project. Based on common estimation project can be delayed to 2021. SvK will evaluate the project and the timetable in ongoing studies | 2021 | 2021 | 1 | Finland North (FI) | Sweden North (SE) | 111. 396 | 111. 396 | Third single circuit 400kV AC OHL between Sweden and Finland | 1 | Rescheduled following a review of priorities and dependencies for all grid reinforcements in Sweden. Thanks to postponement of this investment, other internal investments will be commissioned on time | 2025 | 2025 | 1 | Finland North (FI) | Sweden bidding area SE1/SE2 | 111 | 396 | 3rd AC Finland-Sweden north | Third single circuit 400kV AC OHL between Sweden and Finland | 1 | Rescheduled | Rescheduled following a review of priorities and dependencies for all grid reinforcements in Sweden. Thanks to postponement of this investment, other internal investments will be commissioned on time | 2025 | 2025 | 1 | Finland North (FI) | Sweden bidding area SE1/SE2 | 396 | Third single circuit 400kV AC OHL between Sweden and Finland | 1 | Investment on time | Progressed as planned | 2025 | 2025 | 1 | Finland North (FI) | Sweden bidding area SE1/SE2 | 111 | 396 | 3rd AC Finland-Sweden north | 3rd AC Finland-Sweden north | Third AC 400 kV overhead line interconnector between Finland north and Sweden SE1. Strengthening the AC connection between Finland and Sweden is necessary due to new wind power generation, larger conventional units and decomissioning of the existing 220 kV interconnector. | 1 | Investment on time |  | 2025 | 2025 | 1 |  | 1 | Finland North (FI) | Sweden bidding area SE1/SE2 | Overhead Line | AC | 800 | 400 | 200 | New | 111 | 396 | 3rd AC Finland-Sweden north | 3rd AC Finland-Sweden north | 3 | Investment on time |  | 2025 | 2025 | 1 | FINGRID;SVK | Keminmaa (Finland) | Messaure (Sweden, bidding area SE1) | Overhead Line | AC | 400 | 111 | 396 | 3rd AC Finland-Sweden north | 3rd AC Finland-Sweden north | Third AC 400 kV overhead line interconnector between Finland north and Sweden SE1. | 3 | Investment on time |  | 2025 | 2025 | 1 | FINGRID Svenska Kraftnät |  | 1 | 1 | Keminmaa (Finland) | Messaure (Sweden, bidding area SE1) | ACTransmissionLine | AC | 200 | New | 111 | 396 | Aurora line (3rd AC Finland-Sweden north) | 3rd AC Finland-Sweden north | Third AC 400 kV overhead line interconnector between Finland north and Sweden SE1. | 3 | Investment on time |  | 12-2025 | 2025 | 1 | Fingrid, Svenska Kraftnät | 4.10.1 and 4.10.2 | 1 | 1 | Viitajärvi (Finland) | Messaure (Sweden, bidding area SE1) | ACTransmissionLine | AC | 0 | 400 | 226 | New | 111 | 396 | Aurora line (3rd AC Finland-Sweden north) | 3rd AC Finland-Sweden north | Third AC 400 kV overhead line interconnector between Finland north and Sweden SE1. | 3 | Investment on time |  | 12-2025 | 2025 | 1 | Fingrid, Svenska Kraftnät | 3.4.1 and 3.4.2 | 1 | 1 | Viitajärvi (Finland) | Messaure (Sweden, bidding area SE1) | ACTransmissionLine | AC | 0 | 400 | 226 | New | [5 empty] | 5 | Commissioned |  |  | 0 | [5 empty] | 2021 | 2025 | 4 | 13 | FIN;SWE | Viitajärvi | Messaure | 61.2068 | 25.0316 | 66.6853 | 20.3351
742 | 2015 | 2015 | [2015] | 399 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 |  |  | 399 | Upgrade of existing single circuit 220kV lines to 400kV. The investment is a part of investment 403 | 1 | Investment on time | Progressed as planned | 2021 | 2021 | 1 | Dingtuna (SE) | Karlslund (SE) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2021 | 0 | 6 | SWE | Dingtuna | Karlslund | 59.5724 | 16.3887 | 55.8911 | 12.8386
743 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 4 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 1 | 4 | RES in north of Portugal | New 129km double-circuit 400kV OHL V.Minho (PT) - Ribeira de Pena (PT) - Fridão (PT) - Feira (PT) (one circuit operated at 220kV between V.P. Aguiar and Estarreja) with a new 400/60kV substation in Rib. Pena. In a first step, only the 139km section Rib. de Pena (PT) - Feira (PT) will be constructed and operated at 220kV as Vila Pouca Aguiar (PT) - Carrapatelo (PT) - Estarreja (PT). In a second step, one circuit of this line will be operated at 400kV. | 3 | Delayed | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was delayed. | 2018 | 2018 | 1 | V.Minho (by Ribeira de Pena and Fridão) | Feira (by Ribeira de Pena and Fridão) | 4 | New 129km double-circuit 400kV OHL V.Minho (PT) - Ribeira de Pena (PT) - Fridão (PT) - Feira (PT) (one circuit operated at 220kV between V.P. Aguiar and Estarreja) with a new 400/60kV substation in Rib. Pena. In a first step, only the 139km section Rib. de Pena (PT) - Feira (PT) will be constructed and operated at 220kV as Vila Pouca Aguiar (PT) - Carrapatelo (PT) - Estarreja (PT). In a second step, one circuit of this line will be operated at 400kV. | 3 | Rescheduled | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was rescheduled. | 2021 | 2021 | 1 | V.Minho (by Ribeira de Pena and Fridão) | Feira (by Ribeira de Pena and Fridão) | 1 | 4 | RES in north of Portugal | V.Minho -R.Pena-Fridão-Feira | New 132km double-circuit 400kV OHL V.Minho (PT) - Ribeira de Pena (PT) - Fridão (PT) - Feira (PT) (one circuit operated at 220kV between V.P. Aguiar and Estarreja) with a new 400/60kV substation in Rib. Pena. In a first step, only the 69km section Rib. de Pena (PT) - Feira (PT) will be constructed and operated at 220kV as Vila Pouca Aguiar (PT) - Carrapatelo (PT) - Estarreja (PT). In a second step, one circuit of this line will be operated at 400kV. | 3 | Rescheduled | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was rescheduled. | 31/ 12/ 2021 | 2021 | 1 |  | 0 | V.Minho (by Ribeira de Pena and Fridão) | Feira (by Ribeira de Pena and Fridão) | Overhead Line | AC | 890 | 400 | 132 | New | 1 | 4 | RES in north of Portugal | V.Minho -R.Pena-Fridão-Feira | 3 | Rescheduled | Due to the expected delay of the connection of new RES generation, the commissioning date of this investment item was rescheduled | 2022-2024 | 2024 | 1 |  | V.Minho (by Ribeira de Pena and Fridão) | Feira (by Ribeira de Pena and Fridão) | Overhead Line | AC | 400 | 1 | 4 | RES in north of Portugal | V.Minho -R.Pena-Feira | New double-circuit 400kV OHL Vieira do Minho (PT) - Ribeira de Pena (PT) - Feira (PT). | 3 | Ahead of time |  | 2022 | 2022 | 1 | Rede Elétrica Nacional | 2.16.1 and 2.16.3 | 1 | 0 | V.Minho (by Ribeira de Pena) | Feira (by Ribeira de Pena) | ACTransmissionLine | AC | 131 | New | 1 | 4 | RES in north of Portugal | V.Minho -R.Pena-Feira | New double-circuit 400kV OHL Vieira do Minho (PT) - Ribeira de Pena (PT) - Feira (PT). | 4 | Investment on time | Although the construction started on the section Feira-Ribeira de Pena, there is a public opposition to the project that is delaying the construction. Section V.Minho-Ribeira de Pena was comissioned in 2021. | 12-2022 | 2022 | 1 | Rede Elétrica Nacional | 2.16.3 | 1 | 0 | V.Minho (by Ribeira de Pena) | Feira (by Ribeira de Pena) | ACTransmissionLine | AC | 0 | 400 | 131 | New | 1 | 4 | RES in north of Portugal | V.Minho -R.Pena-Feira | New double-circuit 400kV OHL Vieira do Minho (PT) - Ribeira de Pena (PT) - Feira (PT). | 4 | Delayed | Although the construction started on the section Feira-Ribeira de Pena, there is a public opposition to the project that is delaying the construction. Section V.Minho-Ribeira de Pena was comissioned in 2021. | 06-2024 | 2024 | 1 | Rede Elétrica Nacional | 2.16.3 | 1 | 0 | V.Minho (by Ribeira de Pena) | Feira (by Ribeira de Pena) | ACTransmissionLine | AC | 0 | 400 | 138.58 | New | 1 | 4 | RES in north of Portugal | V.Minho -R.Pena-Feira | New double-circuit 400kV OHL Vieira do Minho (PT) - Ribeira de Pena (PT) - Feira (PT). | 4 |  | 01-2026 | 2026 | 1 | Rede Elétrica Nacional | 0 | XX | XX | New | 2018 | 2026 | 8 | 12 | PRT | V.Minho | Feira |  |  | 40.9317 | -8.5523
744 | 2014 | 2024 | [2014, 2015, 2016, 2018, 2020, 2022, 2024] | 403 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 126 | 403 | SE North-south reinforcements | Based on a joint Statnett & Svenska Kraftnät study for North-South reinforcements, this contains reinforcements in cut 1 and 2 in Sweden | 1 | Investment on time | The investment now combine new investments and the previous 399, 786, 787, 788 and 806. All of the old investments appear only in the list of cancelled investments in the regional plan | 2025 | 2025 | 1 | Sweden bidding area SE1 | Sweden bidding area SE3 | 403 | Based on a joint Statnett & Svenska Kraftnät study for North- South reinforcements, this contains reinforcements in cut 1 and 2 in Sweden | 1 | Investment on time | Progressed as planned | 2025 | 2025 | 1 | Sweden bidding area SE1 | Sweden bidding area SE3 | 126 | 403 | SE North-south reinforcements | Reinforcements SE2-3 in Sweden | Reactive measures in substations and series compensations in order to increase capacity between SE2 and SE3. Replacement of ageing overhead lines that also will contribute to the increased capacity. The need for capacity is driven by RES integration in northern Sweden and nuclear decommission in southern Sweden. | 1 | Investment on time | The investment now combine new investments in various reactive compensation components and other reinforcements not yet specified. | 2025 | 2025 | 1 |  | 0 | Sweden bidding area SE2 | Sweden bidding area SE3 | Compensation |  | 1500 | 400 | 900 | New | 126 | 403 | SE North-south reinforcements | Reinforcements SE2-SE3 in Sweden | 1 | Investment on time |  | 2030 | 2030 | 1 | SVK | SE2 | SE3 | Compensation | AC | 400 | 126 | 403 | SE North-south short-term reinforcements | Reinforcements SE2-SE3 in Sweden | Reactive measures in substations and series compensations in order to increase capacity between SE2 and SE3. Replacement of ageing overhead lines that also will contribute to the increased capacity. The need for capacity is driven by RES integration in northern Sweden and nuclear decommission in southern Sweden. | 2 | Investment on time |  | 2030 | 2030 | 1 | Svenska Kraftnät |  | 1 | 0 | Ramsele (SE2) | Hamra (SE3) | ReactiveCompensationDevice | AC | 1200 | Upgrade | 126 | 403 | SE North-south short-term reinforcements | Reinforcements SE2-SE3 in Sweden | Reactive measures in substations and series compensations in order to increase capacity between SE2 and SE3. Replacement of ageing overhead lines that also will contribute to the increased capacity. The need for capacity is driven by RES integration in northern Sweden and nuclear decommission in southern Sweden. | 2 | Investment on time |  | 01-2035 | 2035 | 1 | Svenska Kraftnät |  | 1 | 0 | Ramsele (SE2) | Hamra (SE3) | ReactiveCompensationDevice | AC | 0 | 400 | 1200 | Upgrade | 126 | 403 | SE North-south short-term reinforcements | Reinforcements SE2-SE3 in Sweden | Reactive measures in substations and series compensations in order to increase capacity between SE2 and SE3. Replacement of ageing overhead lines that also will contribute to the increased capacity. The need for capacity is driven by RES integration in northern Sweden and nuclear decommission in southern Sweden. | 2 | Investment on time |  | 01-2035 | 2035 | 1 | Svenska Kraftnät |  | 1 | 0 | Ramsele (SE2) | Hamra (SE3) | ReactiveCompensationDevice | AC | 0 | 400 | 1200 | Upgrade | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2025 | 2035 | 10 | 21 | SWE | Ramsele | Hamra | 63.5381 | 16.4687 | 61.7567 | 14.8024
745 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 406 | Commissioned | [5 empty] | 0 |  |  | 37 | 37. 406 | Voltage uprating of existing 300 kV line Sauda/Saurdal - Lyse - Tonstad - Feda - 1&2, Feda - Kristiansand; Sauda-Samnanger in long term. Voltage upgrading of existing single circuit 400kV OHL Tonstad-Solhom-Arendal. Reactive power devices in 400kV substations. | 3 | Revised progress. Due to more demanding system operations and time needed to obtain necessary government permits for reinforcing the national grid. The investment now embed former TYNDP 2010's investments 407 and 409 and the technical description has been updated accordingly. | 2016 (2013-2018) | 2018 | 1 | (Southern part of Norway) (NO) |  | 37. 406 | 37. 406 | Voltage uprating of existing 300 kV line Sauda/Saurdal - Lyse - Ertsmyra - Feda - 1&2, Feda - Kristiansand; Sauda-Samnanger in long term. Voltage upgrading of existing single circuit 400kV OHL Tonstad-Solhom-Arendal. Reactive power devices in 400kV substations. | 3 | Revised progress due to more demanding system operations and time needed to obtain necessary government permits. Commissioning date expected 2019-2021 | 2020 | 2020 | 1 | (Southern part of Norway) (NO) | (Southern part of Norway)(NO) | 37 | 406 | Southern Norway - Germany | Voltage uprating of existing 300 kV line Sauda/Saurdal - Lyse - Ertsmyra - Feda - 1&2, Feda - Kristiansand; Sauda-Samnanger in long term. Voltage upgrading of existing single circuit 400kV OHL Tonstad-Solhom-Arendal. Reactive power devices in 400kV substations. | 3 | Delayed | Revised progress due to less flexible system operations in a running system (voltage upgrade of existing lines). Commissioning date expected 2019-2021. | 2020 | 2020 | 1 | (Southern part of Norway) (NO) | (Southern part of Norway)(NO) | 406 | Voltage uprating of existing 300 kV line Sauda/Saurdal - Lyse - Ertsmyra - Feda - 1&2, Feda - Kristiansand; Sauda- Samnanger in long term. Voltage upgrading of existing single circuit 400kV OHL Tonstad-Solhom-Arendal. Reactive power devices in 400kV substations. | 3 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | (Southern part of Norway) (NO) | (Southern part of Norway)(NO) | 37 | 406 | Norway - Germany, NordLink | Western corridor | Voltage uprating of existing 300 kV line Sauda/Saurdal - Lyse - Ertsmyra - Feda - 1&2, Feda - Kristiansand; Sauda-Samnanger in long term. Voltage upgrading of existing single circuit 400kV OHL Tonstad-Solhom-Arendal. Reactive power devices in 400kV substations. | 4 | Delayed | Revised progress due to less flexible system operations in a running system (voltage upgrade of existing lines). Commissioning date expected 2019-2021. | 2020 | 2020 | 1 |  | 0 | (Southern part of Norway) (NO) | (Southern part of Norway)(NO) | Overhead Line | AC | 1000 | 400 | 400 | Upgrade | 37 | 406 | "Norway - Germany, NordLink" | Western corridor | 4 |  |  | 2020 | 2020 | 1 |  | (Southern part of Norway) (NO) | (Southern part of Norway)(NO) | Overhead Line | AC | 400 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2020 | 2 | 8 | NOR | Southern Part Of Norway | Southern Part Of Norway
746 | 2014 | 2020 | [2014, 2015, 2016, 2018, 2020] | 424 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 110 | 424 | Norway-Great Britain | A 720 km long 500 kV 1400 MW HVDC subsea interconnector between western Norway and eastern England. | 3 | Investment on time | On time | 2020 | 2020 | 1 | Kvilldal (NO) | Blythe (GB) | 424 | A 720 km long 500 kV 1400 MW HVDC subsea interconnector between western Norway and eastern England. | 3 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Kvilldal (NO) | Blythe (GB) | 110 | 424 | Norway-Great Britain North Sea Link | Norway - Great Britain | A 720 km long 500 kV 1400 MW HVDC subsea interconnector between western Norway and eastern England. | 4 | Investment on time | On time | 2021 | 2021 | 1 |  | 1 | Kvilldal (NO) | Blythe (GB) | Subsea Cable | DC | 0 | 500 | 720 | New | 110 | 424 | Norway-Great Britain NSN | Norway - Great Britain | 4 |  |  | 2021 | 2021 | 1 | NGIHL;STATNETT | Kvilldal (NO) | Blythe (GB) | Subsea Cable | DC | 500 | 110 | 424 | Norway-Great Britain, North Sea Link | Norway - Great Britain | A 720 km long 515 kV 1400 MW HVDC subsea interconnector between western Norway and eastern England. | 4 | Investment on time |  | 2021 | 2021 | 1 | National Grid STATNETT | 1.10.1 | 1 | 1 | Kvilldal (NO) | Blyth (GB) | OffshoreDCTransmissionCable | DC | 720 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2021 | 1 | 7 | GBR;NOR | Kvilldal | Blyth | 59.5165 | 6.6364 | 55.1271 | -1.51
747 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 427 | Commissioned | 427 | COBRA: New single circuit HVDC connection between Jutland and the Netherlands via 350km subsea cable; the DC voltage will be up to 450kVand the capacity 600-700MW. | 3 | 2016 | 2016 | 1 | Endrup (DK) | Eemshaven (NL) | 71 | 71. 427 | COBRA: New single circuit HVDC connection between Jutland and the Netherlands via 350km subsea cable; the DC voltage will be up to 320kVand the capacity 600-700MW. | 3 | Progresses as planned | 2016 | 2016 | 1 | Endrup (DK) | Eemshaven (NL) | 71. 427 | 71. 427 | COBRA: New single circuit HVDC connection between Jutland and the Netherlands via 350km subsea cable; the DC voltage will be 320kV and the capacity 700MW. | 3 | Rescheduled to account for the time of development of a solid regional business case and acceptance by the authorities of a preferred route. | 2018 | 2018 | 1 | Endrup (DK) | Eemshaven (NL) | 71 | 427 | COBRA cable | COBRA: New single circuit HVDC connection between Jutland and the Netherlands via 350km subsea cable; the DC voltage will be 320kV and the capacity 700MW. | 3 | Delayed | Rescheduled to develop a solid regional business case (including additional project partners); and to account for the time needed for the acceptance by the authorities of a preferred route. | 2019 | 2019 | 1 | Endrup (DK) | Eemshaven (NL) | 427 | COBRA: New single circuit HVDC connection between Jutland and the Netherlands via 350km subsea cable; the DC voltage will be 320kV and the capacity 700MW. | 3 | Investment on time | Final investment decision obtained, EIA application procedure initiated and tender procedure for cable and converters started. | 2019 | 2019 | 1 | Endrup (DK) | Eemshaven (NL) | 71 | 427 | COBRA cable | COBRA Cable | COBRA; New single circuit HVDC connection between Jutland and the Netherlands via 350km subsea cable; the DC voltage will be 320kV and the capacity 700MW. | 4 | Investment on time | Permits in place, main contracts signed, construction started. | 31/03/ 2019 | 2019 | 1 |  | 1 | Endrup (DK) | Eemshaven (NL) | Subsea Cable | DC | 700 | 320 | 350 | New | 71 | 427 | COBRA cable | COBRA Cable | 4 | Investment on time |  | 2019 | 2019 | 1 | Energinet,TENNET-NL | Endrup (DK) | Eemshaven (NL) | Subsea Cable | DC | 400 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2019 | 3 | 9 | DNK;NLD | Endrup | Eemshaven | 55.5235 | 8.7183 | 53.4484 | 6.8465
748 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 436 | Cancelled | [5 empty] | 0 |  |  | 72 | 72. 436 | New 74km single circuit 400kV line via cable with capacity of approx. 1200MW. | 1 | Envisaged route changed from Idomlund-Tjele to Idomlund-Endrup | 2018/2020 | 2020 | 1 | Idomlund (DK) | Endrup (DK) | 72. 436 | 72. 436 | New 74km single circuit 400kV line via cable with capacity of approx. 1200MW. | 6 | Replaced by upgrade of existing route to Idomlund to be proposed for TYNDP 2014. |  |  | 1 | Idomlund (DK) | Endrup (DK) | 167 | 436 | Viking DKW-GB | New 74km single circuit 400kV line via cable with capacity of approx. 1200MW. | 1 | Rescheduled | In national plan route is replaced by different project, upgrading an existing route from Tjele to Idomlund (72.898). The known route (Endrup-Idomlund) from the TYNDP12 would additionally be necessary as soon as the interconnection to GB is built. | 2030 | 2030 | 1 | Idomlund (DK) | Endrup (DK) | 436 | New 74km single circuit 400kV line via cable with capacity of approx. 1200MW. | 6 | Cancelled | new connection point for Viking link facilitates avoiding this link. |  |  | 1 | Idomlund (DK) | Endrup (DK) | 167 | 436 | Viking DKW-GB | Endrup - Idomlund | New 95 km single circuit 400 kV line | 2 | Investment on time | The connection to GB requires this upgrade of the internal Danish grid in order to harvest the full benefits of the Viking link. As this investment serves multi-purposes, only part of it is allocated to the Viking project | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Idomlund (DK) | Endrup (DK) | Underground Cable | AC | 1360 | 400 | 74 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2022 | 2 | 10 | DNK | Idomlund | Endrup | 56.3542 | 8.5441 | 55.5235 | 8.7183
749 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 438 | Cancelled | 438 | New 175-200km AC overhead line with capacity of 2x2650 MVA of 380kV. | 3 | 2016 | 2016 | 1 | Eemshaven (NL) | Diemen (NL) | 103 | 103. 438 | New 175-200km AC overhead line with capacity of 2x2650 MVA of 380kV. | 3 | Delays due to authorization process. | 2018 | 2018 | 1 | Eemshaven (NL) | Diemen (NL) | 103. 438 | 103. 438 | New 175-200km AC overhead line with capacity of 2x2650 MVA of 380kV. | 3 |  | 2018 | 2018 | 1 | Eemshaven (NL) | Diemen (NL) | 103 | 438 | Reinforcements Ring NL | New 175-200km AC overhead line with capacity of 2x2650 MVA of 380kV. In the first phase a connection between Eemshaven Oude Schip and Vierverlaten will be built as well as an upgrade of the existing line Diemen - Lelystad - Ens | 3 | Investment on time | Changes in plans of thermal plants at Eemshaven offers the opportunity to phase the grid expansions. The a first phase consists of a new 380 kV connection between Eemshaven-Oudeschip and Vierverlaten and the upgrade the circuits form Diemen-Lelystad-Ens | 2018 | 2018 | 1 | Eemshaven (NL) | Diemen (NL) | 438 | New 175-200km AC overhead line with capacity of 2x2650 MVA of 380kV. In the first phase a connection between Eemshaven Oude Schip and Vierverlaten will be built as well as an upgrade of the existing line Diemen - Lelystad - Ens. Last phase of the project expected after 2025. | 3 | Rescheduled | Changes in plans of thermal plants at Eemshaven offers the opportunity to phase the grid expansions. The a first phase consists of a new 380 kV connection between Eemshaven-Oudeschip and Vierverlaten and the upgrade the circuits form Diemen-Lelystad-Ens | 2023 | 2023 | 1 | Eemshaven (NL) | Diemen (NL) | 103 | 438 | Reinforcements Ring NL | Noord-West 380 kV | New 175-200km AC overhead line with capacity of 2x2650 MVA of 380kV. In the first phase a connection between Eemshaven Oude Schip and Vierverlaten will be built as well as an upgrade of the existing line Diemen - Lelystad - Ens. Last phase of the project expected after 2025. | 3 | Investment on time | Changes in plans of thermal plants at Eemshaven offers the opportunity to phase the grid expansions. The a first phase consists of a new 380 kV connection between Eemshaven-Oudeschip and Vierverlaten and the upgrade the circuits form Diemen-Lelystad-Ens. The second phase is a future project and consists of a new 380 kV connection between Vierverlaten and Ens. The second phase of the project expected after 2030. | 1/ 1/ 2020 | 2020 | 1 |  | 0 | Eemshaven (NL) | Diemen (NL) | Overhead Line | AC | 125 | 380 | 175 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2020 | 4 | 10 | NLD | Eemshaven | Diemen | 53.4484 | 6.8465 | 52.335 | 4.9843
750 | 2014 | 2016 | [2014, 2015, 2016] | 439 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 103 | 439 | Reinforcements Ring NL | New 100-130km double-circuit 380kV OHL with 2x2650 MVA capacity. | 3 | Investment on time | With a 380 kV substation at Rilland, the Zuid-West 380 kV project can be taken into service in two parts. The first part consists of the Borssele - Rilland line including substation Rilland and the second part consist of the Rilland – Tilburg line. | 2016 | 2016 | 1 | Borssele (NL) | Tilburg (NL) | 439 | New 100-130km double-circuit 380kV OHL with 2x2650 MVA capacity. Phase 1:2019; phase 2 2025. | 3 | Delayed | With a 380 kV substation at Rilland, the Zuid-West 380 kV project can be taken into service in two parts. The first part consists of the Borssele Rilland line including substation Rilland and the second part consist of the Rilland – Tilburg line. | 2023 | 2023 | 1 | Borssele (NL) | Tilburg (NL) | 103 | 439 | Reinforcements Ring NL | Zuid-West 380 kV | New 100-130km double-circuit 380kV OHL with 2x2650 MVA capacity. Phase 1&#58;2019; phase 2 2025. | 3 | Delayed | With a 380 kV substation at Rilland, the Zuid-West 380 kV project can be taken into service in two parts. The first part consists of the Borssele - Rilland line including substation Rilland (2020) and the second part consist of the Rilland – Tilburg line (2025). | 1/ 1/ 2025 | 2025 | 1 |  | 0 | Borssele (NL) | Tilburg (NL) | Overhead Line | AC | 125 | 380 | 100 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2025 | 9 | 11 | NLD | Borssele | Tilburg | 51.4255 | 3.7379 | 51.5856 | 5.0661
751 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 440 | Cancelled | 440 | New 380 kV double-circuit mixed project (OHL+ underground cable) including approximately 20km of underground cable for 2650 MVA. The cable sections are a pilot project. The total length of cable at 380kV is frozen until more experience is gained. | 4 | 2013 | 2013 | 1 | Maasvlakte (NL) | Beverwijk (NL) | 103 | 103. 440 | New 380 kV double-circuit mixed project (OHL+ underground cable) including approximately 20km of underground cable for 2650 MVA. The cable sections are a pilot project. The total length of cable at 380kV is frozen until more experience is gained. | 4 | Delays due to authorization process. | 2016 | 2016 | 1 | Maasvlakte (NL) | Beverwijk (NL) | 103. 440 | 103. 440 | New 380 kV double-circuit mixed project (OHL+ underground cable) including approximately 20km of underground cable for 2650 MVA. The cable sections are a pilot project. The total length of cable at 380kV is frozen until more experience is gained. | 4 | Permitting procedures take longer than expected | 2017 | 2017 | 1 | Maasvlakte (NL) | Beverwijk (NL) | 103 | 440 | Reinforcements Ring NL | New 380 kV double-circuit mixed project (OHL+ underground cable) including approximately 20km of underground cable for 2650 MVA. The cable sections are a pilot project. The total length of cable at 380kV is frozen until more experience is gained. | 4 | Delayed | Permitting procedures took longer than expected. The part from Maasvlakte to Bleiswijk has been commissioned. | 2017 | 2017 | 1 | Maasvlakte (NL) | Beverwijk (NL) | 440 | New 380 kV double-circuit mixed project (OHL+ underground cable) including approximately 20km of underground cable for 2650 MVA. The cable sections are a pilot project. The total length of cable at 380kV is frozen until more experience is gained. | 4 | Delayed | Permitting procedures took longer than expected. The part from Maasvlakte to Bleiswijk has been commisssioned. | 2019 | 2019 | 1 | Maasvlakte (NL) | Beverwijk (NL) | 103 | 440 | Reinforcements Ring NL | Randstad380 | New 380 kV double-circuit mixed project (OHL+ underground cable) including approximately 20km of underground cable for 2650 MVA. The cable sections are a pilot project. The total length of cable at 380kV is frozen until more experience is gained. | 4 | Investment on time | The part from Maasvlakte to Bleiswijk has been commisssioned. Phase 2 between Bleiswijk and Beverwijk wll be commissioned in 2019. | 1/ 1/ 2019 | 2019 | 1 |  | 0 | Maasvlakte (NL) | Beverwijk (NL) | Overhead Line | AC | 125 | 380 | 65 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2013 | 2019 | 6 | 9 | NLD | Maasvlakte | Beverwijk | 51.9544 | 4.0198 | 52.4788 | 4.6728
752 | 2014 | 2016 | [2014, 2015, 2016] | 441 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 103 | 441 | Reinforcements Ring NL | BELUX INTERIM As a first interim step a PST will be integrated in Schifflange, and connected to an existing OH-line to control the transit flows from Germany to Belgium as from end 2015. | 4 | Investment on time | Studies for interim step are finalized; Investment decision has been taken mid-2014 and PST is planned to be operational end 2015. | 2015 | 2015 | 1 | Zwolle (NL) | Under analysis (BE) | 441 | Upgrade of the capacity of the existing 300km double circuit 380kV OHL to reach a capacity of 2x2650 MVA along the Dutch Central ring (Hengelo-Zwolle-Ens Diemen-Krimpen- Geertruidenberg-Eindhoven-Maasbracht); First phase 2019; last phase 2025 | 2 | Investment on time | The investment is merged with the Ring Zuid project | 2019 | 2019 | 1 | Zwolle (NL) | Maasbracht (NL) | 103 | 441 | Reinforcements Ring NL | Upgrade Dutch Ring | Upgrade of the capacity of the existing 300km double circuit 380kV OHL to reach a capacity of 2x2650 MVA along the Dutch Central ring (Hengelo-Zwolle-Ens Diemen-Krimpen-Geertruidenberg-Eindhoven-Maasbracht); First phase 2019; last phase 2025 | 2 | Investment on time | Upgrade of the capacity of the existing 300km double circuit 380kV OHL to reach a capacity of 2x2650 MVA along the Dutch Central ring (Hengelo-Zwolle-Ens Diemen-Krimpen-Geertruidenberg-Eindhoven-Maasbracht); First phase (Ens-Zwolle) 2025; last phase 2030 | 1/ 1/ 2030 | 2030 | 1 |  | 0 | Zwolle (NL) | Maasbracht (NL) | Overhead Line | AC | 125 | 380 | 300 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2030 | 15 | 16 | NLD | Zwolle | Maasbracht | 52.5146 | 6.0977 | 51.1429 | 5.8831
753 | 2016 | 2016 | [2016] | 442 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 103 | 442 | Reinforcements Ring NL | Upgrade Krimpen - Maasbracht |  | 3 | Investment on time | Upgrade of Krimpen-Geertruidenberg is expected in 2023, Geertruidenberg-Maasbracht completed in 2027. | 01-01-2027 | 2027 | 1 |  | 0 | Krimpen aan de IJssel (NL) | Maasbracht (NL) | Overhead Line | AC | 100 | 400 | 150 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2027 | 2027 | 0 | 11 | NLD | Krimpen Aan De Ijssel | Maasbracht | 51.9167 | 4.6084 | 51.1429 | 5.8831
754 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 443 | Commissioned | [5 empty] | 0 |  |  | 74 | 74. 443 | Nemo Project: New DC sea link including 135km of 250kV DC subsea cable with 1000MW capacity | 2 | Investment delayed to 2018 due to authorization delays related to needed internal grid reinforcements | 2018 | 2018 | 1 | Richborough (GB) | Zeebrugge (BE) | 74. 443 | 74. 443 | Nemo Project: New DC sea link including 135km of 250kV DC subsea cable with 1000MW capacity | 3 |  | 2018 | 2018 | 1 | Richborough (GB) | Zeebrugge (BE) | 74 | 443 | Thames Estuary Cluster (NEMO) | Nemo Project: New DC sea link including 135km of 400kV (voltage level is subject to outcome of detailed engineering) DC subsea cable with 1000MW capacity | 3 | Investment on time | Investment on time, with a technical commissioning planned end 2018 leading to commercial operation in 2019 | 2018 | 2018 | 1 | Richborough (GB) | Zeebrugge (BE) | 443 | Nemo Project: New DC sea link including 135km of 400kV (voltage level is subject to outcome of detailed engineering) DC subsea cable with 1000MW capacity | 3 | Investment on time | Final Investment Decision has been taken and confirms the target date of technical commissioning end 2018 with commercial operation in 2019. | 2018 | 2018 | 1 | Richborough (GB) | Zeebrugge (BE) | 74 | 443 | Thames Estuary Cluster (NEMO) | NEMO | New DC sea link of 1000 MW over a distance of around 140 km between Richborough (GB) and Gezelle (BE) | 4 | Investment on time | Final Investment Decision has been taken and confirms the target date of technical commissioning end 2018 with commercial operation in 2019. | 1/ 1/ 2019 | 2019 | 1 |  | 1 | Richborough (GB) | Gezelle (BE) | Subsea Cable | DC | 1000 | 400 | 140 | New | 74 | 443 | Thames Estuary Cluster (NEMO-Link) | NEMO | 4 | Investment on time |  | 1/ 1/ 2019 | 2019 | 1 | ELIA, NGIHL, NGET | Richborough (GB) | Gezelle (BE) | Subsea Cable | DC | 400 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2019 | 1 | 7 | BEL;GBR | Richborough | Gezelle | 51.2955 | 1.3252 | 50.9505 | 3.1286
755 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 444 | Commissioned | 444 | New approx 50km double-circuit 380kV 5000MVA OHL line between Zomergem and Zeebrugge to evacuate the locally (offshore) produced power line. | 3 | 2014 | 2014 | 1 | Zomergem (BE) | Zeebrugge (BE) | 75 | 75. 444 | New approx. 50km double-circuit 380kV ( 3000MVA for each circuit) between Zomergem and Zeebrugge to evacuate the locally (offshore) produced power line and allow connection of NEMO to 380 kV grid. | 3 | Progresses as planned | 2014 | 2014 | 1 | Zomergem (BE) | Zeebrugge (BE) | 75. 444 | 75. 444 | New approx. 50km double-circuit 380kV ( 3000MVA for each circuit) between Zomergem and Zeebrugge to evacuate the locally (offshore) produced power line and allow connection of NEMO to 380 kV grid. | 3 | The Environmental Impact assessment(EIA)and the land use act (GRUP) have been delayed.The delay is caused by the request of a number 3rd parties to examine more alternatives. | 2016 | 2016 | 1 | Zomergem (BE) | Zeebrugge (BE) | 75 | 444 | Stevin (backbone)+BE offshore | STEVIN The Stevin project envisions the extension of the 380kV backbone to the coastal area, via the construction of new +-50km (40km OHL; 10km cable) double-circuit (3000MVA for each circuit) between Zomergem and Zeebrugge., including the construction of a new substation in Zeebrugge. | 3 | Delayed | Delay due to request of 3rd parties to examine more alternatives, and procedures launched , and due to appeals against the GRUP (land use act) by 3rd parties in States Council. Meanwile arrangements have been made, and the updated planning envisions end 2017/begin 2018 as new commissioning date. | 2018 | 2018 | 1 | Zomergem (BE) | Zeebrugge (BE) | 444 | STEVIN The Stevin project envisions the extension of the 380kV backbone to the coastal area, via the construction of new +- 50km (40km OHL; 10km cable) double-circuit (3000MVA for each circuit) between Zomergem and Zeebrugge., including the construction of a new substation in Zeebrugge. | 4 | Investment on time | State Council procedures no longer pending due to agreements reached with involved stakeholders. Construction phase initiated -planned to be in operation by 31/12/2017 | 2017 | 2017 | 1 | Zomergem (BE) | Zeebrugge (BE) | 75 | 444 | STEVIN & Modular Offshore Grid | STEVIN | The STEVIN project extends the 380 kV backbone from the substation Horta (Zomergem) to a new substation Stevin at Zeebrugge. The substation Stevin will be integrated via two 380/150 kV transformers to the existing 150 kV grid at Zeebrugge and will also contain a 220 kV part o facilitate the integration of offshore wind. This new 380 kV corridor will be constructed as a double-circuit (3000 MVA capacity per circuit) overhead line, except for the section of 10 km between two new substations "Van Maerland" & "Gezelle which will be realized as an underground solution via four 380 kV cables. As part of the STEVIN project, the existing 150 kV line between Eeklo Pokmoer and Brugge Waggelwater will be decomissioned and the existing 150kV line between Eeokle Noord and Brugge Waggelwater will be undergrounded. | 4 | Investment on time | State Council procedures no longer pending due to agreements reached with involved stakeholders. Construction phase initiated. | 31/12/2017 | 2017 | 1 |  | 0 | Horta (BE - Zomergem) | Stevin (BE - Zeebrugge) | Overhead Line | AC | 3000 | 380 | 50 | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2014 | 2017 | 3 | 7 | BEL | Horta | Stevin | 50.8259 | 4.3457 | 51.2065 | 3.2226
756 | 2010 | 2022 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022] | 445 | Commissioned | 445 | Doubling of the axis Zandvliet-Mercator via Lillo by erecting a new 35km 380kV double circuit OHL with 1500 MVA capacity. | 3 | 2014 | 2014 | 1 | Zandvliet (BE) | Lillo (BE) | 24 | 24. 445 | Brabo Project : Doubling of the axis Zandvliet-Mercator via Lillo. Second part : erecting a new 22km double circuit 380kV OHL with 1500 MVA capacity Lillo and Zandvliet and a new 400 kV substation in Lillo. | 3 | Permits cancelled by national authority . New permitting procedure has started | 2017 | 2017 | 1 | Zandvliet (BE) | Lillo (BE) | 24. 445 | 24. 445 | Brabo Project : Doubling of the axis Zandvliet-Mercator via Lillo. Second part : erecting a new 22km double circuit 380kV OHL with 1900 MVA capacity between Lillo and Zandvliet. | 3 | New permitting procedure is ongoing. Permitting procedure asked evaluation of several alternative solutions. | 2017 | 2017 | 1 | Zandvliet (BE) | Lillo (BE) | 24 | 445 | Belgian North Border | Brabo: part Zandvliet-Lillo: Brabo allows to realize the intended market capacity increase on the North Border in a more robust way (greater scenario independence compared to PST 4 only) , and reinforces the network to facilitate increased demand and connection of possible new generation around Antwerp Harbour area. It consists of constructing a new 380kV circuit Zandvliet-Lillo(new substation)-Mercator, in addition to the existing Zandvliet - Mercator connection. This investment item concerns the part between Zandvliet and Lillo substations. | 3 | Delayed | Permitting procedure for adaptation of land use (GRUP) had to be reinitiated, in order to comply with the demand of investigating alternative solutions. | 2018 | 2018 | 1 | Zandvliet (BE) | Lillo (BE) | 445 | BRABO II: Zandvliet-Lillo-Liefkenshoek + restructuring 150kV BRABO II + III allow to realize the intended market capacity increase on the North Border after BRABO I in a more robuste way, to secure increased demand around Antwerp Harbour area (mainly BRABO II) and to create capacity for connection of possible new generation (mainly BRABO III) This by constructing a new 380kV connection Zandvliet-Lillo- Mercator, in addition to the existing Zandvliet - Mercator connection. This investment item concerns the part from Zandvliet via Lillo to Liefkenshoek where the new line will be the temporarily connected onto the existing Doel-Mercator line. It also involves also a restructuring of the adjacent 150kV network. | 3 | Delayed | Progress made in permitting procedures brought clarification to preferential trajectory. Planning has been reviewed accordingly with 2019 based upon the hypothesis of acquiring all necessary permits as currently planned. | 2020 | 2020 | 1 | Zandvliet (BE) | Lillo (BE) | 297 | 445 | Belgian North Border: BRABO II + III | BRABO II: Zandvliet - Lillo - Liefkenshoek | The second phase of the BRABO project consists of the construction of a new double circuit 380kV overhead line from Zandvliet via Lillo to Liefkenshoek where the new line will be the temporarily connected to the existing 380kV line Doel-Mercator. This new line will be constructed making use of the corridor of the existing 150kV overhead line Zandvliet-Oorderen-Lillo, which will be undergrounded. | 3 | Delayed | Progress made in permitting procedures brought clarification to preferential trajectory. Planning has been reviewed accordingly with 2020 based upon the hypothesis of acquiring all necessary permits as currently planned. | 01/01/2020 | 2020 | 1 |  | 0 | Zandvliet | Lillo - Liefkenshoek | Overhead Line | AC | 1000 | 380 | 18 | New | 297 | 445 | BRABO II + III | BRABO II: Zandvliet - Lillo - Liefkenshoek | 4 | Investment on time |  | 31/12/2020 | 2020 | 1 | ELIA | Zandvliet | Lillo - Liefkenshoek | Overhead Line | AC | 380 | 297 | 445 | BRABO II + III | BRABO II: Zandvliet - Lillo - Liefkenshoek | The second phase of the BRABO project consists of the construction of a new double circuit 380kV overhead line from Zandvliet via Lillo to Liefkenshoek where the new line will be the temporarily connected to the existing 380kV line Doel-Mercator.This new line will be constructed making use of the corridor of the existing 150kV overhead line Zandvliet-Oorderen-Lillo, which will be undergrounded. | 4 | Investment on time |  | 2020 | 2020 | 1 | ELIA | 2.23 | 1 | 0 | Zandvliet | Lillo - Liefkenshoek | ACTransmissionLine | AC | 18 | New | 297 | 445 | BRABO II + III | BRABO II: Zandvliet - Lillo - Liefkenshoek | The second phase of the BRABO project consists of the construction of a new double circuit 380kV overhead line from Zandvliet via Lillo to Liefkenshoek where the new line will be the temporarily connected to the existing 380kV line Doel-Mercator.This new line will be constructed making use of the corridor of the existing 150kV overhead line Zandvliet-Oorderen-Lillo, which will be undergrounded. | 5 | Commissioned |  | 01-2021 | 2021 | 1 | Elia | 2.23 | 1 | 0 | Zandvliet | Lillo - Liefkenshoek | ACTransmissionLine | AC | 0 | 380 | 18 | New | [10 empty] | 0 | [21 empty] | 0 | [5 empty] | 2014 | 2021 | 7 | 11 | BEL | Zandvliet | Lillo - Liefkenshoek | 51.36 | 4.3087
757 | 2014 | 2015 | [2014, 2015] | 446 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 40 | 446 | Luxembourg-Belgium Interco | As a first interim step a PST is commissioned in 2016 in Schifflange and connected to an existing OH-line with an additional 3.5km cable between Biff(CREOS-LU) and Substation Bascharage (CREOS-LU). | 4 | Investment on time | Studies for interim step are finalized, Investment decision expected by mid of 2014 | 2015 | 2015 | 1 | Schifflange (LU) |  | 446 | As a first interim step a PST is commissioned in 2016 in Schifflange and connected to an existing OH-line with an additional 3.5km cable between Biff(CREOS-LU) and Substation Bascharage (CREOS-LU). | 4 | Investment on time | Phase shift transformer commissioned July 2014, delivery June 2015, in operation December 2015- interconnection BE-LU in operation with limited cross border capacities until invest. item 447 LUXRING is finalized | 2016 | 2016 | 1 | Schifflange (LU) | [6 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2016 | 1 | 2 | LUX | Schifflange |  | 49.5063 | 6.0118
758 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 447 | Commissioned | 447 | New 20km double-circuit mixed (underground cable+OHL) 225kV project with 1000 MVA capacity including substations for infeed in lower voltage levels. | 3 | 2012/2020 | 2020 | 1 | Heisdorf (LU) | Berchem (LU) | 40 | 40. 447 | New 20km double-circuit mixed (underground cable+OHL) 225kV project with 1000 MVA capacity including substations for in feed in lower voltage levels. | 3 | Progresses as planned | 2012/2017 | 2017 | 1 | Heisdorf (LU) | Berchem (LU) | 40. 447 | 40. 447 | New 20km double-circuit mixed (underground cable+OHL) 225kV project with 1000 MVA capacity including substations for in feed in lower voltage levels. | 3 | Substation Blooren is authorized and under construction, Authorization for line section is still pending | 2017 | 2017 | 1 | Heisdorf (LU) | Berchem (LU) | 40 | 447 | Luxembourg-Belgium Interco | Erection of a new 20km 225kV double-circuit mixed (cable+OHL)line with 1000 MVA capacity in order to create a loop around Luxembourg city including substations for in feed in lower voltage levels. | 3 | Investment on time | Substation Blooren is authorized and under construction, Authorization for line section is still pending | 2017 | 2017 | 1 | Heisdorf (LU) | Berchem (LU) | 447 | Erection of a new 20km 225kV double-circuit mixed (cable+OHL)line with 1000 MVA capacity in order to create a loop around Luxembourg city including substations for in feed in lower voltage levels. | 4 | Investment on time | Substation Blooren is under construction, line section Heisdorf Blooren is under construction | 2017 | 2017 | 1 | Heisdorf (LU) | Berchem (LU) | 40 | 447 | Luxembourg-Belgium Interco | LUXEMBOURG RING | Erection of a new 20km 225kV double-circuit mixed (cable+OHL)line with 1000 MVA capacity in order to create a loop around Luxembourg city including substations for in feed in lower voltage levels. | 4 | Investment on time | Substation Blooren is under construction, line section Heisdorf Blooren is under construction | 1/ 1/ 2017 | 2017 | 1 |  | 0 | Heisdorf (LU) | Berchem (LU) | Overhead Line | AC | 700 | 220 | 20 | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2017 | -3 | 7 | LUX | Heisdorf | Berchem | 49.6751 | 6.1394 | 49.5428 | 6.1338
759 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 449 | Commissioned | [5 empty] | 0 |  |  | 74 | 74. 449 | New 400kV double circuit OHL and new 400kV substation in Richborough | 2 | Progresses as planned | 2019/2020 | 2020 | 1 | Richborough (GB) | Canterbury (GB) | 74. 449 | 74. 449 | New 400kV double circuit OHL and new 400kV substation in Richborough. | 2 |  | 2020 | 2020 | 1 | Richborough (GB) | Canterbury (GB) | 74 | 449 | Thames Estuary Cluster (NEMO) | New 400kV double circuit and new 400kV substation in Richborough connecting the new Belgium interconnector providing greater market coupling between the UK and the European mainland. | 2 | Investment on time | Investment on time | 2018 | 2018 | 1 | Richborough (GB) | Canterbury (GB) | 449 | New 400kV double circuit and new 400kV substation in Richborough connecting the new Belgium interconnector providing greater market coupling between the UK and the European mainland. | 3 | Investment on time | Investment on time | 2018 | 2018 | 1 | Richborough (GB) | Canterbury (GB) | 74 | 449 | Thames Estuary Cluster (NEMO) | Richborough - Canterbury | New 400kV double circuit and new 400kV substation in Richborough connecting the new Belgium interconnector providing greater market coupling between the UK and the European mainland. | 3 | Investment on time | Investment on time | 1/ 1/ 2018 | 2018 | 1 |  | 0 | Richborough (GB) | Canterbury (GB) | Overhead Line | AC | 1000 | 400 | 20 | New | 74 | 449 | Thames Estuary Cluster (NEMO-Link) | Richborough - Canterbury | 3 | Rescheduled |  | 2018 | 2018 | 1 |  | Richborough (GB) | Canterbury (GB) | Overhead Line | AC | 400 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2018 | -2 | 6 | GBR | Richborough | Canterbury | 51.2955 | 1.3252 | 51.28 | 1.0803
760 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 450 | Commissioned | [5 empty] | 0 |  |  | 74 | 74. 450 | Reconductor Sellindge-Dungeness | 2 | The reconductoring of the Sellindge to Dungeness circuits (Project 450) remain as originally planned in the TYNDP 2010. | 2014/2015 | 2015 | 1 | Sellindge (GB) | Dungeness (GB) | 74. 450 | 74. 450 | Reconductor the existing circuit which runs from Sellindge - Dungeness with a higher rated conductor. | 3 |  | 2015 | 2015 | 1 | Sellindge (GB) | Dungeness (GB) | 74 | 450 | Thames Estuary Cluster (NEMO) | Reconductoring the existing circuit which runs from Sellindge - Dungeness with a higher rated conductor. This will facilitate the connection of more interconnectors on the South coast and prevent thermal overloading of this area. | 3 | Investment on time | Investment on time | 2015 | 2015 | 1 | Sellindge (GB) | Dungeness (GB) | 450 | Reconductor the existing circuit which runs from Sellindge - Dungeness with a higher rated conductor. This will facilitate the connection of more interconnectors on the South coast and prevent thermal overloading of this area. | 4 | Delayed | Delayed by one year due to interconnector progression. | 2016 | 2016 | 1 | Sellindge (GB) | Dungeness (GB) | 74 | 450 | Thames Estuary Cluster (NEMO) | SELL - DUNG Reconductoring | Reconductor the existing circuit which runs from Sellindge - Dungeness with a higher rated conductor. This will facilitate the connection of more interconnectors on the South coast and prevent thermal overloading of this area. | 4 | Delayed | Delayed by one year due to interconnector progresion. | 1/ 1/ 2016 | 2016 | 1 |  | 0 | Sellindge (GB) | Dungeness (GB) | Overhead Line | AC | 400 | 400 | 26 | Upgrade | 74 | 450 | Thames Estuary Cluster (NEMO-Link) | SELL - DUNG Reconductoring |  | Investment on time |  | 30/ 11/ 2016 | 2016 | 1 |  | Sellindge (GB) | Dungeness (GB) | Overhead Line | AC | 400 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2016 | 1 | 4 | GBR | Sellindge | Dungeness | 51.1086 | 0.98837 | 50.9142 | 0.97289
761 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 452 | Commissioned | [5 empty] | 0 |  |  | 77 | 77. 452 | New 2000MW HVDC Link via 360km 500kV DC subsea cable on the West Coast of the UK and new 400kV substation in Deeside | 3 | Progresses as planned (still targetting the financial year 2015/2016) | 2015/2016 | 2016 | 1 | Deeside (GB) | Hunterston (GB) | 77. 452 | 77. 452 | A new 2.4GW (short term rating) submarine HVDC cable route from Hunterston to Deeside with associated AC network reinforcement works at both ends. | 3 |  | 2016 | 2016 | 1 | Hunterston (GB) | Deeside (GB) | 77 | 452 | Anglo-Scottish Cluster | A new 2.4GW (short term rating) submarine HVDC cable route from Hunterston to Deeside with associated AC network reinforcement works at both ends. | 3 | Investment on time | Investment on time | 2016 | 2016 | 1 | Hunterston (GB) | Deeside (GB) | 452 | A new 2.4GW (short term rating) submarine HVDC cable route from Hunterston to Deeside with associated AC network reinforcement works at both ends. | 4 | Delayed | Delay due to complexity in construction phase | 2017 | 2017 | 1 | Hunterston (GB) | Deeside (GB) | 77 | 452 | Anglo-Scottish -1 | Western HVDC Link | A new 2.4GW (short term rating) submarine HVDC cable route from Hunterston to Deeside with associated AC network reinforcement works at both ends. | 4 | Delayed | Delayed due to complexity in construction and issues with the | 1/ 1/ 2017 | 2017 | 1 |  | 0 | Hunterston (GB) | Deeside (GB) | Subsea Cable | DC | 2400 | 500 | 360 | New | 77 | 452 | Anglo-Scottish -1 | Western HVDC Link | 4 | Investment on time |  | 2017 | 2017 | 1 | NGET; SPT | Hunterston (GB) | Deeside (GB) | Subsea Cable | DC | 500 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2017 | 1 | 5 | GBR | Hunterston | Deeside
762 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 453 | Cancelled | [5 empty] | 0 |  |  | 77 | 77. 453 | New 2000MW HVDC Link via 365km 500kV DC subsea cable on the East Coast of the UK and new 400kV substation in Hawthorn Pit | 2 | Progresses as planned (still targetting the financial year 2018/2019) | 2018/2019 | 2019 | 1 | Peterhead (GB) | Hawthorn Pit (GB) | 77. 453 | 77. 453 | A new ~2GW submarine HVDC cable route from Peterhead to Hawthorn Pit with associated AC network reinforcement works at both ends with possible offshore HVDC integration in the Firth of Forth area. | 2 |  | 2019 | 2019 | 1 | Peterhead (GB) | Hawthorn Pit (GB) | 77 | 453 | Anglo-Scottish Cluster | A new ~2GW submarine HVDC cable route from Peterhead to Hawthorn Pit with associated AC network reinforcement works at both ends with possible offshore HVDC integration in the Firth of Forth area. | 1 | Investment on time | Investment on time | 2020 | 2020 | 1 | Peterhead (GB) | Hawthorn Pit (GB) | 453 | A new ~2GW submarine HVDC cable route from Peterhead to Hawthorn Pit with associated AC network reinforcement works at both ends with possible offshore HVDC integration in the Firth of Forth area. | 1 | Rescheduled | Changes in the generation background | 2023 | 2023 | 1 | Peterhead (GB) | Hawthorn Pit (GB) | 298 | 453 | Anglo-Scottish Cluster -2 | Eastern HVDC Link | A new ~2GW submarine HVDC cable route from Peterhead to Hawthorn Pit with associated AC network reinforcement works at both ends with possible offshore HVDC integration in the Firth of Forth area. | 1 | Rescheduled | Changes in the generation background | 1/ 1/ 2023 | 2023 | 1 |  | 0 | Peterhead (GB) | Hawthorn Pit (GB) | Subsea Cable | DC | 2000 | 500 | 365 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2023 | 4 | 11 | GBR | Peterhead | Hawthorn Pit | 57.5053 | -1.7813
763 | 2012 | 2020 | [2012, 2013, 2014, 2015, 2016, 2018, 2020] | 458 | Cancelled | [5 empty] | 0 |  |  | 78 | 78. 458 | New 60km double circuit 400kV OHL | 3 | Seabank has been delayed by three years due to corresponding delays to the associated new nuclear project. | 2019/20 | 2019 | 1 | Hinkley (GB) | Seabank (GB) | 78. 458 | 78. 458 | New 400kV substation at Hinkley Point. New 400kV transmission route from Hinkley Point to Seabank. Reconstruction of Bridgewater substation for 400kV operation. Uprate Bridgewater - Melksham to 400kV. | 3 | Rescheduled due to anticipated changes in the local generation background. | 2021 | 2021 | 1 | Hinkley Point (GB) | Seabank (GB) | 78 | 458 | South West Cluster | New 400kV substation at Hinkley Point. New 400kV transmission route from Hinkley Point to Seabank. Reconstruction of Bridgewater substation for 400kV operation. Uprate Bridgewater - Melksham to 400kV. | 3 | Investment on time | Based on current generation connection dates this investment is progressing on time. | 2019 | 2019 | 1 | Hinkley Point (GB) | Seabank (GB) | 458 | New 400kV substation at Hinkley Point. New 400kV transmission route from Hinkley Point to Seabank. Reconstruction of Bridgewater substation for 400kV operation. Uprate Bridgewater - Melksham to 400kV. | 3 | Rescheduled | Based on current the generation connection dates the investment has been rescheduled. | 2022 | 2022 | 1 | Hinkley Point (GB) | Seabank (GB) | 78 | 458 | South West Cluster | HINP-SEAB New Double Circuit | New 400kV substation at Hinkley Point. New 400kV transmission route from Hinkley Point to Seabank. Reconstruction of Bridgewater substation for 400kV operation. Uprate Bridgewater - Melksham to 400kV. | 3 | Rescheduled | Based on current the generation connection dates the investment has been rescheduled. | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Hinkley Point (GB) | Seabank (GB) | Overhead Line | AC | 3200 | 400 | 60 | New | 78 | 458 | South West Cluster | HINP-SEAB New Double Circuit | 3 | Rescheduled |  | 2024 | 2024 | 1 | NGET | Hinkley Point (GB) | Seabank (GB) | Overhead Line | AC | 400 | 78 | 458 | South West Cluster | HINP-SEAB New Double Circuit | New 400kV substation at Hinkley Point. New 400kV transmission route from Hinkley Point to Seabank. Reconstruction of Bridgewater substation for 400kV operation. Uprate Bridgewater - Melksham to 400kV. | 3 | Investment on time |  | 2024 | 2024 | 1 | National Grid |  | 1 | 0 | Hinkley Point (GB) | Seabank (GB) | ACTransmissionLine | AC | 60 | MostlyNew | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2024 | 5 | 12 | GBR | Hinkley Point | Seabank
764 | 2012 | 2026 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 462 | [6 empty] | 0 |  |  | 81 | 81. 462 | A new 140 km single circuit 400 kV 1500 MVA OHL from Turleenan 400/275 kV in Northern Ireland to Woodland 400/220 kV in Ireland. This is a new interconnector project between Ireland and Northern Ireland. | 3 | Project delayed due to permitting process in both jurisdictions. The intermediate station Moyhill is differed pending outcome of future load growth. | 2016 | 2016 | 1 | Woodland (IE) | Turleenan (NI) | 81. 462 | 81. 462 | A new 140 km single circuit 400 kV 1500 MVA OHL from Turleenan 400/275 kV in Northern Ireland to Woodland 400/220 kV in Ireland. This is a new interconnector project between Ireland and Northern Ireland. | 3 | Further studies required before re-submission for planning consents | 2017 | 2017 | 1 | Woodland (IE) | Turleenan (NI) | 81 | 462 | North South Interconnector | A new 140 km single circuit 400 kV 1500 MVA OHL from Turleenan 400/275 kV in Northern Ireland to Woodland 400/220 kV in Ireland. This is a new interconnector project between Ireland and Northern Ireland. | 3 | Delayed | Further studies required before re-submission for planning consents | 2017 | 2017 | 1 | Woodland (IE) | Turleenan (NI) | 462 | A new 140 km single circuit 400 kV 1500 MVA OHL from Turleenan 400/275 kV in Northern Ireland to Woodland 400/220 kV in Ireland. This is a new interconnector project between Ireland and Northern Ireland. | 3 | Investment on time | Progressed as planned | 2017 | 2017 | 1 | Woodland (IE) | Turleenan (NI) | 81 | 462 | North South Interconnector | 462 | A new 140 km single circuit 400 kV 1500 MVA OHL from Turleenan 400/275 kV in Northern Ireland to Woodland 400/220 kV in Ireland. This is a new interconnector project between Ireland and Northern Ireland. |  | Delayed | Further studies required before re-submission for planning consents |  |  | 1 |  | 1 | Woodland (IE) | Turleenan (NI) | Overhead Line | AC | 0 | 400 | 140 | New | 81 | 462 | North South Interconnector | 462 | 3 | Delayed | Investment delayed due to judicial reviews of planning consent in IE and delayed approval of planning consent in NI. | 2020 | 2020 | 1 | EIRGRID, SONI | Woodland (IE) | Turleenan (NI) | Overhead Line | AC | 400 | 81 | 462 | North South Interconnector | 462 | A new 138 km single circuit 400 kV 1500 MVA OHL from Turleenan 400/275 kV in Northern Ireland to Woodland 400/220 kV in Ireland. This is a new interconnector project between Ireland and Northern Ireland. | 3 | Delayed | Investment delayed due to judicial reviews of planning consent in IE and delayed approval of planning consent in NI. | 2023 | 2023 | 1 | EIRGRID SONI | PCI 2.13.1 | 1 | 1 | Woodland (IE) | Turleenan (NI) | ACTransmissionLine | AC | 138 | New | 81 | 462 | North South Interconnector | 462 | A new 138 km single circuit 400 kV 1500 MVA OHL from Turleenan 400/275 kV in Northern Ireland to Woodland 400/220 kV in Ireland. This is a new interconnector project between Ireland and Northern Ireland. | 3 | Delayed | Investment delayed due to judicial reviews of planning consent in IE and delayed approval of planning consent in NI. | 11-2025 | 2025 | 1 | Eirgrid, SONI |  | 1 | 1 | Woodland (IE) | Turleenan (NI) | ACTransmissionLine | AC | 0 | 400 | 138 | New | 81 | 462 | North South Interconnector | 462 | A new 138 km single circuit 400 kV 1500 MVA OHL from Turleenan 400/275 kV in Northern Ireland to Woodland 400/220 kV in Ireland. This is a new interconnector project between Ireland and Northern Ireland. | 3 | Delayed | Investment delayed due to judicial reviews of planning consent in IE and delayed approval of planning consent in NI. | 11-2025 | 2025 | 1 | Eirgrid, SONI |  | 1 | 1 | Woodland (IE) | Turleenan (NI) | ACTransmissionLine | AC | 0 | 400 | 138 | New | 81 | 462 | North South Interconnector | 462 | A new 138 km single circuit 400 kV 1500 MVA OHL from Turleenan 400/275 kV in Northern Ireland to Woodland 400/220 kV in Ireland. This is a new interconnector project between Ireland and Northern Ireland. | 4 |  | 10-2031 | 2031 | 1 | Eirgrid, SONI | 1 | XX | XX | New | 2016 | 2031 | 15 | 19 | GBR;IRL | Woodland | Turleenan | 53.293 | -6.1987 | 54.4658 | -6.6803
765 | 2012 | 2020 | [2012, 2013, 2014, 2015, 2016, 2018, 2020] | 463 | Cancelled | [5 empty] | 0 |  |  | 82 | 82. 463 | Strengthening of EHV networks (partial uprate and new) into Donegal and North and West of Northern Ireland and enhanced links between the two countries. Various technologies are being considered. | 1 | New investment in TYNDP | 2020 | 2020 | 1 | tbd (IE) | tbd (NI) | 82. 463 | 82. 463 | A new EHV overhead line from Srananagh in Co. Sligo to a new substation in south Co. Donegal | 2 | The preferred scheme has been selected since the last TYNDP; this is one of the elements of the preferred scheme. | 2020 | 2020 | 1 | Srananagh (IE) | New substation in South Donegal (IE) | 82 | 463 | RIDP I | A new EHV overhead line from Srananagh in Co. Sligo to a new substation in south Co. Donegal | 2 | Investment on time | The preferred scheme has been selected since the last TYNDP; this is one of the elements of the preferred scheme. | 2020 | 2020 | 1 | Srananagh (IE) | New substation in South Donegal (IE) | 463 | A new EHV overhead line from Srananagh in Co. Sligo to a new substation in south Co. Donegal | 2 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Srananagh (IE) | New substation in South Donegal (IE) | 82 | 463 | RIDP I | Srananagh - South Donegal | A new EHV overhead line from Srananagh in Co. Sligo to a new substation in south Co. Donegal |  | Investment on time | The preferred scheme has been selected since the last TYNDP; this is one of the elements of the preferred scheme. |  |  | 1 |  | 0 | Srananagh (IE) | New substation in South Donegal (IE) | Overhead Line | AC | 500 | 220 | 76 | New | 82 | 463 | RIDP I | Srananagh - South Donegal | 2 | Rescheduled | A capacity review of committed generators and upcoming new connection policy rules will impact on renewable generation totals that drive the date of need for this investment. | 2029 | 2029 | 1 | EIRGRID, SONI | Srananagh (IE) | New substation in South Donegal (IE) | Overhead Line | AC | 220 | 82 | 463 | RIDP I | Srananagh - South Donegal | A new EHV overhead line from Srananagh in Co. Sligo to a new substation in south Co. Donegal | 2 | Rescheduled | A capacity review of committed generators and upcoming new connection policy rules will impact on renewable generation totals that drive the date of need for this investment. | 2030 | 2030 | 1 | EIRGRID SONI | 2.13.2 | 0 | 1 | Srananagh (IE) | New substation in South Donegal (IE) | ACTransmissionLine | AC | 83 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2030 | 10 | 18 | GBR;IRL | Srananagh | New In South Donegal | 54.1686 | -8.3933
766 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 474 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 1 | 474 | RES in north of Portugal | New 400/60kV substation in Rib. Pena. | 3 | Delayed | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was delayed. | 2017 | 2017 | 1 | Ribeira de Pena (PT) |  | 474 | New 400/60kV substation in Rib. Pena. | 3 | Rescheduled | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was rescheduled. | 2020 | 2020 | 1 | Ribeira de Pena (PT) |  | 1 | 474 | RES in north of Portugal | Rib. Pena | New 400/60kV substation in Rib. Pena. | 3 | Rescheduled | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was rescheduled. | 31/ 12/ 2020 | 2020 | 1 |  | 0 | Ribeira de Pena (PT) |  | Substation |  | 890 | 400 |  | New | 1 | 474 | RES in north of Portugal | Substation Ribeira de Pena | 3 | Rescheduled | Due to the expected delay of the connection of new RES generation, the commissioning date of this investment item was rescheduled | 2022-2024 | 2024 | 1 |  | Ribeira de Pena (PT) | - | Substation | AC | 400 | 1 | 474 | RES in north of Portugal | Substation Ribeira de Pena | New 400/60kV substation in Ribeira de Pena. | 3 | Ahead of time |  | 2021 | 2021 | 1 | Rede Elétrica Nacional | 2.16.1 and 2.16.3 | 1 | 0 | Ribeira de Pena (PT) | - | OnshoreSubstation | AC | 0 | New | 1 | 474 | RES in north of Portugal | Substation Ribeira de Pena | New 400/60kV substation in Ribeira de Pena. | 5 | Investment on time |  | 12-2021 | 2021 | 1 | Rede Elétrica Nacional | 2.16.3 | 1 | 0 | Ribeira de Pena (PT) | - | OnshoreSubstation | AC | 0 | 400 | 0 | New | 1 | 474 | RES in north of Portugal | Substation Ribeira de Pena | New 400/60kV substation in Ribeira de Pena. | 5 | Investment on time |  | 12-2021 | 2021 | 1 | Rede Elétrica Nacional | 2.16.3 | 1 | 0 | Ribeira de Pena (PT) | - | OnshoreSubstation | AC | 0 | 400 | 0 | New | 1 | 474 | RES in north of Portugal | Substation Ribeira de Pena | New 400/60kV substation in Ribeira de Pena. | 5 | Commissioned | 12-2021 | 2021 | 1 | Rede Elétrica Nacional | 0 | XX | XX | New | 2017 | 2021 | 4 | 7 | PRT | Ribeira De Pena |  | 41.5217 | -7.7951
767 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 476 | Cancelled | 6 | New 400+220kV double circuit OHL (initially only used at 220kV) Vila Pouca Aguiar - (Rib. Pena) - Carrapatelo - Estarreja . Total length of line: 2x(90+49)km. | 3 | 2012/2013 | 2013 | 1 | V. P. Aguiar - Carrapatelo - Estarreja (PT) |  | 1 | 1. 6 | New 400+220kV double circuit OHL (initially only used at 220kV) Vila Pouca Aguiar - (Rib. Pena) - Carrapatelo - Estarreja . Total length of line: 2x(90+49)km. | 3 | Delays due to authorization process. | 2013 | 2013 | 1 | V. P. Aguiar - Carrapatelo - Estarreja (PT) |  | 1. 6 | 1. 6 | New 400+220kV double circuit OHL (initially only used at 220kV) Vila Pouca Aguiar - (Rib. Pena) - Carrapatelo - Estarreja . Total length of line: 2x(96+49)km. 220kV circuit. | 3 | Due to the expected delay of the connection of new RES generation in Portugal, the commissioning date of this investment is delayed. | 2017 | 2017 | 1 | V. P. Aguiar (by Carrapatelo) | Estarreja (by Carrapatelo) | 1 | 476 | RES in north of Portugal | New 400+220kV double circuit OHL (initially only used at 220kV) Vila Pouca Aguiar - (Rib. Pena) - Carrapatelo - Estarreja . Total length of line: 2x(96+49)km. 220kV circuit. | 3 | Delayed | Due to the expected delay of the connection of new RES generation in Portugal, the commissioning date of this investment item is delayed | 2017 | 2017 | 1 | V. P. Aguiar (by Carrapatelo) | Estarreja (by Carrapatelo) | 476 | New 400+220kV double circuit OHL (initially only used at 220kV) Vila Pouca Aguiar - (Rib. Pena) - Carrapatelo - Estarreja . Total length of line: 2x(96+49)km. 220kV circuit. | 3 | Rescheduled | Due to the expected delay of the connection of new RES generation in Portugal, the commissioning date of this investment item was rescheduled | 2020 | 2020 | 1 | V. P. Aguiar (by Carrapatelo) | Estarreja (by Carrapatelo) | 1 | 476 | RES in north of Portugal | V.P.Aguiar-Carrap.-Estarreja | New 400+220kV double circuit OHL (initially only used at 220kV) Vila Pouca Aguiar - (Rib. Pena) - Carrapatelo - Estarreja . Total length of line 121,7 km. | 3 | Rescheduled | Due to the expected delay of the connection of new RES generation in Portugal, the commissioning date of this investment item was rescheduled | 31/ 12/ 2020 | 2020 | 1 |  | 0 | V. P. Aguiar (by Carrapatelo) | Estarreja (by Carrapatelo) | Overhead Line | AC | 600 | 220 | 121.7 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2013 | 2020 | 7 | 10 | PRT | V. P. Aguiar | Estarreja |  |  | 40.7523 | -8.5703
768 | 2014 | 2016 | [2014, 2015, 2016] | 478 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 2 | 478 | RES in center of Portugal | New double circuit 400kV OHL (15km) to connect Penela substation to Paraimo-Batalha line. | 3 | Investment on time | design & permitting | 2016 | 2016 | 1 | Penela (PT) | Paraimo / Batalha (PT) | 478 | New double circuit 400kV OHL (15km) to connect Penela substation to Paraimo-Batalha line. | 3 | Rescheduled | Due to the expected delay of the connection of new hydro power plant, the commissioning date of this investment item was rescheduled | 2019 | 2019 | 1 | Penela (PT) | Paraimo / Batalha (PT) | 2 | 478 | RES in center of Portugal | Penela-Paraimo/Batalha | New double circuit 400kV OHL (15km) to connect Penela substation to Paraimo-Batalha line. | 3 | Rescheduled | Due to the expected delay of the connection of new hydro power plant, the commissioning date of this investment item was rescheduled | 31/ 12/ 2019 | 2019 | 1 |  | 0 | Penela (PT) | Paraimo / Batalha (PT) | Overhead Line | AC | 1780 | 400 | 15 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2019 | 3 | 5 | PRT | Penela | Paraimo Batalha | 40.0294 | -8.3902
769 | 2014 | 2016 | [2014, 2015, 2016] | 481 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 2 | 481 | RES in center of Portugal | Expansion of the existing Penela substation to include 400kV facilities. | 3 | Investment on time | Design & Permitting | 2016 | 2016 | 1 | Penela (PT) |  | 481 | Expansion of the existing Penela substation to include 400kV facilities. | 3 | Rescheduled | Due to the expected delay of the connection of new hydro power plant, the commissioning date of this investment item was rescheduled | 2019 | 2019 | 1 | Penela (PT) |  | 2 | 481 | RES in center of Portugal | Penela 400kV | Expansion of the existing Penela substation to include 400kV facilities. | 3 | Rescheduled | Due to the expected delay of the connection of new hydro power plant, the commissioning date of this investment item was rescheduled | 31/ 12/ 2019 | 2019 | 1 |  | 0 | Penela (PT) |  | Substation |  | 1780 | 400 |  | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2019 | 3 | 5 | PRT | Penela |  | 40.0294 | -8.3902
770 | 2014 | 2016 | [2014, 2015, 2016] | 484 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 2 | 484 | RES in center of Portugal | New 400/220kV substations in Fundão. | 3 | Delayed | Due to the expected delay on the connection of new RES generation in the centre of Portugal, the commissioning date of this investment item is delayed | 2017 | 2017 | 1 | Fundão (PT) |  | 484 | New 400/220kV substations in Fundão. |  | Investment on time | Project on time | 2017 | 2017 | 1 | Fundão (PT) |  | 2 | 484 | RES in center of Portugal | Fundão | New 400/220kV substation in Fundão. | 3 | Investment on time | Project on time | 31/ 12/ 2017 | 2017 | 1 |  | 0 | Fundão (PT) |  | Substation |  | 450 | 400 |  | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2017 | 0 | 3 | PRT | Fundão |  | 40.1408 | -7.5018
771 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 496 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 4 | 496 | Interconnection Portugal-Spain | New northern interconnection. New 400kV OHL Fontefría (ES) - Viana do Castelo (PT) - Vila do Conde (PT). | 3 | Delayed | Delays in authorization process due to a change on the route and on the location of substations were induced by environmental concerns | 2016 | 2016 | 1 | Fontefría (ES) | Vila do Conde (PT) (By Viana do Castelo) | 496 | New northern interconnection. New 400kV OHL Fontefría (ES) - Viana do Castelo (PT) - Vila do Conde (PT). | 3 | Delayed | Due to local opposition in the border area REN had to withdraw the Portuguese section of the interconnection of the ongoing EIA process to maintain the schedule of other investments included in the EIA needed for connecting new hydro in Cávado | 2018 | 2018 | 1 | Fontefría (ES) | Vila do Conde (PT) (By Viana do Castelo) | 4 | 496 | Interconnection Portugal-Spain | Fontefría (ES) - Vila Nova de Famalicão (PT) | New northern interconnection. New 400kV OHL Fontefría (ES) - Ponte de Lima (PT) - Vila Nova de Famalicão (PT). | 3 | Delayed | Due to local opposition in the border area REN had to withdraw the Portuguese section of the interconnection of the ongoing EIA process to maintain the schedule of other investments included in the EIA needed for connecting new hydro in Cávado | 31/ 12/ 2018 | 2018 | 1 |  | 1 | Fontefría (ES) | Vila Nova de Famalicão (PT) (By Ponte de Lima) | Overhead Line | AC | 1000 | 400 | 135 | New | 4 | 496 | Interconnection Portugal-Spain | Fontefria (ES) - Vila Nova de FamalicÆo (PT) | 3 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 1/ 1/ 2021 | 2021 | 1 |  | Fontefria (ES) | Vila Nova de FamalicÆo (PT) (By Ponte de Lima) | Overhead Line | AC | 400 | 4 | 496 | Interconnection Portugal-Spain | Fontefria (ES) - Vila Nova de Famalicão (PT) | New northern interconnection. New 400kV OHL Fontefria (ES) - Ponte de Lima (PT) - Vila Nova de Famalicão (PT). | 3 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 2022 | 2022 | 1 | Red Eléctrica de España Rede Elétrica Nacional | 2.17 | 1 | 1 | Fontefria (ES) | Vila Nova de Famalicão (PT) (By Ponte de Lima) | ACTransmissionLine | AC | 140.21 | New | 4 | 496 | Interconnection Portugal-Spain | Fontefria (ES) - Vila Nova de Famalicão (PT) | New 400kV OHL Fontefria (ES) - Ponte de Lima (PT) - Vila Nova de Famalicão (PT). | 3 | Delayed | Delays in the Environmental Impact Assessment process. Section Vila Nova de Famalicão-Ponte de Lima was comissioned in 2021. | 06-2024 | 2024 | 1 | REN and Red Eléctrica | 2.17 | 1 | 1 | Fontefria (ES) | Vila Nova de Famalicão (PT) (By Ponte de Lima) | ACTransmissionLine | AC | 0 | 400 | 94.71 | New | 4 | 496 | Interconnection Portugal-Spain | Fontefria (ES) - Vila Nova de Famalicão (PT) | New 400kV OHL Fontefria (ES) - Ponte de Lima (PT) - Vila Nova de Famalicão (PT). | 3 | Delayed | Delays in the Environmental Impact Assessment process. Section Vila Nova de Famalicão-Ponte de Lima was comissioned in 2021. | 12-2024 | 2024 | 1 | REN and Red Eléctrica | 1.1 | 1 | 1 | Fontefria (ES) | Vila Nova de Famalicão (PT) (By Ponte de Lima) | ACTransmissionLine | AC | 0 | 400 | 94.71 | New | 4 | 496 | Interconnection Portugal-Spain | Fontefria (ES) - Vila Nova de Famalicão (PT) | New 400kV OHL Fontefria (ES) - Ponte de Lima (PT) - Vila Nova de Famalicão (PT). | 4 |  | 11-2025 | 2025 | 1 | REN and Red Eléctrica | 1 | XX | XX | New | 2016 | 2025 | 9 | 11 | ESP;PRT | Fontefria | Vila Nova De Famalicão Pt | 42.387 | -7.9464 | 41.3867 | -8.4603
772 | 2014 | 2016 | [2014, 2015, 2016] | 497 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 4 | 497 | Interconnection Portugal-Spain | New double circuit 400kV OHL between Vila do Conde (PT) - Recarei/Vermoim (PT). | 3 | Delayed | Partial sections from the line found environmental problems in his original route. The problems are being solved with the identification of new routes, prompting a delay in the commissioning date. | 2015 | 2015 | 1 | Vila do Conde (PT) | Recarei/Vermoim (PT) | 497 | New double circuit 400kV OHL between Vila do Conde (PT) - Recarei/Vermoim (PT). | 4 | Investment on time | Progressed as planned | 2015 | 2015 | 1 | Vila do Conde (PT) | Recarei/Verm oim (PT) | 4 | 497 | Interconnection Portugal-Spain | Vila Nova de Famalicão-Recarei/Vermoim | New double circuit 400kV OHL between Vila Nova de Famalicão (PT) - Recarei/Vermoim (PT). | 5 | Commissioned | Line commissioned | 17/ 12/ 2015 | 2015 | 1 |  | 0 | Vila Nova de Famalicão (PT) | Recarei/Vermoim (PT) | Overhead Line | AC | 1000 | 400 | 26 | New | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 1 | PRT | Vila Nova De Famalicão | Recareivermoim | 41.4065 | -8.5188
773 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 498 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 4 | 498 | Interconnection Portugal-Spain | New northern interconnection. New 400kV substation Fontefria (ES), previously O Covelo. | 3 | Delayed | Delays in the authorization process, due to a change of location of the substation. Timing correlated to investment 18 | 2016 | 2016 | 1 | Fontefria (ES) |  | 498 | New northern interconnection. New 400kV substation Fontefria (ES), previously O Covelo. | 3 | Delayed | The delay of this investment is affected by the explanation in the investment 496. Also, environmental problems lead to re-routing | 2017 | 2017 | 1 | Fontefria (ES) |  | 4 | 498 | Interconnection Portugal-Spain | SE Fontefria 400/220kV | New northern interconnection. New 400kV substation Fontefria (ES), previously O Covelo. | 3 | Delayed | The delay of this investment is affected by the explanation in the investment 496. Also, environmental problems lead to re-routing | 1/ 1/ 2017 | 2017 | 1 |  | 0 | Fontefria (ES) |  | Substation |  | 1000 | 400 |  | New | 4 | 498 | Interconnection Portugal-Spain | SE Fontefria 400/220kV | 3 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 1/ 1/ 2021 | 2021 | 1 |  | Fontefria (ES) | REE | Substation | AC | 400 | 4 | 498 | Interconnection Portugal-Spain | SE Fontefria 400/220kV | New northern interconnection. New 400kV substation Fontefria (ES), previously O Covelo. | 3 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 2022 | 2022 | 1 | Red Eléctrica de España Rede Elétrica Nacional | 2.17 | 1 | 1 | Fontefria (ES) | REE | Transformer | AC | 0 | New | 4 | 498 | Interconnection Portugal-Spain | SE Fontefria 400/220kV | New 400kV substation Fontefria (ES), previously O Covelo. | 3 | Delayed | Delays in the Environmental Impact Assessment process | 06-2024 | 2024 | 1 | REN and Red Eléctrica | 2.17 | 1 | 1 | Fontefria (ES) | REE | Transformer | AC | 0 | 400 | 0 | New | 4 | 498 | Interconnection Portugal-Spain | SE Fontefria 400/220kV | New 400kV substation Fontefria (ES), previously O Covelo. | 3 | Delayed | Delays in the Environmental Impact Assessment process | 06-2024 | 2024 | 1 | REN and Red Eléctrica | 1.1 | 1 | 1 | Fontefria (ES) | REE | Transformer | AC | 0 | 400 | 0 | New | 4 | 498 | Interconnection Portugal-Spain | SE Fontefria 400/220kV | New 400kV substation Fontefria (ES), previously O Covelo. | 5 | Commissioned | 12-2024 | 2024 | 1 | REN and Red Eléctrica | 1 | XX | XX | New | 2016 | 2024 | 8 | 10 | ESP;PRT | Fontefria | Ree | 42.387 | -7.9464
774 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 499 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 4 | 499 | Interconnection Portugal-Spain | New northern interconnection. New 400kV substation Beariz (ES), previously Boboras | 3 | Delayed | Delays in the authorization process, due to a change of location of the substation. Timing correlated to investment 18 | 2016 | 2016 | 1 | Beariz (ES) |  | 499 | New northern interconnection. New 400kV substation Beariz (ES), previously Boboras | 3 | Delayed | The delay of this investment is affected by the explanation in the investment 496. Also, environmental problems lead to re-routing | 2017 | 2017 | 1 | Beariz (ES) |  | 4 | 499 | Interconnection Portugal-Spain | Beariz 400kV (ES) | New northern interconnection. New 400kV substation Beariz (ES), previously Boboras | 3 | Delayed | The delay of this investment is affected by the explanation in the investment 496. Also, environmental problems lead to re-routing | 1/ 1/ 2017 | 2017 | 1 |  | 0 | Beariz (ES) |  | Substation |  | 1000 | 400 |  | New | 4 | 499 | Interconnection Portugal-Spain | Beariz 400kV (ES) | 3 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 1/ 1/ 2021 | 2021 | 1 |  | Beariz (ES) | Beariz (ES) | Substation | AC | 400 | 4 | 499 | Interconnection Portugal-Spain | Beariz 400kV (ES) | New northern interconnection. New 400kV substation Beariz (ES), previously Boboras | 3 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 2022 | 2022 | 1 | Red Eléctrica de España Rede Elétrica Nacional | 2.17 | 1 | 1 | Beariz (ES) | Beariz (ES) | OnshoreSubstation | AC | 0 | New | 4 | 499 | Interconnection Portugal-Spain | Beariz 400kV (ES) | New 400kV substation Beariz (ES), previously Boboras | 3 | Delayed | Delays in the Environmental Impact Assessment process | 06-2024 | 2024 | 1 | REN and Red Eléctrica | 2.17 | 1 | 1 | Beariz (ES) | Beariz (ES) | OnshoreSubstation | AC | 0 | 400 | 0 | New | 4 | 499 | Interconnection Portugal-Spain | Beariz 400kV (ES) | New 400kV substation Beariz (ES), previously Boboras | 3 | Delayed | Delays in the Environmental Impact Assessment process | 06-2024 | 2024 | 1 | REN and Red Eléctrica | 1.1 | 1 | 1 | Beariz (ES) | Beariz (ES) | OnshoreSubstation | AC | 0 | 400 | 0 | New | 4 | 499 | Interconnection Portugal-Spain | Beariz 400kV (ES) | New 400kV substation Beariz (ES), previously Boboras | 5 | Commissioned | 05-2024 | 2024 | 1 | REN and Red Eléctrica | 1 | XX | XX | New | 2016 | 2024 | 8 | 10 | ESP;PRT | Beariz | Beariz | 42.4865 | -8.2876 | 42.4865 | -8.2876
775 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 500 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 4 | 500 | Interconnection Portugal-Spain | New 400/150kV substation V.Castelo (PT). | 3 | Delayed | Delays in the authorization process, due to a change of location of the substation. Timing correlated to investment 496. | 2016 | 2016 | 1 | V. Castelo (PT) |  | 500 | New 400/150kV substation V.Castelo (PT). | 3 | Delayed | Substation renamed to Ponte de Lima. See Investment 496. | 2018 | 2018 | 1 | V. Castelo (PT) |  | 4 | 500 | Interconnection Portugal-Spain | Ponte de Lima (PT) | New 400/150kV substation Ponte de Lima (PT), previously V. Castelo. | 3 | Delayed | Substation renamed to Ponte de Lima. See Investment 496. | 31/ 12/ 2018 | 2018 | 1 |  | 0 | Ponte de Lima (PT) |  | Substation |  | 1000 | 400 |  | New | 4 | 500 | Interconnection Portugal-Spain | Ponte de Lima (PT) | 3 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 2020-2021 | 2021 | 1 |  | Ponte de Lima (PT) | Ponte de Lima (PT) | Substation | AC | 400 | 4 | 500 | Interconnection Portugal-Spain | Ponte de Lima (PT) | New 400/150kV substation Ponte de Lima (PT), previously V. Castelo. | 3 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 2022 | 2022 | 1 | Red Eléctrica de España Rede Elétrica Nacional | 2.17 | 1 | 1 | Ponte de Lima (PT) | Ponte de Lima (PT) | OnshoreSubstation | AC | 0 | New | 4 | 500 | Interconnection Portugal-Spain | Ponte de Lima (PT) | New 400/150kV substation Ponte de Lima (PT), previously V. Castelo. | 3 | Delayed | Delays due to correlation with other delayed infrastructure investments. | 06-2024 | 2024 | 1 | REN and Red Eléctrica | 2.17 | 1 | 1 | Ponte de Lima (PT) | Ponte de Lima (PT) | OnshoreSubstation | AC | 0 | 400 | 0 | New | 4 | 500 | Interconnection Portugal-Spain | Substation Ponte de Lima (PT) | New 400/150kV substation Ponte de Lima (PT), previously V. Castelo. | 3 | Delayed | Delays due to correlation with other delayed infrastructure investments. | 12-2024 | 2024 | 1 | REN and Red Eléctrica | 1.1 | 1 | 1 | Ponte de Lima (PT) | Ponte de Lima (PT) | OnshoreSubstation | AC | 0 | 400 | 0 | New | 4 | 500 | Interconnection Portugal-Spain | Substation Ponte de Lima (PT) | New 400/150kV substation Ponte de Lima (PT), previously V. Castelo. | 4 |  | 11-2025 | 2025 | 1 | REN and Red Eléctrica | 1 | XX | XX | New | 2016 | 2025 | 9 | 11 | ESP;PRT | Ponte De Lima | Ponte De Lima | 41.7675 | -8.5831 | 41.7675 | -8.5831
776 | 2014 | 2016 | [2014, 2015, 2016] | 501 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 4 | 501 | Interconnection Portugal-Spain | New 400kV substation Vila do Conde (PT). | 3 | Delayed | Delays in the authorization process, due to a change of location of the substation. Timing correlated to investment 497. | 2015 | 2015 | 1 | Vila do Conde (PT) |  | 501 | New 400kV substation Vila do Conde (PT). | 4 | Investment on time | Substation renamed to Vila Nova de Famalicão. Progressed as planned. | 2015 | 2015 | 1 | Vila do Conde (PT) |  | 4 | 501 | Interconnection Portugal-Spain | Vila Nova de Famalicão (PT) | New 400kV substation Vila Nova de Famalicão (PT), previously Vila do Conde. | 5 | Commissioned | Substation commissioned. | 17/ 12/ 2015 | 2015 | 1 |  | 0 | Vila Nova de Famalicão (PT) |  | Substation |  | 1000 | 400 |  | New | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 1 | PRT | Vila Nova De Famalicão |  | 41.4065 | -8.5188
777 | 2015 | 2015 | [2015] | 503 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 |  |  | 503 | New 220kV JM Oriol-New Oriol -Arenales-Caceres. It requires new subestation Oriol | 3 | Delayed | Delays due to change of the definition of the project and national law RDL 13/2012 has frozen the permitting process until publication of the next NDP | 2018 | 2018 | 1 | JM Oriol (ES) | Arenales - Caceres (ES) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2018 | 0 | 3 | ESP | Jm Oriol | Arenales - Caceres |  |  | 39.6134 | -6.4269
778 | 2015 | 2015 | [2015] | 504 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 |  |  | 504 | New Arenales substation. | 3 | Delayed | National law RDL 13/2012 has frozen the permitting process until publication of the next NDP | 2018 | 2018 | 1 | Arenales (ES) | [6 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2018 | 0 | 3 | ESP | Arenales |  | 28.1156 | -15.4201
779 | 2014 | 2015 | [2014, 2015] | 505 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 5 | 505 | Eastern interconnection ES-FR | Converter station of the new HVDC (VSC) bipolar interconnection in the Eastern part of the border, via 320kV DC underground cable using existing infrastructures corridors. | 4 | Delayed | Works completed in 2014; commercial operation expected after test period at the same time as the cable (investment 36). | 2015 | 2015 | 1 | Sta.Llogaia (ES) |  | 505 | Converter station of the new HVDC (VSC) bipolar interconnection in the Eastern part of the border, via 320kV DC underground cable using existing infrastructures corridors. | 5 | Commissioned | Construction finalized in December 2014. Commissioned for commercial operation in June 2015 | 2015 | 2015 | 1 | Sta.Llogaia (ES) | [11 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 1 | ESP | Sta.Llogaia |  | 42.5767 | 1.0887
780 | 2014 | 2015 | [2014, 2015] | 506 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 5 | 506 | Eastern interconnection ES-FR | Converter station of the new HVDC (VSC) bipolar interconnection in the Eastern part of the border, via 320kV DC underground cable using existing infrastructures corridors. | 4 | Delayed | Works completed in 2014; commercial operation expected after test period at the same time as the cable (investment 36). | 2015 | 2015 | 1 | Baixas (FR) |  | 506 | Converter station of the new HVDC (VSC) bipolar interconnection in the Eastern part of the border, via 320kV DC underground cable using existing infrastructures corridors. | 5 | Commissioned | Works completed in 2014; commercial operation after test period in Summer 2015. | 2015 | 2015 | 1 | Baixas (FR) | [11 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 1 | FRA | Baixas |  | 41.3976 | 2.1446
781 | 2014 | 2015 | [2014, 2015] | 508 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 213 | 508 | Santa Llogaia - Bescano | New 400kV substation in Ramis with two 400/220kV transformers; connection as input/output in Santa Llogaia - Bescano line | 3 | Delayed | Answering all concerns expressed during the authorization process led to postponing the investment. | 2015 | 2015 | 1 | Ramis (ES) |  | 508 | New 400kV substation in La Farga with two 400/220kV transformers; connection as input/output in Santa Llogaia - Bescano line | 3 | Delayed | Final phase of permitting. Investment pending of its publication in the BOE. | 2016 | 2016 | 1 | Ramis (ES) | [6 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2016 | 1 | 2 | ESP | Ramis |  | 41.4317 | 1.3456
782 | 2014 | 2015 | [2014, 2015] | 509 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 213 | 509 | Santa Llogaia - Bescano | New 400kV substation Sta.Llogaia. | 4 | Delayed | Answering all concerns expressed during the authorization process led to postponing the investment. | 2014 | 2014 | 1 | Santa Llogaia (ES) |  | 509 | New 400kV substation Sta.Llogaia. | 5 | Commissioned | The investment progressed as previously planned | 2014 | 2014 | 1 | Santa Llogaia (ES) | [11 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2014 | 2014 | 0 | 0 | ESP | Santa Llogaia |  | 42.5767 | 1.0887
783 | 2014 | 2016 | [2014, 2015, 2016] | 522 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 151 | 522 | Asturian Ring | New 400kV substation Sama in the new Asturias Ring with connection to Lada and a new reactance. | 1 | Rescheduled | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by) | 2026 | 2026 | 1 | Sama (ES) |  | 522 | New 400kV substation Sama in the new Asturias Ring with connection to Lada and a new reactance. | 2 | Rescheduled | Changes due to correlation with Asturias Ring (investment 928) | 2020 | 2020 | 1 | Sama (ES) |  | 151 | 522 | Asturian Ring | New substation Sama | New 400kV substation Sama in the new Asturias Ring with connection to Lada and a new reactance. | 2 | Ahead of time | Changes in the Spanish Master Plan, approved after the released of the project candidate list. This project is considered in the assessment as a future project instead a midterm one. | 1/ 1/ 2020 | 2020 | 1 |  | 0 | Sama (ES) |  | Substation |  | 1220 | 400 |  | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2026 | 2020 | -6 | 6 | ESP | Sama |  | 43.2918 | -5.6795
784 | 2014 | 2016 | [2014, 2015, 2016] | 523 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 151 | 523 | Asturian Ring | New 400kV substation Reboria in the Asturian ring with 2 transformers 400/220 kV | 1 | Rescheduled | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by) | 2026 | 2026 | 1 | Reboria (ES) |  | 523 | New 400kV substation Reboria in the Asturian ring with 1 transformer 400/220 kV | 2 | Rescheduled | Changes due to correlation with Asturias Ring (investment 928) | 2020 | 2020 | 1 | Reboria (ES) |  | 151 | 523 | Asturian Ring | New substation Reboria | New 400kV substation Reboria in the Asturian ring with 1 transformer 400/220 kV | 2 | Ahead of time | Changes in the Spanish Master Plan, approved after the released of the project candidate list. This project is considered in the assessment as a future project instead a midterm one. | 1/ 1/ 2020 | 2020 | 1 |  | 0 | Reboria (ES) |  | Substation |  | 1220 | 400 |  | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2026 | 2020 | -6 | 6 | ESP | Reboria |  | 43.5531 | -5.7495
785 | 2014 | 2015 | [2014, 2015] | 524 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 151 | 524 | Asturian Ring | New 400kV substation Costa Verde in the Asturian Ring with 2 new transformer units 400/220 kV | 1 | Rescheduled | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by) | 2026 | 2026 | 1 | Costa Verde (ES) |  | 524 | New 400kV substation Costa Verde in the Asturian Ring with 2 new transformer units 400/220 kV | 1 | Investment on time | The investment progressed as planned | 2026 | 2026 | 1 | Costa Verde (ES) | [6 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2026 | 2026 | 0 | 12 | ESP | Costa Verde |  | 40.9676 | -5.6678
786 | 2014 | 2016 | [2014, 2015, 2016] | 537 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 203 | 537 | Aragón-Castellón | New 400kV substation Mudejar and connection to the axis Aragón-Teruel | 3 | Delayed | Delayed because National law RDL 13/2012 has frozen the permitting process until publication of the next NDP | 2016 | 2016 | 1 | Mudejar (ES) |  | 537 | New 400kV substation Mudejar and connection to the axis Aragón-Teruel | 4 | Investment on time | The investment progressed as previously planned | 2016 | 2016 | 1 | Mudejar (ES) |  | 203 | 537 | Aragón-Castellón | New substation Mudejar | New 400kV substation Mudejar and connection to the axis Aragón-Teruel | 5 | Commissioned |  |  |  | 1 |  | 0 | Mudejar (ES) |  | Substation |  | 1420 | 400 |  | New | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 |  |  |  | ESP | Mudejar |  | 39.9111 | -0.57183
787 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 538 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 203 | 538 | Aragón-Castellón | Southern part of the new Cantabric-Mediterranean axis. New double circuit Morella-la Plana 400kV-OHL. | 3 | Delayed | Delayed because National law RDL 13/2012 has frozen the permitting process until publication of the next NDP | 2018 | 2018 | 1 | Morella (ES) | La Plana(ES) | 538 | Southern part of the new Cantabric-Mediterranean axis. New double circuit Morella-la Plana 400kV-OHL. | 3 | Investment on time | The investment progressed as previously planned | 2018 | 2018 | 1 | Morella (ES) | La Plana(ES) | 203 | 538 | Aragón-Castellón | Morella-La Plana | Southern part of the new Cantabric-Mediterranean axis. New double circuit Morella-la Plana 400kV-OHL. | 3 | Investment on time | The investment progressed as previously planned | 1/ 1/ 2018 | 2018 | 1 |  | 0 | Morella (ES) | La Plana(ES) | Overhead Line | AC | 1420 | 400 | 78 | New | 203 | 538 | Morella-La Plana (previosly Aragón-Castellon) | Morella-La Plana | 3 | Delayed | Delay due to long permitting process | 2020 | 2020 | 1 | REE | Morella (ES) | La Plana(ES) | Overhead Line | AC | 400 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2020 | 2 | 6 | ESP | Morella | La Plana | 40.6188 | -0.099803 | 42.0534 | 1.8711
788 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 545 | Cancelled | [5 empty] | 0 |  |  | 8 | 8. 25a | New single circuit Escatrón-Els Aubals-La Secuita 400kV OHL with new 400kV substation in Els Aubals and La Secuita with 400/220kV transformer. | 3 | Delays due to authorization process. | 2015 | 2015 | 1 | Escatron (ES) | La Secuita (ES) | 8. 25a | 8. 25a | New single circuit Escatrón-Els Aubals-La Secuita 400kV OHL. | 3 | National law RDL 13/2012 has frozen the permitting process until publication of the next NDP. | 2017 | 2017 | 1 | Escatron (ES) | La Secuita (ES) | 157 | 545 | Aragón-Catalonia south | New single circuit Escatrón-Els Aubals-La Secuita 400kV OHL. | 1 | Rescheduled | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by) | 2027 | 2027 | 1 | Escatron (ES) | La Secuita (ES) | 545 | New single circuit Escatrón-Els Aubals-La Secuita 400kV OHL. | 1 | Investment on time | The investment progressed as previously planned | 2027 | 2027 | 1 | Escatron (ES) | La Secuita (ES) | 157 | 545 | Aragón-Catalonia south | Escatrón-La Secuita | New single circuit Escatrón-Els Aubals-La Secuita 400kV OHL. | 1 | Investment on time | The investment progressed as previously planned | 1/ 1/ 2027 | 2027 | 1 |  | 0 | Escatron (ES) | La Secuita (ES) | Overhead Line | AC | 200 | 400 | 125 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2027 | 12 | 15 | ESP | Escatron | La Secuita | 41.2871 | -0.32495 | 41.2041 | 1.2802
789 | 2014 | 2016 | [2014, 2015, 2016] | 546 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 157 | 546 | Aragón-Catalonia south | New 400kV substation in Els Aubals. | 1 | Rescheduled | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by) | 2027 | 2027 | 1 | Els Aubals (ES) |  | 546 | New 400kV substation in Els Aubals. | 1 | Investment on time | The investment progressed as previously planned | 2027 | 2027 | 1 | Els Aubals (ES) |  | 157 | 546 | Aragón-Catalonia south | New substation Els Aubals | New 400kV substation in Els Aubals. | 1 | Investment on time | The investment progressed as previously planned | 1/ 1/ 2027 | 2027 | 1 |  | 0 | Els Aubals (ES) |  | Substation |  | 200 | 400 |  | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2027 | 2027 | 0 | 13 | ESP | Els Aubals
790 | 2014 | 2016 | [2014, 2015, 2016] | 547 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 157 | 547 | Aragón-Catalonia south | New 400kV substation in La Secuita with 400/220kV transformer. | 1 | Rescheduled | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by) | 2027 | 2027 | 1 | La Secuita (ES) |  | 547 | New 400kV substation in La Secuita with 400/220kV transformer. | 1 | Investment on time | The investment progressed as previously planned | 2027 | 2027 | 1 | La Secuita (ES) |  | 157 | 547 | Aragón-Catalonia south | New substation La Secuita | New 400kV substation in La Secuita with 400/220kV transformer. | 1 | Investment on time | The investment progressed as previously planned | 1/ 1/ 2027 | 2027 | 1 |  | 0 | La Secuita (ES) |  | Substation |  | 200 | 400 |  | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2027 | 2027 | 0 | 13 | ESP | La Secuita |  | 41.2041 | 1.2802
791 | 2010 | 2018 | [2010, 2012, 2013, 2014, 2015, 2016, 2018] | 55 | Commissioned | 55 | "Savoie - Piémont" Project : New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 500MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way. | 3 | long term |  | 1 | Grande Ile (FR) | Piossasco (IT) | 21 | 21. 55 | "Savoie - Piémont" Project : New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 600MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and possibly also along the existing motorways' right-of-way. | 3 | Progresses as planned | 2017/2018 | 2018 | 1 | Grande Ile (FR) | Piossasco (IT) | 21. 55 | 21. 55 | "Savoie - Piémont" Project : New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 600MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and also along the existing motorways' right-of-way. | 3 | Some delay in the works of the Frejus service gallery of the motorway, in which the cables will be installed. The investment timeline has also been updated taking into account the permitting and technical issues for this very specific investment. | 2019 | 2019 | 1 | Grande Ile (FR) | Piossasco (IT) | 21 | 55 | Italy-France | "Savoie - Piémont" Project : New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 600MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and also along the existing motorways' right-of-way. | 4 | Delayed | After some delay in the works of the Frejus service gallery of the motorway, in which the cables will be installed, the project timeline has been updated. Works are already in progress. | 2019 | 2019 | 1 | Grande Ile (FR) | Piossasco (IT) | 55 | "Savoie - Piémont" Project : New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 600MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and also along the existing motorways' right-of-way. | 4 | Investment on time | Works in progress. | 2019 | 2019 | 1 | Grande Ile (FR) | Piossasco (IT) | 21 | 55 | Italy-France | Savoie - Piémont | "Savoie - Piémont" Project; New 190km HVDC (VSC) interconnection FR-IT via underground cable and converter stations at both ends (two poles, each of them with 600MW capacity). The cables will be laid in the security gallery of the Frejus motorway tunnel and also along the existing motorways' right-of-way. | 4 | Investment on time | Works in progress. | 1/ 1/ 2019 | 2019 | 1 |  | 1 | Grande Ile (FR) | Piossasco (IT) | Underground Cable | DC | 1200 | 320 | 190 | New | 21 | 55 | Italy-France | Savoie - Pièmont | 4 | Investment on time |  | 2019 | 2019 | 1 | RTE;TERNA | Grande Ile (FR) | Piossasco (IT) | Underground Cable | DC | 320 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2019 |  | 9 | FRA;ITA | Grande Ile | Piossasco |  |  | 44.9909 | 7.4629
792 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 561 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 194 | 561 | Cartuja | New 400kV substation Cartuja with a 400/220kV transformer. | 1 | Rescheduled | Investment rescheduled as the associated new wind power plants have been postponed | 2022 | 2022 | 1 | Cartuja (ES) |  | 561 | New 400kV substation Cartuja with a 400/220kV transformer. | 1 | Investment on time | The investment progressed as previously planned | 2022 | 2022 | 1 | Cartuja (ES) |  | 194 | 561 | Cartuja | New substation Cartuja | New 400kV substation Cartuja with a 400/220kV transformer. | 1 | Rescheduled | Rescheduled due to changes in the Spanish Master Plan that consider a delay in the commissioning of the renewable generation link to this project | 1/ 1/ 2029 | 2029 | 1 |  | 0 | Cartuja (ES) |  | Substation |  | 1320 | 400 |  | New | 194 | 561 | Cartuja | New substation Cartuja | 1 | Investment on time |  | 2029 | 2029 | 1 | REE | Cartuja (ES) | Cartuja (ES) | Substation | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2029 | 7 | 15 | ESP | Cartuja | Cartuja | 37.4072 | -6.0101 | 37.4072 | -6.0101
793 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 569 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 13 | 569 | Baza project | New 400kV substation in Baza | 1 | Rescheduled | Investment rescheduled due to, and in accordance with, delayed development of new power plant, as considered in the Master Plan 2020 in progress | 2025 | 2025 | 1 | Baza (ES) |  | 569 | New 400kV substation in Baza | 1 | Investment on time | Progressed as planned | 2025 | 2025 | 1 | Baza (ES) |  | 13 | 569 | Baza project | New substation Baza | New 400kV substation in Baza | 1 | Investment on time | Investment rescheduled due to, and in accordance with, delayed development of new power plant, as considered in the Master Plan 2020 in progress | 1/ 1/ 2025 | 2025 | 1 |  | 0 | Baza (ES) |  | Substation |  | 2060 | 400 |  | New | 13 | 569 | Baza project | New substation Baza | 1 | Investment on time |  | 2025 | 2025 | 1 |  | Baza (ES) | Baza (ES) | Substation | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 11 | ESP | Baza | Baza | 37.4282 | -2.8475 | 37.4282 | -2.8475
794 | 2014 | 2016 | [2014, 2015, 2016] | 57 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 22 | 57 | Lake Geneva West | Reconductoring of the existing 225kV double circuit line Genissiat-Verbois with high temperature conductors. | 2 | Investment on time | - | 2020 | 2020 | 1 | Genissiat (FR) | Verbois (CH) | 57 | Upgrading of the existing 225kV double circuit line Genissiat- Verbois to increase its capacity. | 2 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Genissiat (FR) | Verbois (CH) | 22 | 57 | Lake Geneva West | Geneva's lake (West) | Upgrading of the existing 225kV double circuit line Genissiat-Verbois to increase its capacity. | 2 | Rescheduled | Feasibility studies showed the works are lighter and could be achieved earlier than initially thought. | 1/ 1/ 2018 | 2018 | 1 |  | 1 | Genissiat (FR) | Verbois (CH) | Overhead Line | AC | 500 | 220 | 20 | Upgrade |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2018 | -2 | 4 | CHE;FRA | Genissiat | Verbois | 46.0505 | 5.7673 | 46.193 | 6.0289
795 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 570 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 13 | 570 | Baza project | New 400kV substation in La Ribina (will be connected as an input/output in Carril-Litoral 400kV line ). | 1 | Rescheduled | Investment rescheduled due to, and in accordance with, delayed development of new power plant, as considered in the Master Plan 2020 in progress | 2025 | 2025 | 1 | La Ribina (ES) |  | 570 | New 400kV substation in La Ribina (will be connected as an input/output in Carril-Litoral 400kV line ). | 1 | Investment on time |  | 2025 | 2025 | 1 | La Ribina (ES) |  | 13 | 570 | Baza project | New substation La Ribina | New 400kV substation in La Ribina (will be connected as an input/output in Carril-Litoral 400kV line ). | 1 | Investment on time | Investment rescheduled due to, and in accordance with, delayed development of new power plant, as considered in the Master Plan 2020 in progress | 1/ 1/ 2025 | 2025 | 1 |  | 0 | La Ribina (ES) |  | Substation |  | 2060 | 400 |  | New | 13 | 570 | Baza project | New substation La Ribina | 1 | Investment on time |  | 2025 | 2025 | 1 |  | La Ribina (ES) | La Ribina (ES) | Substation | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2025 | 0 | 11 | ESP | La Ribina | La Ribina | 37.2472 | -1.8585 | 37.2472 | -1.8585
796 | 2014 | 2016 | [2014, 2015, 2016] | 594 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 184 | 594 | PST Arkale | New PST in Arkale-Argia 220 kV interconnection line | 2 | Investment on time | Draft NDP expected to be published during the preparation of TYNDP 2012 was not finally approved and published, so the investment is yet in a planning stage. If the new NDP is published by 2014, as expected, commissioning date would not be affected. | 2016 | 2016 | 1 | Arkale (ES) |  | 594 | New PST in Arkale-Argia 220 kV interconnection line | 3 | Delayed | delays associated to the contract process and internal approval of budget including financing | 2017 | 2017 | 1 | Arkale (ES) |  | 184 | 594 | PST Arkale | PST Arkale | New PST in Arkale-Argia 220 kV interconnection line | 3 | Delayed | Delays because of closure on budget and financing | 1/ 1/ 2017 | 2017 | 1 |  | 1 | Arkale (ES) |  | Phase Shift Transformer |  | 500 | 220 |  | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2017 | 1 | 3 | ESP | Arkale |  | 43.3369 | -1.7994
797 | 2014 | 2016 | [2014, 2015, 2016] | 597 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 158 | 597 | Massif Central South | New 175-km 400kV double circuit OHL Gaudière-Rueyres substituting to the existing single circuit 400kV OHL | 1 | Investment on time | Studies conducted after TYNDP2012 release have led to better investment definition. | 2023 | 2023 | 1 | La Gaudière (FR) | Rueyres (FR) | 597 | New 175-km 400kV double circuit OHL Gaudière-Rueyres substituting to the existing single circuit 400kV OHL | 2 | Investment on time | Further studies performed after TYNDP2014 confirmed the feasibility of the project. | 2023 | 2023 | 1 | La Gaudière (FR) | Rueyres (FR) | 158 | 597 | Massif Central South | Southern Massif Central | New 175-km 400kV double circuit OHL Gaudière-Rueyres substituting to the existing single circuit 400kV OHL | 2 | Rescheduled | Further studies performed after TYNDP2014 confirmed the feasibility of the project. The commisionning date follows the amount of generation installation in the area (Hydro, Solar and Wind). | 1/ 1/ 2025 | 2025 | 1 |  | 0 | La Gaudière (FR) | Rueyres (FR) | Overhead Line | AC | 3500 | 400 | 175 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2025 | 2 | 11 | FRA | La Gaudière | Rueyres | 48.6349 | -1.1066 | 44.7481 | 1.8464
798 | 2010 | 2020 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020] | 60 | Commissioned | 60 | to be determined. | 1 | long term |  | 1 | under consideration (FR) | under consideration (BE) | 23 | 23. 60 | To be determined. |  | Project entered a feasibility study phase. Expected date of commissioning is now 2018. | 2018-2020 | 2020 | 1 | under consideration (FR) | under consideration (BE) | 23. 60 | 23. 60 | France -Belgium | 1 | The final commissioning date is not yet finalized, it is expected to be commissioned between 2018-2020 : investment progresses as planned | 2019 | 2019 | 1 | Avelin/Mastaing (FR) | Horta (new 400-kV substation) (BE) | 23 | 60 | France-Belgium Phase 1 | Replacement of the current conductors on the axis Avelin/Mastaing - Avelgem - Horta with high performance conductors (HTLS = High Temperature Low Sag) | 2 | Rescheduled | Investment was at conceptual stage in TYNDP2012; on-going feasibility studies lead to a more accurate commissioning date. | 2021 | 2021 | 1 | Avelin/Mastaing (FR) | Horta (new 400-kV substation) (BE) | 60 | Replacement of the current conductors on the axis Avelin/Mastaing - Avelgem - Horta with high performance conductors (HTLS = High Temperature Low Sag) | 3 | Rescheduled | Planning has been actualized in accordance to achieved progress, with the evaluation of the final investment decision currently planned in 2018 | 2022 | 2022 | 1 | Avelin/Mastai ng (FR) | Horta (new 400-kV substation) (BE) | 23 | 60 | France-Belgium Phase 1 | France -Belgium | Replacement of the current conductors on the axis Avelin/Mastaing - Avelgem - Horta with high performance conductors (HTLS = High Temperature Low Sag) | 3 | Rescheduled | Detailed feasibility studies showed the works could be achieved by 2022, earlier than initially planned, assuming acquisition of all necessary permits as planned. | 1/ 1/ 2022 | 2022 | 1 |  | 1 | Avelin/Mastaing (FR) | Horta (BE) | Overhead Line | AC | 1000 | 400 | 80 | Upgrade | 23 | 60 | FR-BE I: Avelin/Mastaing-Avelgem-Horta HTLS | FR-BE I: Avelin/Mastaing-Avelgem-Horta HTLS | 3 | Rescheduled | Project is expected 1 year earlier than TYNDP16 | 1/1/2022 | 2022 | 1 | ELIA; RTE | Avelin/Mastaing (FR) | Horta (BE) | Overhead Line | AC | 400 | 23 | 60 | FR-BE: Avelin/Mastaing-Avelgem-Horta HTLS | FR-BE I: Avelin/Mastaing-Avelgem-Horta HTLS | Replacement of the current conductors on the axis Avelin/Mastaing - Avelgem - Horta with high performance conductors (HTLS = High Temperature Low Sag) | 4 | Rescheduled | Rescheduled due to technical issue on HTLS cable | 2022 | 2022 | 1 | ELIA RTE |  | 1 | 1 | Avelin/Mastaing (FR) | Horta (BE) | ACTransmissionLine | AC | 80 | Upgrade | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2022 |  | 12 | BEL;FRA | Avelinmastaing | Horta |  |  | 50.8259 | 4.3457
799 | 2010 | 2024 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024] | 604 | Commissioned | 60a | Doubling of the axis Zandvliet-Mercator via Lillo by erecting a new 35km 380kV double circuit OHL with 1500 MVA capacity. | 3 | 2018 | 2018 | 1 | Lillo (BE) | Mercator (BE) | 24 | 24. 60a | Brabo Project : Doubling of the axis Zandvliet-Mercator via Lillo. First part : erecting a new 22km double circuit 380kV OHL with 1500 MVA capacity Lillo and Mercator. | 3 | New date of operation advanced to 2017 due to new generation projects. | 2017 | 2017 | 1 | Lillo (BE) | Mercator (BE) | 24. 60a | 24. 60a | Brabo Project : Doubling of the axis Zandvliet-Mercator via Lillo. First part : erecting a new 22km double circuit 380kV OHL with 1900 MVA capacitybetween Lillo and Mercator. | 3 |  | 2017 | 2017 | 1 | Lillo (BE) | Mercator (BE) | 24 | 604 | Belgian North Border | Brabo: part Lillo-Mercator + restructuring 150kV. Brabo allows to realize the intended market capacity increase on the North Border in a more robust way (greater scenario independence compared to PST 4 only) , and reinforces the network to facilitate increased demand and connection of possible new generation around Antwerp Harbour area. It consists of constructing a new 380kV circuit Zandvliet-Lillo(new substation)-Mercator, in addition to the existing Zandvliet - Mercator connection. This investment item concerns the part between Lillo and Mercator substations, involving a restructuring of the adjacent 150kV network. | 3 | Delayed | Permitting procedure for adaptation of land use (GRUP) had to be reinitiated, in order to comply with the demand of investigating alternative solutions. | 2018 | 2018 | 1 | Lillo (BE) | Mercator (BE) | 604 | BRABO II + III allow to realize the intended market capacity increase on the North Border after BRABO I in a more robuste way, to secure increased demand around Antwerp Harbour area (mainly BRABO II) and to create capacity for connection of possible new generation (mainly BRABO III). This by constructing a new 380kV connection Zandvliet- Lillo(new substation)-Mercator, in addition to the existing Zandvliet - Mercator connection. This investment item concerns the part from Liefkenshoek to Mercator, where an existing 150kV link will be replaced by the new 380 kV link. | 3 | Rescheduled | With the hypothesis of the nuclear phase out taking place as per the current legal framework in combination with the cancellation of plans to construct new production units in the area, the third phase of BRABO has been rescheduled. | 2023 | 2023 | 1 | Lillo (BE) | Mercator (BE) | 297 | 604 | Belgian North Border: BRABO II + III | BRABO III: Liefkenshoek - Mercator | The existing 150kV overhead will be upgraded to a single 380kV overhead line between the site Liefkenshoek and the substation Mercator. To facilitate this upgrade, the adjacent 150kV grid will be adapted. This investment would be needed in an earlier stage (before 2023, 2020 earliest possible) to secure the intended interconnection capacity increase, if a production scenario would occur where all four nuclear units at Doel are present. | 3 | Rescheduled | BRABO III will be realized sequentially after BRABO II in anticipation of potential future integration of production unit / interconnectors in the Antwerp area, hereby safeguarding the long-term character of the increase of interconnection capacity of the North Border. | 01/01/2023 | 2023 | 1 |  | 0 | Liefkenshoek (BE) | Mercator (BE) | Overhead Line | AC | 1000 | 380 | 18 | New | 297 | 604 | BRABO II + III | BRABO III: Liefkenshoek - Mercator | 3 | Investment on time |  | 01/01/2023 | 2023 | 1 |  | Liefkenshoek (BE) | Mercator (BE) | Overhead Line | AC | 380 | 297 | 604 | BRABO II + III | BRABO III: Liefkenshoek - Mercator | The existing 150kV overhead will be upgraded to a single 380kV overhead line between the site Liefkenshoek and the substation Mercator. To facilitate this upgrade, the adjacent 150kV grid will be adapted. | 3 | Investment on time |  | 2025 | 2025 | 1 | ELIA | 2.23 | 0 | 0 | Liefkenshoek (BE) | Mercator (BE) | ACTransmissionLine | AC | 19 | New | 297 | 604 | BRABO II + III | BRABO III: Liefkenshoek - Mercator | The existing 150kV overhead will be upgraded to a single 380kV overhead line between the site Liefkenshoek and the substation Mercator. To facilitate this upgrade, the adjacent 150kV grid will be adapted. | 4 | Investment on time |  | 07-2025 | 2025 | 1 | Elia | 2.23 | 0 | 0 | Liefkenshoek (BE) | Mercator (BE) | ACTransmissionLine | AC | 0 | 380 | 19 | New | 297 | 604 | BRABO III | BRABO III: Liefkenshoek - Mercator | The existing 150kV overhead will be upgraded to a single 380kV overhead line between the site Liefkenshoek and the substation Mercator. To facilitate this upgrade, the adjacent 150kV grid will be adapted. | 4 | Delayed | Permitting process took longer than expected | 12-2026 | 2026 | 1 | Elia | 1.9 | 1 | 0 | Liefkenshoek (BE) | Mercator (BE) | ACTransmissionLine | AC | 0 | 380 | 19 | Upgrade | [5 empty] | 5 | Commissioned |  |  | 0 | [5 empty] | 2018 | 2026 | 8 | 16 | BEL | Liefkenshoek | Mercator | 51.0113 | 3.8801 | 50.9097 | 4.3963
800 | 2014 | 2022 | [2014, 2015, 2016, 2018, 2020, 2022] | 605 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 24 | 605 | Belgian North Border | Brabo - substation Lillo 380: Brabo allows to realize the intended market capacity increase on the North Border in a more robust way (greater scenario independence compared to PST 4 only) , and reinforces the network to facilitate increased demand and connection of possible new generation around Antwerp Harbour area. It consists of constructing a new 380kV circuit Zandvliet-Lillo(new substation)-Mercator, in addition to the existing Zandvliet - Mercator connection. This investment item concerns the erection of new 380kV substation Lillo. | 3 | Delayed | Permitting procedure for adaptation of land use (GRUP) had to be reinitiated, in order to comply with the demand of investigating alternative solutions. | 2018 | 2018 | 1 | Lillo (BE) |  | 605 | This investment item concerns the construction of the 380kV substation Lillo as part of the BRABO II project. | 3 | Delayed | Progress made in permitting procedures brought clarification to preferential trajectory. Planning has been reviewed accordingly with 2019 based upon the hypothesis of acquiring all necessary permits as currently planned. | 2020 | 2020 | 1 | Lillo (BE) |  | 297 | 605 | Belgian North Border: BRABO II + III | BRABO II: Lillo 380 | This concerns the construction of the 380kV substation Lillo, including a 380/150 kV transformer, as part of the second phase of the BRABO-project. | 3 | Delayed | Progress made in permitting procedures brought clarification to preferential trajectory. Planning has been reviewed accordingly with 2019 based upon the hypothesis of acquiring all necessary permits as currently planned. | 01/01/2019 | 2019 | 1 |  | 0 | Lillo (BE) |  | Substation |  | 1000 | 380 |  | New | 297 | 605 | BRABO II + III | BRABO II: Lillo 380 | 4 | Investment on time |  | 31/03/2019 | 2019 | 1 |  | Lillo (BE) | Lillo (BE) | Substation | AC | 380 | 297 | 605 | BRABO II + III | BRABO II: Lillo 380 | "This concerns the construction of the 380kV substation Lillo, including a 380/150 kV transformer, as part of the second phase of the BRABO-project." | 4 | Investment on time |  | 2019 | 2019 | 1 | ELIA | 2.23 | 0 | 0 | Lillo (BE) | Lillo (BE) | OnshoreSubstation | AC | 0 | New | 297 | 605 | BRABO II + III | BRABO II: Lillo 380 | "This concerns the construction of the 380kV substation Lillo, including a 380/150 kV transformer, as part of the second phase of the BRABO-project." | 5 | Commissioned |  | 01-2020 | 2020 | 1 | Elia | 2.23 | 0 | 0 | Lillo (BE) | Lillo (BE) | OnshoreSubstation | AC | 0 | 380 | 0 | New | [10 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2020 | 2 | 6 | BEL | Lillo | Lillo | 51.3048 | 4.2902 | 51.3048 | 4.2902
801 | 2014 | 2015 | [2014, 2015] | 606 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 24 | 606 | Belgian North Border | Gramme-Van Eyck: second 380kV circuit First phase of reinforcement on the axis Gramme-Van Eyck, needed to facilitate connection of possible new central generation and to prepare for increasing transit fluxes whilst securing market capacity between BE & NL. This investment consist of creating a second 380kV line on the axis Gramme-Van Eyck - Section Van Eyck - Zutendaal (30 km): need to erect a new single circuit. Done with high performance conductors in order to be future proof (cfr. phase 2) - Section Gramme - Zutendaal (55km): reconfiguration of 150kV network so that an existing 150kV line can be operated at 380kV | 4 | Delayed | Implementation of the project has been aligned with maintenance period of nuclear units ==> commissioning now foreseen in 2015 instead of end 2014 | 2015 | 2015 | 1 | Gramme (BE) | Van Eyck (BE) | 606 | Gramme-Van Eyck Part 1: second 380kV circuit. First phase of reinforcement on the axis Gramme-Van Eyck, needed to facilitate connection of possible new central generation and to prepare for increasing transit fluxes whilst securing market capacity between BE & NL. This investment consist of creating a second 380kV line on the axis Gramme-Van Eyck - Section Van Eyck - Zutendaal (30 km): need to erect a new single circuit. Done with high performance conductors in order to be future proof (cfr. phase 2) - Section Grammme - Zutendaal (55km): reconfiguration of 150kV network so that an existing 150kV line can be operated at 380kV | 4 | Investment on time | Progressed as planned. | 2015 | 2015 | 1 | Gramme (BE) | Van Eyck (BE) | [5 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 1 | BEL | Gramme | Van Eyck | 50.4163 | 4.447 | 51.2108 | 4.4116
802 | 2014 | 2015 | [2014, 2015] | 607 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 24 | 607 | Belgian North Border | Gramme-Van Eyck: substation Van Eyck 380 First phase of reinforcement on the axis Gramme-Van Eyck, needed to facilitate connection of possible new central generation and to prepare for increasing transit fluxes whilst securing market capacity between BE & NL. This investment item consists of construction a 380kV substation named "Van Eyck", needed to integrate the second 380 kV line on the axis Gramme-Van Eyck. | 4 | Delayed | Commissioning date of this inv. item aligned with implementation of inv. item 606 thus now 2015 instead of 2014 | 2015 | 2015 | 1 | Van Eyck (BE) |  | 607 | Gramme-Van Eyck Part 1: substation Van Eyck 380. First phase of reinforcement on the axis Gramme-Van Eyck, needed to facilitate connection of possible new central generation and to prepare for increasing transit fluxes whilst securing market capacity between BE & NL. This investment item consists of construction a 380kV substation named "Van Eyck", needed to integrate the second 380 kV line on the axis Gramme-Van Eyck. | 4 | Investment on time | Progressed as planned. | 2015 | 2015 | 1 | Van Eyck (BE) | [6 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 1 | BEL | Van Eyck |  | 51.2108 | 4.4116
803 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 608 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 24 | 608 | Belgian North Border | Horta-Mercator in HTLS The axis Horta-Mercator needs to be upgraded in order to transport the envisioned higher fluxes between France, Stevin & the Netherlands, and to facilitate connection of possible new generation (+-1000 MW) . Upgrade consists of replacing the current double circuit 380kV by high performance conductors allowing to double its transport capacity. The line currently passing Mercator going to Doel will be integrated into Mercator substation to obtain a better flux balance and avoid an upgrade between Mercator & Doel at this stage. | 3 | Investment on time | The expected commissioning date of 2019 is based on the hypothesis of acquiring all necessary permits as planned, followed by the assessment of the final investment decision in 2016. Meanwhile the drivers behind this investment will be further monitored and its timing managed accordingly. | 2019 | 2019 | 1 | Horta (BE) | Mercator (BE) | 608 | Horta-Mercatorin HTLS. Critical element in the Belgian backbone, which needs to be upgraded in order to transport higher north-south fluxes (transit flows + additional market flows) and to allow connection of possible new generation (+-1000 MW) on the axis. Upgrade consists of replacing the current double circuit 380kV by high performance conductors allowing to double its transport capacity. The line currently passing Mercator going to Doel will be integrated into Mercator substation to obtain a better flux balance and avoid an upgrade between Mercator & Doel at this stage. | 3 | Ahead of time | The expected commissioning date of 2019 is based on the hypothesis of acquiring all necessary permits as planned, followed by the assessment of the final investment decision towards 2017. | 2019 | 2019 | 1 | Horta (BE) | Mercator (BE) / (Doel)(BE) | 236 | 608 | Internal Belgian Backbone West | Horta-Mercator: HTLS upgrade | The project consists of replacing the current double circuit 380 kV overhead line between Horta and Mecator with high performance conductors. The 380kV circuit currently bypassing Mercator onwards to Doel will be integrated into the Mercator substation to obtain a better flux balance and avoid an upgrade between Mercator & Doel at this stage. | 3 | Investment on time | The expected commissioning date of 2019 is based on the hypothesis of acquiring all necessary permits as planned. | 01/01/2019 | 2019 | 1 |  | 0 | Horta (BE) | Mercator (BE) | Overhead Line | AC | 1500 | 380 | 50 | Upgrade | 236 | 608 | Internal Belgian Backbone West: HTLS upgrade Horta-Mercator | HTLS upgrade Horta-Mercator | 4 | Investment on time |  | 31/12/2019 | 2019 | 1 | ELIA | Horta (BE) | Mercator (BE) | Overhead Line | AC | 380 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2019 | 0 | 5 | BEL | Horta | Mercator | 50.8259 | 4.3457 | 50.9097 | 4.3963
804 | 2014 | 2016 | [2014, 2015, 2016] | 609 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 24 | 609 | Belgian North Border | Horta-Mercator in HTLS The axis Horta-Mercator needs to be upgraded in order to transport the envisioned higher fluxes between France, Stevin & the Netherlands, and to facilitate connection of possible new generation (+-1000 MW) . Upgrade consists of replacing the current double circuit 380kV by high performance conductors allowing to double its transport capacity. The line currently passing Mercator going to Doel will be integrated into Mercator substation to obtain a better flux balance and avoid an upgrade between Mercator & Doel at this stage. | 4 | Investment on time | Installation of PST (plus upgrade of line Doel-Zandvliet) will be done as a first reinforcement in the Antwerp area. The PST has been ordered, as such the status of this investment is "under construction" with an expected commissioning date of 2016. | 2016 | 2016 | 1 | Zandvliet (BE) |  | 609 | New PST in Zandvliet substation making it the 4 th PST on the Belgian North Border, allowing a more symmetrical utilisation of the PST's. Enabling this PST to increase import capacity from NL to BE implies that the current 150kV line Zandvliet-Doel is converted to 380kV, involving adaptations to be made to the configurations of Zandvliet & Doel substations and a solution to cover the supply of Doel 150kV (probably transfo 380/150). Integrating this PST at Zandvliet also implies that a "langskoppeling" is put at Zandvliet as temporary interface between Zandvliet and the NL network until the post "Rilland" is constructed in NL (investment item 439 as part of project # 103 "Reinforcements Ring NL"). Note that the realization of investment item 439 is needed as well to allow a capacity increase direction BE to NL. | 4 | Investment on time | Progressed as planned. | 2016 | 2016 | 1 | Zandvliet (BE) |  | 24 | 609 | Belgian North Border: BRABO I | BRABO I: PST 4 + Doel-Zandvliet | New PST in Zandvliet substation making it the 4th PST on the Belgian North Border. Enabling this PST to increase import capacity from NL to BE implies that the current single 150 kV overhead line Zandvliet-Doel is upgraded to 380 kV, including i) adaptations to the Zandvliet & Doel substations ii) the installation of a 380/150 kV transformer in Doel iii) the installation of a 150kV cable Kallo-Ketenisse-Lillo with 150kV substation at Ketenisse The integration of this PST at Zandvliet implies that a "langskoppeling" is put at Zandvliet as temporary interface between Zandvliet and the NL network until the post "Rilland" is constructed in NL (investment item 439 as part of project # 103 "Reinforcements Ring NL"). Note that the realization of investment item 439 is needed as well to allow a capacity increase direction BE to NL. | 4 | Investment on time | Progressed as planned. | 31/10/ 2016 | 2016 | 1 |  | 1 | Zandvliet (BE) |  | Phase Shift Transformer |  | 1000 | 380 |  | Upgrade |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2016 | 0 | 2 | BEL | Zandvliet |  | 51.36 | 4.3087
805 | 2014 | 2022 | [2014, 2015, 2016, 2018, 2020, 2022] | 614 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 26 | 614 | Austria - Italy | interconnector IT-AT (phase 1) | 3 | Investment on time | - | 2018 | 2018 | 1 | Nauders (AT) | Glorenza (IT) | 614 | interconnector IT-AT (phase 1) | 3 | Investment on time | Progressed as planned | 2018 | 2018 | 1 | Nauders (AT) | Glorenza (IT) | 26 | 614 | Austria - Italy | 614 | interconnector IT-AT | 3 | Delayed | Common planning progress between Terna an APG ongoing. | 1/ 1/ 2020 | 2020 | 1 |  | 1 | Nauders (AT) | Glorenza (IT) | Overhead Line | AC | 300 | 220 | 15 | New | 26 | 614 | Reschenpass Interconnector Project | Reschenpass Interconnector | 3 | Rescheduled | Slight delay in the project development. | 2021 | 2021 | 1 | APG; TERNA | Nauders (AT) | Glorenza (IT) | Underground Cable | AC | 220 | 26 | 614 | Reschenpass Interconnector Project | Reschenpass Interconnector | interconnector IT-AT | 4 | Rescheduled | Delay in Permitting procedure | 2023 | 2023 | 1 | Austrian Power Grid TERNA |  | 1 | 1 | Nauders (AT) | Glorenza (IT) | ACTransmissionLine | AC | 26 | New | 26 | 614 | Reschenpass Interconnector Project | Reschenpass Interconnector | Interconnector IT-AT | 4 | Investment on time |  | 06-2023 | 2023 | 1 | TERNA; APG |  | 1 | 1 | Nauders (AT) | Glorenza (IT) | ACTransmissionLine | AC | 0 | 220 | 26 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2023 | 5 | 9 | AUT;ITA | Nauders | Glorenza | 46.8918 | 10.5026 | 46.6715 | 10.5539
806 | 2014 | 2015 | [2014, 2015] | 615 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 148 | 615 | CCS new | Installation of a new 400kV PST in Okroglo which is a part of a double 400 kV OHL Okroglo(SI)-Udine(IT). | 2 | Investment on time | End of construction works are planned by the end of 2021. Full operation is expected by end of 2021 (beginning of 2022). | 2021 | 2021 | 1 | Okroglo (SI) |  | 615 | Installation of a new 400kV PST in Okroglo which is a part of a double 400 kV OHL Okroglo(SI)-Udine(IT). | 1 | Rescheduled | The project is under consideration following to the changing scenario conditions. | 2030 | 2030 | 1 | Okroglo (SI) | [6 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2030 | 9 | 16 | SVN | Okroglo |  | 46.2585 | 14.3205
807 | 2012 | 2026 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 616 | [6 empty] | 0 |  |  | 27 | 27. A96 | New interconnection between Italy and Slovenia | 1 | Feasibility studies ongoing including the internal reinforcements. | long term |  | 1 | New interconnection between Italy and Slovenia |  | 27. A96 | 27. A96 | The project includes a new HVDC link between Italy and Slovenia. The new HVDC line between Slovenia and Italy will strengthen the connection between Slovenia and Italy and will increase existing power exchange capacity. | 1 |  | 2022 | 2022 | 1 | Slovenia (SI) | Salgareda (IT) | 150 | 616 | CCS new 10 | New HVDC link between Italy and Slovenia. | 1 | Investment on time | Project is under feasibility study. | 2022 | 2022 | 1 | Slovenia (SI) | Salgareda (IT) | 616 | New HVDC link between Italy and Slovenia. | 3 | Investment on time | Progressed as planned | 2022 | 2022 | 1 | Slovenia (SI) | Salgareda (IT) | 150 | 616 | Italy-Slovenia | ITA-6 | New HVDC link between Italy and Slovenia. | 3 | Investment on time | On Slovenian side: Project in the study phase. On Italian side: Permitting procedure is still in progress. | 1/ 1/ 2022 | 2022 | 1 |  | 1 | Slovenia (SI) | Salgareda (IT) | Underground Cable | DC | 800 | 500 | 240 | New | 150 | 616 | Italy-Slovenia | Salgareda - Border IT-SI | 3 | Delayed | permitting procedure | 2022 | 2022 | 1 | TERNA;ELES | Salgareda (IT) | Border IT-SI | Underground Cable | DC | 500 | 150 | 616 | Italy-Slovenia | Salgareda - Bericevo | New HVDC link between Salgareda (IT) and Bericevo/Divaca (SI) | 3 | Delayed | Project under consideration on SI side (permitting not started yet in Slovenia) | 2028 | 2028 | 1 | ELES TERNA | 3.21 | 1 | 1 | Salgareda (IT) | Bericevo (SI) | DCTransmissionLine | DC | 0 | New | 150 | 616 | Italy-Slovenia | Salgareda - Bericevo | New HVDC link between Salgareda (IT) and Bericevo/Divaca (SI) | 1 | Delayed | Project under consideration on SI side (permitting not started yet in Slovenia) | 12-2042 | 2042 | 1 | Eles, Terna |  | 1 | 1 | Salgareda (IT) | Bericevo (SI) | DCTransmissionLine | DC | 1000 | 500 | 0 | New | 150 | 616 | Italy-Slovenia | Salgareda - Divaca | New HVDC link between Salgareda (IT) and Divaca (SI) including reinforcements of the existing grid | 1 | Delayed | Project under consideration on SI side (permitting not started yet in Slovenia) | 12-2042 | 2042 | 1 | Eles, Terna |  | 1 | 1 | Salgareda (IT) | Divaca (SI) | DCTransmissionLine | DC | 1000 | 500 | 100 | MostlyNew | 150 | 616 | Italy-Slovenia | Salgareda - Divaca | New HVDC link between Salgareda (IT) and Divaca (SI) | 1 |  | 12-2042 | 2042 | 1 | Eles, Terna | 1 | XX | XX | Mostly new |  | 2042 |  | 30 | ITA;SVN | Salgareda | Divaca | 45.7034 | 12.5222 | 45.6869 | 14.0125
808 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 617 | Cancelled | [5 empty] | 0 |  |  | 27 | 27. A105 | New 55km single circuit 400 kV OHL replacing aging 220 kV overhead line | 2 | Strengthening of the 400 kV corridor across the Adriatic coast in Croatia in LT period and removal of regional congestion at north-south axis , also to accommodate power transfers from Croatia and Bosnia&Herzegovina to Italy through new IT-ME DC link (Investment 70). | 2020 | 2020 | 1 | Lika(HR) | Brinje(HR) | 27. A105 | 27. A105 | New 55 km single circuit 400 kV OHL replacing aging 220 kV overhead line | 2 | Feasibility study is expected to be launched. | 2020 | 2020 | 1 | Lika(HR) | Brinje(HR) | 136 | 617 | CSE1 | New 55 km single circuit 400 kV OHL replacing aging 220 kV overhead line | 2 | Investment on time | Feasibility study is expected to be launched. | 2020 | 2020 | 1 | Lika(HR) | Brinje(HR) | 617 | New 55 km single circuit 400 kV OHL replacing aging 220 kV overhead line | 2 | Rescheduled | Feasibility study is expected to be launched and it will be financed by EBRD. The Terms of Reference for the study will be finalized soon and will be followed by the process of procurement and contracting | 2021 | 2021 | 1 | Lika(HR) | Brinje(HR) | 136 | 617 | CSE1 | OHL 400 kV Lika - Brinje | New 55 km single circuit 400 kV OHL replacing aging 220 kV overhead line | 1 | Rescheduled | Feasibility study is expected to be launched. | 1/ 1/ 2025 | 2025 | 1 |  | 0 | Lika(HR) | Brinje(HR) | Overhead Line | AC | 215 | 400 | 55 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2025 | 5 | 13 | HRV | Lika | Brinje | 44.6259 | 15.3436 | 44.9998 | 15.1313
809 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 618 | Cancelled | [5 empty] | 0 |  |  | 27 | 27. A106 | New 60km single circuit 400 kV OHL replacing aging 220 kV overhead line | 2 | Strengthening of the 400 kV corridor across the Adriatic coast in Croatia in LT period and removal of regional congestion at north-south axis , also to accommodate power transfers from Croatia and Bosnia&Herzegovina to Italy through new IT-ME DC link (Investment 70). | 2020 | 2020 | 1 | Lika(HR) | Velebit(HR) | 27. A106 | 27. A106 | New 60 km single circuit 400 kV OHL replacing aging 220 kV overhead line | 2 | Feasibility study is expected to be launched. | 2020 | 2020 | 1 | Lika(HR) | Velebit(HR) | 136 | 618 | CSE1 | New 60 km single circuit 400 kV OHL replacing aging 220 kV overhead line | 2 | Investment on time | Feasibility study is expected to be launched. | 2020 | 2020 | 1 | Lika(HR) | Velebit(HR) | 618 | New 60 km single circuit 400 kV OHL replacing aging 220 kV overhead line | 2 | Rescheduled | Feasibility study is expected to be launched and it will be financed by EBRD. The Terms of Reference for the study will be finalized soon and will be followed by the process of procurement and contracting | 2021 | 2021 | 1 | Lika(HR) | Velebit(HR) | 136 | 618 | CSE1 | OHL 400 kV Lika - Velebit | New 60 km single circuit 400 kV OHL replacing aging 220 kV overhead line | 1 | Rescheduled | Feasibility study is expected to be launched. | 1/ 1/ 2025 | 2025 | 1 |  | 0 | Lika(HR) | Velebit(HR) | Overhead Line | AC | 215 | 400 | 60 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2025 | 5 | 13 | HRV | Lika | Velebit | 44.6259 | 15.3436 | 44.4094 | 15.3345
810 | 2014 | 2016 | [2014, 2015, 2016] | 619 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 136 | 619 | CSE1 | New 400/110 kV substation, 2x300 MVA | 2 | Delayed | Feasibility study is expected to be launched. | 2018 | 2018 | 1 | Lika (HR) |  | 619 | New 400/110 kV substation, 2x300 MVA | 2 | Rescheduled | Feasibility study is expected to be launched and it will be financed by EBRD. The Terms of Reference for the study will be finalized soon and will be followed by the process of procurement and contracting | 2021 | 2021 | 1 | Lika (HR) |  | 136 | 619 | CSE1 | Substation 400/110 kV Lika | New 400/110 kV substation, 2x300 MVA | 1 | Rescheduled | Feasibility study is expected to be launched. | 1/ 1/ 2027 | 2027 | 1 |  | 0 | Lika (HR) |  | Substation |  | 215 | 400 |  | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2027 | 9 | 13 | HRV | Lika |  | 44.6259 | 15.3436
811 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 62 | Commissioned | [5 empty] | 0 |  |  | 25 | 25. 62 | IFA2:New subsea HVDC link between the UK and France. Capacity is still to be determined. (Possibly 1000MW) |  | Further investigations during the feasibility phase have led to reassess the expected commissioning date for "IFA2" | 2020 | 2020 | 1 | Under Consideration (FR) | Under Consideration (GB) | 25. 62 | 25. 62 | IFA2:New subsea HVDC link between the UK and France. Capacity around 1000 MW. | 1 | Extensive feasibility studies (e.g. seabed surveys) have been conducted to determine the most suitable route; the investment develops according to the planned schedule. | 2020 | 2020 | 1 | Tourbe (FR) | Chilling (GB) | 25 | 62 | IFA2 | New subsea HVDC VSC link between the UK and France with a capacity around 1000 MW. PCI 1.7.2 (NSCOG corridor) | 3 | Investment on time | Extensive feasibility studies (e.g. seabed surveys) have been conducted to determine the most suitable route; on the French side, the ministry of energy acknowledged the notification of the investment on 08/04/14. | 2020 | 2020 | 1 | Tourbe (FR) | Chilling (GB) | 62 | New subsea HVDC VSC link between the UK and France with a capacity around 1000 MW. PCI 1.7.2 (NSCOG corridor) | 3 | Investment on time | On the French side, the Ministry of Energy acknowledged the notification of the investment on 08/04/14. | 2020 | 2020 | 1 | Tourbe (FR) | Chilling (GB) | 25 | 62 | IFA2 | IFA2 | New subsea HVDC VSC link between the UK and France with a capacity around 1000 MW. PCI 1.7.2 (NSCOG corridor) | 3 | Investment on time | On the French side, the Ministry of Energy aknowledged the notification of the investment on 08/04/14. | 1/ 1/ 2020 | 2020 | 1 |  | 1 | Tourbe (FR) | Chilling (GB) | Subsea Cable | DC | 1000 | 320 | 250 | New | 25 | 62 | IFA2 | IFA2 | 4 | Investment on time |  | 1/ 1/ 2020 | 2020 | 1 | NGIHL,RTE | Tourbe (FR) | Chilling (GB) | Subsea Cable | DC | 320 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 8 | FRA;GBR | Tourbe | Chilling | 49.1021 | 4.67 | 45.1887 | 5.7271
812 | 2014 | 2016 | [2014, 2015, 2016] | 620 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 136 | 620 | CSE1 | New 400/220 kV substation, 1x400 MVA | 2 | Investment on time | Feasibility study is expected to be launched. | 2020 | 2020 | 1 | Brinje (HR) |  | 620 | New 400/220 kV substation, 1x400 MVA | 2 | Rescheduled | Feasibility study is expected to be launched and it will be financed by EBRD. The Terms of Reference for the study will be finalized soon and will be followed by the process of procurement and contracting | 2021 | 2021 | 1 | Brinje (HR) |  | 136 | 620 | CSE1 | Substation 400/220 kV Brinje | New 400/220 kV substation, 1x400 MVA | 1 | Rescheduled | Feasibility study is expected to be launched. | 1/ 1/ 2025 | 2025 | 1 |  | 0 | Brinje (HR) |  | Substation |  | 215 | 400 |  | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2025 | 5 | 11 | HRV | Brinje |  | 44.9998 | 15.1313
813 | 2014 | 2015 | [2014, 2015] | 621 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 28 | 621 | 28 | Converter station of the new 1000MW HVDC interconnection line between Italy and Montenegro via 375km 500kV DC subsea cable. | 4 | Delayed | rescheduling of work due to further secondary permitting during land rights acquisition and construction phase | 2017 | 2017 | 1 | Villanova (IT) |  | 621 | Converter station of the new 1000MW HVDC interconnection line between Italy and Montenegro via 393km 500kV DC subsea cable. | 4 | Investment on time | Progressed as planned | 2017 | 2017 | 1 | Villanova (IT) | [6 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2017 | 0 | 3 | ITA | Villanova |  | 43.0071 | 12.3278
814 | 2014 | 2015 | [2014, 2015] | 622 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 28 | 622 | 28 | Converter station in Montenegro of the new 1000MW HVDC sub-sea 500 kV cable between Italy and Montenegro. | 4 | Delayed | rescheduling of work due to further secondary permitting during land rights acquisition and construction phase | 2017 | 2017 | 1 | Lastva (ME) |  | 622 | Converter station in Montenegro of the new 1000MW HVDC sub-sea 500 kV cable between Italy and Montenegro. | 4 | Investment on time | Progressed as planned | 2017 | 2017 | 1 | Lastva (ME) | [6 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2017 | 0 | 3 | MNE | Lastva |  | 42.8396 | 19.249
815 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 624 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 28 | 624 | 28 | New 400 kV substation Lastva in Montenegro will be connected to the existing line 400kV Podgorica 2(ME)-Trebinje(BA), with two transformers 2X300MVA 400/110kV. This substation will enable secure supply of the Montenegrin coastal network, and connection of the convertor station for the HVDC cable between Montenegro and Italy. | 3 | Investment on time | on time | 2015 | 2015 | 1 | Lastva (ME) |  | 624 | New 400 kV substation Lastva in Montenegro will be connected to the existing line 400kV Podgorica 2(ME)- Trebinje(BA), with two transformers 2X300MVA 400/110kV. This substation will enable secure supply of the Montenegrin coastal network, and connection of the convertor station for the HVDC cable between Montenegro and Italy. | 4 | Delayed | The commissioning date has been updated to be coherent with the new schedule of the activities also considering that the construction phase of the substation started in mid-2014 | 2016 | 2016 | 1 | Lastva (ME) |  | 28 | 624 | Italy-Montenegro | SS 400/110 kV Lastva | New 400 kV substation Lastva in Montenegro will be connected to the existing line 400kV Podgorica 2(ME)-Trebinje(BA), with two transformers 2X300MVA 400/110kV. This substation will enable secure supply of the Montenegrin coastal network, and connection of the convertor station for the HVDC cable between Montenegro and Italy. | 4 | Rescheduled | The commissioning date has been updated to be coherent with the new schedule of the activities also considering that the construction phase of the substation started in mid 2014 | 1/ 1/ 2016 | 2016 | 1 |  | 0 | Lastva (ME) |  | Substation |  | 1000 | 400 |  | New | 28 | 624 | Italy-Montenegro | SS 400/110 kV Lastva | 4 | Rescheduled | The commissioning date has been been updated to be consistent with the new plan of activities | 31/12/ 2018 | 2018 | 1 |  | Lastva (ME) |  | Substation | AC | 400 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2018 | 3 | 4 | MNE | Lastva |  | 42.8396 | 19.249
816 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 625 | Commissioned | [5 empty] | 0 |  |  | 28 | 28. 233b | New 160 km double circuit 400kV OHL existing substation Pljevlja and new substation Tivat. | 3 | Feasibility study covering the aspects of route planning, substation location, environmental and social issues and equipment selection is due to end in second half of 2011 | 2016 | 2016 | 1 | Lastva (ME) | Pljevlja (ME) | 28. 233b | 28. 233b | New 160 km double circuit 400kV OHL existing substation Pljevlja and new substation Lastva. | 3 |  | 2016 | 2016 | 1 | Lastva (ME) | Pljevlja (ME) | 146 | 625 | CSE8 Transbalkan Corridor | Reinforcement of the Montenegrin internal 400 kV transmission network with new 160 km double circuit 400kV AC OHL between existing substation Pljevlja and new substation Lastva. The investment will enable secure supply of Montenegrin power system and power transits directed to new HVDC link towards Italy. Also, this investment will enable connection of Renewable energy sources along its route. | 3 | Investment on time | on time | 2016 | 2016 | 1 | Lastva (ME) | Pljevlja (ME) | 625 | Reinforcement of the Montenegrin internal 400 kV transmission network with new 160 km double circuit 400kV AC OHL between existing substation Pljevlja and new substation Lastva. The investment will enable secure supply of Montenegrin power system and power transits directed to new HVDC link towards Italy. Also, this investment will enable connection of Renewable energy sources along its route. | 4 | Investment on time | on time | 2016 | 2016 | 1 | Lastva (ME) | Pljevlja (ME) | 146 | 625 | CSE8 Transbalkan Corridor | 400 kV OHL Lastva - Pljevlja | Reinforcement of the Montenegrin internal 400 kV transmission network with new 160 km double circuit 400kV AC OHL between existing substation Pljevlja and new substation Lastva. The investment will enable secure supply of Montenegrin power system and power transits directed to new HVDC link towards Italy. Also, this investment will enable connection of Renewable energy sources along its route. | 4 | Investment on time | on time | 1/ 1/ 2016 | 2016 | 1 |  | 0 | Lastva (ME) | Pljevlja (ME) | Overhead Line | AC | 1095 | 400 | 160 | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2016 | 0 | 4 | MNE | Lastva | Pljevlja | 42.8396 | 19.249 | 43.3562 | 19.3579
817 | 2012 | 2026 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 627 | [6 empty] | 0 |  |  | 28 | 28. A109 | New 400kV interconnection OHL between Serbia and BiH, and reconstruction of existing two OHL 220 kV between BiH and Serbia. | 2 | New investment in TYNDP | >2016 | 2016 | 1 | Bajina Basta (RS) | Visegrad (BA) | 28. A109 | 28. A109 | Description of broader context - New double circuit 400kV OHL connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equiped. In the second phase New SS Bistrica (RS) would be connected to the exisitng double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 2 | Ongoing Regional trilateral feasibility study (financed by WBIF and supported by EC) between three TSOs (EMS, NOS BiH and CGES), including ESIA and preliminary design. Expected finalization time mid 2014. | 2020 | 2020 | 1 | Bajina Basta (RS) | Visegrad (BA) | 227 | 627 | CSE8 Transbalkan Corridor | Description of broader context - New double circuit 400kV OHL connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equipped. In the second phase New SS Bistrica (RS) would be connected to the existing double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 2 | Investment on time | Ongoing Regional trilateral feasibility study (financed by WBIF and supported by EC) between three TSOs (EMS, NOS BiH and CGES), including ESIA and preliminary design. Expected finalization time mid 2014. | 2020 | 2020 | 1 | Bajina Basta (RS) | Visegrad (BA) | 627 | Description of broader context - New double circuit 400kV OHL connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equiped. In the second phase New SS Bistrica (RS) would be connected to the exisitng double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 3 | Delayed | These projects are delayed because of delaying investment No 628 double OHL 400 kV B. Basta – Obrenovac and optimistic planning | 2022 | 2022 | 1 | Bajina Basta (RS) | Visegrad (BA) | 227 | 627 | CSE8 Transbalkan Corridor | 400kV interconnection RS-BA | Description of broader context - New double circuit 400kV OHL connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equiped. In the second phase New SS Bistrica (RS) would be connected to the exisitng double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 3 | Delayed | Del_ Financing issues | 2022 | 2022 | 1 |  | 1 | Bajina Basta (RS) | Visegrad (BA) | Overhead Line | AC | 500 | 400 | 45 | New | 227 | 627 | Transbalkan Corridor | 400kV interconnection RS-BA | 3 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 2024 | 2024 | 1 | EMS, CGES, NOSBiH | Bajina Basta (RS) | Visegrad (BA) | Overhead Line | AC | 400 | 227 | 627 | Transbalkan Corridor | 400kV interconnection RS-BA | Description of broader context - New double circuit 400kV OHL connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equiped. In the second phase New SS Bistrica (RS) would be connected to the exisitng double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 3 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 2026 | 2026 | 1 | EMS NOS-BIH CGES |  | 1 | 1 | Bajina Basta (RS) | Visegrad (BA) | ACTransmissionLine | AC | 45.2 | MostlyNew | 227 | 627 | Transbalkan Corridor | 400 kV interconnection RS-BA | Description of broader context - New double circuit 400 kV OHL connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equiped. In the second phase New SS Bistrica (RS) would be connected to the exisitng double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 3 | Investment on time |  | 09-2026 | 2026 | 1 | EMS, NOS-BIH, CGES |  | 1 | 1 | SS Bajina Basta | SS Visegrad | ACTransmissionLine | AC | 0 | 400 | 45.2 | MostlyNew | 227 | 627 | Transbalkan Corridor | 400 kV interconnection RS-BA | Description of broader context - New double circuit 400 kV OHL connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equiped. In the second phase New SS Bistrica (RS) would be connected to the exisitng double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 3 | Delayed | Updated information regarding the scope of works and investments that will be necessary in order to complete this project. | 09-2027 | 2027 | 1 | EMS, NOS-BIH, CGES |  | 1 | 1 | SS Bajina Basta | SS Visegrad | ACTransmissionLine | AC | 0 | 400 | 45.2 | MostlyNew | 227 | 627 | Transbalkan Corridor | 2x400 kV interconnection RS-BA | Description of broader context - New double circuit 400 kV OHL connecting existing substation Pljevlja (ME) and substation Bajina Bašta (RS) and new double circuit 400kV OHL connecting existing substation Višegrad (BA) and substation Bajina Bašta (RS). New PSHPP Bistrica (RS) will be connected to the double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. |  |  | 09-2028 | 2028 | 1 | EMS, NOS-BIH, CGES | 1 | XX | XX | Mostly new | 2016 | 2028 | 12 | 16 | BIH;MNE;SRB | Bajina Basta | Visegrad | 43.9712 | 19.566
818 | 2012 | 2026 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 628 | [6 empty] | 0 |  |  | 28 | 28. A110 | New double circuit 400 kV OHL between new substation Bajina Basta (see infra), and substation Obrenovac | 3 | New investment in TYNDP | >2016 | 2016 | 1 | Bajina Basta (RS) | TPP Obrenovac (RS) | 28. A110 | 28. A110 | Double circuit 400 kV OHL between upgraded substation Bajina Basta and substation Obrenovac. Part of larger regional transmission corridor northeast-southwest. | 3 | Feasibility study, ESIA and preliminary design finalized (financed by WBIF and supported by EC). Ongoing process of adoption to local legislation needs. | 2018 | 2018 | 1 | SS Bajina Basta (RS) | SS Obrenovac (RS) | 227 | 628 | CSE8 Transbalkan Corridor | Double circuit 400 kV OHL between upgraded substation Bajina Basta and substation Obrenovac. Part of larger regional transmission corridor northeast-southwest. | 3 | Delayed | Feasibility study, ESIA and preliminary design finalized (financed by WBIF and supported by EC). Ongoing process of adoption to local legislation needs. | 2019 | 2019 | 1 | SS Bajina Basta (RS) | SS Obrenovac (RS) | 628 | Double circuit 400 kV OHL between upgraded substation Bajina Basta and substation Obrenovac. Part of larger regional transmission corridor northeast-southwest. | 3 | Delayed | The project is delayed because of need to accommodate Feasibility study (granted by WBIF and done according to WBIF needs) to national law needs.“ | 2020 | 2020 | 1 | SS Bajina Basta (RS) | SS Obrenovac (RS) | 227 | 628 | CSE8 Transbalkan Corridor | 400kV OHL B.Basta-Obrenovac | Double circuit 400 kV OHL between upgraded substation Bajina Basta and substation Obrenovac. Part of larger regional transmission corridor northeast-southwest. | 3 | Delayed | Del_ Financing issues | 2021 | 2021 | 1 |  | 0 | SS Bajina Basta (RS) | SS Obrenovac (RS) | Overhead Line | AC | 500 | 400 | 115 | New | 227 | 628 | Transbalkan Corridor | 400kV OHL B.Basta-Obrenovac | 3 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 2024 | 2024 | 1 |  | SS Bajina Basta (RS) | SS Obrenovac (RS) | Overhead Line | AC | 400 | 227 | 628 | Transbalkan Corridor | 400kV OHL B.Basta-Obrenovac | Double circuit 400 kV OHL between upgraded substation Bajina Basta and substation Obrenovac. Part of larger regional transmission corridor northeast-southwest. | 3 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 2024 | 2024 | 1 | EMS NOS-BIH CGES |  | 0 | 1 | SS Bajina Basta (RS) | SS Obrenovac (RS) | ACTransmissionLine | AC | 109 | MostlyNew | 227 | 628 | Transbalkan Corridor | 2x400 kV OHL B.Basta-Obrenovac | Double circuit 400 kV OHL between upgraded substation Bajina Basta and substation Obrenovac. Part of larger regional transmission corridor northeast-southwest. | 3 | Delayed | The investment suffered a one-year delay compared to the previous TYNDP due to the negotiations for closing the financial structure (grants, loans and own funds). | 09-2025 | 2025 | 1 | EMS, NOS-BIH, CGES |  | 0 | 1 | SS Bajina Basta | SS Obrenovac | ACTransmissionLine | AC | 0 | 400 | 109 | MostlyNew | 227 | 628 | Transbalkan Corridor | 2x400 kV OHL B.Basta-Obrenovac | Double circuit 400 kV OHL between upgraded substation Bajina Basta and substation Obrenovac. Part of larger regional transmission corridor northeast-southwest. | 3 | Delayed | Updated information regarding the scope of works and investments that will be necessary in order to complete this project. | 09-2026 | 2026 | 1 | EMS, NOS-BIH, CGES |  | 0 | 1 | SS Bajina Basta | SS Obrenovac | ACTransmissionLine | AC | 0 | 400 | 109 | MostlyNew | 227 | 628 | Transbalkan Corridor | 2x400 kV OHL SS Bajina Bašta - SS Obrenovac | Double circuit 400 kV OHL between upgraded substation Bajina Bašta and substation Obrenovac. Part of larger regional transmission corridor northeast-southwest. |  |  | 09-2027 | 2027 | 1 | EMS, NOS-BIH, CGES | 1 | XX | XX | Mostly new | 2016 | 2027 | 11 | 15 | BIH;MNE;SRB | Bajina Basta | Obrenovac | 43.9712 | 19.566 | 43.7508 | 17.8445
819 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 63 | Cancelled | 63 | The project foresees the reconstruction of the existing 220kV-interconnection line as 380kV-line on an optimized route to minimize the environmental impact. Total length should be in the range of 100-150km. | 2 | long term |  | 1 | Lienz (AT) | Veneto region (IT) | 26 | 26. 63 | The project foresees the reconstruction of the existing 220kV-interconnection line as 380kV-line on an optimized route to minimize the environmental impact. Total length should be in the range of 100-150km. |  | Progresses as planned | long term |  | 1 | Lienz (AT) | Veneto region (IT) | 26. 63 | 26. 63 | The project foresees the reconstruction of the existing 220kV-interconnection line as 380kV-line on an optimized route to minimize the environmental impact. Total length should be in the range of approx. 100km. | 2 | Planning in progress coordinated between TERNA and APG | 2022 | 2022 | 1 | Lienz (AT) | Veneto region (IT) | 26 | 63 | Austria - Italy | The project foresees the reconstruction of the existing 220kV-interconnection line as 380kV-line on an optimized route to minimize the environmental impact. Total length should be in the range of approx. 140km. | 2 | Investment on time | Planning in progress co-ordinately between TERNA and APG | 2023 | 2023 | 1 | Lienz (AT) | Veneto region (IT) | 63 | The project foresees the reconstruction of the existing 220kV-interconnection line as 380kV-line on an optimized route to minimize the environmental impact. Total length should be in the range of approx. 140km. | 2 | Investment on time | Planning in progress coordinated between TERNA and APG | 2023 | 2023 | 1 | Lienz (AT) | Veneto region (IT) | 26 | 63 | Austria - Italy | 63 | The project foresees the reconstruction of the existing 220kV-interconnection line as 380kV-line on an optimized route to minimize the environmental impact. Total length should be in the range of approx. 140km. | 2 | Rescheduled | Planning in progress coordinatedly between TERNA and APG | 1/ 1/ 2024 | 2024 | 1 |  | 1 | Lienz (AT) | Veneto region (IT) | Overhead Line | AC | 800 | 400 | 140 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2024 |  | 14 | AUT;ITA | Lienz | Veneto Region | 46.8299 | 12.7681
820 | 2012 | 2026 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 630 | [6 empty] | 0 |  |  | 28 | 28. A111 | New 86 km single circuit 400kV OHL connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS). | 2 | New investment in TYNDP | >2016 | 2016 | 1 | Bajina Basta (RS) | Pljevlja (ME) | 28. A111 | 28. A111 | Description of broader context - New double circuit 400kV OHL (105km RS + 16km ME) connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equiped. In the second phase New SS Bistrica (RS) would be connected to the exisitng double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 2 | Ongoing Regional trilateral feasibility study (financed by WBIF and supported by EC) between three TSOs (EMS, NOS BiH and CGES), including ESIA and preliminary design. Expected finalization time mid 2014. | 2020 | 2020 | 1 | Bajina Basta (RS) | Pljevlja (ME) | 227 | 630 | CSE8 Transbalkan Corridor | Description of broader context - New double circuit 400kV OHL (105km RS + 16km ME) connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equipped. In the second phase New SS Bistrica (RS) would be connected to the existing double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 2 | Investment on time | Ongoing Regional trilateral feasibility study (financed by WBIF and supported by EC) between three TSOs (EMS, NOS BiH and CGES), including ESIA and preliminary design. Expected finalization time mid 2014. | 2020 | 2020 | 1 | Bajina Basta (RS) | Pljevlja (ME) | 630 | Description of broader context - New double circuit 400kV OHL (105km RS + 16km ME) connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equiped. In the second phase New SS Bistrica (RS) would be connected to the exisitng double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 3 | Delayed | Regional trilateral feasibility study (financed by WBIF and supported by EC) between three TSOs (EMS, NOS BiH and CGES), including ESIA and preliminary design is finished. | 2022 | 2022 | 1 | Bajina Basta (RS) | Pljevlja (ME) | 227 | 630 | CSE8 Transbalkan Corridor | 400kV interconnection RS-ME | Description of broader context - New double circuit 400kV OHL (105km RS + 16km ME) connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equiped. In the second phase New SS Bistrica (RS) would be connected to the exisitng double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 3 | Delayed | Del_ Financing issues | 2022 | 2022 | 1 |  | 1 | Bajina Basta (RS) | Pljevlja (ME) | Overhead Line | AC | 500 | 400 | 121 | New | 227 | 630 | Transbalkan Corridor | 400kV interconnection RS-ME | 3 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 2024 | 2024 | 1 |  | Bajina Basta (RS) | Pljevlja (ME) | Overhead Line | AC | 400 | 227 | 630 | Transbalkan Corridor | 400kV interconnection RS-ME | Description of broader context - New double circuit 400kV OHL (105km RS + 16km ME) connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equiped. In the second phase New SS Bistrica (RS) would be connected to the exisitng double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 3 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 2026 | 2026 | 1 | EMS NOS-BIH CGES |  | 1 | 1 | Bajina Basta (RS) | Pljevlja (ME) | ACTransmissionLine | AC | 100 | MostlyNew | 227 | 630 | Transbalkan Corridor | 400 kV interconnection RS-ME | Description of broader context - New double circuit 400kV OHL connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equiped. In the second phase New SS Bistrica (RS) would be connected to the exisitng double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 3 | Investment on time |  | 09-2026 | 2026 | 1 | EMS, NOS-BIH, CGES |  | 1 | 1 | SS Bajina Basta | SS Pljevlja | ACTransmissionLine | AC | 0 | 400 | 98.4 | MostlyNew | 227 | 630 | Transbalkan Corridor | 400 kV interconnection RS-ME | Description of broader context - New double circuit 400kV OHL connecting existing substation Pljevlja (ME) and substation Bajina Basta (RS) and new double circuit 400kV OHL connecting existing substation Visegrad (BA) and substation Bajina Basta (RS). In the first phase one 400 kV circuit would be equiped. In the second phase New SS Bistrica (RS) would be connected to the exisitng double circuit 400 kV OHL between SS Bajina Basta (RS), SS Visegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. | 3 | Delayed | Updated information regarding the scope of works and investments that will be necessary in order to complete this project. | 09-2027 | 2027 | 1 | EMS, NOS-BIH, CGES |  | 1 | 1 | SS Bajina Basta | SS Pljevlja | ACTransmissionLine | AC | 0 | 400 | 98.4 | MostlyNew | 227 | 630 | Transbalkan Corridor | 2x400 kV interconnection RS-ME | Description of broader context - New double circuit 400kV OHL connecting existing substation Pljevlja (ME) and substation Bajina Bašta (RS) and new double circuit 400kV OHL connecting existing substation Višegrad (BA) and substation Bajina Bašta (RS). New PSHPP Bistrica (RS) will be connected to the double circuit 400 kV OHL between SS Bajina Bašta (RS), SS Višegrad (BA) and SS Pljevlja (ME). Part of regional transmission corridor northeast-southwest. |  |  | 09-2028 | 2028 | 1 | EMS, NOS-BIH, CGES | 1 | XX | XX | Mostly new | 2016 | 2028 | 12 | 16 | BIH;MNE;SRB | Bajina Basta | Pljevlja | 43.9712 | 19.566 | 43.3562 | 19.3579
821 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 631 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 227 | 631 | CSE8 Transbalkan Corridor | Upgrade of existing 220/110 kV substation in Bajina Basta to 400/220/110 kV substation as part of overall western Serbia system upgrade to 400 kV voltage level. Part of larger regional transmission corridor northeast-southwest. | 3 | Delayed | Feasibility study, ESIA and preliminary design finalized (financed by WBIF and supported by EC). Ongoing process of adoption to local legislation needs. | 2019 | 2019 | 1 | Bajina Basta (RS) |  | 631 | Upgrade of existing 220/110 kV substation in Bajina Basta to 400/220/110 kV substation as part of overall western Serbia system upgrade to 400 kV voltage level. Part of larger regional transmission corridor northeast-southwest. | 3 | Delayed | Feasibility study, ESIA and preliminary design finalized (financed by WBIF and supported by EC). Ongoing process of adoption to local legislation needs. | 2021 | 2021 | 1 | Bajina Basta (RS) |  | 227 | 631 | CSE8 Transbalkan Corridor | 400kV SS B.Basta upgrade | Upgrade of existing 220/110 kV substation in Bajina Basta to 400/220/110 kV substation as part of overall western Serbia system upgrade to 400 kV voltage level. Part of larger regional transmission corridor northeast-southwest. | 3 | Delayed | Del_ Financing issues | 2021 | 2021 | 1 |  | 0 | Bajina Basta (RS) |  | Substation |  | 500 | 400 |  | Upgrade | 227 | 631 | Transbalkan Corridor | 400kV SS B.Basta upgrade | 3 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 2024 | 2024 | 1 |  | Bajina Basta (RS) | Bajina Basta (RS) | Substation | AC | 400 | 227 | 631 | Transbalkan Corridor | 400kV SS B.Basta upgrade | Upgrade of existing 220/110 kV substation in Bajina Basta to 400/220/110 kV substation as part of overall western Serbia system upgrade to 400 kV voltage level. Part of larger regional transmission corridor northeast-southwest. | 3 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 2024 | 2024 | 1 | EMS NOS-BIH CGES |  | 0 | 1 | Bajina Basta (RS) | Bajina Basta (RS) | OnshoreSubstation | AC | 0 | MostlyNew | 227 | 631 | Transbalkan Corridor | Upgrading SS Bajina Basta to 400 kV voltage level | Upgrade of existing 220/110 kV substation in Bajina Basta to 400/220/110 kV substation as part of overall western Serbia system upgrade to 400 kV voltage level. Part of larger regional transmission corridor northeast-southwest. | 3 | Delayed | The investment suffered a one-year delay compared to the previous TYNDP due to the negotiations for closing the financial structure (grants, loans and own funds). | 09-2025 | 2025 | 1 | EMS, NOS-BIH, CGES |  | 0 | 1 | Bajina Basta (RS) | Bajina Basta (RS) | OnshoreSubstation | AC | 0 | 400 | 0 | MostlyNew | 227 | 631 | Transbalkan Corridor | Upgrading SS Bajina Basta to 400 kV voltage level | Upgrade of existing 220/110 kV substation in Bajina Basta to 400/220/110 kV substation as part of overall western Serbia system upgrade to 400 kV voltage level. Part of larger regional transmission corridor northeast-southwest. | 3 | Delayed | Updated information regarding the scope of works and investments that will be necessary in order to complete this project. | 09-2026 | 2026 | 1 | EMS, NOS-BIH, CGES |  | 0 | 1 | Bajina Basta (RS) | Bajina Basta (RS) | OnshoreSubstation | AC | 0 | 400 | 0 | MostlyNew | 227 | 631 | Transbalkan Corridor | Upgrading SS Bajina Bašta to 400 kV voltage level | Upgrade of existing 220/110 kV substation in Bajina Bašta to 400/220/110 kV substation as part of overall western Serbia system upgrade to 400 kV voltage level. Part of larger regional transmission corridor northeast-southwest. |  |  | 09-2027 | 2027 | 1 | EMS, NOS-BIH, CGES | 1 | XX | XX | Mostly new | 2019 | 2027 | 8 | 13 | BIH;MNE;SRB | Bajina Basta | Bajina Basta | 43.9712 | 19.566 | 43.9712 | 19.566
822 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 633 | Cancelled | [5 empty] | 0 |  |  | 28 | 28. A114 | New 100km single circuit 400 kV OHL replacing ageing 220 kV overhead line | 2 | Strengthening of the 400 kV corridor across the Adriatic coast in Croatia in LT period and removal of regional congestion at north-south axis , also to accommodate power transfers from Croatia and Bosnia&Herzegovina to Italy through new IT-ME DC link (Investment 70). | 2020 | 2020 | 1 | Konjsko(HR) | Velebit(HR) | 28. A114 | 28. A114 | New 100km single circuit 400 kV OHL replacing ageing 220 kV overhead line | 2 | It is expected to start creating a feasibility study. | 2020 | 2020 | 1 | Konjsko(HR) | Velebit(HR) | 136 | 633 | CSE1 | New 100km single circuit 400 kV OHL replacing ageing 220 kV overhead line | 2 | Investment on time | Feasibility study is expected to be launched. | 2020 | 2020 | 1 | Konjsko(HR) | Velebit(HR) | 633 | New 100km single circuit 400 kV OHL replacing ageing 220 kV overhead line | 2 | Rescheduled | Feasibility study is expected to be launched and it will be financed by EBRD. The Terms of Reference for the study will be finalized soon and will be followed by the process of procurement and contracting | 2021 | 2021 | 1 | Konjsko(HR) | Velebit(HR) | 136 | 633 | CSE1 | OHL 400 kV Konjsko - Velebit | New 100km single circuit 400 kV OHL replacing ageing 220 kV overhead line | 1 | Rescheduled | Feasibility study is expected to be launched. | 1/ 1/ 2025 | 2025 | 1 |  | 0 | Konjsko(HR) | Velebit(HR) | Overhead Line | AC | 215 | 400 | 100 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2025 | 5 | 13 | HRV | Konjsko | Velebit | 42.6444 | 18.4769 | 44.4094 | 15.3345
823 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 635 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 29 | 635 | Italy-North Africa | New interconnection between Italy and North Africa-new DC submarine cable | 1 | Investment on time | - | 2030 | 2030 | 1 | Sicily Area (IT) | North Africa node | 635 | New interconnection between Italy and North Africa-new DC submarine cable | 1 | Investment on time | Progressed as planned | 2030 | 2030 | 1 | Sicily Area (IT) | North Africa node | 29 | 635 | Italy-Tunisia | ITA-7 | New interconnection between Italy and Tunisia -new DC submarine cable | 2 | Investment on time | - | 31/ 12/ 2022 | 2022 | 1 |  | 1 | Sicily Area (IT) | Tunisia node | Subsea Cable | DC | 600 | 500 | 200 | New | 29 | 635 | Italy-Tunisia | Elmed Project | 3 | Rescheduled |  | 2025 | 2025 | 1 | TERNA; STEG | Sicily Area (IT) | Tunisia node | Subsea Cable | DC | 400 | 29 | 635 | Italy-Tunisia | Elmed Project | New interconnection between Italy and Tunisia - new HVDC submarine cable | 3 | Investment on time |  | 2027 | 2027 | 1 | TERNA STEG | 3.27 | 1 | 1 | Sicily Area (IT) | Tunisia node | DCTransmissionLine | DC | 200 | New | 29 | 635 | Italy-Tunisia | Elmed Project | New interconnection between Italy and Tunisia - new HVDC submarine cable | 3 | Investment on time |  | 12-2028 | 2028 | 1 | Terna, STEG | 2.33 | 1 | 1 | Sicily Area (IT) | Mlaaba | DCTransmissionLine | DC | 600 | 400 | 200 | New | 29 | 635 | Italy-Tunisia | Elmed Project | New interconnection between Italy and Tunisia - New HVDC submarine cable and conventer stations at both ending points | 3 | Investment on time |  | 01-2028 | 2028 | 1 | Terna, STEG | 1.19 | 1 | 1 | Partanna (IT) | Mlaabi (TN) | OffshoreDCTransmissionCable | DC | 600 | 500 | 220 | New | 29 | 635 | Italy-Tunisia | Elmed Project | New interconnection between Italy and Tunisia - New HVDC submarine cable and conventer stations at both ending points | 4 |  | 01-2028 | 2028 | 1 | Terna, STEG | 1 | XX | XX | New | 2030 | 2028 | -2 | 14 | ITA;TUN | Partanna | Mlaabi | 37.7278 | 12.8885
824 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 642 | Cancelled | [5 empty] | 0 |  |  | 31 | 31. A101 | Up to 4 interconnection projects are under discussion, one or two probably will be implemented | 1 | This investment replaces investment n° 120 mentioned on TYNDP 2010. The previous investment evolved so much that it is substituted by a new project. Feasibility studies ongoing including the internal reinforcements. | long term |  | 1 | New interconnections between Italy and Switzerland |  | 31. A101 | 31. A101 | New interconnection project beetween Italy and Switzerland; | 3 | Permitting process started on the Italian side since September 2012 | 2022 | 2022 | 1 | Airolo (CH) | Pallanzeno(IT)-Baggio(IT) | 31 | 642 | Italy-Switzerland | New interconnection project between Italy and Switzerland; | 3 | Investment on time | permitting process started on the Italian side since September 2012 | 2022 | 2022 | 1 | Airolo (CH) | Pallanzeno(IT)-Baggio(IT) | 642 | New interconnection project beetween Italy and Switzerland; | 3 | Investment on time | Progressed as planned | 2022 | 2022 | 1 | Airolo (CH) | Pallanzeno(IT )-Baggio(IT) | 31 | 642 | Italy-Switzerland | ITA-4 | New interconnection project beetween Italy and Switzerland | 3 | Investment on time | progressed as planned | 1/ 1/ 2022 | 2022 | 1 |  | 1 | Airolo (CH) | Pallanzeno(IT)-Baggio(IT) | Overhead Line | AC | 1000 | 380 | 100 | New | 31 | 642 | Italy-Switzerland | San Giacomo Project | 3 | Rescheduled |  | 2025 | 2025 | 1 | SWISSGRID;TERNA | All'Acqua (CH) | Pallanzeno(IT)-Baggio(IT) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2025 |  | 13 | CHE;ITA | Allacqua | Pallanzenoit-Baggio | 45.58 | 8.2079
825 | 2012 | 2026 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 645 | [6 empty] | 0 |  |  | 32 | 32. A99 | New 400kV OHL between the existing substations of Laino and Altomonte in Calabria and a new 380/150 kV substation in Aliano connected in and out to the existing 400 line kV "Matera - Laino" and to the local HV network. Related to this project will be acted a great restructuring of the local HV network, downgrading the existing 220 kV lines to 150 kV level and the demolition of great part of existing 150 kV lines inside the Pollino Park. | 4 | New investment in TYNDP (initial design partially changed, evolution including new reinforcements and rearrangements activities on the neighboring areas resulting from further studies) | 2012/mid term | 2012 | 1 | Restructuring of North Calabria (IT) |  | 32. A99 | 32. A99 | New 400kV OHL between the existing substations of Laino and Altomonte in Calabria.Related to this project will be acted a great restructuring of the local HV network, downgrading the existing 220 kV lines to 150 kV level and the demolition of great part of existing 150 kV lines inside the Pollino Park. | 3 | Longer permitting process than expected (EIA) | 2017 | 2017 | 1 | Laino (IT) | Altomonte (IT) | 127 | 645 | 127 | New 400kV OHL between the existing substations of Laino and Altomonte in Calabria. | 3 | Delayed | delay in the permitting process (EIA) | 2017 | 2017 | 1 | Laino (IT) | Altomonte (IT) | 645 | New 400kV OHL between the existing substations of Laino and Altomonte in Calabria. | 3 | Delayed | delay in the permitting process (EIA) | 2018 | 2018 | 1 | Laino (IT) | Altomonte (IT) | 127 | 645 | Central Southern Italy | ITA-3 | New 400kV OHL between the existing substations of Laino and Altomonte in Calabria. | 3 | Delayed | delay in the permitting process (EIA) | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Laino (IT) | Altomonte (IT) | Overhead Line | AC | 250 | 400 | 50 | New | 127 | 645 | Central Southern Italy | ITA-3 | 3 | Rescheduled |  | 1/ 1/ 2022 | 2022 | 1 |  | Laino (IT) | Altomonte (IT) | Overhead Line | AC | 400 | 1059 | 645 | Southern Italy | ITA-3 | New 400kV OHL between the existing substations of Laino and Altomonte in Calabria (investment previously included in P127). | 3 | Rescheduled |  | 2027 | 2027 | 1 | TERNA |  | 0 | 0 | Laino (IT) | Altomonte (IT) | ACTransmissionLine | AC | 50 | New | 1059 | 645 | Southern Italy | OHL between the Laino and Altomonte in Calabria | New 400kV OHL between the existing substations of Laino and Altomonte in Calabria (investment previously included in P127). | 3 | Delayed | Delay due to permitting reasons. | 12-2029 | 2029 | 1 | Terna |  | 0 | 0 | Laino (IT) | Altomonte (IT) | ACTransmissionLine | AC | 0 | 400 | 50 | New | 1059 | 645 | Southern Italy | OHL between the Laino and Altomonte in Calabria | New 400kV OHL between the existing substations of Laino and Altomonte in Calabria. | 3 | Rescheduled |  | 12-2029 | 2029 | 1 | Terna |  | 0 | 0 | Laino (IT) | Altomonte (IT) | ACTransmissionLine | AC | 0 | 400 | 50 | New | 1059 | 645 | Southern Italy | OHL between the Laino and Altomonte in Calabria | New 400kV OHL between the existing substations of Laino and Altomonte in Calabria. |  |  | 12-2030 | 2030 | 1 | Terna | 0 | XX | XX | New | 2012 | 2030 | 18 | 18 | ITA | Laino | Altomonte |  |  | 39.6979 | 16.1271
826 | 2012 | 2024 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024] | 650 | Cancelled | [5 empty] | 0 |  |  | 40 | 40. A29 | New interconnection with neighbor(s) either 220kV or 400kV | 1 | New investment in TYNDP | 2020 | 2020 | 1 | Bascharage (LU) | tbd (BE, DE, &/o FR) | 40. A29 | 40. A29 | In a second step: new 220 kV interconnection with neighbour(s) between Creos grid in LU and ELIA grid in BE via a 16km double circuit 225kV underground cable with a capacity of 1000 MVA (first step = 220 kV PST in Schifflange (LU) in 2016) | 1 | An ongoing network study investigates the robustness of the planned 220kV connection between LU and BE. | 2020 | 2020 | 1 | Bascharage (LU) | Aubange (BE) | 40 | 650 | Luxembourg-Belgium Interco | BELUX LT In a second step: new 220 kV interconnection with neighbour(s) between Creos grid in LU and ELIA grid in BE via a 16km double circuit 225kV underground cable with a capacity of 1000 MVA. | 1 | Investment on time | An ongoing network study investigates the robustness of the planned 220kV connection between LU and BE. | 2020 | 2020 | 1 | Bascharage (LU) | Aubange (BE) | 650 | BELUX Long-Term: in a second step a new 220 kV interconnection between substation Bascharage (CREOS- LU)and substation Aubange (ELIA-BE) is envisioned via a 16km double circuit underground cable with a total capacity of 1000 MVA. The final technical solution with potential addition of PST's on the cables is subject to further studies taking into account the robustness of the solution towards the different visions. | 1 | Rescheduled | Robustness of the envisioned solution towards the long- term perspective of the energy transition is subject of ongoing studies. | 2022 | 2022 | 1 | Bascharage (LU) | Aubange (BE) | 40 | 650 | Luxembourg-Belgium Interco | BELUX Long-Term | A 220 kV interconnection between substation Bascharage (CREOS-LU) and substation Aubange (ELIA-BE) is envisioned via a 16km double circuit underground cable with a total capacity of ~1000 MVA. The technical solution, with potential need to add PSTs to the cables, is subject to complementary studies. | 1 | Rescheduled | Robustness of the envisioned reference solution towards the long-term perspective of the energy transition is subject of ongoing studies. | 1/ 1/ 2022 | 2022 | 1 |  | 1 | Bascharage (LU) | Aubange (BE) | Underground Cable | AC | 300 | 220 | 16 | New | 40 | 650 | Belgium-Luxemburg-Germany: long-term perspective | BE-LUX-DE Long-Term perspective | 1 | Rescheduled | An increase of transfer capacity across the BE-LU-DE corridor is envisioned towards the 2030-2040 time horizon. | 2035 | 2035 | 1 | CREOS; ELIA; AMPRION | Aubange (TBC) | LUX-DE (TBC) | Underground Cable | AC | 0 | 40 | 650 | Belgium-Luxembourg-Germany: long-term perspective | BE-LUX-DE Long-Term perspective | The technical solution is subject to further studies | 1 | Rescheduled | An increase of transfer capacity across the BE-LU-DE corridor is envisioned towards the 2030-2040 time horizon. | 2035 | 2035 | 1 | AMPRION CREOS ELIA |  | 1 | 1 | Aubange (TBC) | LUX-DE (TBC) | OnshoreACTransmissionCable | AC | 16 | New | 40 | 650 | Belgium-Luxembourg-Germany: long-term perspective | BE-LUX-DE Long-Term perspective | The technical solution is subject to further studies | 1 | Rescheduled |  | 12-2040 | 2040 | 1 | Amprion, Creos, Elia |  | 1 | 1 | Aubange (TBC) | LUX-DE (TBC) | OnshoreACTransmissionCable | AC | 0 | 0 | 16 | New | 40 | 650 | Belgium-Luxembourg-Germany: long-term perspective | BE-LUX-DE Long-Term perspective | The technical solution is subject to further studies | 1 | Rescheduled |  | 12-2040 | 2040 | 1 | Amprion, Creos, Elia |  | 1 | 1 | Aubange (TBC) | LUX-DE (TBC) | OnshoreACTransmissionCable | AC | 0 | 0 | 16 | New | [5 empty] | 6 | Cancelled |  |  | 0 | [5 empty] | 2020 | 2040 | 20 | 28 | BEL;DEU;LUX | Aubange | Lux-De | 49.5672 | 5.8045 | 50.8782 | 4.6988
827 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 654 | Commissioned | [5 empty] | 0 |  |  | 42 | 42. A82 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 160 km. Line capacity: 900 MW | 4 | New investment in TYNDP, for connection of new off-shore wind-farms | mid term |  | 1 | Cluster DolWin2 (DE) | Dörpen/West (DE) | 42. A82 | 42. A82 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 160 km. Line capacity: 900 MW | 4 |  | 2015 | 2015 | 1 | Cluster DolWin2 (DE) | Dörpen/West (DE) | 42 | 654 | OWP TenneT Northsea part 1 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 138 km. Line capacity: 900 MW | 4 | Investment on time |  | 2015 | 2015 | 1 | Cluster DolWin2 (DE) | Dörpen/West (DE) | 654 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 138 km. Line capacity: 900 MW | 4 | Investment on time | on time | 2015 | 2015 | 1 | Cluster DolWin2 (DE) | Dörpen/West (DE) | 42 | 654 | OWP TenneT Northsea part 1 | DolWin2 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 138 km. Line capacity&#58; 900 MW | 4 | Delayed | due to the project | 1/ 1/ 2016 | 2016 | 1 |  | 0 | Cluster DolWin2 (DE) | Dörpen/West (DE) | Subsea Cable | DC | 900 | 400 | 138 | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2016 |  | 4 | DEU | Cluster Dolwin | Dörpenwest
828 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 655 | Commissioned | [5 empty] | 0 |  |  | 42 | 42. A83 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 160 km. Line capacity: 900 MW | 3 | New investment in TYNDP, for connection of new off-shore wind-farms | mid term |  | 1 | Cluster DolWin3 (DE) | Dörpen/West (DE) | 42. A83 | 42. A83 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 160 km. Line capacity: 900 MW | 4 |  | 2017 | 2017 | 1 | Cluster DolWin3 (DE) | Dörpen/West (DE) | 42 | 655 | OWP TenneT Northsea part 1 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 162 km. Line capacity: 900 MW | 4 | Investment on time |  | 2017 | 2017 | 1 | Cluster DolWin3 (DE) | Dörpen/West (DE) | 655 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 162 km. Line capacity: 900 MW | 4 | Investment on time | on time | 2017 | 2017 | 1 | Cluster DolWin3 (DE) | Dörpen/West (DE) | 42 | 655 | OWP TenneT Northsea part 1 | DolWin3 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 162 km. Line capacity&#58; 900 MW | 4 | Investment on time | on time | 1/ 1/ 2017 | 2017 | 1 |  | 0 | Cluster DolWin3 (DE) | Dörpen/West (DE) | Subsea Cable | DC | 900 | 400 | 162 | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2017 |  | 5 | DEU | Cluster Dolwin | Dörpenwest
829 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 656 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 191 | 656 | OWP TenneT Northsea Part 2 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 160 km. Line capacity: 900 MW | 3 | Investment on time |  | 2018 | 2018 | 1 | Cluster BorWin3 | Emden/Ost (DE) | 656 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 160 km. Line capacity: 900 MW | 4 | Delayed | delay is due to long permitting process | 2019 | 2019 | 1 | Cluster BorWin3 | Emden/Ost (DE) | 191 | 656 | OWP TenneT Northsea Part 2 | BorWin3 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 160 km. Line capacity&#58; 900 MW | 4 | Delayed | due to the project | 1/ 1/ 2019 | 2019 | 1 |  | 0 | Cluster BorWin3 | Emden/Ost (DE) | Subsea Cable | DC | 900 | 400 | 160 | New | 191 | 656 | OWP TenneT Northsea Part 2 | BorWin3 | 4 | Investment on time |  | 2019 | 2019 | 1 | TENNET-DE | Cluster BorWin3 | Emden/East (DE) | Subsea Cable | DC | 320 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2019 | 1 | 5 | DEU | Cluster Borwin | Emdeneast
830 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 657 | Commissioned | [5 empty] | 0 |  |  | 42 | 42. A85 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 145km. Line capacity: 690 MW | 4 | New investment in TYNDP, for connection of new off-shore wind-farms | mid term |  | 1 | Cluster HelWin2 | Büttel (DE) | 42. A85 | 42. A85 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 145km. Line capacity: 690 MW | 4 |  | 2015 | 2015 | 1 | Cluster HelWin2 | Büttel (DE) | 42 | 657 | OWP TenneT Northsea part 1 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 133 km. Line capacity: 690 MW | 4 | Investment on time |  | 2015 | 2015 | 1 | Cluster HelWin2 | Büttel (DE) | 657 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 133 km. Line capacity: 690 MW | 4 | Investment on time | on time | 2015 | 2015 | 1 | Cluster HelWin2 | Büttel (DE) | 42 | 657 | OWP TenneT Northsea part 1 | HelWin2 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 133 km. Line capacity&#58; 690 MW | 5 | Commissioned | on time | 1/ 1/ 2015 | 2015 | 1 |  | 0 | Cluster HelWin2 | Büttel (DE) | Subsea Cable | DC | 690 | 400 | 133 | New | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2015 |  | 3 | DEU | Cluster Helwin | Büttel |  |  | 53.9 | 9.2284
831 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 658 | Cancelled | [5 empty] | 0 |  |  | 42 | 42. A86 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 185 km. Line capacity: 900 MW | 1 | New investment in TYNDP, for connection of new off-shore wind-farms | long term |  | 1 | Cluster BorWin4 (DE) | Emden/Ost (DE) | 42. A86 | 42. A86 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 185 km. Line capacity: 900 MW | 3 |  | 2019 | 2019 | 1 | Cluster BorWin4 (DE) | Emden/Ost (DE) | 191 | 658 | OWP TenneT Northsea Part 2 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 172 km. Line capacity: 900 MW | 3 | Investment on time |  | 2019 | 2019 | 1 | Cluster BorWin4 (DE) | Emden/Ost (DE) | 658 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 172 km. Line capacity: 900 MW | 3 | Investment on time | Progressed as planned. | 2019 | 2019 | 1 | Cluster BorWin4 (DE) | Area of Wilhelmshav en | 129 | 658 | OWP Northsea TenneT Part 4 | BorWin4 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 180 km. Line capacity&#58; 900 MW | 1 | Investment on time |  | 1/ 1/ 2029 | 2029 | 1 |  | 0 | Cluster BorWin4 (DE) | area of Cloppenburg/East | Subsea Cable | DC | 900 | 400 | 180 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2029 |  | 17 | DEU | Cluster Borwin | Cloppenburgeast
832 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 659 | Cancelled | [5 empty] | 0 |  |  | 42 | 42. A87 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 210km. Line capacity: 800 MW | 1 | New investment in TYNDP, for connection of new off-shore wind-farms | long term |  | 1 | Cluster SylWin2 (DE) | Büttel (DE) | 42. A87 | 42. A87 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 210km. Line capacity: 800 MW | 1 |  | 2023 | 2023 | 1 | Cluster SylWin2 (DE) | Büttel (DE) | 192 | 659 | OWP Northsea TenneT Part 3 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 205 km. Line capacity: 900 MW | 1 | Investment on time |  | 2023 | 2023 | 1 | Cluster SylWin2 (DE) | Büttel (DE) | 659 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 205 km. Line capacity: 900 MW | 1 | Investment on time | Progressed as planned. | 2023 | 2023 | 1 | Cluster SylWin2 (DE) | Büttel (DE) | 192 | 659 | OWP Northsea TenneT Part 3 | SylWin2 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 205 km. Line capacity&#58; 900 MW | 1 | Delayed | due to the project | 1/ 1/ 2026 | 2026 | 1 |  | 0 | Cluster SylWin2 (DE) | Büttel (DE) | Subsea Cable | DC | 900 | 400 | 205 | New | 192 | 659 | OWP Northsea TenneT Part 3 | SylWin2 | 2 | Investment on time |  | 2025 | 2025 | 1 | TENNET-DE | Cluster SylWin2 (DE) | Büttel (DE) | Subsea Cable | DC | 320 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2025 |  | 13 | DEU | Cluster Sylwin | Büttel |  |  | 53.9 | 9.2284
833 | 2012 | 2026 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 660 | [6 empty] | 0 |  |  | 43 | 43. A81 | New HVDC-lines from Osterath to Philippsburg to integrate new wind generation especially from North/ Baltic Sea towards Central-South Germany for consumption and storage. | 1 | New investment in TYNDP, due to long distance RES integration; voltage stability of the grid; SOS in the South of Germany | long term |  | 1 | Osterath (DE) | Philippsburg (DE) | 43. A81 | 43. A81 | New HVDC-lines from Osterath to Philippsburg to integrate new wind generation especially from North/ Baltic Sea towards Central-South Germany for consumption and storage. | 2 | The project has started and the planning has been refined after confirmation by the German network development Plan 2012. | 2018 | 2018 | 1 | Osterath (DE) | Philippsburg (DE) | 134 | 660 | N-S Western DE_section South | New HVDC-lines from Osterath to Philippsburg to integrate new wind generation especially from North Sea towards Central-South Germany for consumption and storage. | 3 | Investment on time | Progress as planned. | 2019 | 2019 | 1 | Osterath (DE) | Philippsburg (DE) | 660 | New HVDC-lines from Osterath to Philippsburg to integrate new wind generation especially from North Sea towards Central-South Germany for consumption and storage. | 3 | Investment on time | Progressed as planned. | 2019 | 2019 | 1 | Osterath (DE) | Philippsburg (DE) | 254 | 660 | Ultranet | HVDC Line A South - Ultranet | New HVDC-lines from Osterath to Philippsburg to integrate new wind generation especially from North Sea towards Central-South Germany for consumption and storage. | 3 | Delayed | Delays due to permit granting reasons. | 01/01/2021 | 2021 | 1 |  | 0 | Osterath (DE) | Philippsburg (DE) | Overhead Line | DC | 3049 | 400 | 340 | New | 254 | 660 | Ultranet | HVDC Line A South - Ultranet | 3 | Rescheduled |  | 01/01/2021 | 2021 | 1 | Amprion;TransnetBW | Osterath (DE) | Philippsburg (DE) | Overhead Line | DC | 400 | 254 | 660 | HVDC Ultranet Osterath to Philippsburg | HVDC Line A South - Ultranet | New HVDC-lines from Osterath to Philippsburg to integrate new wind generation especially from North Sea towards Central-South Germany for consumption and storage. | 3 | Rescheduled |  | 2024 | 2024 | 1 | AMPRION TRANSNET-BW | 2.9 | 1 | 0 | Osterath (DE) | Philippsburg (DE) | DCTransmissionLine | DC | 340 | New | 254 | 660 | HVDC Ultranet Osterath to Philippsburg | HVDC Line A South - Ultranet | New HVDC-lines from Osterath to Philippsburg to integrate new wind generation especially from North Sea towards Central-South Germany for consumption and storage. | 3 | Rescheduled | Adjustment of commissioning date to 2026 due to the long and complex approval process. | 12-2026 | 2026 | 1 | Amprion, TransnetBW | 2.9 | 1 | 0 | Osterath (DE) | Philippsburg (DE) | DCTransmissionLine | DC | 2000 | 400 | 343 | New | 254 | 660 | HVDC Ultranet Osterath to Philippsburg | HVDC Line A South - Ultranet | New HVDC-lines from Osterath to Philippsburg to integrate new wind generation especially from North Sea towards Central-South Germany for consumption and storage. | 3 | Investment on time |  | 12-2026 | 2026 | 1 | Amprion, TransnetBW | 1.6 | 1 | 0 | Osterath (DE) | Philippsburg (DE) | DCTransmissionLine | DC | 2000 | 400 | 342 | New | 254 | 660 | HVDC Ultranet Osterath to Philippsburg | HVDC Line A South - Ultranet | New HVDC-lines from Osterath to Philippsburg to integrate new wind generation especially from North Sea towards Central-South Germany for consumption and storage. |  |  | 12-2026 | 2026 | 1 | Amprion, TransnetBW | 0 | XX | XX | New |  | 2026 |  | 14 | DEU | Osterath | Philippsburg | 51.2691 | 6.6207 | 49.2367 | 8.4547
834 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 661 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 132 | 661 | N-S Western DE_section North_2 | New HVDC-lines from Emden to Osterath to integrate new wind generation especially from North Sea towards Central Germany for consumption. | 2 | Investment on time | Progress as planned. | 2022 | 2022 | 1 | Emden East (DE) | Osterath (DE) | 661 | New HVDC-lines from Emden to Osterath to integrate new wind generation especially from North Sea towards Central Germany for consumption. | 2 | Rescheduled | The commissioning date of the Investment has been rescheduled due to the postponing of the development of offshore windfarms in the North Sea. | 2025 | 2025 | 1 | Emden East (DE) | Osterath (DE) | 132 | 661 | RES-Integration in North-West Germany 2 | HVDC Line A-North | New HVDC-lines from Emden to Osterath to integrate new wind generation especially from North Sea towards Central Germany for consumption. | 2 | Rescheduled | The commissioning date of the investment has been rescheduled due to the postponement of the development of offshore windfarms in the North Sea. | 1/ 1/ 2025 | 2025 | 1 |  | 0 | Emden East (DE) | Osterath (DE) | Overhead Line | DC | 3049 | 400 | 320 | New | 132 | 661 | HVDC Line A-North | HVDC Line A-North |  | Investment on time |  | 1/ 1/ 2025 | 2025 | 1 | Amprion | Emden East (DE) | Osterath (DE) | Overhead Line | DC | 400 | 132 | 661 | HVDC Line A-North | HVDC Line A-North | New HVDC line from Emden to Osterath to integrate new wind generation especially from North Sea towards Central Germany for consumption. | 3 | Investment on time |  | 2025 | 2025 | 1 | AMPRION |  | 1 | 0 | Emden East (DE) | Osterath (DE) | DCTransmissionLine | DC | 300 | New | 132 | 661 | HVDC Line A-North | HVDC Line A-North | New HVDC line from Emden to Osterath to integrate new wind generation especially from North Sea towards Central Germany for consumption. | 3 | Delayed |  | 12-2027 | 2027 | 1 | Amprion | 2.31.1 | 1 | 0 | Emden East (DE) | Osterath (DE) | DCTransmissionLine | DC | 2400 | 400 | 300 | New | 132 | 661 | HVDC Line A-North | HVDC Line A-North | New HVDC line from Emden to Osterath to integrate new wind generation especially from North Sea towards Central Germany for consumption. | 3 | Investment on time |  | 12-2027 | 2027 | 1 | Amprion | 1.4.1 | 1 | 0 | Emden East (DE) | Osterath (DE) | DCTransmissionLine | DC | 2400 | 400 | 300 | New | 132 | 661 | HVDC Line A-North | HVDC Line A-North | New HVDC line from Emden to Osterath to integrate new wind generation especially from North Sea towards Central Germany for consumption. |  |  | 12-2027 | 2027 | 1 | Amprion | 0 | XX | XX | New | 2022 | 2027 | 5 | 13 | DEU | Emden East | Osterath |  |  | 51.2691 | 6.6207
835 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 662 | Cancelled | [5 empty] | 0 |  |  | 43 | 43. A153 | New lines in HVDC technology from the region of Lower Saxony to North Baden-Württemberg to integrate new wind generation especially from North Sea towards Central-South Europe for consumption and storage. The investment is part of the transmission corridor Cloppenburg - North Baden-Württemberg. | 1 | New investment in TYNDP, due to long distance RES integration; voltage stability of the grid; SOS in the South of Germany | long term |  | 1 | Wehrendorf (DE) | Urberach (DE) | 43. A153 | 43. A153 | New lines in HVDC technology from the region of Lower Saxony to North Baden-Württemberg to integrate new wind generation especially from North Sea towards Central-South Europe for consumption and storage. The investment is part of the transmission corridor Cloppenburg - North Baden-Württemberg. | 1 | The need for this long-term investment was not confirmed by the German Network development Plan 2012. Therefore further studies on this investment are ongoing. | 2020 | 2020 | 1 | Wehrendorf (DE) | Urberach (DE) | 135 | 662 | N-S Western DE_parallel lines | New lines in HVDC technology from Wehrendorf to Urberach to integrate new wind generation especially from North Sea towards Central-South Europe for consumption and storage. | 1 | Rescheduled | The need for this long-term investment was not confirmed by the regulatory authority within the national grid development plan 2012. Therefore further studies on this project are ongoing. | 2022 | 2022 | 1 | Wehrendorf (DE) | Urberach (DE) | 662 | New lines in HVDC technology from Wehrendorf to Urberach to integrate new wind generation especially from North Sea towards Central-South Europe for consumption and storage. | 1 | Delayed | The need for this long-term investment was not confirmed by the regulatory authority within the national grid development plan. Therefore further studies on this project are ongoing. | 2022 | 2022 | 1 | Wehrendorf (DE) | Urberach (DE) | 133 | 662 | Longterm RES-Integration in Germany | HVDC Line B | New lines in HVDC technology from Wehrendorf to Urberach to integrate new wind generation especially from North Sea towards Central-South Europe for consumption and storage. | 1 | Rescheduled | The need for this long-term investment was not confirmed by the regulatory authority within the national grid development plan 2014. Therefore the project has been rescheduled and further studies on this project are ongoing. | >2030 | 2030 | 1 |  | 0 | Wehrendorf (DE) | Urberach (DE) | Overhead Line | DC | 2000 | 400 | 380 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2030 |  | 18 | DEU | Wehrendorf | Urberach | 52.3322 | 8.3133 | 49.9734 | 8.7981
836 | 2014 | 2016 | [2014, 2015, 2016] | 663 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 132 | 663 | N-S Western DE_section North_2 | New 380-kV double circuit over-head-line Cloppenburg East - Merzen with a total length of ca. 55 km. New errection of a 380-kV substation Merzen. | 2 | Investment on time | Progress as planned. | 2022 | 2022 | 1 | Cloppenburg East (DE) | Merzen (DE) | 663 | New 380-kV double circuit over-head-line Cloppenburg East - Merzen with a total length of ca. 55 km. New errection of a 380-kV substation Merzen. | 2 | Rescheduled |  | 2021 | 2021 | 1 | Cloppenburg East (DE) | Merzen (DE) | 132 | 663 | RES-Integration in North-West Germany 2 | Cloppenburg East - Merzen | New 380-kV double circuit over-head-line Cloppenburg East - Merzen with a total length of ca. 55 km. New errection of a 380-kV substation Merzen. | 2 | Investment on time |  | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Cloppenburg East (DE) | Merzen (DE) | Overhead Line | AC | 3386 | 380 | 55 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2022 | 0 | 8 | DEU | Cloppenburg East | Merzen |  |  | 52.4776 | 7.8308
837 | 2012 | 2026 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 664 | [6 empty] | 0 |  |  | 43 | 43. A88 | New DC-lines to integrate new wind generation from Northern Germany towards Southern Germany and Southern Europe for consumption and storage. | 1 | New Investment. | long term |  | 1 | Brunsbüttel (DE), Wilster (DE), Kaltenkirchen (DE) | Großgartach (DE), Goldshöfe (DE), Grafenrheinfeld (DE) | 43. A88 | 43. A88 | New DC-lines to integrate new wind generation from Northern Germany towards Southern Germany and Southern Europe for consumption and storage. | 2 | The expected commissioning date is 2017 - 2022. | 2017 | 2017 | 1 | Brunsbüttel, Wilster, Kreis Segeberg | Großgartach, Goldshöfe, Grafenrheinfeld | 164 | 664 | N-S Eastern DE_central section | New DC-lines to integrate new wind generation from Northern Germany towards Southern Germany and Southern Europe for consumption and storage. | 2 | Investment on time | The expected commissioning date is 2017 - 2022 | 2022 | 2022 | 1 | Brunsbüttel, Wilster, Kreis Segeberg | Großgartach, Goldshöfe, Grafenrheinfeld | 664 | New DC-lines to integrate new wind generation from Northern Germany towards Southern Germany and Southern Europe for consumption and storage. | 2 | Investment on time | The expected commissioning date is 2017 2022 Substation 2 has been changed from Goldshöfe to the area of Wendlingen | 2022 | 2022 | 1 | Brunsbüttel, Wilster, Kreis Segeberg | Großgartach, Wendlingen, Grafenrheinf eld | 235 | 664 | HVDC Brunsbüttel/Wilster to Großgartach/Grafenrheinfeld | HVDC Line C | New DC-lines to integrate new wind generation from Northern Germany towards Southern Germany and Southern Europe for consumption and storage. | 2 | Delayed | The commissioning date of the investment is delayed due to new preference of underground cable instead of overhead lines by german legal requirement. | 1/ 1/ 2025 | 2025 | 1 |  | 0 | Brunsbüttel, Wilster | Großgartach, Grafenrheinfeld | Overhead Line | DC | 3575 | 500 | 770 | New | 235 | 664 | HVDC Brunsbüttel/Wilster to Großgartach/Grafenrheinfeld | HVDC Line C | 3 | Investment on time |  | 2025 | 2025 | 1 | TenneT-DE; TransnetBW | "Brunsbüttel, Wilster" | "Großgartach, Grafenrheinfeld" | Underground Cable | DC | 520 | 235 | 664 | HVDC SuedLink Brunsbüttel/Wilster to Großgartach/Grafenrheinfeld | HVDC Line C | New DC-lines to integrate new wind generation from Northern Germany towards Southern Germany and Southern Europe for consumption and storage. | 3 | Delayed | Due to complex and long approval process | 2026 | 2026 | 1 | TRANSNET-BW TenneT DE |  | 1 | 0 | Brunsbüttel, Wilster | Großgartach, Grafenrheinfeld | DCTransmissionLine | DC | 700 | New | 235 | 664 | HVDC SuedLink Brunsbüttel/Wilster to Großgartach/Bergrheinfeld West | HVDC LINE C - SUEDLINK | New DC-lines to integrate new wind generation from Northern Germany towards Southern Germany and Southern Europe for consumption and storage. | 3 | Investment on time |  | 12-2026 | 2026 | 1 | TransnetBW, Tennet DE | 2.10 | 1 | 0 | Brunsbüttel, Wilster | Großgartach, Bergrheinfeld West | DCTransmissionLine | DC | 4000 | 525 | 700 | New | 235 | 664 | HVDC SuedLink Brunsbüttel/Wilster to Großgartach/Bergrheinfeld West | HVDC LINE C - SUEDLINK | New DC-lines to integrate new wind generation from Northern Germany towards Southern Germany and Southern Europe for consumption and storage. | 3 | Rescheduled |  | 12-2028 | 2028 | 1 | TransnetBW, Tennet DE | 1.5 | 1 | 0 | Brunsbüttel, Wilster | Großgartach, Bergrheinfeld West | DCTransmissionLine | DC | 4000 | 525 | 1250 | New | 235 | 664 | HVDC SuedLink Brunsbüttel/Wilster to Großgartach/Bergrheinfeld West | HVDC LINE C - SUEDLINK | New HVDC-lines to integrate new wind generation from Northern Germany towards Southern Germany and Southern Europe for consumption and storage. |  |  | 12-2028 | 2028 | 1 | Tennet DE, TransnetBW | 0 | XX | XX | New |  | 2028 |  | 16 | DEU | Brunsbüttel Wilster | Großgartach Bergrheinfeld West
838 | 2012 | 2026 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 665 | [6 empty] | 0 |  |  | 43 | 43. A75 | New DC- lines to integrate new wind generation from Baltic Sea towards Central/south Europe for consumption and storage. | 1 | New Investment due to increase of RES and changes in conventional power plants in Germany and increase transits | long term |  | 1 | Lauchstadt (DE) | Meitingen (DE) | 43. A75 | 43. A75 | New DC- lines to integrate new wind generation from Baltic Sea towards Central/south Europe for consumption and storage. | 2 | The project was confirmed within the German network development plan 2012. | 2022 | 2022 | 1 | Lauchstädt (DE) | Meitingen (DE) | 130 | 665 | N-S Eastern DE_section East | New DC- lines to integrate new wind generation from control area 50Hertz especially Mecklenburg-Vorpommern, Brandenburg and Sachsen-Anhalt towards Central/south Europe for consumption and storage. | 2 | Investment on time | Result from National Grid Development Plan | 2022 | 2022 | 1 | Lauchstädt (DE) | Meitingen (DE) | 665 | New DC- lines to integrate new wind generation from control area 50Hertz especially Mecklenburg-Vorpommern, Brandenburg and Sachsen-Anhalt towards Central/south Europe for consumption and storage. | 2 | Investment on time | Progressed as planned. | 2022 | 2022 | 1 | Wolmistedt (DE) | Area of Gundremmin gen (DE) | 130 | 665 | HVDC Wolmirstedt to area Isar | Wolmirstedt-Isar | New DC- lines to integrate new wind generation from control area 50Hertz especially Mecklenburg-Vorpommern, Brandenburg and Sachsen-Anhalt towards Central/south Europe for consumption and storage. Due to ongoing political discussions a change of the connection point Gundremmingen is under consideration. | 2 | Delayed | The commissioning date of the investment is delayed due to new preference of underground cable instead of overhead lines by german legal requirement. | 1/ 1/ 2025 | 2025 | 1 |  | 0 | Wolmistedt (DE) | Isar (DE) | Overhead Line | DC | 3583 | 500 | 450 | New | 130 | 665 | HVDC Wolmirstedt to area Isar | Wolmirstedt | 3 | Investment on time |  | 2025 | 2025 | 1 | 50Hertz Transmission, TenneT DE | Wolmirstedt (DE) | Isar (DE) | Underground Cable | DC |  | 130 | 665 | HVDC SuedOstLink Wolmirstedt to area Isar | Wolmirstedt-Isar | New DC-line to integrate new wind generation from control area 50Hertz especially Mecklenburg-Vorpommern, Brandenburg and Sachsen-Anhalt towards Central/south Europe for consumption and storage. | 3 | Investment on time |  | 2025 | 2025 | 1 | 50HERTZ TenneT DE | 3.12 | 1 | 0 | Wolmirstedt (DE) | Isar (DE) | DCTransmissionLine | DC | 540 | New | 130 | 665 | HVDC SuedOstLink Wolmirstedt to area Isar | Wolmirstedt-Isar | New DC-line to integrate new wind generation from control area 50Hertz especially Mecklenburg-Vorpommern, Brandenburg and Sachsen-Anhalt towards Central/south Europe for consumption and storage. | 3 | Investment on time |  | 12-2025 | 2025 | 1 | 50Hertz, TenneT DE | 3.12 | 1 | 0 | Wolmirstedt (DE) | Isar (DE) | DCTransmissionLine | DC | 2000 | 525 | 539 | New | 130 | 665 | HVDC SuedOstLink Wolmirstedt to area Isar | Wolmirstedt-Isar | New DC-line to integrate new wind generation from control area 50Hertz especially Mecklenburg-Vorpommern, Brandenburg and Sachsen-Anhalt towards Central/south Europe for consumption and storage. | 3 | Investment on time |  | 12-2027 | 2027 | 1 | 50Hertz, TenneT DE | 2.2 | 1 | 0 | Wolmirstedt (DE) | Isar (DE) | DCTransmissionLine | DC | 2000 | 525 | 539 | New | 130 | 665 | HVDC SuedOstLink Wolmirstedt to area Isar | Wolmirstedt-Isar | New DC-line to integrate new wind generation from control area 50Hertz especially Mecklenburg-Vorpommern, Brandenburg and Sachsen-Anhalt towards Central/south Europe for consumption and storage. |  |  | 12-2027 | 2027 | 1 | 50Hertz, TenneT DE | 0 | XX | XX | New |  | 2027 |  | 15 | DEU | Wolmirstedt | Isar | 52.2485 | 11.6267 | 48.2511 | 11.684
839 | 2014 | 2016 | [2014, 2015, 2016] | 666 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 132 | 666 | N-S Western DE_section North_2 | New 380-kV-line in existing OHL corridor for integration of on- and offshore Wind generation. Incl. new 380-kV-switchgear in Cloppenburg and new transformers in Cloppenburg | 2 | Investment on time | TYDNP 2012 investment 43.A89 is divided in several parts | 2022 | 2022 | 1 | Conneforde (DE) | Cloppenburg (DE) | 666 | New 380-kV-line in existing OHL corridor for integration of on- and offshore Wind generation. Incl. new 380-kV- switchgear in Cloppenburg and new transformers in Cloppenburg | 2 | Investment on time | TYDNP 2012 investment 43.A89 is divided in several parts | 2022 | 2022 | 1 | Conneforde (DE) | Cloppenburg (DE) | 132 | 666 | RES-Integration in North-West Germany 2 | Conneforde - Cloppenburg East | New 380-kV-line in existing OHL corridor for integration of on- and offshore Wind generation. Incl. new 380-kV-switchgear in Cloppenburg and new transformers in Cloppenburg | 2 | Investment on time |  | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Conneforde (DE) | Cloppenburg (DE) | Overhead Line | AC | 3386 | 380 | 60 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2022 | 0 | 8 | DEU | Conneforde | Cloppenburg | 53.3258 | 8.0578 | 52.8461 | 8.0439
840 | 2014 | 2020 | [2014, 2015, 2016, 2018, 2020] | 667 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 209 | 667 | Reinforcement Northeastern DE | About 135 km new 380-kV-lines and around 10 new transformers for integration of onshore Wind in Schleswig-Holstein and increase of NTC between DE and DK | 2 | Delayed | The old investment 43.A90 is now divided in several parts. | 2018 | 2018 | 1 | Brunsbüttel (DE) | Niebüll | 667 | About 135 km new 380-kV-lines and around 10 new transformers for integration of onshore Wind in Schleswig- Holstein and increase of NTC between DE and DK | 2 | Investment on time | The old investment 43.A90 is now divided in several parts. in time relative to TYNDP14 | 2018 | 2018 | 1 | Brunsbüttel (DE) | Niebüll | 258 | 667 | Westcoast line | Brunsbüttel - Niebüll | About 135 km new 380-kV-lines and around 10 new transformers for integration of onshore Wind in Schleswig-Holstein and increase of NTC between DE and DK | 3 | Investment on time | in time relative to TYNDP14 | 1/ 1/ 2018 | 2018 | 1 |  | 0 | Brunsbüttel (DE) | Niebüll | Overhead Line | AC | 2014 | 380 | 135 | New | 258 | 667 | Westcoast line | Brunsbttel - Klixbüll | 3 | Delayed | Delay due to long permitting process | 2019 | 2019 | 1 | TenneT-DE | Brunsbüttel (DE) | Klixbüll (DE) | Overhead Line | AC | 380 | 258 | 667 | Westcoast line | Heide/West - Klixbüll | About 135 km new 380-kV-lines and around 10 new transformers for integration of onshore Wind in Schleswig-Holstein and increase of NTC between DE and DK | 4 | Investment on time |  | 2022 | 2022 | 1 | TenneT DE |  | 1 | 0 | Brunsbüttel (DE) | Klixbüll (DE) | ACTransmissionLine | AC | 125 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2022 | 4 | 8 | DEU | Brunsbüttel | Klixbüll | 53.8973 | 9.1395 | 54.8021 | 8.89
841 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 675 | Cancelled | [5 empty] | 0 |  |  | 44 | 44. A155 | Upgrade of 230-kV-circuit Unterweser-Conneforde to 400kV , Line length: 32 km. | 1 | New Investment due to increase of RES and changes in conventional power plants in Germany and increase transits | long term |  | 1 | Conneforde (DE) | Unterweser (DE) | 44. A155 | 44. A155 | Upgrade of 230-kV-circuit Unterweser-Conneforde to 400kV , Line length: 32 km. | 1 | Delay due to missing confirmation by the regulator | 2019 | 2019 | 1 | Conneforde (DE) | Unterweser (DE) | 207 | 675 | Reinforcement Northwestern DE | Upgrade of 220-kV-circuit Unterweser-Conneforde to 380kV , Line length: 32 km. | 1 | Rescheduled | Delay due to missing confirmation by the regulator | 2024 | 2024 | 1 | Conneforde (DE) | Unterweser (DE) | 675 | Upgrade of 220-kV-circuit Unterweser-Conneforde to 380kV , Line length: 32 km. | 1 | Investment on time | on time relative to TYNDP14 | 2024 | 2024 | 1 | Conneforde (DE) | Unterweser (DE) | 207 | 675 | Reinforcement Northwestern DE | Unterweser - Conneforde | Upgrade of 220-kV-circuit Unterweser-Conneforde to 380kV , Line length; 32 km. | 1 | Investment on time | on time relative to TYNDP14 | 1/ 1/ 2024 | 2024 | 1 |  | 0 | Conneforde (DE) | Unterweser (DE) | Overhead Line | AC | 4068 | 380 | 32 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2024 |  | 12 | DEU | Conneforde | Unterweser | 53.3258 | 8.0578 | 53.3256 | 8.4806
842 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 676 | Cancelled | [5 empty] | 0 |  |  | 44 | 44. A156 | New 400 kV line in existing OHL corridor Dollern - Elsfleht/West Length:100 km | 1 | New Investment due to increase of RES and changes in conventional power plants in Germany and increase transits | long term |  | 1 | Dollern (DE) | Elsfleht/West (DE) | 44. A156 | 44. A156 | New 400 kV line in existing OHL corridor Dollern - Elsfleht/West Length:100 km | 1 | Delay due to missing confirmation by the regulator | 2018 | 2018 | 1 | Dollern (DE) | Elsfleht/West (DE) | 207 | 676 | Reinforcement Northwestern DE | New 380 kV line in existing OHL corridor Dollern - Elsfleht/West Length:100 km | 1 | Rescheduled | Delay due to missing confirmation by the regulator | 2024 | 2024 | 1 | Dollern (DE) | Elsfleht/West (DE) | 676 | New 380 kV line in existing OHL corridor Dollern - Elsfleht/West Length:100 km | 2 | Investment on time | on time relative to TYNDP14 | 2024 | 2024 | 1 | Dollern (DE) | Elsfleht/West (DE) | 207 | 676 | Reinforcement Northwestern DE | Dollern - Elsfleth/West | New 380 kV line in existing OHL corridor Dollern - Elsfleht/West Length;100 km | 2 | Investment on time | on time relative to TYNDP14 | 1/ 1/ 2024 | 2024 | 1 |  | 0 | Dollern (DE) | Elsfleht/West (DE) | Overhead Line | AC | 2849 | 380 | 100 | New | 207 | 676 | Reinforcement Northwestern DE | Dollern - Elsfleth/West | 3 | Delayed | Delay due to long permitting process | 2026 | 2026 | 1 | TENNET-DE | Dollern (DE) | Elsfleht/West (DE) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2026 |  | 14 | DEU | Dollern | Elsflehtwest | 53.5378 | 9.5385
843 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 677 | Cancelled | [5 empty] | 0 |  |  | 44 | 44. A157 | New 400 kV line in existing OHL corridor Dollern-Sottrum-Wechold-Landesbergen (130 km) | 1 | New Investment due to increase of RES and changes in conventional power plants in Germany and increase transits | long term |  | 1 | Dollern (DE) | Landesbergen (DE) | 44. A157 | 44. A157 | New 400 kV line in existing OHL corridor Dollern-Sottrum-Wechold-Landesbergen (130 km) | 2 |  | 2017 | 2017 | 1 | Dollern (DE) | Landesbergen (DE) | 164 | 677 | N-S Eastern DE_central section | New 380 kV line in existing OHL corridor Dollern-Sottrum-Wechold-Landesbergen (130 km) | 2 | Investment on time |  | 2022 | 2022 | 1 | Dollern (DE) | Landesbergen (DE) | 677 | New 380 kV line in existing OHL corridor Dollern-Sottrum- Wechold-Landesbergen (130 km) | 2 | Investment on time | Progressed as planned. | 2022 | 2022 | 1 | Dollern (DE) | Landesberge n (DE) | 164 | 677 | N-S Eastern DE_central section | Dollern - Landesbergen | New 380 kV line in existing OHL corridor Dollern-Sottrum-Wechold-Landesbergen (130 km) | 3 | Delayed | Delay due to long permitting process | 1/ 1/ 2023 | 2023 | 1 |  | 0 | Dollern (DE) | Landesbergen (DE) | Overhead Line | AC | 3749 | 380 | 130 | New | 164 | 677 | N-S Eastern DE_central section | Dollern - Landesbergen | 3 | Investment on time |  | 2023 | 2023 | 1 |  | Dollern (DE) | Landesbergen (DE) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2023 |  | 11 | DEU | Dollern | Landesbergen | 53.5378 | 9.5385 | 52.561 | 9.1238
844 | 2014 | 2015 | [2014, 2015] | 68 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 148 | 68 | CCS new | New 120km double circuit 400kV OHL between Okroglo(SI) and future substation of South Udine (IT) with PST in Okroglo. The thermal rating will be 1870 MVA per circuit. | 2 | Investment on time | There are some issues with social acceptance and territorial constraints. End of construction works are planned by the end of 2021.Full operation is expected by end of 2021(beginning of 2022). | 2021 | 2021 | 1 | Okroglo (SI) | South Udine (IT) | 68 | New 120km double circuit 400kV OHL between Okroglo(SI) and future substation of Udine Sud (IT) with PST in Okroglo. | 1 | Rescheduled | The project is under consideration following to the changing scenario conditions. | 2030 | 2030 | 1 | Okroglo (SI) | Udine Sud (IT) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2030 | 9 | 16 | ITA;SVN | Okroglo | Udine Sud | 46.2585 | 14.3205 | 46.0178 | 13.2168
845 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 680 | Cancelled | [5 empty] | 0 |  |  | 44 | 44. A160 | New line and extension of existing line to 400 kV double circuit OHL Urberach - Pfungstadt - Weinheim - Daxlanden including extension of existing substations. Length: 219 km | 1 | New Investment due to increase of RES and changes in conventional power plants in Germany and increase transits | long term |  | 1 | Urberach (DE) | Daxlanden (DE) | 44. A160 | 44. A160 | New line and extension of existing line to 400 kV double circuit OHL Urberach - Weinheim - Daxlanden including extension of existing substations. | 2 |  | 2018 | 2018 | 1 | Urberach (DE) | Daxlanden (DE) | 134 | 680 | N-S Western DE_section South | New line and extension of existing line to 380 kV double circuit overhead line Urberach - Weinheim - Daxlanden. Extension of existing substations are included. | 2 | Investment on time | Progress as planned. | 2021 | 2021 | 1 | Urberach (DE) | Daxlanden (DE) | 680 | New line and extension of existing line to 380 kV double circuit overhead line Urberach - Weinheim - Daxlanden. Extension of existing substations are included. | 2 | Investment on time | Commissioning is planned end of 2021 / beginning of 2022. Therefore the commissioning is set to 2022. | 2022 | 2022 | 1 | Urberach (DE) | Daxlanden (DE) | 134 | 680 | Grid Reinforcements in South-West Germany | Urberach - Daxlanden | New line and extension of existing line to 380 kV double circuit overhead line Urberach - Weinheim - Daxlanden. Extension of existing substations are included. | 2 | Investment on time | Commissioning is planned for the end of 2021 / beginning of 2022. Therefore, the commissioning date is set to 2022. | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Urberach (DE) | Daxlanden (DE) | Overhead Line | AC | 1833 | 400 | 219 | New | 134 | 680 | N-S Western DE_section South | Urberach - Daxlanden |  | Investment on time |  | 1/ 1/ 2023 | 2023 | 1 |  | Urberach (DE) | Daxlanden (DE) | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2023 |  | 11 | DEU | Urberach | Daxlanden | 49.9734 | 8.7981 | 49.0014 | 8.3386
846 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 680 | Cancelled | [5 empty] | 0 |  |  | 44 | 44. A160 | New line and extension of existing line to 400 kV double circuit OHL Urberach - Pfungstadt - Weinheim - Daxlanden including extension of existing substations. Length: 219 km | 1 | New Investment due to increase of RES and changes in conventional power plants in Germany and increase transits | long term |  | 1 | Urberach (DE) | Daxlanden (DE) | 44. A160 | 44. A160 | New line and extension of existing line to 400 kV double circuit OHL Urberach - Weinheim - Daxlanden including extension of existing substations. | 2 |  | 2018 | 2018 | 1 | Urberach (DE) | Daxlanden (DE) | 134 | 680 | N-S Western DE_section South | New line and extension of existing line to 380 kV double circuit overhead line Urberach - Weinheim - Daxlanden. Extension of existing substations are included. | 2 | Investment on time | Progress as planned. | 2021 | 2021 | 1 | Urberach (DE) | Daxlanden (DE) | 680 | New line and extension of existing line to 380 kV double circuit overhead line Urberach - Weinheim - Daxlanden. Extension of existing substations are included. | 2 | Investment on time | Commissioning is planned end of 2021 / beginning of 2022. Therefore the commissioning is set to 2022. | 2022 | 2022 | 1 | Urberach (DE) | Daxlanden (DE) | 134 | 680 | Grid Reinforcements in South-West Germany | Urberach - Daxlanden | New line and extension of existing line to 380 kV double circuit overhead line Urberach - Weinheim - Daxlanden. Extension of existing substations are included. | 2 | Investment on time | Commissioning is planned for the end of 2021 / beginning of 2022. Therefore, the commissioning date is set to 2022. | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Urberach (DE) | Daxlanden (DE) | Overhead Line | AC | 1833 | 400 | 219 | New | 134 | 680 | N-S Western DE_section South | Urberach - Daxlanden |  | Investment on time |  | 1/ 1/ 2023 | 2023 | 1 |  | Urberach (DE) | Daxlanden (DE) | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2023 |  | 11 | DEU | Urberach | Daxlanden | 49.9734 | 8.7981 | 49.0014 | 8.3386
847 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 680 | Cancelled | [5 empty] | 0 |  |  | 44 | 44. A160 | New line and extension of existing line to 400 kV double circuit OHL Urberach - Pfungstadt - Weinheim - Daxlanden including extension of existing substations. Length: 219 km | 1 | New Investment due to increase of RES and changes in conventional power plants in Germany and increase transits | long term |  | 1 | Urberach (DE) | Daxlanden (DE) | 44. A160 | 44. A160 | New line and extension of existing line to 400 kV double circuit OHL Urberach - Weinheim - Daxlanden including extension of existing substations. | 2 |  | 2018 | 2018 | 1 | Urberach (DE) | Daxlanden (DE) | 135 | 680 | N-S Western DE_parallel lines | New line and extension of existing line to 380 kV double circuit overhead line Urberach - Weinheim - Daxlanden. Extension of existing substations are included. | 2 | Investment on time | Progress as planned. | 2021 | 2021 | 1 | Urberach (DE) | Daxlanden (DE) | 680 | New line and extension of existing line to 380 kV double circuit overhead line Urberach - Weinheim - Daxlanden. Extension of existing substations are included. | 2 | Investment on time | Commissioning is planned end of 2021 / beginning of 2022. Therefore the commissioning is set to 2022. | 2022 | 2022 | 1 | Urberach (DE) | Daxlanden (DE) | 134 | 680 | Grid Reinforcements in South-West Germany | Urberach - Daxlanden | New line and extension of existing line to 380 kV double circuit overhead line Urberach - Weinheim - Daxlanden. Extension of existing substations are included. | 2 | Investment on time | Commissioning is planned for the end of 2021 / beginning of 2022. Therefore, the commissioning date is set to 2022. | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Urberach (DE) | Daxlanden (DE) | Overhead Line | AC | 1833 | 400 | 219 | New | 134 | 680 | N-S Western DE_section South | Urberach - Daxlanden |  | Investment on time |  | 1/ 1/ 2023 | 2023 | 1 |  | Urberach (DE) | Daxlanden (DE) | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2023 |  | 11 | DEU | Urberach | Daxlanden | 49.9734 | 8.7981 | 49.0014 | 8.3386
848 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 680 | Cancelled | [5 empty] | 0 |  |  | 44 | 44. A160 | New line and extension of existing line to 400 kV double circuit OHL Urberach - Pfungstadt - Weinheim - Daxlanden including extension of existing substations. Length: 219 km | 1 | New Investment due to increase of RES and changes in conventional power plants in Germany and increase transits | long term |  | 1 | Urberach (DE) | Daxlanden (DE) | 44. A160 | 44. A160 | New line and extension of existing line to 400 kV double circuit OHL Urberach - Weinheim - Daxlanden including extension of existing substations. | 2 |  | 2018 | 2018 | 1 | Urberach (DE) | Daxlanden (DE) | 135 | 680 | N-S Western DE_parallel lines | New line and extension of existing line to 380 kV double circuit overhead line Urberach - Weinheim - Daxlanden. Extension of existing substations are included. | 2 | Investment on time | Progress as planned. | 2021 | 2021 | 1 | Urberach (DE) | Daxlanden (DE) | 680 | New line and extension of existing line to 380 kV double circuit overhead line Urberach - Weinheim - Daxlanden. Extension of existing substations are included. | 2 | Investment on time | Commissioning is planned end of 2021 / beginning of 2022. Therefore the commissioning is set to 2022. | 2022 | 2022 | 1 | Urberach (DE) | Daxlanden (DE) | 134 | 680 | Grid Reinforcements in South-West Germany | Urberach - Daxlanden | New line and extension of existing line to 380 kV double circuit overhead line Urberach - Weinheim - Daxlanden. Extension of existing substations are included. | 2 | Investment on time | Commissioning is planned for the end of 2021 / beginning of 2022. Therefore, the commissioning date is set to 2022. | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Urberach (DE) | Daxlanden (DE) | Overhead Line | AC | 1833 | 400 | 219 | New | 134 | 680 | N-S Western DE_section South | Urberach - Daxlanden |  | Investment on time |  | 1/ 1/ 2023 | 2023 | 1 |  | Urberach (DE) | Daxlanden (DE) | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2023 |  | 11 | DEU | Urberach | Daxlanden | 49.9734 | 8.7981 | 49.0014 | 8.3386
849 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 682 | Cancelled | [5 empty] | 0 |  |  | 44 | 44. A162 | Extension of existing 400-kV-line Großgartach - Endersbach. (Lenght: 32 km) | 1 | New Investment due to increase of RES and changes in conventional power plants in Germany and increase transits | long term |  | 1 | Großgartach (DE) | Endersbach (DE) | 44. A162 | 44. A162 | Extension of existing 380 kV line Großgartach - Endersbach. (Length: 32 km) | 2 |  | 2020 | 2020 | 1 | Großgartach (DE) | Endersbach (DE) | 206 | 682 | Reinforcement Southern DE | AC-extension of the "C corridor" at one ending point in Southern Germany towards the consumption areas allowing the existing grid to deal with the additionnal flows from DC-link | 2 | Investment on time | Standard processing 2018-2019 | 2019 | 2019 | 1 | Großgartach (DE) | Endersbach (DE) | 682 | AC-extension of the "C corridor" at one ending point in Southern Germany towards the consumption areas allowing the existing grid to deal with the additionnal flows from DC- link | 3 | Ahead of time | Standard processing | 2018 | 2018 | 1 | Großgartach (DE) | Endersbach (DE) | 206 | 682 | Reinforcement Southern DE | Großgartach - Endersbach | AC-extension of the "C corridor" at one ending point in Southern Germany towards the consumption areas allowing the existing grid to deal with the additionnal flows from DC-link | 2 | Rescheduled | Standard processing | 1/ 1/ 2020 | 2020 | 1 |  | 0 | Großgartach (DE) | Endersbach (DE) | Overhead Line | AC | 1340 | 380 | 32 | New | 206 | 682 | Reinforcement Southern DE | Großgartach - Endersbach | 2 | Rescheduled |  | 2025 | 2025 | 1 | TENNET-DE;TRANSNET-BW | Großgartach (DE) | Endersbach (DE) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2025 |  | 13 | DEU | Großgartach | Endersbach | 49.1425 | 9.1259 | 48.8103 | 9.3655
850 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 685 | Cancelled | [5 empty] | 0 |  |  | 45 | 45. A165 | New double circuit OHL 400-kV-line (130 km) | 1 | New Investment due to increase of RES and changes in conventional power plants in Germany and increase transits | long term |  | 1 | Mecklar (DE) | Grafenrheinfeld (DE) | 45. A165 | 45. A165 | New double circuit OHL 400-kV-line (130 km) | 2 |  | 2017 | 2017 | 1 | Mecklar (DE) | Grafenrheinfeld (DE) | 164 | 685 | N-S Eastern DE_central section | New double circuit OHL 400-kV-line (130 km) | 2 | Investment on time |  | 2022 | 2022 | 1 | Mecklar (DE) | Grafenrheinfeld (DE) | 685 | New double circuit OHL 400-kV-line (130 km) | 2 | Investment on time | Progressed as planned. | 2022 | 2022 | 1 | Mecklar (DE) | Grafenrheinf eld (DE) | 164 | 685 | N-S Eastern DE_central section | Mecklar - Grafenrheinfeld | New double circuit OHL 380-kV-line (130 km). Due to ongoing political discussions a change of the connection point Grafenrheinfeld is under consideration. | 2 | Investment on time |  | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Mecklar (DE) | Grafenrheinfeld (DE) | Overhead Line | AC | 2387 | 380 | 130 | New | 164 | 685 | N-S Eastern DE_central section | Mecklar - Grafenrheinfeld | 2 | Investment on time |  | 2027 | 2027 | 1 |  | Mecklar (DE) | Grafenrheinfeld (DE) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2027 |  | 15 | DEU | Mecklar | Grafenrheinfeld | 50.9175 | 9.7612 | 49.9907 | 10.2099
851 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 686 | Cancelled | [5 empty] | 0 |  |  | 45 | 45. A166 | New double circuit OHL 400-kV-line (130 km) | 1 | New Investment due to increase of RES and changes in conventional power plants in Germany and increase transits | long term |  | 1 | Altenfeld (DE) | Grafenrheinfeld (DE) | 45. A166 | 45. A166 | New double circuit OHL 400-kV-line (130 km) | 1 | Delay due to missing confirmation by the regulator | 2019 | 2019 | 1 | Schalkau / area of Altenfeld (DE) | area of Grafenrheinfeld (DE) | 204 | 686 | N-S transmission DE_par_line_2 | New double circuit OHL 380-kV-line (130 km) | 1 | Rescheduled | Delay due to missing confirmation by the regulator | 2024 | 2024 | 1 | Schalkau / area of Altenfeld (DE) | area of Grafenrheinfeld (DE) | 686 | New double circuit OHL 380-kV-line (130 km) | 2 | Investment on time | no delay related to TYNDP2014 | 2024 | 2024 | 1 | Schalkau / area of Altenfeld (DE) | area of Grafenrheinf eld (DE) | 204 | 686 | Grid extension between Thuringa and Bavaria | Altenfeld-Grafenrheinfeld | New double circuit OHL 380-kV-line (130 km). Due to ongoing political discussions a change of the connection point Grafenrheinfeld is under consideration. | 2 | Investment on time | In time relative to TYNDP14. | 1/ 1/ 2024 | 2024 | 1 |  | 0 | Schalkau / area of Altenfeld (DE) | area of Grafenrheinfeld (DE) | Overhead Line | AC | 2408 | 380 | 130 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2024 |  | 12 | DEU | Schalkau Altenfeld | Grafenrheinfeld |  |  | 49.9907 | 10.2099
852 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 687 | Cancelled | [5 empty] | 0 |  |  | 45 | 45. A167 | New double circuit OHL 400 kV line in existing OHL corridor Redwitz-Mechlenreuth-Etzenricht-Schwandorf (185 km) | 1 | New Investment due to increase of RES and changes in conventional power plants in Germany and increase transits | long term |  | 1 | Redwitz (DE) | Schwandorf (DE) | 45. A167 | 45. A167 | New double circuit OHL 400 kV line in existing OHL corridor Redwitz-Mechlenreuth-Etzenricht-Schwandorf (185 km) | 2 |  | 2017 | 2017 | 1 | Redwitz (DE) | Schwandorf (DE) | 206 | 687 | Reinforcement Southern DE | New double circuit OHL 380 kV line in existing OHL corridor Redwitz-Mechlenreuth-Etzenricht-Schwandorf (185 km) | 2 | Investment on time |  | 2020 | 2020 | 1 | Redwitz (DE) | Schwandorf (DE) | 687 | New double circuit OHL 380 kV line in existing OHL corridor Redwitz-Mechlenreuth-Etzenricht-Schwandorf (185 km) | 2 | Investment on time | Progressed as planned. | 2020 | 2020 | 1 | Redwitz (DE) | Schwandorf (DE) | 206 | 687 | Reinforcement Southern DE | Redwitz - Schwandorf | New double circuit OHL 380 kV line in existing OHL corridor Redwitz-Mechlenreuth-Etzenricht-Schwandorf (185 km) | 3 | Delayed | Delay due to long permitting process | 1/ 1/ 2023 | 2023 | 1 |  | 0 | Redwitz (DE) | Schwandorf (DE) | Overhead Line | AC | 1218 | 380 | 185 | New | 206 | 687 | Reinforcement Southern DE | Redwitz - Schwandorf | 3 | Investment on time |  | 2023 | 2023 | 1 |  | Redwitz (DE) | Schwandorf (DE) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2023 |  | 11 | DEU | Redwitz | Schwandorf | 50.1692 | 11.2084 | 49.3153 | 12.0866
853 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 688 | Cancelled | [5 empty] | 0 |  |  | 45 | 45. A168 | New 400 kV line in existing OHL corridor Raitersaich - Ludersheim - Sittling - Isar (160 km) | 1 | New Investment due to increase of RES and changes in conventional power plants in Germany and increase transits | long term |  | 1 | Raitersaich (DE) | Isar (DE) | 45. A168 | 45. A168 | New 400 kV line in existing OHL corridor Raitersaich - Ludersheim - Sittling - Isar or Altheim (160 km) | 1 | Delay due to missing confirmation by the regulator | 2017 | 2017 | 1 | Raitersaich (DE) | Isar (DE) | 206 | 688 | Reinforcement Southern DE | New 380 kV line in existing OHL corridor Raitersaich - Ludersheim - Sittling - Isar or Altheim (160 km) | 1 | Rescheduled | Delay due to missing confirmation by the regulator | 2024 | 2024 | 1 | Raitersaich (DE) | Isar (DE) | 688 | New 380 kV line in existing OHL corridor Raitersaich - Ludersheim - Sittling - Isar or Altheim (160 km) | 1 | Investment on time | in time relative to TYNDP 2014 | 2024 | 2024 | 1 | Raitersaich (DE) | Isar (DE) | 206 | 688 | Reinforcement Southern DE | Altheim - Isar | New 380 kV line in existing OHL corridor Raitersaich - Ludersheim - Sittling - Altheim (160 km) | 2 | Investment on time | in time relative to TYNDP 2014 | 1/ 1/ 2024 | 2024 | 1 |  | 0 | Raitersaich (DE) | Altheim (DE) | Overhead Line | AC | 1902 | 380 | 160 | New | 206 | 688 | Reinforcement Southern DE | Raitersaich-Altheim | 2 | Delayed | Delay due to long permitting | 2026 | 2026 | 1 |  | Raitersaich (DE) | Altheim (DE) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2026 |  | 14 | DEU | Raitersaich | Altheim | 49.373 | 10.8446 | 48.5808 | 10.0271
854 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 689 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 47 | 689 | AT - DE | Upgrade of an existing over head line to 380 kV, extension of existing and errection of new 380-kV-substations including 380/110-kV-transformers. Transmission route Vöhringen (DE) -Westtirol (AT). This project will increase the current power exchange capacity between the DE, AT. | 2 | Investment on time | Progress as planned. | 2020 | 2020 | 1 | Vöhringen (DE) | Westtirol (AT) | 689 | Upgrade of an existing over head line to 380 kV, extension of existing and errection of new 380-kV-substations including 380/110-kV-transformers. Transmission route Vöhringen (DE) -Westtirol (AT). This project will increase the current power exchange capacity between the DE, AT. | 2 | Investment on time | Progressed as planned. | 2020 | 2020 | 1 | Vöhringen (DE) | Westtirol (AT) | 47 | 689 | Austria - Germany | Vöhringen (DE) - Westtirol (AT) | Upgrade of an existing over head line to 380 kV, extension of existing and errection of new 380-kV-substations including 380/110-kV-transformers. Transmission route Vöhringen (DE) -Westtirol (AT). This project will increase the current power exchange capacity between the DE, AT. | 2 | Investment on time |  | 1/ 1/ 2020 | 2020 | 1 |  | 1 | Vöhringen (DE) | Westtirol (AT) | Overhead Line | AC | 585 | 400 | 114 | Upgrade | 47 | 689 | Westtirol - Vöhringen | 689: Vöhringen (DE) - Westtirol (AT) | 2 | Delayed | Scope of the project changed due to technical reasons. | 2024 | 2024 | 1 |  | Vöhringen (DE) | Westtirol (AT) | Overhead Line | AC | 380 | 47 | 689 | Westtirol (AT) - Vöhringen (DE) | 689: Vöhringen (DE) - Westtirol (AT) | Upgrade of an existing over head line to 380 kV, extension of existing and errection of new 380-kV-substations including 380/110-kV-transformers. Transmission route Vöhringen (DE) -Westtirol (AT). This project will increase the current power exchange capacity between the DE, AT. | 2 | Delayed | Scope of the project changed due to technical reasons. | 2027 | 2027 | 1 | AMPRION Austrian Power Grid |  | 1 | 1 | Vöhringen (DE) | Westtirol (AT) | ACTransmissionLine | AC | 157 | Upgrade | 47 | 689 | Westtirol (AT) - Vöhringen (DE) | 689: Vöhringen (DE) - Westtirol (AT) | Upgrade of an existing over head line to 380 kV, extension of existing and errection of new 380-kV-substations including 380/110-kV-transformers. Transmission route Vöhringen (DE) -Westtirol (AT). This project will increase the current power exchange capacity between the DE, AT. | 2 | Delayed | Scope of the project changed due to technical reasons. | 12-2030 | 2030 | 1 | Amprion, Austrian Power Grid |  | 1 | 1 | Vöhringen (DE) | Westtirol (AT) | ACTransmissionLine | AC | 0 | 380 | 157 | Upgrade | 47 | 689 | Westtirol (AT) - Vöhringen (DE) | 689: Vöhringen (DE) - Westtirol (AT) | Upgrade of an existing over head line to 380 kV, extension of existing and errection of new 380-kV-substations including 380/110-kV-transformers. Transmission route Vöhringen (DE) -Westtirol (AT). This project will increase the current power exchange capacity between the DE, AT. | 2 | Delayed | Scope of the project changed due to technical reasons. | 12-2030 | 2030 | 1 | Amprion, Austrian Power Grid |  | 1 | 1 | Vöhringen (DE) | Westtirol (AT) | ACTransmissionLine | AC | 0 | 380 | 157 | Upgrade | 47 | 689 | Westtirol (AT) - Vöhringen (DE) | Vöhringen (DE) - Westtirol (AT) | Upgrade of an existing over head line to 380 kV, extension of existing and errection of new 380-kV-substations including 380/110-kV-transformers. Transmission route Vöhringen (DE) -Westtirol (AT). This project will increase the current power exchange capacity between the DE, AT. | 2 |  | 12-2030 | 2030 | 1 | Amprion, Austrian Power Grid | 1 | XX | XX | Upgrade | 2020 | 2030 | 10 | 16 | AUT;DEU | Vöhringen | Westtirol | 48.2833 | 10.0833 | 47.2439 | 10.8743
855 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 695 | Cancelled | [5 empty] | 0 |  |  | 48 | 48. A126 | Connection of the two existing substations (R.Sobota (SK) - Sajoóivánka (HU)) by the new 2x400 kV line (preliminary armed only with one circuit). | 1 | New investment in TYNDP | 2016 | 2016 | 1 | Rimavská Sobota (SK) | Sajóivánka (HU) | 48. A126 | 48. A126 | Connection of the two existing substations (R.Sobota (SK) - Sajoóivánka (HU)) by the new 2x400 kV line (preliminary armed only with one circuit). | 1 | No change. Negotiations between SEPS and MAVIR are still ongoing. | 2016 | 2016 | 1 | Rimavská Sobota (SK) | Sajóivánka (HU) | 48 | 695 | New SK-HU intercon. - phase 1 | Connection of the two existing substations (R.Sobota (SK) - Sajoóivánka (HU)) by the new 2x400 kV line (preliminary armed only with one circuit). | 2 | Delayed | Expected commission date postponed on 2018 by reason of difficulties associated with finding the common national border crossing point. | 2018 | 2018 | 1 | Rimavská Sobota (SK) | Sajóivánka (HU) | 695 | Connection of the two existing substations (R.Sobota (SK) - Sajoóivánka (HU)) by the new 2x400 kV line (preliminary armed only with one circuit). | 3 | Investment on time | Investment's preparation proceeds in line with joint SK- HU negotiations. Any delays are expected. | 2018 | 2018 | 1 | Rimavská Sobota (SK) | Sajóivánka (HU) | 48 | 695 | New SK-HU intercon. - phase 1 | 2. SK-HU interconnection | Connection of the two existing substations (R.Sobota (SK) - Sajoóivánka (HU)) by the new 2x400 kV line (preliminary armed only with one circuit on the Hungarian side). | 2 | Delayed | The approval of the Contract of Construction for each PCI in the project between the two promoters has been in delay compared to the original schedule. The project promoters agreed jointly in November 2015 to set a new feasible commissioning date, which will also figure in the Contract. | 31/12/2019 | 2019 | 1 |  | 1 | Rimavská Sobota (SK) | Sajóivánka (HU) | Overhead Line | AC | 800 | 400 | 48 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2019 | 3 | 7 | HUN;SVK | Rimavská Sobota | Sajóivánka | 48.3834 | 20.0181 | 48.2661 | 20.5794
856 | 2014 | 2020 | [2014, 2015, 2016, 2018, 2020] | 696 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 48 | 696 | New SK-HU intercon. - phase 1 | 2x70 Mvar shunt reactors in station Sajóivánka (HU) | 2 | Delayed | Expected commission date postponed to 2018 as a result of negotiations between SEPS and MAVIR. | 2018 | 2018 | 1 | Sajóivánka (HU) |  | 696 | 2x70 Mvar shunt reactors in station Sajóivánka (HU) | 2 | Investment on time | Progressed as planned | 2018 | 2018 | 1 | Sajóivánka (HU) |  | 48 | 696 | New SK-HU intercon. - phase 1 | Hunew 1 | 2x70 Mvar shunt reactors in station Sajóivánka (HU) | 2 | Delayed | The approval of the Contract of Construction for each PCI in the project between the two promoters has been in delay compared to the original schedule. The project promoters agreed jointly in November 2015 to set a new feasible commissioning date, which will also figure in the Contract. | 12/31/2019 | 2019 | 1 |  | 0 | Sajóivánka (HU) |  | Compensation |  | 800 | 400 |  | New | 48 | 696 | New SK-HU intercon. - phase 1 | Hunew 1 | 3 | Delayed | The commissioning date was changed to 2020, as the ivestment is tied to the cross-border invetment (R. Sobota-Sajóivánka). | 2020 | 2020 | 1 | MAVIR,SEPS | Sajóivánka (HU) |  | Compensation | AC | 400 | 48 | 696 | New SK-HU intercon. - phase 1 | Hunew 1 | 2x70 Mvar shunt reactors in station Sajóivánka (HU) | 4 | Investment on time |  | 2020 | 2020 | 1 | MAVIR SEPS | 3.16, 3.17 | 0 | 1 | Sajóivánka (HU) |  | ReactiveCompensationDevice | AC | 0 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2020 | 2 | 6 | HUN;SVK | Sajóivánka |  | 48.2661 | 20.5794
857 | 2014 | 2020 | [2014, 2015, 2016, 2018, 2020] | 697 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 48 | 697 | New SK-HU intercon. - phase 1 | Second 400/120 kV transformer in station Sajóivánka (HU) | 2 | Delayed | Expected commission date postponed to 2018 as a result of negotiations between SEPS and MAVIR. | 2018 | 2018 | 1 | Sajóivánka (HU) |  | 697 | Second 400/120 kV transformer in station Sajóivánka (HU) | 2 | Investment on time | Progressed as planned | 2018 | 2018 | 1 | Sajóivánka (HU) |  | 48 | 697 | New SK-HU intercon. - phase 1 | Hunew 1 | Second 400/120 kV transformer in station Sajóivánka (HU) | 2 | Delayed | The approval of the Contract of Construction for each PCI in the project between the two promoters has been in delay compared to the original schedule. The project promoters agreed jointly in November 2015 to set a new feasible commissioning date, which will also figure in the Contract. | 12/31/2019 | 2019 | 1 |  | 0 | Sajóivánka (HU) |  | Substation |  | 800 | 400 |  | Upgrade | 48 | 697 | New SK-HU intercon. - phase 1 | Hunew 2 | 3 | Delayed | The commissioning date was changed to 2020, as the ivestment is tied to the cross-border invetment (R. Sobota-Sajóivánka). | 2020 | 2020 | 1 |  | Sajóivánka (HU) |  | Substation | AC | 400 | 48 | 697 | New SK-HU intercon. - phase 1 | Hunew 2 | Second 400/120 kV transformer in station Sajóivánka (HU) | 4 | Investment on time |  | 2020 | 2020 | 1 | MAVIR SEPS | 3.16, 3.17 | 0 | 1 | Sajóivánka (HU) |  | Transformer | AC | 0 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2020 | 2 | 6 | HUN;SVK | Sajóivánka |  | 48.2661 | 20.5794
858 | 2014 | 2015 | [2014, 2015] | 698 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 48 | 698 | New SK-HU intercon. - phase 1 | 70 Mvar shunt reactor in station Győr (HU) | 2 | Delayed | Investment rescheduled as a result of changes in planning input data (need delayed) | 2018 | 2018 | 1 | Gyor (HU) |  | 698 | 70 Mvar shunt reactor in station Győr (HU) | 2 | Rescheduled | Investment rescheduled as a result of changes in load forecast | 2024 | 2024 | 1 | Győr (HU) | [6 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2024 | 6 | 10 | HUN | Gyr |  | 47.6591 | 17.7243
859 | 2014 | 2015 | [2014, 2015] | 699 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 48 | 699 | New SK-HU intercon. - phase 1 | Third 400/120 kV transformer in station Győr (HU) | 2 | Delayed | Investment rescheduled as a result of changes in planning input data (need delayed) | 2018 | 2018 | 1 | Gyor (HU) |  | 699 | Third 400/120 kV transformer in station Győr (HU) | 2 | Rescheduled | Investment rescheduled as a result of changes in load forecast | 2024 | 2024 | 1 | Győr (HU) | [6 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2024 | 6 | 10 | HUN | Gyr |  | 47.6591 | 17.7243
860 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 70 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 28 | 70 | 28 | New 1000MW HVDC interconnection line between Italy and Montenegro via 375km 500kV DC subsea cable and converter stations at both ending points. | 4 | Delayed | rescheduling of work due to further secondary permitting during land rights acquisition and construction phase | 2017 | 2017 | 1 | Villanova (IT) | Lastva (ME) | 70 | New 1000MW HVDC interconnection line between Italy and Montenegro via 393km 500kV DC subsea cable and converter stations at both ending points. | 4 | Investment on time | Progressed as planned | 2017 | 2017 | 1 | Villanova (IT) | Lastva (ME) | 28 | 70 | Italy-Montenegro | 70 | New 1200MW HVDC interconnection line between Italy and Montenegro via 475 km 500kV DC subsea cable and converter stations at both ending points. | 4 | Investment on time | Works in progress. | 31/ 12/ 2019 | 2019 | 1 |  | 1 | Villanova (IT) | Lastva (ME) | Subsea Cable | DC | 1200 | 500 | 475 | New | 28 | 70 | Italy-Montenegro | First HVDC Module IT-ME | 4 | Investment on time |  | 2019 | 2019 | 1 | CGES;TERNA | Villanova (IT) | Lastva (ME) | Subsea Cable | DC | 500 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2019 | 2 | 5 | ITA;MNE | Villanova | Lastva | 43.0071 | 12.3278 | 42.8396 | 19.249
861 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 701 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 144 | 701 | Mid Continental East corridor | New 400 kV substation Resita (T400/220 kV 400 MVA + T 400/110 kV 250 MVA), as development of the existing 220/110 kV substation. | 3 | Investment on time | Investment has been split. It is expected that the substation will be commissioned in two stages. In TYNDP 2012, timing referred only to the adjacent lines. | 2017 | 2017 | 1 | Resita (RO) |  | 701 | New 400 kV substation Resita (T400/220 kV 400 MVA + T 400/110 kV 250 MVA), as development of the existing 220/110 kV substation. | 3 | Investment on time | Investment has been split. It is expected that the substation will be commissioned in two stages. | 2017 | 2017 | 1 | Resita (RO) |  | 144 | 701 | Mid Continental East corridor | 400 kV Substation Resita | New 400 kV substation Resita (T400/220 kV 400 MVA + T 400/110 kV 250 MVA), as development of the existing 220/110 kV substation. | 3 | Delayed | This investment is in correlation with investment no 269. | 01/ 03/ 2018 | 2018 | 1 |  | 0 | Resita (RO) | Resita (RO) | Substation |  | 350 | 400 |  | New | 144 | 701 | Mid Continental East corridor | 400 kV Substation Resita | 4 | Delayed | The works contract regarding 400 kV Resita substation was canceled at the request of the legal administrator of the executor -in insolvency. Transelectrica analyzes different options to continue and complete the works. | 2019 | 2019 | 1 |  | Resita (RO) | Resita (RO) | Substation | AC | 400 | 144 | 701 | Mid Continental East corridor | 400 kV Substation Resita | New 400 kV substation Resita (T400/220 kV 400 MVA + T 400/110 kV 250 MVA), as development of the existing 220/110 kV substation. | 4 | Delayed | The contractor responsible for the execution of the investment has gone into insolvency and thus the auction must be resumed | 2025 | 2025 | 1 | EMS TRANSELECTRICA | 3.22 | 0 | 1 | Resita (RO) | Resita (RO) | OnshoreSubstation | AC | 0 | MostlyNew | 144 | 701 | Mid Continental East corridor | 400 kV Substation Resita | New 400 kV substation Resita (T400/220 kV 400 MVA + T 400/110 kV 250 MVA), as development of the existing 220/110 kV substation. | 4 | Investment on time |  | 12-2025 | 2025 | 1 | EMS, Transelectrica | 3.22 | 0 | 1 | Resita (RO) | Resita (RO) | OnshoreSubstation | AC | 0 | 400 | 0 | MostlyNew | 144 | 701 | Mid Continental East corridor | 400 kV Substation Resita | New 400 kV substation Resita (T400/220 kV 400 MVA + T 400/110 kV 250 MVA), as development of the existing 220/110 kV substation. | 4 | Investment on time |  | 12-2025 | 2025 | 1 | EMS, Transelectrica | 3.22 Cluster Romania-Serbia [currently known as "Mid Continental East corridor''] | 0 | 1 | Resita (RO) | Resita (RO) | OnshoreSubstation | AC | 0 | 0 | 0 | MostlyNew | 144 | 701 | Mid Continental East corridor | 400 kV Substation Resita | New 400 kV substation Resita (T400/220 kV 400 MVA + T 400/110 kV 250 MVA), as development of the existing 220/110 kV substation. | 4 |  | 12-2025 | 2025 | 1 | EMS, Transelectrica | 1 | XX | XX | Mostly new | 2017 | 2025 | 8 | 11 | ROU;SRB | Resita | Resita | 45.289 | 21.8879 | 45.289 | 21.8879
862 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 705 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 144 | 705 | Mid Continental East corridor | Replacement of 220 kV substation Timisoara with 400 kV substation (2x250 MVA 400/110 kV) | 3 | Investment on time | Investments 269 and 701 have to be finalized first. | 2022 | 2022 | 1 | Timisoara (RO) |  | 705 | Replacement of 220 kV substation Timisoara with 400 kV substation (2x250 MVA 400/110 kV) | 3 | Investment on time | Investments 269 and 701 have to be finalized first. | 2022 | 2022 | 1 | Timisoara (RO) |  | 144 | 705 | Mid Continental East corridor | 400 kV Substation Timisoara | Replacement of 220 kV substation Timisoara with 400 kV substation (2x250 MVA 400/110 kV) | 3 | Delayed | Investments 269 and 701 have to be finalized first. | 31/ 12/ 2023 | 2023 | 1 |  | 0 | Timisoara (RO) | Timisoara (RO) | Substation |  | 180 | 400 |  | Upgrade | 144 | 705 | Mid Continental East corridor | 400 kV Substation Timisoara | 3 | Delayed | Delays due to correlation with other delayed infrastructure investment. | 2023 | 2023 | 1 |  | Timisoara (RO) | Timisoara (RO) | Substation | AC | 400 | 144 | 705 | Mid Continental East corridor | 400 kV Substation Timisoara | Replacement of 220 kV substation Timisoara with 400 kV substation (2x250 MVA 400/110 kV) | 3 | Delayed | Long duration of the procurement procedure, delays due to executor and the pandemic impact of COVID 19. | 2025 | 2025 | 1 | EMS TRANSELECTRICA | 3.22 | 0 | 1 | Timisoara (RO) | Timisoara (RO) | OnshoreSubstation | AC | 0 | MostlyNew | 144 | 705 | Mid Continental East corridor | 400 kV Substation Timisoara | Completion of 220 kV substation Timisoara and partially replacement with 400 kV substation (2x250 MVA 400/110 kV) | 4 | Delayed | Long duration of the procurement procedure, delays due to executor and pandemic impact of COVID 19 | 12-2026 | 2026 | 1 | EMS, Transelectrica | 3.22 | 0 | 1 | Timisoara (RO) | Timisoara (RO) | OnshoreSubstation | AC | 0 | 400 | 0 | MostlyNew | 144 | 705 | Mid Continental East corridor | 400 kV Substation Timisoara | Completion of 220 kV substation Timisoara and partially replacement with 400 kV substation (2x250 MVA 400/110 kV) | 4 | Delayed | The execution contract is terminated | 12-2028 | 2028 | 1 | EMS, Transelectrica | 3.22 Cluster Romania-Serbia [currently known as "Mid Continental East corridor''] | 0 | 1 | Timisoara (RO) | Timisoara (RO) | OnshoreSubstation | AC | 0 | 0 | 0 | MostlyNew | 144 | 705 | Mid Continental East corridor | 400 kV Substation Timisoara | Completion of 220 kV substation Timisoara and partially replacement with 400 kV substation (2x250 MVA 400/110 kV) | 4 |  | 12-2028 | 2028 | 1 | EMS, Transelectrica | 1 | XX | XX | Mostly new | 2022 | 2028 | 6 | 14 | ROU;SRB | Timisoara | Timisoara | 45.7538 | 21.2257 | 45.7538 | 21.2257
863 | 2016 | 2016 | [2016] | 707 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 147 | 707 | South Balkan (CSE9) | 239 | New 400/110 kV substation in Ohrid area connected in/out to the new 400 kV line Bitola-Elbasan. | 3 | Rescheduled | additional investigation of feasibility | 1/ 1/ 2020 | 2020 | 1 |  | 0 | Ohrid area (MK) |  | Substation |  | 0 | 400 |  | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 4 | MKD | Ohrid Area
864 | 2014 | 2016 | [2014, 2015, 2016] | 708 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 147 | 708 | CSE9 | New 400kV substation in Lagadas in Thessaloniki area. | 4 | Delayed | Delays due to environmental licensing process | 2014 | 2014 | 1 | Lagadas (GR) |  | 708 | New 400kV substation in Lagadas in Thessaloniki area. | 4 | Delayed | Delays due to environmental licensing process | 2015 | 2015 | 1 | Lagadas (GR) |  | 147 | 708 | South Balkan (CSE9) | 708 | New 400kV substation in Lagadas in Thessaloniki area. | 5 | Commissioned |  | 1/ 1/ 2016 | 2016 | 1 |  | 0 | Lagadas (GR) |  | Substation |  | 301 | 400 |  | New | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2014 | 2016 | 2 | 2 | GRC | Lagadas |  | 40.7435 | 23.0106
865 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 715 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 138 | 715 | Black Sea Corridor | To reinforce the cross-section between the Black Sea coast wind generation in Romania and Bulgaria and the consumption and storage centres to the West, the 220 kV OHL Stalpu-Teleajen-Brazi is upgraded to 400 kV, as a continuation of the 400 kV d.c. OHL Cernavoda-Stalpu. The 220/110 kV substation Stalpu is upgraded to 400/110kV (1x250MVA). | 2 | Delayed | The investment was rescheduled in correlation with project 273. | 2019 | 2019 | 1 | Stalpu (RO) |  | 715 | To reinforce the cross-section between the Black Sea coast wind generation in Romania and Bulgaria and the consumption and storage centers to the West, the 220 kV OHL Stalpu-Teleajen-Brazi is upgraded to 400 kV, as a continuation of the 400 kV d.c. OHL Cernavoda-Stalpu. The 220/110 kV substation Stalpu is upgraded to 400/110kV (1x250MVA). | 2 | Investment on time | No change of status | 2019 | 2019 | 1 | Stalpu (RO) |  | 138 | 715 | Black Sea Corridor | 220kV Stalpu substation upgrade to 400 kV | To reinforce the cross-section between the Black Sea coast wind generation in Romania and Bulgaria and the consumption and storage centers to the West, the 220 kV OHL Stalpu-Teleajen-Brazi is upgraded to 400 kV, as a continuation of the 400 kV d.c. OHL Cernavoda-Stalpu. The 220/110 kV substation Stalpu is upgraded to 400/110kV (1x250MVA). | 3 | Delayed | This project is complementing with project 273. | 31/ 12/ 2020 | 2020 | 1 |  | 0 | Stalpu (RO) | Stalpu (RO) | Substation |  | 808 | 400 |  | Upgrade | 138 | 715 | Black Sea Corridor | 220kV Stalpu substation upgrade to 400 kV | 3 | Delayed | National law changes affecting permitting, including complexities with the implementation of the new legislation implementing Regulation (EU) 347/2013 for permitting.Delays related to acquisition of and access to land. | 2020 | 2020 | 1 |  | Stalpu (RO) | Stalpu (RO) | Substation | AC | 400 | 138 | 715 | Black Sea Corridor | 220kV Stalpu substation upgrade to 400 kV | To reinforce the cross-section between the Black Sea coast wind generation in Romania and Bulgaria and the consumption and storage centers to the West, the 220 kV OHL Stalpu-Teleajen-Brazi is upgraded to 400 kV, as a continuation of the 400 kV d.c. OHL Cernavoda-Stalpu. The 220/110 kV substation Stalpu is upgraded to 400/110kV (1x250MVA). | 4 | Delayed | Delays due to the amendment of the public procurement legislation and resumption of auction due to non-compliant offers. | 2023 | 2023 | 1 | ESO TRANSELECTRICA | 3.8 | 0 | 0 | Stalpu (RO) | Stalpu (RO) | OnshoreSubstation | AC | 0 | MostlyNew | 138 | 715 | Black Sea Corridor | 220kV Stalpu substation upgrade to 400 kV | To reinforce the cross-section between the Black Sea coast wind generation in Romania and Bulgaria and the consumption and storage centers to the West, the 220 kV OHL Stalpu-Teleajen-Brazi is upgraded to 400 kV, as a continuation of the 400 kV d.c. OHL Cernavoda-Stalpu. The 220/110 kV substation Stalpu is upgraded to 400/110kV (1x250MVA). | 4 | Delayed | The contractor responsible for the construction has gone into insolvency | 12-2024 | 2024 | 1 | ESO, Transelectrica |  | 0 | 0 | Stalpu (RO) | Stalpu (RO) | OnshoreSubstation | AC | 0 | 400 | 0 | MostlyNew | 138 | 715 | Black Sea Corridor | 220kV Stalpu substation upgrade to 400 kV | The 220/110 kV substation Stalpu is upgraded to 400/110kV (1x250MVA). | 4 | Delayed | The contractor responsible for the construction has gone into insolvency | 12-2026 | 2026 | 1 | ESO, Transelectrica |  | 0 | 0 | Stalpu (RO) | Stalpu (RO) | OnshoreSubstation | AC | 0 | 400 | 0 | MostlyNew | 138 | 715 | Black Sea Corridor | 220kV Stalpu substation upgrade to 400 kV | The 220/110 kV substation Stalpu is upgraded to 400/110kV (1x250MVA). | 4 |  | 12-2027 | 2027 | 1 | ESO, Transelectrica | 0 | XX | XX | Mostly new | 2019 | 2027 | 8 | 13 | BGR;ROU | Stalpu | Stalpu | 45.0852 | 26.7084 | 45.0852 | 26.7084
866 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 720 | Cancelled | [5 empty] | 0 |  |  | 54 | 54. A127 | Erection of new 2x400 line between SK and Hungary (substation on Hungarian side still to be defined) | 1 | New investment in TYNDP | 2021 | 2021 | 1 | Veľké Kapušany (SK) | tbd (HU) | 54. A127 | 54. A127 | Erection of new 2x400 line between SK and Hungary (substation on Hungarian side still to be defined). The Investment is under consideration. | 1 |  | 2021 | 2021 | 1 | Velké Kapušany (SK) | tbd (HU) | 54 | 720 | New SK-HU intercon. - phase 2 | Erection of new 2x400 line between SK and Hungary (substation on Hungarian side still to be defined). The Investment is under consideration. | 1 | Investment on time | No change. | 2021 | 2021 | 1 | Velké Kapušany (SK) | tbd (HU) | 720 | Erection of new 2x400 line between SK and Hungary (substation on Hungarian side still to be defined). The Investment is under consideration. | 1 | Rescheduled | Investment is dependent on the future operation of the SK-UA existing cross-border line, which has been prolonged till around 2030 based on the diagnostics. | 2029 | 2029 | 1 | Veľké Kapušany (SK) | tbd (HU) | 54 | 720 | New SK-HU intercon. - phase 2 | 3. SK-HU interconnection | Erection of new 2x400 line between SK and Hungary (substation on Hungarian side still to be defined). The Investment is under consideration. | 1 | Rescheduled | Investment is dependant on the future operation of the SK-UA existing cross-border line, which has been prolongued till around 2030 based on the diagnostics. | 1/1/2029 | 2029 | 1 |  | 1 | Veľké Kapušany (SK) | Kisvárda area (HU) | Overhead Line | AC | 500 | 400 | 40 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2029 | 8 | 17 | HUN;SVK | Veké Kapuany | Kisvárda Area
867 | 2014 | 2015 | [2014, 2015] | 726 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 58 | 726 | GerPol Power Bridge | New 400 kV substation Gubin located near the PL-DE border. The substation will be connected by the new line Plewiska (PL)-Eisenhüttenstadt (DE). | 2 | Rescheduled | Change of the commissioning date as the investment is correlated with the investment 140. | 2030 | 2030 | 1 | Gubin (PL) |  | 726 | New 400 kV substation Gubin located near the PL-DE border. The substation will be conntected by the new line Plewiska (PL)-Eisenhüttenstadt (DE). | 1 | Rescheduled | The project is under consideration and will be realized if the decision on the construction of the third PL-DE line will be taken. | 2030 | 2030 | 1 | Gubin (PL) | [6 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | POL | Gubin |  | 51.9509 | 14.7293
868 | 2014 | 2015 | [2014, 2015] | 727 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 58 | 727 | GerPol Power Bridge | Construction of new substation Plewiska Bis (PL) to connect the new line Plewiska (PL)-Eisenhüttenstadt (DE). | 2 | Investment on time | The project is at the planning stage. | 2020 | 2020 | 1 | Plewiska (PL) |  | 727 | Construction of new substation Plewiska Bis (PL) to connect the new line Plewiska (PL)-Eisenhüttenstadt (DE). | 1 | Rescheduled | Due to change of plans of investments 58.140 and 58.726 this investment is also no longer associated with cross border development. However the same location for new substation is under consideration regarding the needs of local distribution operator. | 2030 | 2030 | 1 | Plewiska (PL) | [6 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2030 | 10 | 16 | POL | Plewiska |  | 52.3665 | 16.8098
869 | 2014 | 2015 | [2014, 2015] | 728 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 59 | 728 | LitPol Link Stage 1 | Construction of new substation Łomża to connect the line Ełk-Łomża. | 4 | Investment on time | The project is under construction. | 2015 | 2015 | 1 | Lomza (PL) |  | 728 | Construction of new substation Łomża to connect the line Ełk-Łomża. | 5 | Commissioned | Commissioned. | 2015 | 2015 | 1 | Łomża (PL) | [11 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 1 | POL | Oma |  | 52.2408 | 21.0239
870 | 2014 | 2015 | [2014, 2015] | 729 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 59 | 729 | LitPol Link Stage 1 | A new 400 kV switchgear in existing substation Ostroleka (in two stages) with transformation 400/220kV 500 MVA and with transformation 400/110kV 400 MVA. | 4 | Investment on time | The project is under construction. | 2015 | 2015 | 1 | Ostroleka (PL) |  | 729 | A new 400 kV switchgear in existing substation Ostroleka (in two stages) with transformation 400/220kV 500 MVA and with transformation 400/110kV 400 MVA. | 4 | Investment on time | The project is under construction. | 2015 | 2015 | 1 | Ostrołęka (PL) | [6 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 1 | POL | Ostroka
871 | 2014 | 2015 | [2014, 2015] | 730 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 59 | 730 | LitPol Link Stage 1 | New substation 400kV Stanisławów will be connected by splitting and extending existing line Miłosna-Narew and Miłosna-Siedlce. | 4 | Expected earlier than planned previously | In TYNDP 2012 the building of the substation Stanisławów was reported as part of a line Ostrołęka-Stanisławów. The commissioning time has been aligned with the construction of the line Miłosna-Siedlce Ujrzanów which is expected in 2015. | 2015 | 2015 | 1 | Stanislawów (PL) |  | 730 | New substation 400kV Stanisławów will be connected by splitting and extending existing line Miłosna-Narew and Miłosna-Siedlce. | 5 | Commissioned | Commissioned. | 2015 | 2015 | 1 | Stanisławów (PL) | [11 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 1 | POL | Stanisawów
872 | 2012 | 2020 | [2012, 2013, 2014, 2015, 2016, 2018, 2020] | 733 | Cancelled | [5 empty] | 0 |  |  | 60 | 60. A52 | New single circuit 400 kV OHL | 1 | New investment in TYNDP | 2019 | 2019 | 1 | Ekhyddan (SE) | Nybro/Hemsjö (SE) | 60. A52 | 60. A52 | New single circuit 400 kV OHL | 2 | Rescheduled, thanks to postponement, other internal investments will be commissioned on time. Congestions due to the delay will be handled by investing in a system protection scheme. | 2023 | 2023 | 1 | Ekhyddan (SE) | Nybro/Hemsjö (SE) | 124 | 733 | NordBalt phase 2 | New single circuit 400 kV OHL. A key investment to accomplish full utilization of the NordBalt cable between Lithuania and Sweden (project 60) at all times. | 2 | Rescheduled | Thanks to postponement, other internal investments will be commissioned on time. Congestions due to the delay will be handled by investing in a temporary system protection scheme. | 2021 | 2021 | 1 | Ekhyddan (SE) | Nybro/Hemsjö (SE) | 733 | New single circuit 400 kV OHL. A key investment to accomplish full utilization of the NordBalt cable between Lithuania and Sweden (project 60) at all times. | 3 | Delayed | Main reasons for delay are:- Permission for access to land corridor for the grids planned route from land owners more difficult than previous foreseen. -Svenska kraftnät has changed estimated time for the permission process due to new information. | 2023 | 2023 | 1 | Ekhyddan (SE) | Nybro/Hemsj ö (SE) | 124 | 733 | NordBalt phase 2 | Ekhyddan-Nybro-Hemsjö | Second phase includes the internal network reinforcements in Sweden to be able to fully utilize the interconnector between Lithuania and Sweden. | 3 | Rescheduled | Commissioning date is current estimation | 2023 | 2023 | 1 |  | 0 | Ekhyddan (SE) | Nybro/Hemsjö (SE) | Overhead Line | AC | 700 | 400 | 160 | New | 124 | 733 | NordBalt phase 2 | Ekhyddan-Nybro-Hemsjo | 3 | Investment on time |  | 2023 | 2023 | 1 |  | Ekhyddan (SE) | Nybro/Hemsjo (SE) | Overhead Line | AC | 400 | 124 | 733 | NordBalt phase 2 | Ekhyddan-Nybro-Hemsjo | Second phase includes the internal network reinforcements in Sweden to be able to fully utilize the interconnector between Lithuania and Sweden. The internal reinforcement consists of the new 400 kV single circuit overhead transmission line between Ekhyddan-Nybro-Hemsjo. | 3 | Delayed | Permit denied. Appeal process ongoing | 2026 | 2026 | 1 | AST Lietuvos energijos gamyba, AB Svenska Kraftnät LITGRID AB | 4.4 | 1 | 1 | Ekhyddan (SE) | Nybro/Hemsjo (SE) | ACTransmissionLine | AC | 160 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2026 | 7 | 14 | LTU;LVA;SWE | Ekhyddan | Nybrohemsjo | 59.3996 | 18.1538
873 | 2010 | 2020 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020] | 735 | Commissioned | 388 | New single circuit 400 ÷ 220 OHL. (Capacity 1200 MVA, 140-160km). Major part of new internal connection will be established on existing right of way on the Western part of Estonian mainland and the line voltage will be 330kV. | 2 | 2018 | 2018 | 1 | Harku (EE) | Sindi (EE) | 62 | 62. 388 | New double circuit OHL with 2 different voltages 330 kV and 110 kV and with capacity 1200 MVA/240 MVA and a length 140 km. Major part of new internal connection will be established on existing right of way on the Western part of Estonian mainland. | 3 | Progresses as planned | 2018 | 2018 | 1 | Harku (EE) | Sindi (EE) | 62. 388 | 62. 388 | New double circuit OHL with 2 different voltages 330 kV and 110 kV and with capacity 1200 MVA/240 MVA and a length 140 km. Major part of new internal connection will be established on existing right of way on the Western part of Estonian mainland. 110kV circuit. | 3 |  | 2018 | 2018 | 1 | Harku (EE) | Sindi (EE) | 62 | 735 | Estonia-Latvia 3rd IC | New double circuit OHL with 2 different voltages 330 kV and 110 kV and with capacity 1200 MVA/240 MVA and a length 140 km. Major part of new internal connection will be established on existing right of way on the western part of Estonian mainland. | 3 | Investment on time | Progress as planned. | 2018 | 2018 | 1 | Harku (EE) | Sindi (EE) | 735 | New double circuit OHL with 2 different voltages 330 kV and 110 kV and with capacity 1143 MVA/240 MVA and a length 175 km. Major part of new internal connection will be established on existing right of way on the western part of Estonian mainland.The investment helps together with 3rd EE-LV interconnector to increase interarea capacity up to 600 MW. | 3 | Rescheduled | Svenska kraftnät has changed estimated time for the permission process due to new information. | 2020 | 2020 | 1 | Harku (EE) | Sindi (EE) | 62 | 735 | Estonia-Latvia 3rd IC | Harku-Sindi 330kV OHL | New double circuit OHL with 2 different voltages 330 kV and 110 kV and with capacity 1143 MVA/240 MVA and a length 175 km. Major part of new internal connection will be established on existing right of way on the western part of Estonian mainland.The investment helps together with 3rd EE-LV interconnector to increase interarea capacity up to 600 MW. | 3 | Investment on time | Planning phase finsished in 2016 | 31/ 12/ 2020 | 2020 | 1 |  | 0 | Harku (EE) | Sindi (EE) | Overhead Line | AC | 600 | 330 | 175 | New | 62 | 735 | Estonia-Latvia 3rd IC | Harku-Sindi 330kV OHL | 4 |  |  | 31/ 12/ 2020 | 2020 | 1 |  | Harku (EE) | Sindi (EE) | Overhead Line | AC | 330 | 62 | 735 | Estonia-Latvia 3rd IC | Harku-Sindi 330kV OHL | New double circuit OHL with 2 different voltages 330 kV and 110 kV and with capacity 1143 MVA/240 MVA and a length 175 km. Major part of new internal connection will be established on existing right of way on the western part of Estonian mainland.The investment helps together with 3rd EE-LV interconnector to increase interarea capacity up to 600 MW. | 4 | Investment on time |  | 2021 | 2021 | 1 | AST ELERING | 4.2 | 0 | 1 | Harku (EE) | Sindi (EE) | ACTransmissionLine | AC | 175 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2021 | 3 | 11 | EST;LVA | Harku | Sindi | 59.3855 | 24.5826 | 58.4075 | 24.6583
874 | 2014 | 2015 | [2014, 2015] | 739 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 64 | 739 | N-S Finland (P1) stage 1 | Second line part of the four new single circuit 400kV OHL are part of project in upgrading Ostrobothnian 220kV system into 400kV, and strengthening the 400 kV grid in Northern Finland. total length of lines: 520 km. Total Expected capacity: 1850 MVA. | 4 | Investment on time | Investment progresses as planned | 2014 | 2014 | 1 | Ulvila (FI) | Kristinestad (FI) | 739 | Second line part of the four new single circuit 400kV OHL are part of project in upgrading Ostrobothnian 220kV system into 400kV, and strengthening the 400 kV grid in Northern Finland. total length of lines: 520 km. Total Expected capacity: 1850 MVA. | 5 | Commissioned | Investment progresses as planned | 2014 | 2014 | 1 | Ulvila (FI) | Kristinestad (FI) | [10 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2014 | 2014 | 0 | 0 | FIN | Ulvila | Kristinestad | 61.4333 | 21.8833 | 62.2742 | 21.3772
875 | 2012 | 2015 | [2012, 2013, 2014, 2015] | 740 | Commissioned | [5 empty] | 0 |  |  | 64 | 64. 393 | Four new single circuit 400kV OHL are part of project in upgrading Ostrobothnian 220kV system into 400kV, and strengthening the 400 kV grid in Northern Finland. Commissioning of first section in year 2011, second in 2014 third in ca. 2018 and fourth ca. 2020. total length of lines: 520 km. Expected capacity: 1850 MVA. | 4 | Project has progressed as planned. Since TYNDP 2010 Seinäjoki-Tuovila has been constructed and Ulvila-Kristinestad has progressed to design and permitting phase. Keminmaa-Pyhänselkä is now presented as a separate investment item. | 2011/2020 | 2020 | 1 | Seinäjoki Ulvila Ventusneva (FI) | Tuovila (FI) Kristinestad (FI) Pyhänselkä (FI) | 64. 393 | 64. 393 | Third line part of the four new single circuit 400kV OHL are part of project in upgrading Ostrobothnian 220kV system into 400kV, and strengthening the 400 kV grid in Northern Finland. total length of lines: 520 km. Total Expected capacity: 1850 MVA. | 3 | Station name updated from Ventusneva to Hirvisuo. Investment decision has been made and schedule has been updated. | 2016 | 2016 | 1 | Hirvisuo (FI) | Pyhänselkä (FI) | 64 | 740 | N-S Finland (P1) stage 1 | Third line part of the four new single circuit 400kV OHL are part of project in upgrading Ostrobothnian 220kV system into 400kV, and strengthening the 400 kV grid in Northern Finland. total length of lines: 520 km. Total Expected capacity: 1850 MVA. | 3 | Expected earlier than planned previously | Station name updated from Ventusneva to Hirvisuo. Investment decision has been made and schedule has been updated. | 2016 | 2016 | 1 | Hirvisuo (FI) | Pyhänselkä (FI) | 740 | Third line part of the four new single circuit 400kV OHL are part of project in upgrading Ostrobothnian 220kV system into 400kV, and strengthening the 400 kV grid in Northern Finland. total length of lines: 520 km. Total Expected capacity: 1850 MVA. | 4 | Investment on time | Station name updated from Ventusneva to Hirvisuo. Investment decision has been made and schedule has been updated. | 2016 | 2016 | 1 | Hirvisuo (FI) | Pyhänselkä (FI) | [5 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2016 | -4 | 4 | FIN | Hirvisuo | Pyhänselkä | 60.2197 | 24.6321
876 | 2014 | 2020 | [2014, 2015, 2016, 2018, 2020] | 742 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 197 | 742 | N-S Finland P1 stage 2 | New single circuit 400 kV OHLs will be built from middle Finland to Oulujoki Area to increase the capacity between North and South Finland. Will replace existing 220 kV lines. | 3 | Delayed | Rescheduled due to timing of system changes that trigger the investment. End station name updated. | 2023 | 2023 | 1 | Pyhänselkä (FI) | Petäjävesi (FI) | 742 | New single circuit 400 kV OHLs will be built from middle Finland to Oulujoki Area to increase the capacity between North and South Finland. Will replace existing 220 kV lines. | 3 | Investment on time | Progresses as planned | 2023 | 2023 | 1 | Pyhänselkä (FI) | Petäjävesi (FI) | 197 | 742 | N-S Finland P1 stage 2 | Pyhänselkä-Petäjävesi | New single circuit 400 kV OHLs will be built from middle Finland to Oulujoki Area to increase the capacity between North and South Finland. Will replace existing 220 kV lines. | 3 | Investment on time | Progresses as planned | 1/ 1/ 2023 | 2023 | 1 |  | 0 | Pyhänselkä (FI) | Petäjävesi (FI) | Overhead Line | AC | 1000 | 400 | 320 | New | 197 | 742 | N-S Finland P1 stage 2 | Pyhanselka-Petajavesi | 3 | Investment on time |  | 1/ 7/ 2022 | 2022 | 1 | FINGRID | Pyhanselka (FI) | Petajavesi (FI) | Overhead Line | AC | 400 | 197 | 742 | N-S Finland P1 stage 2 | Pyhanselka-Petajavesi | New single circuit 400 kV OHLs will be built from middle Finland to Oulujoki Area to increase the capacity between North and South Finland. Substations to connect wind farms in the region are also in consideration. | 4 | Investment on time |  | 2022 | 2022 | 1 | FINGRID |  | 1 | 0 | Pyhanselka (FI) | Petajavesi (FI) | ACTransmissionLine | AC | 300 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2022 | -1 | 8 | FIN | Pyhanselka | Petajavesi |  |  | 62.2505 | 25.2005
877 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 747 | Cancelled | [5 empty] | 0 |  |  | 69 | 69. 424j | New 400kV double circuit | 3 | Delayed by one year to 2018/19 due to an anticipated slower growth in the uptake of wind. | 2018/2019 | 2019 | 1 | Bramford (GB) | Twinstead (GB) | 69. 424j | 69. 424j | Construction of a new transmission route from Bramford to the Twinstead Tee Point creating Bramford - Pelham and Bramford - Braintree - Rayleigh Main double circuits; the rebuild of Bramford substation and the installation of an MSC at Barking. | 3 |  | 2019 | 2019 | 1 | Bramford (GB) | Twinstead (GB) | 69 | 747 | East Anglia Cluster | Construction of a new transmission route from Bramford to the Twinstead Tee Point creating Bramford - Pelham and Bramford - Braintree - Rayleigh Main double circuits; the rebuild of Bramford substation and the installation of an MSC at Barking. | 3 | Investment on time | Delay in project requirement due to generation going back. | 2022 | 2022 | 1 | Bramford (GB) | Twinstead (GB) | 747 | Construction of a new transmission route from Bramford to the Twinstead Tee Point creating Bramford - Pelham and Bramford - Braintree - Rayleigh Main double circuits; the rebuild of Bramford substation and the installation of an MSC at Barking. | 3 | Delayed | Delay in project requirement due to generation going back. | 2023 | 2023 | 1 | Bramford (GB) | Twinstead (GB) | 69 | 747 | East Anglia Cluster | Bramford - Twinstead | Construction of a new transmission route from Bramford to the Twinstead Tee Point creating Bramford - Pelham and Bramford - Braintree - Rayleigh Main double circuits; the rebuild of Bramford substation and the installation of an MSC at Barking. | 3 | Delayed | Delay in project requirement due to generation going back. | 1/ 1/ 2023 | 2023 | 1 |  | 0 | Bramford (GB) | Twinstead (GB) | Overhead Line | AC | 1950 | 400 | 35 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2023 | 4 | 11 | GBR | Bramford | Twinstead | 52.0754 | 1.1006 | 51.9965 | 0.70873
878 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 75 | Commissioned | 75 | New 90km double circuit 400kV line, partly via subsea cable and partly via OHL. This line is part of a larger project that foresees the creation of the future 400kV ring grid of Sicily. | 4 | 2013 | 2013 | 1 | Sorgente (IT) | Rizziconi (IT) | 30 | 30. 75 | New 90km double circuit 400kV line, partly via subsea cable and partly via OHL. This line is part of a larger project that foresees the creation of the future 400kV ring grid of Sicily. | 4 | Delays on construction phase | 2014 | 2014 | 1 | Sorgente (IT) | Rizziconi (IT) | 30. 75 | 30. 75 | New 90km double circuit 400kV line, partly via subsea cable and partly via OHL. This line is part of a larger project that foresees the creation of the future 400kV ring grid of Sicily. | 4 | Rescheduling of 6 months work due to technical issues during construction phase | 2015 | 2015 | 1 | Sorgente (IT) | Rizziconi (IT) | 30 | 75 | 30 | New 90km double circuit 400kV line, partly via subsea cable and partly via OHL. This line is part of a larger project that foresees the creation of the future 400kV grid of Sicily. | 4 | Delayed | rescheduling of 6 months work due to technical issues during construction phase | 2015 | 2015 | 1 | Sorgente (IT) | Rizziconi (IT) | 75 | New 90km double circuit 400kV line, partly via subsea cable and partly via OHL. This line is part of a larger project that foresees the creation of the future 400kV grid of Sicily. | 4 | Investment on time | Progressed as planned | 2015 | 2015 | 1 | Sorgente (IT) | Rizziconi (IT) | [5 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2013 | 2015 | 2 | 5 | ITA | Sorgente | Rizziconi
879 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 752 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 75 | 752 | Stevin (backbone)+BE offshore | Belgian Offshore Grid (BOG) The Belgian Offshore Grid investment consists of the eruption of an offshore hub connected to onshore AC grid (at Zeebrugge) via underground cables, including the necessary reactive compensation for the cables. Subject to result of ongoing design, legal, ownership & regulatory concertation with stakeholders. | 3 | Delayed | 2018 is the earliest possible date: project is subject to outcome of ongoing design, legal, ownership & regulatory framework concertation with stakeholders. | 2018 | 2018 | 1 | Offshore hub (BE) | Stevin (Zeebrugge) | 752 | The Belgian Offshore Grid envisions the eruption of an offshore hub connected to onshore AC grid (at Zeebrugge) via underground cables, including the necessary reactive compensation for the cables. BOG is subject to the result of ongoing design, legal, ownership & regulatory concertation with stakeholders and presented here into the extent that it would be considered as regulated infrastructure. | 3 | Investment on time | 2018 refers to 1st step in modular construction of an offshore hub. Further evolution subject of ongoing alignment with wind farm developers. BOG is presented here into the extent that it would be considered as regulated infrastructure. | 2018 | 2018 | 1 | Offshore platform(s) | Stevin (Zeebrugge) | 75 | 752 | STEVIN & Modular Offshore Grid | Modular Offshore Grid | The Modular Offshore Grid envisions the modular creation of the offshore infrastructure for the integration of the wind farms of four offshore wind farms in the Belgian part of the North Sea. The offshore infrastructure would then consist of an offshore hub to centralize the production from these offshore wind farms, and then transport it via 220 kV subsea AC cables to the onshore substation Stevin at Zeebrugge. | 3 | Rescheduled | 2019 refers to 1st step in modular construction of an offshore hub. Subject of ongoing alignment with wind farm developers and competent authorities. MOG is presented here into the extent that it would be considered as regulated infrastructure. | 01/01/2019 | 2019 | 1 |  | 0 | Offshore platform(s) | Stevin (Zeebrugge) | Subsea Cable | AC | 1835 | 220 | 50 | New | 75 | 752 | Modular Offshore Grid (MOG) | Modular Offshore Grid | 4 | Investment on time |  | 2020 | 2020 | 1 | ELIA | Offshore platform | Stevin (Zeebrugge) | Subsea Cable | AC | 220 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2020 | 2 | 6 | BEL | Platform | Stevin |  |  | 51.2065 | 3.2226
880 | 2012 | 2015 | [2012, 2013, 2014, 2015] | 753 | Cancelled | [5 empty] | 0 |  |  | 76 | 76. A42 | Reconductor Pelham-Rye House-Waltham Cross | 3 | New investment in TYNDP | 2015/2016 | 2016 | 1 | Pelham (GB) | Waltham Cross (GB) | 76. A42 | 76. A42 | Reconductor the existing circuit which runs from Pelham - Rye House - Waltham Cross with a higher rated conductor. | 3 |  | 2016 | 2016 | 1 | Pelham (GB) | Waltham Cross (GB) | 76 | 753 | London Cluster | Reconductoring the existing circuit which runs from Pelham - Rye House - Waltham Cross with a higher rated conductor. | 3 | Delayed | Postponed due to the slow build up of generation in the East Anglia area and also in demand within London. | 2021 | 2021 | 1 | Pelham (GB) | Waltham Cross (GB) | 753 | Reconductor the existing circuit which runs from Pelham - Rye House - Waltham Cross with a higher rated conductor. | 6 | Cancelled | Cancelled due to the slow build-up of generation in the East Anglia area and also in demand within London. |  |  | 1 | Pelham (GB) | Waltham Cross (GB) | [10 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 |  |  |  | GBR | Pelham | Waltham Cross | 50.7233 | -1.9104 | 51.6858 | -0.033
881 | 2012 | 2015 | [2012, 2013, 2014, 2015] | 754 | Cancelled | [5 empty] | 0 |  |  | 76 | 76. A43 | Uprate to 400kV Hackney-Tottenham-Waltham Cross | 3 | New investment in TYNDP | 2015/2016 | 2016 | 1 | Hackney (GB) | Waltham Cross (GB) | 76. A43 | 76. A43 | Uprating and reconductoring of the Hackney - Tottenham - Brimsdown - Waltham Cross double circuits. Construction of a new 400kV substation at Waltham Cross and modifications to the Tottenham substation and the installation of two new transformers at Brimsdown substation. | 3 |  | 2016 | 2016 | 1 | Hackney (GB) | Waltham Cross (GB) | 76 | 754 | London Cluster | Uprating and Reconductoring of the Hackney - Tottenham - Brimsdown - Waltham Cross double circuits. Construction of a new 400kV substation at Waltham Cross and modifications to the Tottenham substation and the installation of two new transformers at Brimsdown substation. | 3 | Delayed | Postponed due to the build up of generation schemes in the East Anglia area and demand increases in London. | 2021 | 2021 | 1 | Hackney (GB) | Waltham Cross (GB) | 754 | Uprating and reconductoring of the Hackney - Tottenham - Brimsdown - Waltham Cross double circuits. Construction of a new 400kV substation at Waltham Cross and modifications to the Tottenham substation and the installation of two new transformers at Brimsdown substation. | 4 | Rescheduled | Postponed due to the build-up of generation schemes in the East Anglia area and demand increases in London. | 2022 | 2022 | 1 | Hackney (GB) | Waltham Cross (GB) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2022 | 6 | 10 | GBR | Hackney | Waltham Cross | 51.5432 | -0.049362 | 51.6858 | -0.033
882 | 2012 | 2015 | [2012, 2013, 2014, 2015] | 755 | Cancelled | [5 empty] | 0 |  |  | 76 | 76. A44 | New 400kV St. John's Wood-Hackney double circuit | 3 | New investment in TYNDP | 2017/2018 | 2018 | 1 | Hackney (GB) | St. John's Wood (GB) | 76. A44 | 76. A44 | New Hackney - St. John's Wood 400kV double circuit. | 3 |  | 2018 | 2018 | 1 | Hackney (GB) | St. John's Wood (GB) | 76 | 755 | London Cluster | This is a new Hackney - St. John's Wood 400kV double circuit. It will replace an old asset rated at 275kV that has come to the end of its life. | 4 | Investment on time | Investment on time | 2018 | 2018 | 1 | Hackney (GB) | St. John's Wood (GB) | 755 | This is a new Hackney - St. John's Wood 400kV double circuit. It will replace an old asset rated at 275kV that has come to the end of its life. | 4 | Rescheduled | Reschedules due to changes in generation background | 2022 | 2022 | 1 | Hackney (GB) | St. John's Wood (GB) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2022 | 4 | 10 | GBR | Hackney | St. Johns Wood | 51.5432 | -0.049362 | 51.4465 | -2.3878
883 | 2012 | 2015 | [2012, 2013, 2014, 2015] | 757 | Cancelled | [5 empty] | 0 |  |  | 76 | 76. A46 | New 400kV St. John's Wood-Wimbledon cables | 3 | New investment in TYNDP | 2017/2018 | 2018 | 1 | St. John's Wood (GB) | Wimbledon (GB) | 76. A46 | 76. A46 | New St. John's Wood - Wimbledon 400kV double circuit. | 3 |  | 2018 | 2018 | 1 | St. John's Wood (GB) | Wimbledon (GB) | 76 | 757 | London Cluster | New St. John's Wood - Wimbledon 400kV double circuit. | 3 | Investment on time | Investment on time | 2018 | 2018 | 1 | St. John's Wood (GB) | Wimbledon (GB) | 757 | New St. John's Wood - Wimbledon 400kV double circuit. | 4 | Investment on time | Investment on time | 2018 | 2018 | 1 | St. John's Wood (GB) | Wimbledon (GB) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2018 | 0 | 6 | GBR | St. Johns Wood | Wimbledon | 51.4465 | -2.3878 | 51.4215 | -0.2064
884 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 769 | Cancelled | [5 empty] | 0 |  |  | 79 | 79. 459b | New HVDC bipolar interconnection with possible offshore connection points at the Irish Sea offshore wind farm. | 2 | Design Change – The design of the HVDC reinforcement circuit from Wylfa has changed from that in the TYNDP 2010 to now terminate at Pembroke instead of Mid-Wales. This has the potential to save some onshore consenting challenges. Additional benefits may be realised by coordinating the development of the offshore transmission assets with that of the onshore system. The location of the Wylfa HVDC termination may yet move offshore to be located closer to the wind turbines. The expected commissioning date has remained at 2020. | 2020/21 | 2020 | 1 | Wylfa (GB) | Pembroke (GB) | 79. 459b | 79. 459b | A new ~2GW submarine HVDC cable route from Wylfa/Irish Sea to Pembroke with associated AC network reinforcement works at both ends. | 2 | Rescheduled due to anticipated changes in the local generation background. | 2022 | 2022 | 1 | Wylfa (GB) | Pembroke (GB) | 79 | 769 | Wales Cluster | A new ~2GW submarine HVDC cable route from Wylfa/Irish Sea to Pembroke with associated AC network reinforcement works at both ends. | 2 | Rescheduled | Delayed due to anticipated changes in the local generation background. | 2025 | 2025 | 1 | Wylfa (GB) | Pembroke (GB) | 769 | A new ~2GW submarine HVDC cable route from Wylfa/Irish Sea to Pembroke with associated AC network reinforcement works at both ends. | 1 | Investment on time | Progressed as planned | 2024 | 2024 | 1 | Wylfa (GB) | Pembroke (GB) | 79 | 769 | Wales Cluster | WYLF-PEMB HVDC Link | A new ~2GW submarine HVDC cable route from Wylfa/Irish Sea to Pembroke with associated AC network reinforcement works at both ends. | 1 | Investment on time | Delayed due to anticipated changes in the local generation background. | 1/ 1/ 2024 | 2024 | 1 |  | 0 | Wylfa (GB) | Pembroke (GB) | Subsea Cable | DC | 2000 | 500 | 260 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2024 | 4 | 12 | GBR | Wylfa | Pembroke | 53.2267 | -4.1352 | 51.674 | -4.9087
885 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 779 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 85 | 779 | Integration of RES in Alentejo | New 122km double-circuit 400+150 kV OHL F. Alentejo-Ourique-Tavira. The realization of this connection can take advantage of some already existing 150kV single lines, which can be reconstructed as double circuit line 400+150kV, investments needs the investment which consist of the extension of existing Ourique substation to include 400 kV facilities. | 2 | Rescheduled | Due to the expected delay on the connection of new RES in Portugal, the commissioning date of this project is delayed | 2025 | 2025 | 1 | F. Alentejo (by Ourique) | Tavira (by Ourique) | 779 | New 122km double-circuit 400+150 kV OHL F. Alentejo- Ourique-Tavira. The realization of this connection can take advantage of some already existing 150kV single lines, which can be reconstructed as double circuit line 400+150kV, investments needs the investment which consist of the extension of existing Ourique substation to include 400 kV facilities. | 2 | Investment on time | Project on time | 2025 | 2025 | 1 | F. Alentejo (by Ourique) | Tavira (by Ourique) | 85 | 779 | Integration of RES in Alentejo | F.Alentejo-Ourique-Tavira | New 107 km double-circuit 400+150 kV OHL F. Alentejo-Ourique-Tavira. The realization of this connection can take advantage of some already existing 150kV single lines, which can be reconstructed as double circuit line 400+150kV, investments needs the investment which consist of the extension of existing Ourique substation to include 400 kV facilities. | 2 | Investment on time | Project on time | 31/ 12/ 2025 | 2025 | 1 |  | 0 | F. Alentejo (by Ourique) | Tavira (by Ourique) | Overhead Line | AC | 1400 | 400 | 107 | Upgrade | 85 | 779 | Integration of RES in Alentejo | F.Alentejo-Ourique-Tavira | 2 | Investment on time |  | 2024-2026 | 2026 | 1 | REN | F. Alentejo (by Ourique) | Tavira (by Ourique) | Overhead Line | AC | 400 | 85 | 779 | Integration of RES in Alentejo | F.Alentejo-Ourique-Tavira | New double-circuit 400+150 kV OHL F. Alentejo-Ourique-Tavira. The realization of this connection can take advantage of some already existing 150kV single lines, which can be reconstructed as double circuit line 400+150kV. | 2 | Ahead of time |  | 2023 | 2023 | 1 | Rede Elétrica Nacional |  | 1 | 0 | F. Alentejo (by Ourique) | Tavira (by Ourique) | ACTransmissionLine | AC | 122 | MostlyUpgrade | 85 | 779 | Integration of RES in Alentejo | F.Alentejo-Ourique-Tavira | New double-circuit 400+150 kV OHL F. Alentejo-Ourique-Tavira. The realization of this connection can take advantage of some already existing 150kV single lines, which can be reconstructed as double circuit line 400+150kV. | 3 | Investment on time |  | 02-2023 | 2023 | 1 | Rede Elétrica Nacional |  | 1 | 0 | F. Alentejo (by Ourique) | Tavira (by Ourique) | ACTransmissionLine | AC | 0 | 400 | 122 | MostlyUpgrade | 85 | 779 | Integration of RES in Alentejo | F.Alentejo-Panóias-Ourique-Tavira | New double-circuit 400+150 kV OHL F. Alentejo-Panóias-Ourique-Tavira. The realization of this connection can take advantage of some already existing 150kV single lines, which can be reconstructed as double circuit line 400+150kV. | 4 | Delayed | Delays in permitting and construction | 12-2024 | 2024 | 1 | Rede Elétrica Nacional |  | 1 | 0 | F. Alentejo (by Panóias\Ourique) | Tavira (by Panóias\Ourique) | ACTransmissionLine | AC | 0 | 400 | 126.441 | MostlyUpgrade | 85 | 779 | Integration of RES in Alentejo | F.Alentejo-Panóias-Ourique-Tavira | New double-circuit 400+150 kV OHL F. Alentejo-Panóias-Ourique-Tavira. The realization of this connection can take advantage of some already existing 150kV single lines, which can be reconstructed as double circuit line 400+150kV. | 5 | Commissioned | 12-2024 | 2024 | 1 | Rede Elétrica Nacional | 0 | XX | XX | Mostly upgrade | 2025 | 2024 | -1 | 10 | PRT | F. Alentejo | Tavira | 41.1641 | -8.1115 | 37.1262 | -7.6499
886 | 2014 | 2022 | [2014, 2015, 2016, 2018, 2020, 2022] | 780 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 85 | 780 | Integration of RES in Alentejo | Extension of existing Ourique substation to include 400 kV facilities. | 2 | Rescheduled | Due to the expected delay on the connection of new RES in Portugal, the commissioning date of this project is delayed | 2025 | 2025 | 1 | Ourique (PT) |  | 780 | Extension of existing Ourique substation to include 400 kV facilities. | 2 | Investment on time | Project on time | 2025 | 2025 | 1 | Ourique (PT) |  | 85 | 780 | Integration of RES in Alentejo | Extension of Ourique | Extension of existing Ourique substation to include 400 kV facilities. | 2 | Investment on time | Project on time | 31/ 12/ 2024 | 2024 | 1 |  | 0 | Ourique (PT) |  | Substation |  | 1400 | 400 |  | Upgrade | 85 | 780 | Integration of RES in Alentejo | Extension of Ourique substation | 2 | Investment on time |  | 2024-2026 | 2026 | 1 | REN | Ourique (PT) | - | Substation | AC | 400 | 85 | 780 | Integration of RES in Alentejo | Extension of Ourique substation | Extension of existing Ourique substation to include 400 kV facilities. | 2 | Ahead of time |  | 2023 | 2023 | 1 | Rede Elétrica Nacional |  | 1 | 0 | Ourique (PT) | - | OnshoreSubstation | AC | 0 | MostlyUpgrade | 85 | 780 | Integration of RES in Alentejo | Extension of Ourique substation | Extension of existing Ourique substation to include 400 kV facilities. | 3 | Investment on time |  | 02-2023 | 2023 | 1 | Rede Elétrica Nacional |  | 1 | 0 | Ourique (PT) | - | OnshoreSubstation | AC | 0 | 400 | 0 | MostlyUpgrade | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2023 | -2 | 9 | PRT | Ourique |  | 37.6511 | -8.2237
887 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 781 | Cancelled | [5 empty] | 0 |  |  | 86 | 86. A49 | KEAD-KILL KILL-SHBA KEAD-GRIW circuit uprate | 1 | New investment in TYNDP | long term |  | 1 | Keadby (GB) | Grimsby West (GB) | 86. A49 | 86. A49 | A very high level indication of the works required for GB East Coast. In detail the projects will consist of multiple offshore HVDC and AC circuits and connecting platforms joining to multiple onshore connection points with their own reinforcement requirements. | 1 |  | 2022 | 2022 | 1 | Under Consideration (GB) 1 | Under Consideration (GB) 1 | 86 | 781 | East Coast Cluster | A very high level indication of the works required for GB East Coast. In detail the projects will consist of multiple offshore HVDC and AC circuits and connecting platforms joining to multiple onshore connection points with their own reinforcement requirements. It enables significant connection of offshore windfarms and provides alternative to onshore reinforcement at a cheaper overall cost. | 1 | Investment on time | Investment on time | 2023 | 2023 | 1 | Under Consideration (GB) 1 | Under Consideration (GB) 1 | 781 | A very high level indication of the works required for GB East Coast. In detail the projects will consist of multiple offshore HVDC and AC circuits and connecting platforms joining to multiple onshore connection points with their own reinforcement requirements. It enables significant connection of offshore windfarms and provides alternative to onshore reinforcement at a cheaper overall cost. | 1 | Rescheduled | Changes on the generation background | 2026 | 2026 | 1 | Under Consideratio n (GB) | Under Consideratio n (GB) | 86 | 781 | East Coast Cluster | East Coast Offshore | A very high level indication of the works required for GB East Coast. In detail the projects will consist of multiple offshore HVDC and AC circuits and connecting platforms joining to multiple onshore connection points with their own reinforcement requirements. It enables significant connection of offshore windfarms and provides alternative to onshore reinforcment at a cheaper overall cost. | 1 | Rescheduled | Investment on time | 1/ 1/ 2026 | 2026 | 1 |  | 0 | Under Consideration (GB) | Under Consideration (GB) | Subsea Cable | AC | 3000 | 400 | 500 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2026 |  | 14 | GBR | Under Consideration | Under Consideration
888 | 2012 | 2016 | [2012, 2013, 2014, 2015, 2016] | 782 | Cancelled | [5 empty] | 0 |  |  | 86 | 86. A50 | Connection of Triton Knoll, Doggerbank & Hornsea GB Wind Farms and all associated works | 1 | This investment groups former 424b, 424c, 424d, 424e, 424f, 424g, 424h and 424i investments of TYNDP 2010. The group of projects on the east coast of Great Britain has been removed as work is in progress to optimize the onshore/offshore coordination and reduce potential consenting issues. Given the potential for more than 20 GW of renewable offshore generation capacity in UK waters on the East Coast it is expected that multiple connection sites will be required together with suitable circuit capacity, both onshore and offshore. | long term |  | 1 | Under Consideration (GB East Coast) | Under Consideration (GB East Coast) | 86. A50 | 86. A50 | Connection of Triton Knoll, Doggerbank & Hornsea GB Wind Farms and all associated works. | 1 |  | 2022 | 2022 | 1 | Under Consideration (GB) 2 | Under Consideration (GB) 2 | 86 | 782 | East Coast Cluster | Connection of Triton Knoll, Doggerbank & Hornsea GB Wind Farms and all associated works. This is in the region of 11GW of offshore generation. | 1 | Investment on time | Investment on time | 2020 | 2020 | 1 | Under Consideration (GB) 2 | Under Consideration (GB) 2 | 782 | Connection of Triton Knoll, Doggerbank & Hornsea GB Wind Farms and all associated works. This is in the region of 11GW of offshore generation. | 1 | Rescheduled | Rescheduled due to changes in the generation timescales. | 2026 | 2026 | 1 | Under Consideratio n (GB) | Under Consideratio n (GB) | 86 | 782 | East Coast Cluster | East Coast Offshore | Connection of Triton Knoll, Doggerbank & Hornsea GB Wind Farms and all associated works. This is in the region of 11GW of offshore generation. | 1 | Rescheduled | Rescheduled due to changes in the generation timescales. | 1/ 1/ 2026 | 2026 | 1 |  | 0 | Under Consideration (GB) | Under Consideration (GB) | Subsea Cable | AC | 3000 | 400 | 500 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2026 |  | 14 | GBR | Under Consideration | Under Consideration
889 | 2015 | 2015 | [2015] | 786 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 |  |  | 786 | New 85 km single circuit 400kV OHL. The investment is a part of investment 403 | 1 | Investment on time | Progressed as planned | 2021 | 2021 | 1 | Ängsberg (SE) | Horndal (SE) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2021 | 0 | 6 | SWE | Ängsberg | Horndal | 60.6241 | 16.9939 | 60.2914 | 16.4022
890 | 2015 | 2015 | [2015] | 787 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 |  |  | 787 | New 90 km single circuit 400kV OHL | 1 | Investment on time | Progressed as planned | 2021 | 2021 | 1 | Horndal (SE) | Dingtuna (SE) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2021 | 0 | 6 | SWE | Horndal | Dingtuna | 60.2914 | 16.4022 | 59.5724 | 16.3887
891 | 2015 | 2015 | [2015] | 788 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 |  |  | 788 | New 50km single circuit 400kV OHL | 1 | Investment on time | Progressed as planned | 2023 | 2023 | 1 | Hamra (SE) | Dingtuna (SE) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2023 | 0 | 8 | SWE | Hamra | Dingtuna | 61.7567 | 14.8024 | 59.5724 | 16.3887
892 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 795 | Commissioned | 125 | New 400kV double circuit (OHL and underground cable) between Schwanden and Limmern. | 3 | 2015 | 2015 | 1 | Schwanden (CH) | Limmern (CH) | 91 | 91. 125 | New 400kV double circuit (OHL and underground cable) between Schwanden and Limmern. | 3 | Progresses as planned | 2015 | 2015 | 1 | Schwanden (CH) | Limmern (CH) | 91. 125 | 91. 125 | New 400kV double circuit (OHL and underground cable) between Schwanden and Limmern. OHL part | 4 |  | 2015 | 2015 | 1 | Schwanden (CH) | Limmern (CH) | 91 | 795 | Swiss Ellipse | New 400kV double circuit (OHL and underground cable) between Schwanden and Limmern. Underground cable part | 4 | Investment on time | none | 2015 | 2015 | 1 | Schwanden (CH) | Limmern (CH) | 795 | New 400kV double circuit (OHL and underground cable) between Schwanden and Limmern. Underground cable part | 4 | Investment on time | Progressed as planned | 2015 | 2015 | 1 | Schwanden (CH) | Limmern (CH) | [5 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2015 | 0 | 5 | CHE | Schwanden | Limmern | 46.9956 | 9.0714 | 47.5293 | 7.6067
893 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 796 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 94 | 796 | GerPol Improvements | Upgrade of 400/220 kV switchgear in substation Krajnik (new 400/220 kV switchyard). | 3 | Delayed | The commissioning time of the investment has been aligned with the schedule for the investment 139. | 2017 | 2017 | 1 | Krajnik (PL) |  | 796 | Upgrade of 400/220 kV switchgear in substation Krajnik (new 400/220 kV switchyard). | 3 | Investment on time | The commissioning date was adjusted to optimize the planning and development of transmission system. | 2017 | 2017 | 1 | Krajnik (PL) |  | 94 | 796 | GerPol Improvements | Krajnik | Upgrade of 400/220 kV switchgear in substation Krajnik (new 400/220 kV switchyard). | 3 | Rescheduled | The commissioning date was adjusted to optimize the planning and development of transmission system. | 31/12/ 2020 | 2020 | 1 |  | 0 | Krajnik (PL) |  | Substation |  | 1200 | 400 |  | New | 94 | 796 | GerPol Improvements | Krajnik | 4 | Investment on time |  | 2019 | 2019 | 1 |  | Krajnik (PL) | Krajnik (PL) | Substation | AC | 400 | [5 empty] | 5 | Commissioned |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2019 | 2 | 5 | POL | Krajnik | Krajnik | 53.1974 | 14.4697 | 53.1974 | 14.4697
894 | 2014 | 2016 | [2014, 2015, 2016] | 799 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 94 | 799 | GerPol Improvements | Installation of new Phase Shift Transformer in substation Mikułowa and the upgrade of substation Mikułowa for the purpose of PST installation. | 3 | Delayed | Investment postponed because of prolongation of the tendering process. Due to complexity of the technical solutions more time is needed for the tendering procedure. | 2015 | 2015 | 1 | Mikulowa (PL) |  | 799 | Installation of new Phase Shift Transformer in substation Mikułowa and the upgrade of substation Mikułowa for the purpose of PST installation. | 4 | Investment on time | Investment on time. | 2015 | 2015 | 1 | Mikułowa (PL) |  | 94 | 799 | GerPol Improvements | PST in Mikułowa | Installation of new Phase Shift Transformer in substation Mikułowa and the upgrade of substation Mikułowa for the purpose of PST installation. | 5 | Commissioned | The PSTs in Mikułowa substation have been constructed in 2015. In first half of 2016 test and trials have been performed. The delay accured due to technical difficulties during starting phase. | 30/06/2016 | 2016 | 1 |  | 1 | Mikułowa (PL) |  | Phase Shift Transformer |  | 300 | 400 |  | New | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2015 | 2016 | 1 | 2 | POL | Mikuowa
895 | 2014 | 2016 | [2014, 2015, 2016] | 8 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 2 | 8 | RES in center of Portugal | New single circuit 400kV OHL Seia-Penela (90km). | 3 | Investment on time | Project on time | 2016 | 2016 | 1 | Seia | Penela | 8 | New single circuit 400kV OHL Seia-Penela (90km). | 3 | Rescheduled | Due to the expected delay of the connection of new hydro power plant, the commissioning date of this investment item was rescheduled | 2020 | 2020 | 1 | Seia | Penela | 2 | 8 | RES in center of Portugal | Seia-Penela | New single circuit 400kV OHL Seia-Penela (108km). | 3 | Rescheduled | Due to the expected delay of the connection of new hydro power plant, the commissioning date of this investment item was rescheduled | 31/ 12/ 2020 | 2020 | 1 |  | 0 | Seia | Penela | Overhead Line | AC | 1780 | 400 | 108 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2020 | 4 | 6 | PRT | Seia | Penela | 40.4201 | -7.7028 | 40.0294 | -8.3902
896 | 2012 | 2026 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 800 | Commissioned | [5 empty] | 0 |  |  | 95 | 95. A119 | New 140km single circuit 400kV OHL in parallel to the existing one. | 2 | New investment in TYNDP, required to accommodate 2000MW RES in Dobrudja region | 2016 | 2016 | 1 | Dobrudja(BG) | Burgas (BG) | 95. A119 | 95. A119 | New 140km single circuit 400kV OHL in parallel to the existing one. | 2 | Delayed due to lack of funding. | 2018 | 2018 | 1 | Dobrudja(BG) | Burgas (BG) | 138 | 800 | Black Sea Corridor | New 140km single circuit 400kV OHL in parallel to the existing one. | 2 | Delayed | Delayed due to lack of funding. | 2018 | 2018 | 1 | Dobrudja(BG) | Burgas (BG) | 800 | New 140km single circuit 400kV OHL in parallel to the existing one. | 2 | Delayed | Delayed due to lack of funding. | 2020 | 2020 | 1 | Varna(BG) | Burgas(BG) | 138 | 800 | Black Sea Corridor | 400 kV OHL Varna-Burgas | New 140km single circuit 400kV OHL in parallel to the existing one. | 2 | Delayed | Delayed due to lack of funding. | 1/ 1/ 2020 | 2020 | 1 |  | 0 | Varna(BG) | Burgas(BG) | Overhead Line | AC | 165 | 400 | 140 | New | 138 | 800 | Black Sea Corridor | 400 kV OHL Varna-Burgas | 3 | Rescheduled | Having dificulities with acquiring the land | 31/ 03/ 2021 | 2021 | 1 |  | Varna(BG) | Burgas(BG) | Overhead Line | AC | 400 | 138 | 800 | Black Sea Corridor | 400 kV OHL Varna-Burgas | New 86 km single circuit 400kV OHL in parallel to the existing one. | 4 | Investment on time |  | 2021 | 2021 | 1 | ESO TRANSELECTRICA | 3.8 | 0 | 0 | Varna(BG) | Burgas(BG) | ACTransmissionLine | AC | 86 | MostlyNew | 138 | 800 | Black Sea Corridor | 400 kV OHL Varna-Burgas | New 86 km single circuit 400kV OHL in parallel to the existing one. | 5 | Investment on time |  | 08-2021 | 2021 | 1 | ESO, Transelectrica |  | 0 | 0 | Varna(BG) | Burgas(BG) | ACTransmissionLine | AC | 0 | 400 | 86 | MostlyNew | 138 | 800 | Black Sea Corridor | 400 kV OHL Varna-Burgas | New 86 km single circuit 400kV OHL in parallel to the existing one. | 5 | Investment on time |  | 08-2021 | 2021 | 1 | ESO, Transelectrica |  | 0 | 0 | Varna(BG) | Burgas(BG) | ACTransmissionLine | AC | 0 | 400 | 86 | MostlyNew | 138 | 800 | Black Sea Corridor | 400 kV OHL Varna-Burgas | New 86 km single circuit 400kV OHL in parallel to the existing one. | 5 | Commissioned | 08-2021 | 2021 | 1 | ESO, Transelectrica | 0 | XX | XX | Mostly new | 2016 | 2021 | 5 | 9 | BGR;ROU | Varna | Burgas | 43.2074 | 27.9167 | 42.4937 | 27.4721
897 | 2012 | 2018 | [2012, 2013, 2014, 2015, 2016, 2018] | 801 | Cancelled | [5 empty] | 0 |  |  | 96 | 96. A64 | Integration of new generation + increased transmission capacity demand. | 1 | New investment in TYNDP, split out from investment 393, and now been moved as a stand-alone project cluster because of his specific benefits. | 2019 | 2019 | 1 | Keminmaa (FI) | Pyhänselkä (FI) | 96. A64 | 96. A64 | Integration of new generation + increased transmission capacity demand. | 1 | Investment progresses as planned, rescheduled slightly since last TYNDP due to expected development on the drivers behind the investment. | 2020 | 2020 | 1 | Keminmaa (FI) | Pyhänselkä (FI) | 96 | 801 | Keminmaa-Pyhänselkä | Integration of new generation + increased transmission capacity demand. | 1 | Rescheduled | Investment progresses as planned, rescheduled slightly since last TYNDP due to expected development on the drivers behind the investment. | 2024 | 2024 | 1 | Keminmaa (FI) | Pyhänselkä (FI) | 801 | Integration of new generation + increased transmission capacity demand. | 2 | Investment on time | Investment progresses as planned, rescheduled slightly since last TYNDP due to expected development on the drivers behind the investment. | 2024 | 2024 | 1 | Keminmaa (FI) | Pyhänselkä (FI) | 96 | 801 | Keminmaa-Pyhänselkä | FI5 KI-PS | Integration of new generation + increased transmission capacity demand. | 2 | Investment on time | Investment progresses as planned, rescheduled slightly since last TYNDP due to expected development on the drivers behind the investment. | 1/ 1/ 2024 | 2024 | 1 |  | 0 | Keminmaa (FI) | Pyhänselkä (FI) | Overhead Line | AC | 1000 | 400 | 156 | New | 96 | 801 | Keminmaa-Pyhänselkä | FI5 KI-PS | 3 | Investment on time |  | 1/ 1/ 2024 | 2024 | 1 | FINGRID | Keminmaa (FI) | Pyhanselka (FI) | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2024 | 5 | 12 | FIN | Keminmaa | Pyhanselka | 65.803 | 24.5209
898 | 2015 | 2015 | [2015] | 806 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 |  |  | 806 | New 55 km single circuit 400kV OHL | 1 | Investment on time | Progressed as planned | 2030 | 2030 | 1 | Råbäcken (SE) | Trolltjärn (SE) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 15 | SWE | Råbäcken | Trolltjärn | 63.4103 | 19.1377 | 63.8425 | 18.0491
899 | 2012 | 2015 | [2012, 2013, 2014, 2015] | 809 | Cancelled | [5 empty] | 0 |  |  | 106 | 106. A34 | A new HVDC subsea connection between Ireland and Great Britain | 1 | New investment in TYNDP, conceptual, cost benefit analysis to be confirmed | long term |  | 1 | tbd (IE) | tbd (GB) | 106. A34 | 106. A34 | A new HVDC subsea connection between Ireland and Great Britain; this may be achieved by a direct link or by integrating an interconnector with a third party connection from Ireland to GB. | 1 | Joint studies between National Grid and EirGrid indicate a strong benefit for a second interconnector between Ireland and GB. | 2025 | 2025 | 1 | Dunstown (IE) | Pentir (GB) | 106 | 809 | Ireland GB Interconnector | A new HVDC subsea connection between Ireland and Great Britain; this may be achieved by a direct link or by integrating an interconnector with a third party connection from Ireland to GB. | 1 | Investment on time | Joint studies between National Grid and EirGrid indicate a strong benefit for a second interconnector between Ireland and GB. | 2025 | 2025 | 1 | Dunstown (IE) | Pentir (GB) | 809 | A new HVDC subsea connection between Ireland and Great Britain; this may be achieved by a direct link or by integrating an interconnector with a third party connection from Ireland to GB. | 1 | Investment on time | Progressed as planned | 2025 | 2025 | 1 | Dunstown (IE) | Pentir (GB) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2025 |  | 13 | GBR;IRL | Dunstown | Pentir |  |  | 53.1959 | -4.1608
900 | 2012 | 2026 | [2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 810 | [6 empty] | 0 |  |  | 107 | 107. A25 | A new HVDC subsea connection between Ireland and France | 1 | New investment in TYNDP, conceptual, cost benefit analysis to be confirmed | long term |  | 1 | tbd (IE) | tbd (FR) | 107. A25 | 107. A25 | A new HVDC subsea connection between Ireland and France | 1 | Feasibility studies are progressing. | 2025 | 2025 | 1 | Great Island or Knockraha (IE) | La Martyre (FR) | 107 | 810 | Celtic Interconnector | A new HVDC subsea connection between Ireland and France | 1 | Investment on time | Feasibility studies are progressing | 2025 | 2025 | 1 | Great Island or Knockraha (IE) | La Martyre (FR) | 810 | A new HVDC subsea connection between Ireland and France | 1 | Investment on time | Progressed as planned | 2025 | 2025 | 1 | Great Island or Knockraha (IE) | La Martyre (FR) | 107 | 810 | Celtic Interconnector | France Ireland Interconnector | A new HVDC subsea connection between Ireland and France | 1 | Rescheduled | The project is now starting the Initial Design and Pre-consultation Phase Feasibility Study resulted in minor commissioning postponement. | 2026 | 2026 | 1 |  | 1 | West Wexford or East Cork (IE) | La Martyre (FR) | Subsea Cable | DC | 700 | 320 | 500 | New | 107 | 810 | Celtic Interconnector | France Ireland Interconnector | 1 | Investment on time |  | 2026 | 2026 | 1 | EIRGRID,RTE | West Wexford or East Cork (IE) | La Martyre (FR) | Subsea Cable | DC | 320 | 107 | 810 | Celtic Interconnector | France Ireland Interconnector | A new HVDC subsea connection between Ireland and France | 3 | Investment on time |  | 2026 | 2026 | 1 | EIRGRID RTE | 1.6 | 1 | 1 | Knockraha (IE) | La Martyre (FR) | OffshoreDCTransmissionCable | DC | 500 | New | 107 | 810 | Celtic Interconnector | France Ireland Interconnector | A new HVDC subsea connection between Ireland and France | 3 | Investment on time |  | 03-2027 | 2027 | 1 | Eirgrid, RTE | 1.6 | 1 | 1 | Knockraha (IE) | La Martyre (FR) | OffshoreDCTransmissionCable | DC | 700 | 320 | 575 | New | 107 | 810 | Celtic Interconnector | France Ireland Interconnector | A new HVDC subsea connection between Ireland and France | 4 | Rescheduled | delay due to COVID crisis and to time required for the contractualisation of the 2 main EPC contracts | 03-2027 | 2027 | 1 | Eirgrid, RTE | 1.3 | 1 | 1 | Knockraha (IE) | La Martyre (FR) | OffshoreDCTransmissionCable | DC | 700 | 320 | 575 | New | 107 | 810 | Celtic Interconnector | France Ireland Interconnector | A new HVDC subsea connection between Ireland and France | 4 |  | 03-2027 | 2027 | 1 | Eirgrid, RTE | 1 | XX | XX | New |  | 2027 |  | 15 | FRA;IRL | Knockraha | La Martyre | 51.9741 | -8.3292 | 48.4484 | -4.158
901 | 2012 | 2015 | [2012, 2013, 2014, 2015] | 811 | Cancelled | [5 empty] | 0 |  |  | 108 | 108. A134 | New 145km double circuit 400kV OHL | 2 | New investment in TYNDP | 2018 | 2018 | 1 | Tarnita (RO) | Mintia (RO) | 108. A134 | 108. A134 | New double circuit 400kV OHL Tarnita(RO)-Mintia(RO) 2x1380 MVA. | 2 | The investment shall be built only if the Hydro Pumped Storage plant shall be built. Final investment decision is pending. | 2018 | 2018 | 1 | Tarnita (RO) | Mintia (RO) | 108 | 811 | 1000MW HPS Tarnita connection | New double circuit 400kV OHL Tarnita(RO)-Mintia(RO) 2x1380 MVA. | 2 | Investment on time | The project shall be built only if the Hydro Pumped Storage plant shall be built. Final investment decision is pending. | 2018 | 2018 | 1 | Tarnita (RO) | Mintia (RO) | 811 | New double circuit 400kV OHL Tarnita(RO)-Mintia(RO) 2x1380 MVA. | 6 | Cancelled | The project shall be built only if the Hydro Pumped Storage plant shall be built. Final investment decision is pending. |  |  | 1 | Tarnita (RO) | Mintia (RO) | [10 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 |  |  |  | ROU | Tarnita | Mintia | 46.1781 | 23.0547 | 45.9239 | 22.8488
902 | 2012 | 2015 | [2012, 2013, 2014, 2015] | 812 | Cancelled | [5 empty] | 0 |  |  | 108 | 108. A135 | New 40km double circuit 400kV OHL | 2 | New investment in TYNDP | 2018 | 2018 | 1 | Tarnita (RO) | Cluj E - Gadalin (RO) | 108. A135 | 108. A135 | New double circuit 400kV OHL Tarnita(RO)- Cluj E-Gadalin (RO) 2x1380 MVA. | 2 | The investment shall be built only if the Hydro Pumped Storage plant shall be built. Final investment decision is pending. | 2018 | 2018 | 1 | Tarnita (RO) | Cluj E - Gadalin (RO) | 108 | 812 | 1000MW HPS Tarnita connection | New double circuit 400kV OHL Tarnita(RO)- Cluj E-Gadalin (RO) 2x1380 MVA. | 2 | Investment on time | The project shall be built only if the Hydro Pumped Storage plant shall be built. Final investment decision is pending. | 2018 | 2018 | 1 | Tarnita (RO) | Cluj E - Gadalin (RO) | 812 | New double circuit 400kV OHL Tarnita(RO)- Cluj E-Gadalin (RO) 2x1380 MVA. | 6 | Cancelled | The project shall be built only if the Hydro Pumped Storage plant shall be built. Final investment decision is pending. |  |  | 1 | Tarnita (RO) | Cluj E - Gadalin (RO) | [10 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 |  |  |  | ROU | Tarnita | Cluj E - Gadalin | 46.1781 | 23.0547
903 | 2014 | 2015 | [2014, 2015] | 813 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 108 | 813 | 1000MW HPS Tarnita connection | New 400kV substation connecting 1000 MW Hydro Pumped Storage Tarnita Lapustesti to the grid. | 2 | Investment on time | The project shall be built only if the Hydro Pumped Storage plant shall be built. Final investment decision is pending. | 2018 | 2018 | 1 | Tarnita (RO) |  | 813 | New 400kV substation connecting 1000 MW Hydro Pumped Storage Tarnita Lapustesti to the grid. | 6 | Cancelled | The project shall be built only if the Hydro Pumped Storage plant shall be built. Final investment decision is pending. |  |  | 1 | Tarnita (RO) | [11 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 |  |  |  | ROU | Tarnita |  | 46.1781 | 23.0547
904 | 2010 | 2026 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 86 |  | 86 | New 178km double circuit 400kV OHL between existing Foggia and Villanova 400kV substations, also connected in and out to the Larino and Gissi substations. A PST will be installed on the new 400kV line. | 3 | 2015 | 2015 | 1 | Foggia (IT) | Villanova (IT) | 28 | 28. 86 | New 178km double circuit 400kV OHL between existing Foggia and Villanova 400kV substations, also connected in and out to the Larino and Gissi substations. A PST will be installed on the new 400kV line. | 3 | Progresses as planned | 2015 | 2015 | 1 | Foggia (IT) | Villanova (IT) | 28. 86 | 28. 86 | New 178km double circuit 400kV OHL between existing Foggia and Villanova 400kV substations, also connected in and out to the Larino and Gissi substations. | 3 | Longer permitting process (EIA) concerning the part Foggia-Gissi still under authorization; the part Villanova Gissi is already authorized | 2019 | 2019 | 1 | Foggia (IT) | Villanova (IT) | 127 | 86 | 127 | New 178km double circuit 400kV OHL between existing Foggia and Villanova 400kV substations, also connected in and out to the Larino and Gissi substations. | 3 | Delayed | delay in the permitting process (EIA) concerning the part Foggia-Gissi still under authorization; the part Villanova Gissi is already authorized | 2019 | 2019 | 1 | Foggia (IT) | Villanova (IT) | 86 | New 178km double circuit 400kV OHL between existing Foggia and Villanova 400kV substations, also connected in and out to the Larino and Gissi substations. | 3 | Investment on time | the part Foggia-Gissi still under authorization; the part Villanova Gissi is under construction | 2019 | 2019 | 1 | Foggia (IT) | Villanova (IT) | 127 | 86 | Central Southern Italy | 86 | New 178km double circuit 400kV OHL between existing Foggia and Villanova 400kV substations, also connected in and out to the Larino and Gissi substations. | 3 | Delayed | the part Foggia-Gissi still under authorization; the part Villanova Gissi has been commissioned in 2016. | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Foggia (IT) | Villanova (IT) | Overhead Line | AC | 600 | 400 | 178 | New | 127 | 86 | Central Southern Italy | 86 | 3 | Investment on time |  | 2022 | 2022 | 1 | TERNA | Foggia (IT) | Villanova (IT) | Overhead Line | AC | 400 | 127 | 86 | Central Southern Italy | 86 | New 178km double circuit 400kV OHL between existing Foggia and Villanova 400kV substations, also connected in and out to the Larino and Gissi substations. | 3 | Investment on time |  | 2024 | 2024 | 1 | TERNA |  | 1 | 0 | Foggia (IT) | Villanova (IT) | ACTransmissionLine | AC | 178 | New | 127 | 86 | Central Southern Italy | New 66km double circuit 400kV OHL between existing Foggia and Villanova 400kV substations, also connected in and out to the Larino and Gissi substations | New 66km double circuit 400kV OHL between existing Foggia and Villanova 400kV substations, also connected in and out to the Larino and Gissi substations. The section between Villanova and Gissi has already been completed, so the remaining section Gissi - Lartino - Foggia is the main project. | 3 | Delayed |  | 12-2028 | 2028 | 1 | Terna |  | 1 | 0 | Foggia (IT) | Villanova (IT) | ACTransmissionLine | AC | 0 | 400 | 178 | New | 127 | 86 | Central Southern Italy | New 66km double circuit 400kV OHL between existing Foggia and Villanova 400kV substations, also connected in and out to the Larino and Gissi substations | New 66km double circuit 400kV OHL between existing Foggia and Villanova 400kV substations, also connected in and out to the Larino and Gissi substations | 3 | Investment on time |  | 12-2028 | 2028 | 1 | Terna |  | 1 | 0 | Foggia (IT) | Villanova (IT) | ACTransmissionLine | AC | 0 | 400 | 178 | New | 127 | 86 | Central Southern Italy | New double circuit 400kV OHL between existing Foggia and Villanova 400kV substations, also connected in and out to the Larino and Gissi substations | New double circuit 400kV OHL between existing Foggia and Villanova 400kV substations, also connected in and out to the Larino and Gissi substations |  |  | 12-2029 | 2029 | 1 | Terna | 0 | XX | XX | New | 2015 | 2029 | 14 | 19 | ITA | Foggia | Villanova | 41.5028 | 15.4529 | 43.0071 | 12.3278
905 | 2014 | 2022 | [2014, 2015, 2016, 2018, 2020, 2022] | 886 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 186 | 886 | east of Austria | To allow the grid integration of the planned renewable energy generation (mainly wind power) in the north-eastern part of Austria ("Weinviertel") and to cover the foreseen load growth in that region the transmission grid infrastructure has to be enforced and new substations for the connection need to be erected | 2 | Rescheduled | The development of wind energy in Lower Austria was temporarily stopped by the federal state government to establish a concept for land use. Final concept was published in beginning of 2014 – project now continues with planned commissioning in 2021. | 2021 | 2021 | 1 | tbd | tbd | 886 | To allow the grid integration of the planned renewable energy generation (mainly wind power) in the north-eastern part of Austria ("Weinviertel") and to cover the foreseen load growth in that region the transmission grid infrastructure has to be enforced and new substations for the connection need to be erected | 3 | Investment on time | Start of the authorisation process (EIA) in mid-2016. | 2021 | 2021 | 1 | tbd | tbd | 186 | 886 | east of Austria | 886 | To allow the grid integration of the planned renewable energy generation (mainly wind power) in the north-eastern part of Austria ("Weinviertel") and to cover the foreseen load growth in that region the transmission grid infrastructure has to be enforced and new substations for the connection need to be erected | 3 | Investment on time | Start of the authorisation process (EIA) in mid 2016. | 1/ 1/ 2021 | 2021 | 1 |  | 0 | Seyring | Neusiedl/Zaya | Overhead Line | AC | 0 | 380 | 60 | New | 186 | 886 | east of Austria | east of Austria | 3 | Investment on time |  | 2021 | 2021 | 1 | APG | Seyring | Neusiedl/Zaya | Overhead Line | AC | 380 | 186 | 886 | East of Austria | 886 - east of Austria | To allow the grid integration of the planned renewable energy generation (mainly wind power) in the north-eastern part of Austria ("Weinviertel") and to cover the foreseen load growth in that region the transmission grid infrastructure has to be enforced and new substations for the connection needs to be erected | 4 | Investment on time |  | 2022 | 2022 | 1 | Austrian Power Grid |  | 1 | 0 | Seyring | Zaya | ACTransmissionLine | AC | 60 | New | 186 | 886 | East of Austria | 886 - east of Austria | To allow the grid integration of the planned renewable energy generation (mainly wind power) in the north-eastern part of Austria ("Weinviertel") and to cover the foreseen load growth in that region the transmission grid infrastructure has to be enforced and new substations for the connection needs to be erected | 4 | Investment on time |  | 12-2022 | 2022 | 1 | Austrian Power Grid |  | 1 | 0 | Seyring | Zaya | ACTransmissionLine | AC | 0 | 380 | 60 | New | [5 empty] | 5 | Commissioned |  |  |  | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2022 | 1 | 8 | AUT | Seyring | Zaya | 48.3321 | 16.485 | 48.5724 | 16.6227
906 | 2014 | 2016 | [2014, 2015, 2016] | 889 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 177 | 889 | PST Hradec | Construction of new PST in substation Hradec with target capacity 2x1700MVA | 3 | Investment on time | Progress as planned | 2016 | 2016 | 1 | Hradec |  | 889 | Construction of new PST in substation Hradec with target capacity 2x1700MVA | 4 | Investment on time | Progressed as planned | 2016 | 2016 | 1 | Hradec |  | 177 | 889 | PST Hradec | PST Hradec | Construction of new PST in substation Hradec with target capacity 2x1700MVA | 4 | Investment on time | Progress as planned | 1/ 1/ 2016 | 2016 | 1 |  | 1 | Hradec |  | Phase Shift Transformer |  | 500 | 400 |  | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2016 | 0 | 2 | CZE | Hradec |  | 49.7119 | 15.2985
907 | 2014 | 2016 | [2014, 2015, 2016] | 894 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 168 | 894 | Spaak NL | New Overhead line from Sliedrecht to Dodewaard of 2x2633 MVA in Wintrack, 65 km | 1 | New Investment | This new investment has been identified as a beneficial project in the NSCOGI study and is part of the national grid development plan | 2025 | 2025 | 1 | Sliedrecht area | Dodewaard | 894 | New Overhead line from Sliedrecht to Dodewaard of 2x2633 MVA in Wintrack, 65 km. Update: AC solution is unlikely at the moment; other solutions are being considered. Until a new solution is found, this project is kept as it is in TYNDP. | 1 | Rescheduled | This new investment has been identified as a beneficial project in the NSCOGI study and is part of the national grid development plan | 2030 | 2030 | 1 | Sliedrecht area | Dodewaard | 168 | 894 | Spaak NL | Spaak NL | New Overhead line from Sliedrecht to Dodewaard of 2x2633 MVA in Wintrack, 65 km. Update&#58; AC solution is unlikely at the moment; other solutions are being considered. Until a new solution is found, this project is kept as it is in TYNDP. | 1 | Investment on time | This conceptual future project could become relevant when large amounts wind power need to be transported from west to east. Internal studies have shown that an AC solution as in the project list is not very likely. This project is investigated as one of the options together with other projects (e.g. 256) and has no formal status within TenneT. | >>2030 | 2030 | 1 |  | 0 | Krimpen aan de Ijssel | Dodewaard | Overhead Line | AC | 0 | 380 | 65 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2030 | 5 | 16 | AUT;ISL;ITA;NLD | Krimpen Aan De Ijssel | Dodewaard | 51.9167 | 4.6084 | 51.914 | 5.6569
908 | 2014 | 2020 | [2014, 2015, 2016, 2018, 2020] | 896 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 82 | 896 | RIDP I | A new 275 kV cross border link between a new substation in South Donegal in Ireland and a new substation established south of Omagh in Northern Ireland | 2 | New Investment | Investment 82.463 of the previous TYNDP described the as then undefined scheme that was the subject of a joint study between NIE and EirGrid. That study has since been completed. This investment is one of a number emerging from the study. | 2024 | 2024 | 1 | South Donegal (IE) | Omagh South (NI) | 896 | A new 275 kV cross border link between a new substation in South Donegal in Ireland and a new substation established south of Omagh in Northern Ireland | 2 | Investment on time | Progressed as planned | 2024 | 2024 | 1 | South Donegal (IE) | Omagh South (NI) | 82 | 896 | RIDP I | Omagh South to South Donegal | A new 275 kV cross border link between a new substation in South Donegal in Ireland and a new substation established south of Omagh in Northern Ireland |  | New Investment | Investment 82.463 of the previous TYNDP described the as then undefined scheme that was the subject of a joint study between NIE and EirGrid. That study has since been completed. This investment is one of a number emerging from the study. |  |  | 1 |  | 1 | South Donegal (IE) | Omagh South (NI) | Overhead Line | AC | 500 | 275 | 58 | New | 82 | 896 | RIDP I | Omagh South to South Donegal | 2 | Rescheduled | A capacity review of committed generators and upcoming new connection policy rules will impact on renewable generation totals that drive the date of need for this investment. | 2029 | 2029 | 1 |  | South Donegal (IE) | Omagh South (NI) | Overhead Line | AC | 275 | 82 | 896 | RIDP I | Omagh South to South Donegal | A new 275 kV cross border link between a new substation in South Donegal in Ireland and a new substation established south of Omagh in Northern Ireland | 2 | Rescheduled | A capacity review of committed generators and upcoming new connection policy rules will impact on renewable generation totals that drive the date of need for this investment. | 2030 | 2030 | 1 | EIRGRID SONI | 2.13.2 | 1 | 1 | South Donegal (IE) | Omagh South (NI) | ACTransmissionLine | AC | 58 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2024 | 2030 | 6 | 16 | GBR;IRL | South Donegal | Omagh South | 55.0332 | -8.0176 | 54.5944 | -7.2952
909 | 2014 | 2020 | [2014, 2015, 2016, 2018, 2020] | 897 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 82 | 897 | RIDP I | A new 275 kV overhead line from a new substation established south of Omagh to a new 400/275 kV substation, established at Turleenan by the North South Interconnection Development | 2 | New Investment | Investment 82.463 of the previous TYNDP described the as then undefined scheme that was the subject of a joint study between NIE and EirGrid. That study has since been completed. This investment is one of a number emerging from the study. | 2020 | 2020 | 1 | Omagh South | Turleenan | 897 | A new 275 kV overhead line from a new substation established south of Omagh to a new 400/275 kV substation, established at Turleenan by the North South Interconnection Development | 2 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Omagh South | Turleenan | 82 | 897 | RIDP I | Omagh South to Turleenan | A new 275 kV overhead line from a new substation established south of Omagh to a new 400/275 kV substation, established at Turleenan by the North South Interconnection Development |  | New Investment | Investment 82.463 of the previous TYNDP described the as then undefined scheme that was the subject of a joint study between NIE and EirGrid. That study has since been completed. This investment is one of a number emerging from the study. |  |  | 1 |  | 0 | Omagh South | Turleenan | Underground Cable | AC | 500 | 275 | 63 | New | 82 | 897 | RIDP I | Omagh South to Turleenan | 2 | Rescheduled | A capacity review of committed generators and upcoming new connection policy rules will impact on renewable generation totals that drive the date of need for this investment. | 2029 | 2029 | 1 |  | Omagh South | Turleenan | Overhead Line | AC | 275 | 82 | 897 | RIDP I | Omagh South to Turleenan | A new 275 kV overhead line from a new substation established south of Omagh to a new 400/275 kV substation, established at Turleenan by the North South Interconnection Development | 2 | Rescheduled | A capacity review of committed generators and upcoming new connection policy rules will impact on renewable generation totals that drive the date of need for this investment. | 2030 | 2030 | 1 | EIRGRID SONI | 2.13.2 | 0 | 1 | Omagh South | Turleenan | ACTransmissionLine | AC | 61 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2030 | 10 | 16 | GBR;IRL | Omagh South | Turleenan | 54.5944 | -7.2952 | 54.4658 | -6.6803
910 | 2014 | 2016 | [2014, 2015, 2016] | 9 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 2 | 9 | RES in center of Portugal | New 400kV double circuit OHL Fundão (PT) -'Castelo Branco zone'-Falagueira (PT) | 3 | Delayed | Adjustments resulting from the new date of renewables projects. | 2017 | 2017 | 1 | Fundão (PT) | Falagueira (PT) | 9 | New 400kV double circuit OHL Fundão (PT) -'Castelo Branco zone'-Falagueira (PT) | 3 | Investment on time | Project on time | 2017 | 2017 | 1 | Fundão (PT) | Falagueira (PT) | 2 | 9 | RES in center of Portugal | Fundão-Falagueira | New 400kV double circuit OHL Fundão (PT) -'Castelo Branco zone'-Falagueira (PT) | 3 | Investment on time | Project on time | 31/ 12/ 2017 | 2017 | 1 |  | 0 | Fundão (PT) | Falagueira (PT) | Overhead Line | AC | 450 | 400 | 99 | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2017 | 0 | 3 | PRT | Fundão | Falagueira | 40.1408 | -7.5018 | 38.7613 | -9.226
911 | 2010 | 2026 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 90 |  | 90 | Voltage upgrade of the existing 80km Calenzano-Colunga 220kV OHL to 400kV, providing in and out connection to the existing 220/150kV substation of S. Benedetto del Querceto (which already complies with 400kV standards). | 3 | short term |  | 1 | Calenzano (IT) | Colunga (IT) | 33 | 33. 90 | Voltage upgrade of the existing 80km Calenzano-Colunga 220kV OHL to 400kV, providing in and out connection to the existing 220/150kV substation of S. Benedetto del Querceto (which already complies with 400kV standards). | 3 | Delays due to authorization process. | mid term |  | 1 | Calenzano (IT) | Colunga (IT) | 33. 90 | 33. 90 | Voltage upgrade of the existing 80km Calenzano-Colunga 220kV OHL to 400kV, providing in and out connection to the existing 220/150kV substation of S. Benedetto del Querceto (which already complies with 400kV standards). | 3 | Delay in the permitting process (EIA) | 2018 | 2018 | 1 | Calenzano (IT) | Colunga (IT) | 33 | 90 | 33 | Voltage upgrade of the existing 80km Calenzano-Colunga 220kV OHL to 400kV, providing in and out connection to the existing 220/150kV substation of S. Benedetto del Querceto (which already complies with 400kV standards). | 3 | Delayed | delay in the permitting process (EIA) | 2018 | 2018 | 1 | Calenzano (IT) | Colunga (IT) | 90 | Voltage upgrade of the existing 80km Calenzano-Colunga 220kV OHL to 400kV, providing in and out connection to the existing 220/150kV substation of S. Benedetto del Querceto (which already complies with 400kV standards). | 3 | Delayed | delay in the permitting process (EIA) | 2019 | 2019 | 1 | Calenzano (IT) | Colunga (IT) | 33 | 90 | Central Northern Italy | 90 | Voltage upgrade of the existing 80km Calenzano-Colunga 220kV OHL to 400kV, providing in and out connection to the existing 220/150kV substation of S. Benedetto del Querceto (which already complies with 400kV standards). | 3 | Delayed | delay in the permitting process (EIA) | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Calenzano (IT) | Colunga (IT) | Overhead Line | AC | 400 | 400 | 80 | New | 33 | 90 | Central Northern Italy | 90 | 3 | Investment on time |  | 2022 | 2022 | 1 | TERNA | Calenzano (IT) | Colunga (IT) | Overhead Line | AC | 400 | 33 | 90 | Central Northern Italy | 90 | Voltage upgrade of the existing 80km Calenzano-Colunga 220kV OHL to 400kV, providing in and out connection to the existing 220/150kV substation of S. Benedetto del Querceto (which already complies with 400kV standards). | 3 | Investment on time |  | 2023 | 2023 | 1 | TERNA |  | 1 | 0 | Calenzano (IT) | Colunga (IT) | ACTransmissionLine | AC | 80 | Upgrade | 33 | 90 | Central Northern Italy | 90 | Voltage upgrade of the existing 80km Calenzano-Colunga 220kV OHL to 400kV, providing in and out connection to the existing 220/150kV substation of S. Benedetto del Querceto (which already complies with 400kV standards). | 4 | Delayed | Delayed due to permitting reasons. | 12-2025 | 2025 | 1 | Terna SpA |  | 1 | 0 | Calenzano (IT) | Colunga (IT) | ACTransmissionLine | AC | 0 | 400 | 80 | Upgrade | 33 | 90 | Central Northern Italy | Voltage upgrade of the existing 80km Calenzano-Colunga 220kV OHL to 400kV | Voltage upgrade of the existing 80km Calenzano-Colunga 220kV OHL to 400kV, providing in and out connection to the existing 220/150kV substation of S. Benedetto del Querceto (which already complies with 400kV standards). | 4 | Investment on time |  | 12-2025 | 2025 | 1 | Terna SpA |  | 1 | 0 | Calenzano (IT) | Colunga (IT) | ACTransmissionLine | AC | 0 | 400 | 80 | Upgrade | 33 | 90 | Central Northern Italy | Voltage upgrade of the existing 80km Calenzano-Colunga 220kV OHL to 400kV | Voltage upgrade of the existing 80km Calenzano-Colunga 220kV OHL to 400kV, providing in and out connection to the existing 220/150kV substation of S. Benedetto del Querceto (which already complies with 400kV standards). Removing limitations on existing 380 kV lines in the northern area, close to the border bidding zone | 4 |  | 12-2026 | 2026 | 1 | Terna SpA | 0 | XX | XX | Upgrade |  | 2026 |  | 16 | ITA | Calenzano | Colunga | 43.8652 | 11.1674 | 44.4728 | 11.4647
912 | 2010 | 2016 | [2010, 2012, 2013, 2014, 2015, 2016] | 91 | Commissioned | 91 | Upgrade of the existing 85km Foggia-Benevento II 400kV OHL and installation of a PST on this line. | 3 | short term |  | 1 | Foggia (IT) | Benevento II (IT) | 32 | 32. 91 | Upgrade of the existing 85km Foggia-Benevento II 400kV OHL and installation of a PST on this line. | 4 | Authorization process ended, construction phase on going | 2013-2014 | 2014 | 1 | Foggia (IT) | Benevento II (IT) | 32. 91 | 32. 91 | Upgrade of the existing 85km Foggia-Benevento II 400kV OHL. | 4 |  | 2014 | 2014 | 1 | Foggia (IT) | Benevento II (IT) | 127 | 91 | 127 | Upgrade of the existing 85km Foggia-Benevento II 400kV OHL. | 4 | Investment on time | No changes | 2014 | 2014 | 1 | Foggia (IT) | Benevento II (IT) | 91 | Upgrade of the existing 85km Foggia-Benevento II 400kV OHL. | 5 | Investment on time | Progressed as planned | 2014 | 2014 | 1 | Foggia (IT) | Benevento II (IT) | 127 | 91 | Central Southern Italy | 91 | Upgrade of the existing 85km Foggia-Benevento II 400kV OHL. | 5 | Commissioned | - | 30/ 06/ 2014 | 2014 | 1 |  | 0 | Foggia (IT) | Benevento II (IT) | Overhead Line | AC | 250 | 400 | 85 | New | [9 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2014 |  | 4 | ITA | Foggia | Benevento Ii | 41.5028 | 15.4529 | 41.1296 | 14.7825
913 | 2016 | 2016 | [2016] | 912 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 | [9 empty] | 0 |  |  | 147 | 912 | South Balkan (CSE9) | SS Kumanovo | New 400/110 kV substation in North East part of FYRO Macedonia area connected in/out to the new 400 kV line Leskovac-Shtip. | 1 | New Investment | it is a new investment | 1/ 1/ 2020 | 2020 | 1 |  | 0 | Kumanovo |  | Substation |  | 0 | 400 |  | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 4 | ALB;SRB;BGR;GRC;MKD | Kumanovo |  | 43.2369 | 22.5141
914 | 2014 | 2016 | [2014, 2015, 2016] | 914 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 31 | 914 | Italy-Switzerland | Upgrade to 380 kV of part of existing 220 kV Cassano Ric.Ovest | 3 | New Investment | The interconnection scheme envisaged in TYNDP 2012 is now defined. The upgrade of Chiari-Cassano is identified as critical to get full advantage of the Giacomo project. | 2022 | 2022 | 1 | Cassano (IT) | Chiari (IT) | 914 | Upgrade to 380 kV of part of existing 220 kV Cassano Ric.Ovest | 3 | Investment on time | Progressed as planned | 2022 | 2022 | 1 | Cassano (IT) | Chiari (IT) | 31 | 914 | Italy-Switzerland | 380 kV btw Milano and Brescia | Upgrade to 380 kV of part of existing 220 kV Cassano Ric.Ovest | 3 | Investment on time | progressed as planned | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Cassano (IT) | Chiari (IT) | Overhead Line | AC | 500 | 380 | 35 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2022 | 0 | 8 | ITA | Cassano | Chiari | 45.5263 | 9.5215 | 45.5365 | 9.9288
915 | 2010 | 2015 | [2010, 2012, 2013, 2014, 2015] | 92 | Commissioned | 92 | New 40km double circuit 400kV OHL between the existing substations of West Udine and Redipuglia, providing in and out connection to the future 400kV substation of South Udine. | 3 | short term |  | 1 | West Udine (IT) | Redipuglia (IT) | 27 | 27. 92 | New 40km double circuit 400kV OHL between the existing substations of West Udine and Redipuglia, providing in and out connection to the future 400kV substation of South Udine. | 3 | The investment is delayed due to longer than expected authorization procedures. | 2015 | 2015 | 1 | West Udine (IT) | Redipuglia (IT) | 27. 92 | 27. 92 | New 40km double circuit 400kV OHL between the existing substations of West Udine and Redipuglia, providing in and out connection to the future 400kV substation of South Udine. | 4 | Permitting only recently completed (March 2013) and construction work had to be rescheduled accordingly | 2016 | 2016 | 1 | West Udine (IT) | Redipuglia (IT) | 148 | 92 | CCS new | New 40km double circuit 400kV OHL between the existing substations of West Udine and Redipuglia, providing in and out connection to the future 400kV substation of South Udine. | 4 | Delayed | permitting only recently completed (March 2013) and construction work had to be rescheduled accordingly. Note that the expected commissioning date for the project is December 2016 | 2016 | 2016 | 1 | West Udine (IT) | Redipuglia (IT) | 92 | New 40km double circuit 400kV OHL between the existing substations of West Udine and Redipuglia, providing in and out connection to the future 400kV substation of South Udine. | 4 | Investment on time | Progressed as planned | 2016 | 2016 | 1 | West Udine (IT) | Redipuglia (IT) | [5 empty] | 5 | Commissioned |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [6 empty] | 2016 |  | 6 | ITA | West Udine | Redipuglia |  |  | 45.8472 | 13.489
916 | 2014 | 2016 | [2014, 2015, 2016] | 922 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 21 | 922 | Italy-France | Removing limitations on the existing 380 kV Rondissone-Trino | 2 | New Investment | The item contributes to get the full advantage of the new HVDC cables was planned for the first time in the Italian National Development Plan 2013 | 2019 | 2019 | 1 | Rondissone (IT) | Trino (IT) | 922 | Removing limitations on the existing 380 kV Rondissone- Trino | 2 | Investment on time | Progressed as planned | 2019 | 2019 | 1 | Rondissone (IT) | Trino (IT) | 21 | 922 | Italy-France | Rondissone (IT) -Trino (IT) | Removing limitations on the existing 380 kV Rondissone-Trino | 2 | Investment on time | - | 2019 | 2019 | 1 |  | 0 | Rondissone (IT) | Trino (IT) | Overhead Line | AC | 300 | 380 | 22 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2019 | 0 | 5 | ITA | Rondissone | Trino | 45.2468 | 7.9654 | 45.1939 | 8.297
917 | 2014 | 2016 | [2014, 2015, 2016] | 923 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 21 | 923 | Italy-France | Removing limitations on the existing 380 kV Lacchiarella-Chignolo Po | 2 | New Investment | The item contributes to get the full advantage of the new HVDC cables was planned for the first time in the Italian National Development Plan 2013 | 2019 | 2019 | 1 | Lacchiarella(IT) | Chignolo Po(IT) | 923 | Removing limitations on the existing 380 kV Lacchiarella- Chignolo Po | 2 | Investment on time | Progressed as planned | 2019 | 2019 | 1 | Lacchiarella(I T) | Chignolo Po(IT) | 21 | 923 | Italy-France | Lacchiarella-Chignolo Po | Removing limitations on the existing 380 kV Lacchiarella-Chignolo Po | 2 | Investment on time | - | 2019 | 2019 | 1 |  | 0 | Lacchiarella(IT) | Chignolo Po(IT) | Overhead Line | AC | 300 | 380 | 39 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2019 | 0 | 5 | ITA | Lacchiarella | Chignolo Po | 45.3216 | 9.1373 | 45.1482 | 9.4816
918 | 2014 | 2015 | [2014, 2015] | 924 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 21 | 924 | Italy-France | Removing limitations on the existing 380 kV Vado-Vignole and Vignole-Spezia | 2 | New Investment | The item contributes to get the full advantage of the new HVDC cables was planned for the first time in the Italian National Development Plan 2013 | 2019 | 2019 | 1 | Vado (IT) | La Spezia (IT) | 924 | Removing limitations on the existing 380 kV Vado-Vignole and Vignole-Spezia | 2 | Investment on time | Progressed as planned | 2019 | 2019 | 1 | Vado (IT) | Vignole (IT) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2019 | 0 | 5 | ITA | Vado | Vignole | 44.3175 | 11.2582 | 46.1397 | 12.1252
919 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 927 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 193 | 927 | Godelleta-Morella/La Plana | New 400 kV axis Godelleta-Morella/La Plana (Spain) | 1 | Rescheduled | Investment rescheduled as a result of changes in planning data inputs. | 2023 | 2023 | 1 | La Plana/Morella | Godelleta | 927 | New 400 kV axis Godelleta-Morella/La Plana (Spain) | 1 | Investment on time | The investment progressed as previously planned | 2023 | 2023 | 1 | La Plana/Morell a | Godelleta | 193 | 927 | Godelleta-Morella/La Plana | La Plana/Morella-Godelleta | New 400 kV axis Godelleta-Morella/La Plana (Spain) | 1 | Investment on time | The investment progressed as previously planned | 1/ 1/ 2023 | 2023 | 1 |  | 0 | La Plana/Morella | Godelleta | Overhead Line | AC | 1415 | 400 | 310 | New | 193 | 927 | Godelleta-Morella/La Plana | La Plana/Morella-Godelleta | 1 | Delayed | The delay of this investment is affected by the explanation in the investment 538. | 2025 | 2025 | 1 | REE | La Plana/Morella | Godelleta | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2025 | 2 | 11 | ESP | La Planamorella | Godelleta |  |  | 39.4276 | -0.67059
920 | 2014 | 2016 | [2014, 2015, 2016] | 928 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 151 | 928 | Asturian Ring | Asturian Ring. New double circuit Gozon-Reboria-Costa Verde-Sama 400 kV | 1 | Rescheduled | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by) | 2026 | 2026 | 1 | GOZON (ES) | SAMA (ES) | 928 | Asturian Ring. New double circuit Gozon-Reboria-Sama 400 kV (in a phase I only one circuit will be installed). Subestation Costa Verde is under consideration yet and wont be part of phase I | 2 | Rescheduled | Rescheduled to be commissioned before than expected due to changes on the drivers on demand and generation in the area. It'll be part of new NDP and build as a DC. In a first step only 1 circuit will be installed. Costa Verde won’t be part of phase I | 2020 | 2020 | 1 | GOZON (ES) | SAMA (ES) | 151 | 928 | Asturian Ring | Double circuit Gozon-Sama | Asturian Ring. New double circuit Gozon-Reboria-Sama 400 kV (in a phase I only one circuit will be installed). Subestation Costa Verde is under consideration yet and wont be part of phase I | 2 | Ahead of time | Changes in the Spanish Master Plan, approved after the released of the project candidate list. This project is considered in the assessment as a future project instead a midterm one. In a first step only 1 circuit will be installed. Costa Verde wont be part of phase I | 1/ 1/ 2020 | 2020 | 1 |  | 0 | GOZON (ES) | SAMA (ES) | Overhead Line | AC | 1220 | 400 | 184 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2026 | 2020 | -6 | 6 | ESP | Gozon | Sama | 43.6057 | -5.843 | 43.2918 | -5.6795
921 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 929 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 194 | 929 | Cartuja | New double circuit Cartuja-Arcos 400 kV | 1 | Rescheduled | Investment rescheduled as the associated new wind power plants have been postponed | 2022 | 2022 | 1 | Cartuja | Arcos | 929 | New double circuit Cartuja-Arcos 400 kV | 1 | Investment on time | The investment progressed as previously planned | 2022 | 2022 | 1 | Cartuja | Arcos | 194 | 929 | Cartuja | Cartuja-Arcos 400 kV | New double circuit Cartuja-Arcos 400 kV | 1 | Rescheduled | Rescheduled due to changes in the Spanish Master Plan that consider a delay in the commissioning of the renewable generation link to this project | 1/ 1/ 2029 | 2029 | 1 |  | 0 | Cartuja | Arcos | Overhead Line | AC | 1320 | 400 | 60 | New | 194 | 929 | Cartuja | Cartuja-Arcos 400 kV | 1 | Investment on time |  | 2029 | 2029 | 1 |  | Cartuja | Arcos | Overhead Line | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2029 | 7 | 15 |  | Cartuja | Arcos | 37.4072 | -6.0101
922 | 2014 | 2016 | [2014, 2015, 2016] | 932 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 31 | 932 | Italy-Switzerland | new 400 kV section in Magenta substation | 3 | Investment on time | HVDC link between Pallanzeno and Baggio will be realized using existing 220 kV line connecting the Magenta 220/132 kV substation. Consequently, a new 400 kV section will be needed to reconnect the Magenta substation to the 400 kV line Turbigo – Baggio | 2020 | 2020 | 1 | Magenta(IT) |  | 932 | new 400 kV section in Magenta substation | 3 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Magenta(IT) |  | 31 | 932 | Italy-Switzerland | Magenta substation | new 400 kV section in Magenta substation | 3 | Investment on time | progressed as planned | 1/ 1/ 2020 | 2020 | 1 |  | 0 | Magenta(IT) |  | Substation |  | 1000 | 400 |  | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 6 | ITA | Magenta |  | 45.4654 | 8.8838
923 | 2014 | 2016 | [2014, 2015, 2016] | 933 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 120 | 933 | 2nd Offshore-Onshore Corridor | Further connection to inland: phase 2 Preliminary analysis shows the need to reinforce the 380kV network with a second offshore-onshore corridor in order to evacuate up to 4 GW of offshore wind. The solutions under study consist of multiple investment items. This investment item envisions the possibility of an AC OR DC solution going from an offshore hub OR onshore substation Stevin in Zeebrugge towards a further inland location. The reference solution presented here is an AC corridor towards Izegem. To be confirmed by further detailed studies in the coming years. The cost estimation does not take into account the offshore part of the corridor. | 1 | New Investment | Additional offshore-onshore corridor needed in order to evacuate full potential of up to 4GW (compared to current target of 2,3 GW) of offshore wind in the Belgian part of the North Sea in visions 3 & 4. | 2030 | 2030 | 1 | Offshore Hub OR Stevin - TBD | Izegem - TBD | 933 | To integrate the full potential of 4 GW, additional solutions are needed on top op the 1 GW connection to the Antwerp area. This could take the form of a complementary connection towards Izegem or Brussels, as well as a larger dimensioning of the connection to the Antwerp area. Subject to further studies. | 1 | Investment on time | Long-term potential of energy transition: additional offshore-onshore corridor needed in order to evacuate up to 4GW of offshore wind in the Belgian part of the North Sea. | 2030 | 2030 | 1 | Alfa OR Stevin - TBD | Antwerp Area OR Izegem - TBD | 120 | 933 | 2nd Offshore-Onshore Corridor (Belgium) | Complementary connection | To integrate the full potential of 4 GW, additional solutions are needed on top op the 1 GW connection to the Antwerp area. This could take the form of a complementary connection towards Izegem or Brussels, as well as a larger dimensioning of the connection to the Antwerp area.Subject to further studies. | 1 | Investment on time | Long-term potential of energy transition&#58; additional offshore-onshore corridor needed in order to evacuate up to 4GW of offshore wind in the Belgian part of the North Sea. | 1/ 1/ 2025 | 2025 | 1 |  | 0 | Offshore Hub OR Stevin - TBD | Antwerp Area OR Izegem - TBD | Underground Cable | AC | 1800 | 380 | 100 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2025 | -5 | 11 | BEL;ISL | Or Stevin - | Antwerp Area Or Izegem -
924 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 934 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 121 | 934 | 2nd Interco Belgium - UK (1GW) | NEMO 2: UK to BE 380kV inland This investment item envisions the possibility of a second 1GW HVDC connection, between UK (Kemsley) and a Belgian 380kV substation further inland in the Antwerp area (Doel, Zandvliet are indicative locations). Subject to further studies. | 1 | New Investment | Preliminary studies on vision 3&4 scenario's have indicated potential fur further regional welfare & RES integration increase by further increasing the interconnection capacity between Belgium & UK up to 2 GW. | 2030 | 2030 | 1 | Kemsley (UK) for example - TBD | Doel/Zandvliet (BE) for example - TBD | 934 | This investment item envisions the possibility of a second 1GW HVDC connection, between UK (Kemsley) and a Belgian 380kV substation further inland in the Antwerp area (Doel, Zandvliet are indicative locations). Subject to further studies. | 1 | Investment on time | Preliminary studies on high RES scenarios have indicated potential for further regional welfare & RES integration increase by further increasing the interconnection capacity between Belgium & UK. | 2030 | 2030 | 1 | Kemsley (UK) for example - TBD | Doel/Zandvlie t (BE) for example - TBD | 121 | 934 | 2nd interconnector Belgium - UK | 2nd interco UK - BE | This investment item envisions the possibility of a second 1GW HVDC connection, between UK (Kemsley) and a Belgian 380kV substation further inland in the Antwerp area (Doel, Zandvliet are indicative locations). Subject to further studies. | 1 | Investment on time | Preliminary studies have indicated potential for further regional welfare & RES integration increase by further increasing the interconnection capacity between Belgium & UK. | 1/ 1/ 2025 | 2025 | 1 |  | 1 | Kemsley (UK) for example - TBD | Doel/Zandvliet (BE) for example - TBD | Subsea Cable | DC | 1000 | 400 | 250 | New | 121 | 934 | Nautilus: 2nd interconnector Belgium - UK | Nautilus: 2nd interco UK - BE | 1 | Rescheduled |  | 2028 | 2028 | 1 | ELIA;NGIHL | Leiston (UK) | TBD (BE) | Subsea Cable | DC | 400 | 121 | 934 | Nautilus: multi-purpose interconnector Belgium - UK | Nautilus: 2nd interco UK - BE | This investment item envisions the possibility of a second HVDC connection between UK and a Belgian 380kV substation near the coast. Subject to further studies | 1 | Investment on time |  | 2028 | 2028 | 1 | ELIA National Grid |  | 1 | 1 | Leiston (UK) | TBD (BE) | OffshoreDCTransmissionCable | DC | 180 | New | 121 | 934 | Nautilus: multi-purpose interconnector Belgium - UK | Nautilus multi purpose interconnection UK - BE | This investment item envisions the possibility of a second HVDC connection between UK and Belgian offshore substation (project 120) near the coast. | 2 | Rescheduled |  | 12-2030 | 2030 | 1 | Elia, National Grid |  | 1 | 1 | Leiston (UK) | MOG2 | OffshoreDCTransmissionCable | DC | 1400 | 1050 | 140 | New | 121 | 934 | Nautilus: multi-purpose interconnector Belgium - UK | Nautilus multi purpose interconnection UK - BE | This investment item envisions the possibility of a second HVDC connection between UK and Belgian offshore substation (project 120) near the coast. | 2 | Investment on time |  | 12-2030 | 2030 | 1 | Elia, National Grid | 4.5 | 1 | 1 | Leiston (UK) | Princess Elisabeth Island | OffshoreDCTransmissionCable | DC | 1400 | 1050 | 140 | New | 121 | 934 | Nautilus: multi-purpose interconnector Belgium - UK | Nautilus multi purpose interconnection UK - BE | This investment item envisions the possibility of a second HVDC connection between UK and Belgian offshore substation (project 120) near the coast. | 2 |  | 12-2032 | 2032 | 1 | Elia, National Grid | 1 | XX | XX | New | 2030 | 2032 | 2 | 18 | BEL;GBR | Leiston | Princess Elisabeth Island | 52.2065 | 1.5764
925 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 935 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 209 | 935 | Reinforcement Northeastern DE | New 380-kV-lineKreis Segeberg - Lübeck - Siems - Göhl, including five new transformers | 1 | Rescheduled | Investment was part of investment 43.A90 in TYNDP 2012. Now separately | 2021 | 2021 | 1 | Kreis Segeberg | Göhl | 935 | New 380-kV-lineKreis Segeberg - Lübeck - Siems - Göhl, including five new transformers | 1 | Investment on time | On time relative to TYNDP14 | 2021 | 2021 | 1 | Kreis Segeberg | Göhl | 209 | 935 | Reinforcement Northeastern DE | Kreis Segeberg - Siems | New 380-kV-lineKreis Segeberg - Lübeck - Siems - Göhl, including five new transformers | 2 | Delayed | Delay due to long permitting process | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Kreis Segeberg | Göhl | Overhead Line | AC | 4482 | 380 | 110 | New | 209 | 935 | Reinforcement Northeastern DE | Kreis Segeberg - Siems | 2 | Investment on time |  | 2022 | 2022 | 1 | TENNET-DE | Kreis Segeberg | Göhl/Siems | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2022 | 1 | 8 | DEU | Kreis Segeberg | Göhlsiems | 53.9337 | 10.1203
926 | 2014 | 2014 | [2014] | 936 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 220 | 936 | Southern Aegean Interconnector | AC Subm. Cable to connect Kandeliousa offshore WF HV substation (18MW) to Syrna SS | 3 | New Investment | Project application to TYNDP 2014. Commissioning date: 2018-2020 | 2020 | 2020 | 1 | KANDELIOUSA | SYRNA |  |  | 6 | Cancelled |  |  |  | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 6 | GRC | Kandeliousa | Syrna |  |  | 36.3429 | 26.6817
927 | 2014 | 2015 | [2014, 2015] | 937 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 209 | 937 | Reinforcement Northeastern DE | New 380-kV-line in existing OHL corridor including 4 new transformers and new 380-kV-switchgears in Kiel/West and Kiel/Süd | 1 | Rescheduled | In TYNDP 2012 this investment was part of investment 43.A90 | 2021 | 2021 | 1 | Audorf | Kiel | 937 | New 380-kV-line in existing OHL corridor including 4 new transformers and new 380-kV-switchgears in Kiel/West and Kiel/Süd | 1 | Investment on time | In TYNDP 2012 this investment was part of investment 43.A90 on time relative to TYNDP14 | 2021 | 2021 | 1 | Audorf | Kiel | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2021 | 0 | 7 | DEU | Audorf | Kiel | 54.3132 | 9.7185 | 54.3227 | 10.1356
928 | 2014 | 2020 | [2014, 2015, 2016, 2018, 2020] | 939 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 207 | 939 | Reinforcement Northwestern DE | New 380-kV-line in existing OHL corridor for integration of RES | 2 | Delayed | In TYNDP 2012 part of investment 43.A89 | 2019 | 2019 | 1 | Conneforde | Emden/Ost | 939 | New 380-kV-line in existing OHL corridor for integration of RES | 2 | Investment on time | In TYNDP 2012 part of investment 43.A89 No delay relative to TYNDP 2014 | 2019 | 2019 | 1 | Conneforde | Emden/Ost | 207 | 939 | Reinforcement Northwestern DE | Conneforde - Emden | New 380-kV-line in existing OHL corridor for integration of RES | 3 | Delayed | Delay due to long permitting process | 1/ 1/ 2021 | 2021 | 1 |  | 0 | Conneforde | Emden/Ost | Overhead Line | AC | 3336 | 380 | 60 | New | 207 | 939 | Reinforcement Northwestern DE | Conneforde - Emden | 3 | Investment on time |  | 2021 | 2021 | 1 |  | Conneforde | Emden/Ost | Overhead Line | AC | 380 | 207 | 939 | Reinforcement Northwestern DE | Conneforde - Emden | New 380-kV-line in existing OHL corridor for integration of RES | 4 | Delayed | Due to complex and long permitting process | 2023 | 2023 | 1 | TenneT DE |  | 1 | 0 | Conneforde | Emden/Ost | ACTransmissionLine | AC | 60 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2023 | 4 | 9 | DEU | Conneforde | Emdenost | 53.3258 | 8.0578
929 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 940 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 207 | 940 | Reinforcement Northwestern DE | New 380-kV-line Emden - Halbemond for RES integration incl. new transformers in Halbemond | 1 | Rescheduled | In TYNDP 2012 part of investment 43.A89 | 2021 | 2021 | 1 | Emden/Ost | Halbemond | 940 | New 380-kV-line Emden - Halbemond for RES integration incl. new transformers in Halbemond | 2 | Investment on time | In TYNDP 2012 part of investment 43.A89 on time relative to TYNDP 2014 | 2021 | 2021 | 1 | Emden/Ost | Halbemond | 207 | 940 | Reinforcement Northwestern DE | Emden - Halbemond | New 380-kV-line Emden - Halbemond for RES integration incl. new transformers in Halbemond | 2 | Delayed | Delay due to long permitting process | 1/ 1/ 2022 | 2022 | 1 |  | 0 | Emden/Ost | Halbemond | Overhead Line | AC | 3336 | 380 | 25 | New | 207 | 940 | Reinforcement Northwestern DE | Emden - Halbemond | 2 | Delayed | Delay due to long permitting process | 2022 | 2022 | 1 |  | Emden/Ost | Halbemond | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2022 | 1 | 8 | DEU | Emdenost | Halbemond |  |  | 53.5658 | 7.2973
930 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 941 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 1 | 941 | RES in north of Portugal | New substation to connect a new hydro power plant. | 2 | New Investment | No changes expected | 2017 | 2017 | 1 | Fridão |  | 941 | New substation to connect a new hydro power plant. | 2 | Rescheduled | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was rescheduled | 2022 | 2022 | 1 | Fridão |  | 1 | 941 | RES in north of Portugal | Fridão | New substation to connect a new hydro power plant. | 3 | Rescheduled | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was rescheduled | 31/ 12/ 2022 | 2022 | 1 |  | 0 | Fridão |  | Substation |  | 890 | 400 |  | New | 1 | 941 | RES in north of Portugal | Switching station Fridão | 3 | Rescheduled | Due to the expected delay of the connection of new RES generation, the commissioning date of this investment item was rescheduled | 2026-2030 | 2030 | 1 |  | Fridão | - | Substation | AC | 400 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2017 | 2030 | 13 | 16 | PRT | Fridão |  | 41.3098 | -8.0343
931 | 2014 | 2016 | [2014, 2015, 2016] | 943 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 129 | 943 | OWP Northsea TenneT Part 4 | Connection of new offshore wind park. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 255 km. Line capacity: 900 MW | 1 | New Investment | new investment | 2028 | 2028 | 1 | NOR-9-1 | Cloppenburg | 943 | Connection of new offshore wind park. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 255 km. Line capacity: 900 MW | 1 | Delayed | due to new planning | 2034 | 2034 | 1 | NOR-9-1 | Unterweser | 129 | 943 | OWP Northsea TenneT Part 4 | NOR-9-1 | Connection of new offshore wind park. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 255 km. Line capacity&#58; 900 MW | 1 | Rescheduled | due to new planning | 1/ 1/ 2035 | 2035 | 1 |  | 0 | NOR-9-1 | area of Unterweser | Subsea Cable | DC | 900 | 400 | 255 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2028 | 2035 | 7 | 21 | DEU | Nor-- | Unterweser | 50.0846 | 8.2411 | 53.3256 | 8.4806
932 | 2014 | 2014 | [2014] | 944 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 220 | 944 | Southern Aegean Interconnector | AC Subm. Cable to connect Pergousa offshore WF HV substation (42MW) to the Kandeliousa SS | 3 | Investment on time | Project application to TYNDP 2014.Commissioning date: 2018-2020 | 2020 | 2020 | 1 | KANDELIOUSA | PERGOUSA |  |  | 6 | Cancelled |  |  |  | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 6 | GRC | Kandeliousa | Pergousa |  |  | 36.5876 | 27.0381
933 | 2014 | 2015 | [2014, 2015] | 945 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 129 | 945 | OWP Northsea TenneT Part 4 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 260km. Line capacity: 900 MW | 1 | New Investment | new investment | 2029 | 2029 | 1 | NOR-10-1 | Cloppenburg | 945 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 260km. Line capacity: 900 MW | 1 | Investment on time | Progressed as planned | 2029 | 2029 | 1 | NOR-10-1 | Unterweser | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2029 | 2029 | 0 | 15 | DEU | Nor-- | Unterweser | 50.0846 | 8.2411 | 53.3256 | 8.4806
934 | 2014 | 2016 | [2014, 2015, 2016] | 946 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 192 | 946 | OWP Northsea TenneT Part 3 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 230km. Line capacity: 900 MW | 1 | New Investment | new investment | 2026 | 2026 | 1 | NOR-11-1 | Elsfleth/West | 946 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 230km. Line capacity: 900 MW | 1 | Delayed | Delay due to long permitting process | 2028 | 2028 | 1 | NOR-11-1 | Wilhelmshav en | 129 | 946 | OWP Northsea TenneT Part 4 | NOR-11-1 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 230km. Line capacity&#58; 900 MW | 1 | Rescheduled |  | 1/ 1/ 2032 | 2032 | 1 |  | 0 | NOR-11-1 | area of Wilhelmshaven | Subsea Cable | DC | 900 | 400 | 230 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2026 | 2032 | 6 | 18 | DEU | Nor-- | Wilhelmshaven | 50.0846 | 8.2411 | 53.5279 | 8.1063
935 | 2014 | 2015 | [2014, 2015] | 947 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 129 | 947 | OWP Northsea TenneT Part 4 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 270km. Line capacity: 900 MW | 1 | New Investment | new investment | 2031 | 2031 | 1 | NOR-11-2 | Wilhelmshafen | 947 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 270km. Line capacity: 900 MW | 1 | Investment on time |  | 2031 | 2031 | 1 | NOR-11-2 | Unterweser | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2031 | 2031 | 0 | 17 | DEU | Nor-- | Unterweser | 50.0846 | 8.2411 | 53.3256 | 8.4806
936 | 2014 | 2016 | [2014, 2015, 2016] | 948 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 192 | 948 | OWP Northsea TenneT Part 3 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 230km. Line capacity: 900 MW | 1 | New Investment | new investment | 2027 | 2027 | 1 | NOR-12-1 | Wilhelmshafen | 948 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 230km. Line capacity: 900 MW | 1 | Delayed | Delay due to long permitting process | 2029 | 2029 | 1 | NOR-12-1 | Wilhelmshafe n 2 | 129 | 948 | OWP Northsea TenneT Part 4 | NOR-12-1 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 240km. Line capacity&#58; 900 MW | 1 | Rescheduled |  | 1/ 1/ 2034 | 2034 | 1 |  | 0 | NOR-12-1 | area of Wilhelmshafen | Subsea Cable | DC | 900 | 400 | 240 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2027 | 2034 | 7 | 20 | DEU | Nor-- | Wilhelmshafen | 50.0846 | 8.2411
937 | 2014 | 2014 | [2014] | 949 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 219 | 949 | EUROASIA interconnector | New HVDC interconnection between Crete and Athens | 2 | New Investment | Project application to TYNDP 2014. | 2020 | 2020 | 1 | Korakia site (CRETE) | Athens site (GREECE) |  |  | 6 | Cancelled |  |  |  | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 6 | GRC | Korakia Site | Athens Site
938 | 2014 | 2016 | [2014, 2015, 2016] | 950 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 192 | 950 | OWP Northsea TenneT Part 3 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 330km. Line capacity: 900 MW | 1 | New Investment | new investment | 2025 | 2025 | 1 | NOR-13-1 | Kreis Segeberg | 950 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 330km. Line capacity: 900 MW | 1 | Delayed | Delay due to long permitting process | 2027 | 2027 | 1 | NOR-13-1 | Kreis Segeberg | 129 | 950 | OWP Northsea TenneT Part 4 | NOR-13-1 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 330km. Line capacity&#58; 900 MW | 1 | Rescheduled |  | 1/ 1/ 2031 | 2031 | 1 |  | 0 | NOR-13-1 | Kreis Segeberg | Subsea Cable | DC | 900 | 400 | 330 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2025 | 2031 | 6 | 17 | DEU | Nor-- | Kreis Segeberg | 50.0846 | 8.2411 | 53.9337 | 10.1203
939 | 2014 | 2015 | [2014, 2015] | 951 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 129 | 951 | OWP Northsea TenneT Part 4 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 330km. Line capacity: 900 MW | 1 | New Investment | new investment | 2030 | 2030 | 1 | NOR-13-2 | Kreis Segeberg | 951 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 330km. Line capacity: 900 MW | 1 | Investment on time | Progressed as planned. | 2030 | 2030 | 1 | NOR-13-2 | Kreis Segeberg | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | DEU | Nor-- | Kreis Segeberg | 50.0846 | 8.2411 | 53.9337 | 10.1203
940 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 952 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 191 | 952 | OWP TenneT Northsea Part 2 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 250 km. Line capacity: 900 MW | 1 | New Investment | new investment | 2021 | 2021 | 1 | Cluster DolWin 5 (NOR-1-1) | Halbemond | 952 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 250 km. Line capacity: 900 MW | 1 | Investment on time | Progressed as planned. | 2021 | 2021 | 1 | Cluster DolWin 5 (NOR-1-1) | Cloppenburg/ East | 191 | 952 | OWP TenneT Northsea Part 2 | Cluster DolWin 5 (NOR 1-1) | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 250 km. Line capacity&#58; 900 MW | 1 | Rescheduled |  | 1/ 1/ 2024 | 2024 | 1 |  | 0 | Cluster DolWin 5 (NOR-1-1) | Halbemond | Subsea Cable | DC | 900 | 400 | 135 | New | 191 | 952 | OWP TenneT Northsea Part 2 | Cluster DolWin 5 (NOR 1-1) | 2 | Investment on time |  | 2024 | 2024 | 1 |  | Cluster DolWin 5 (NOR-1-1) | Emden/East (DE) | Subsea Cable | DC | 320 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2024 | 3 | 10 | DEU | Cluster Dolwin | Emdeneast
941 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 953 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 191 | 953 | OWP TenneT Northsea Part 2 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 60km. Line capacity: 900 MW | 1 | New Investment | new investment | 2021 | 2021 | 1 | Cluster DolWin 6 (NOR-3-3) | Halbemond | 953 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 60km. Line capacity: 900 MW | 1 | Investment on time | Progressed as planned. | 2021 | 2021 | 1 | Cluster DolWin 6 (NOR-3-3) | Halbemond | 191 | 953 | OWP TenneT Northsea Part 2 | Cluster DolWin6 | New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 60km. Line capacity&#58; 900 MW | 1 | Delayed | due to the project | 1/ 1/ 2023 | 2023 | 1 |  | 0 | Cluster DolWin 6 (NOR-3-3) | Emden/East | Subsea Cable | DC | 900 | 400 | 60 | New | 191 | 953 | OWP TenneT Northsea Part 2 | Cluster DolWin6 | 4 | Investment on time |  | 2023 | 2023 | 1 |  | Cluster DolWin 6 (NOR-3-3) | Emden/East | Subsea Cable | DC | 320 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2021 | 2023 | 2 | 9 |  | Cluster Dolwin | Emdeneast
942 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 954 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 191 | 954 | OWP TenneT Northsea Part 2 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 260km. Line capacity: 900 MW | 1 | New Investment | new investment | 2022 | 2022 | 1 | Cluster BorWin 5 (NOR-7-1) | Halbemond | 954 | Connecton of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 260km. Line capacity: 900 MW | 1 | Investment on time | Progressed as planned. | 2022 | 2022 | 1 | Cluster BorWin 5 (NOR-7-1) | Halbemond | 192 | 954 | OWP Northsea TenneT Part 3 | Cluster BorWin 5 (NOR-7-1) | Connecton of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 260km. Line capacity&#58; 900 MW | 1 | Rescheduled |  | 1/ 1/ 2025 | 2025 | 1 |  | 0 | Cluster BorWin 5 (NOR-7-1) | area of Cloppenburg/East | Underground Cable | DC | 900 | 400 | 250 | New | 192 | 954 | OWP Northsea TenneT Part 3 | Cluster BorWin 5 (NOR-7-1) | 2 | Investment on time |  | 2025 | 2025 | 1 |  | Cluster BorWin 5 (NOR-7-1) | area of Cloppenburg/East | Subsea Cable | DC | 320 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2025 | 3 | 11 | DEU | Cluster Borwin | Cloppenburgeast
943 | 2014 | 2016 | [2014, 2015, 2016] | 955 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 192 | 955 | OWP Northsea TenneT Part 3 | Connection of new offshore wind parks. New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 180km. Line capacity: 900 MW | 1 | New Investment | new investment | 2023 | 2023 | 1 | Cluster BorWin6 (NOR-7-2) | Unterweser | 955 | Connection of new offshore wind parks.New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 180km. Line capacity: 900 MW | 1 | Delayed | Delay due to long permitting process | 2024 | 2024 | 1 | Cluster BorWin6 (NOR-7-2) | Wilhelmshav en | 192 | 955 | OWP Northsea TenneT Part 3 | BorWin6 (NOR-7-2) | Connection of new offshore wind parks.New HVDC transmission system consisting of offshore platform, cable and converters with a total length of 255km. Line capacity&#58; 900 MW | 1 | Rescheduled |  | 1/ 1/ 2030 | 2030 | 1 |  | 0 | Cluster BorWin6 (NOR-7-2) | area of Wilhelmshafen | Subsea Cable | DC | 900 | 400 | 255 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2023 | 2030 | 7 | 16 | DEU | Cluster Borwin | Wilhelmshafen
944 | 2014 | 2016 | [2014, 2015, 2016] | 956 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 133 | 956 | Longterm German RES | new DC- line in HVDC technology to integrate new wind generation from northern Germany toward southern Germany and southern Europe for consumption and storage. Connections points north: Brunsbüttel, Wilster, Kreis Segeberg, Stade, Alfsted. South: Großgartach, Goldshöfe, Raitersaich, Vöhringen | 1 | New Investment | new investment | 2030 | 2030 | 1 | Schleswig-Hostein | Baden-Würtemberg / Bavaria | 956 | new DC- line in HVDC technology to integrate new wind generation from northern Germany toward soutern Germany and southern Europe for consumption and storage. Connections points north: Brunsbüttel, Wilster, Kreis Segeberg, Stade, Alfsted. South: Großgartach, Goldshöfe, Raitersaich, Vöhringen | 1 | Investment on time | not new in TYNDP2016 | 2030 | 2030 | 1 | Schleswig- Hostein | Baden- Würtemberg / Bavaria | 133 | 956 | Longterm RES-Integration in Germany | further HCDC connections C | new DC- line in HVDC technology to integrate new wind generation from northern Germany toward soutern Germany and southern Europe for consumption and storage. Connections points north&#58; Brunsbüttel, Wilster, Kreis Segeberg, Stade, Alfsted. South&#58; Großgartach, Goldshöfe, Raitersaich, Vöhringen | 1 | Investment on time |  | >2030 | 2030 | 1 |  | 0 | Schleswig-Hostein | Baden-Würtemberg / Bavaria | Overhead Line | DC | 8000 | 500 | 770 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | DEU | Schleswig-Hostein | Baden-Würtemberg Bavaria |  |  | 49.7342 | 9.339
945 | 2014 | 2016 | [2014, 2015, 2016] | 958 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 133 | 958 | Longterm German RES | New DC- lines to integrate new wind generation from Baltic Sea and control area 50Hertz especially Mecklenburg-Vorpommern towards Central/south Europe for consumption and storage. | 1 | New Investment | New Investment | 2034 | 2034 | 1 | Güstrow (DE) | Meitingen (DE) | 958 | New DC- lines to integrate new wind generation from Baltic Sea and control area 50Hertz especially Mecklenburg- Vorpommern towards Central/south Europe for consumption and storage. | 1 | Investment on time | Public resistance and therefore ongoing planning phase. | 2034 | 2034 | 1 | Güstrow (DE) | Area of Gundremmin gen (DE) | 133 | 958 | Longterm RES-Integration in Germany | DC Güstrow - Area Isar | New DC- lines to integrate new wind generation from Baltic Sea and control area 50Hertz especially Mecklenburg-Vorpommern towards Central/south Europe for consumption and storage. | 1 | Investment on time |  | >2030 | 2030 | 1 |  | 0 | Güstrow (DE) | Area of Isar (DE) | Overhead Line | DC | 2000 | 500 | 770 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2034 | 2030 | -4 | 16 | DEU | Güstrow | Isar | 53.7936 | 12.1765 | 48.2511 | 11.684
946 | 2010 | 2022 | [2010, 2012, 2013, 2014, 2015, 2016, 2018, 2020, 2022] | 96 | Commissioned | 96 | New 30km single circuit 400kV OHL between the future substations of Deliceto and Bisaccia, in the Candela area. | 3 | short term |  | 1 | Deliceto (IT) | Bisaccia (IT) | 32 | 32. 96 | New 30km single circuit 400kV OHL between the future substations of Deliceto and Bisaccia, in the Candela area. | 3 | The 2 substations are in operation from 2011. The connecting line is still in design and permitting. This delay is due to authorization process. | mid term |  | 1 | Deliceto (IT) | Bisaccia (IT) | 32. 96 | 32. 96 | New 30km single circuit 400kV OHL between the future substations of Deliceto and Bisaccia, in the Candela area. | 3 | Longer permitting process than expected (EIA) | 2017 | 2017 | 1 | Deliceto (IT) | Bisaccia (IT) | 127 | 96 | 127 | New 30km single circuit 400kV OHL between the future substations of Deliceto and Bisaccia, in the Candela area. | 3 | Delayed | delay in the permitting process (EIA) | 2017 | 2017 | 1 | Deliceto (IT) | Bisaccia (IT) | 96 | New 30km single circuit 400kV OHL between the future substations of Deliceto and Bisaccia, in the Candela area. | 3 | Delayed | delay in the permitting process (EIA) | 2018 | 2018 | 1 | Deliceto (IT) | Bisaccia (IT) | 127 | 96 | Central Southern Italy | 96 | New 30km single circuit 400kV OHL between the future substations of Deliceto and Bisaccia, in the Candela area. | 3 | Delayed | delay in the permitting process (EIA) | 31/ 12/ 2022 | 2022 | 1 |  | 0 | Deliceto (IT) | Bisaccia (IT) | Overhead Line | AC | 400 | 400 | 30 | New | 127 | 96 | Central Southern Italy | 96 | 3 | Delayed | permitting procedure | 31/ 12/ 2022 | 2022 | 1 |  | Deliceto (IT) | Bisaccia (IT) | Overhead Line | AC | 400 | 127 | 96 | Central Southern Italy | 96 | New 30km single circuit 400kV OHL between the future substations of Deliceto and Bisaccia, in the Candela area | 4 | Investment on time |  | 2021 | 2021 | 1 | TERNA |  | 0 | 0 | Deliceto (IT) | Bisaccia (IT) | ACTransmissionLine | AC | 30 | New | 127 | 96 | Central Southern Italy | New 30km single circuit 400kV OHL between the future substations of Deliceto and Bisaccia, in the Candela area | New 30km single circuit 400kV OHL between the future substations of Deliceto and Bisaccia, in the Candela area | 5 | Commissioned |  | 05-2022 | 2022 | 1 | Terna |  | 0 | 0 | Deliceto (IT) | Bisaccia (IT) | ACTransmissionLine | AC | 0 | 400 | 30 | New | [10 empty] | 0 | [21 empty] | 0 | [6 empty] | 2022 |  | 12 | ITA | Deliceto | Bisaccia | 41.223 | 15.3858 | 41.0121 | 15.3748
947 | 2014 | 2016 | [2014, 2015, 2016] | 969 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 133 | 969 | Longterm German RES | New HVDC line to integrate new wind generation especially from North Sea towards Central Germany for consumption and storage. connections points north: Emden, Conneforde. South: Oberzier, Rommerskirchen | 1 | New Investment | new investment | 2030 | 2030 | 1 | lower saxony | NRW | 969 | New HVDC line to integrate new wind gerneration especially from North Sea towards Central Germany for consumption and storage. connections points north: Emden, Conneforde. South: Oberzier, Rommerskirchen | 1 | Investment on time | not new compared to TYNDP 2014 | 2030 | 2030 | 1 | lower saxony | NRW | 133 | 969 | Longterm RES-Integration in Germany | further HVDC connections A | New HVDC line to integrate new wind gerneration especially from North Sea towards Central Germany for consumption and storage. connections points north&#58; Emden, Conneforde. South&#58; Oberzier, Rommerskirchen | 1 | Investment on time |  | >2030 | 2030 | 1 |  | 0 | Lower Saxony | North Rhine-Westphalia | Overhead Line | DC | 4000 | 500 | 360 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | DEU | Lower Saxony | North Rhine-Westphalia
948 | 2014 | 2016 | [2014, 2015, 2016] | 970 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 133 | 970 | Longterm German RES | New HVDC line to integrate new wind generation especially from North Sea towards South Germany for consumption and storage. Connections points north: Cloppenburg, Elsfelth/West. South: Bürstadt, Philipsburg | 1 | New Investment | new investment | 2030 | 2030 | 1 | lower saxony | Hessen/Baden-Würtemberg | 970 | New HVDC line to integrate new wind gerneration especially from North Sea towards South Germany for consumption and storage. Connectionspoints north: Cloppenburg, Elsfelth/West. South: Bürstadt, Philipsburg | 1 | Investment on time | not new compared to TYNDP 2014 | 2030 | 2030 | 1 | lower saxony | Hessen/Bade n- Würtemberg | 133 | 970 | Longterm RES-Integration in Germany | further HVDC connections B | New HVDC line to integrate new wind gerneration especially from North Sea towards South Germany for consumption and storage. Connectionspoints north: Cloppenburg, Elsfelth/West. South: Bürstadt, Philipsburg | 1 | Investment on time |  | >2030 | 2030 | 1 |  | 0 | Lower Saxony | Hesse/Baden-Würtemberg | Overhead Line | DC | 4000 | 500 | 500 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | DEU | Lower Saxony | Hessebaden-Würtemberg
949 | 2014 | 2014 | [2014] | 971 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 219 | 971 | EUROASIA interconnector | New HVDC interconnection between Cyprus and Crete Islands | 2 | New Investment | Project application to TYNDP 2014. | 2022 | 2022 | 1 | Vasilikos site (CYPRUS) | Korakia site (CRETE) |  |  | 6 | Cancelled |  |  |  | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2022 | 2022 | 0 | 8 | CYP;GRC | Vasilikos Site | Korakia Site
950 | 2014 | 2014 | [2014] | 973 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 220 | 973 | Southern Aegean Interconnector | AC Subm. Cable to connect Syrna offshore WF HV substation (156MW) to the AC part of the Levitha Converter SS | 3 | New Investment | Project application to TYNDP 2014. commissioning date: 2018-2020 | 2020 | 2020 | 1 | SYRNA | LEVITHA |  |  | 6 | Cancelled |  |  |  | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 6 | GRC | Syrna | Levitha | 36.3429 | 26.6817 | 37.0057 | 26.4645
951 | 2014 | 2014 | [2014] | 979 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 220 | 979 | Southern Aegean Interconnector | AC Subm. Cable to connect Kinaros offshore WF HV substation (111MW) to the AC side of the Levitha Converter SS | 3 | New Investment | Project application to TYNDP 2014. commissioning date: 2018=2020 | 2020 | 2020 | 1 | KINAROS | LEVITHA |  |  | 6 | Cancelled |  |  |  | 0 | [12 empty] | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 6 | GRC | Kinaros | Levitha | 36.9804 | 26.2873 | 37.0057 | 26.4645
952 | 2014 | 2016 | [2014, 2015, 2016] | 984 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 198 | 984 | Area of Lake Constance | Herbertingen – Tiengen: Between the two substations Herbertingen and Tiengen a new line will be constructed in an existing corridor. Enhancement of the grid, which will increase transmission capacity noticeably, is needed at the substation Herbertingen. | 2 | Investment on time | Progress as planned. This project is a concretion of TYNDP12 project 44.A77. Due to the ongoing planning stage, this section was developed and an own investment item was created. | 2020 | 2020 | 1 | Herbertingen | Tiengen | 984 | Herbertingen – Tiengen: Between the two substations Herbertingen and Tiengen a new line will be constructed in an existing corridor. Enhancement of the grid, which will increase transmission capacity noticeably, is needed at the substation Herbertingen. | 2 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | Herbertingen | Tiengen | 198 | 984 | Area of Lake Constance | Herbertingen - Tiengen | Herbertingen – Tiengen; Between the two substations Herbertingen and Tiengen a new line will be constructed in an existing corridor. Enhancement of the grid, which will increase transmission capacity noticeably, is needed at the substation Herbertingen. | 2 | Investment on time |  | 1/ 1/ 2020 | 2020 | 1 |  | 1 | Herbertingen (DE) | Tiengen (DE) | Overhead Line | AC | 400 | 380 | 115 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 6 | DEU | Herbertingen | Tiengen | 48.0601 | 9.4347 | 47.9842 | 7.7153
953 | 2014 | 2016 | [2014, 2015, 2016] | 985 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 198 | 985 | Area of Lake Constance | Rommelsbach – Herbertingen: Between point Rommelsbach and substation Herbertingen a new line will be constructed in an existing corridor. This will significantly increase transmission capacity (grid enhancement). | 2 | Investment on time | Progress as planned. This project is a concretion of TYNDP12 project 44.A77. Due to the ongoing planning stage, this section was developed and an own investment item was created. | 2018 | 2018 | 1 | point Rommelsbach | Herbertingen | 985 | Rommelsbach – Herbertingen: Between point Rommelsbach and substation Herbertingen a new line will be constructed in an existing corridor. This will significantly increase transmission capacity (grid enhancement). | 2 | Investment on time | Progressed as planned | 2018 | 2018 | 1 | point Rommelsbac h | Herbertingen | 198 | 985 | Area of Lake Constance | Rommelsb. - Herbertingen | Rommelsbach – Herbertingen; Between point Rommelsbach and substation Herbertingen a new line will be constructed in an existing corridor.This will significantly increase transmission capacity (grid enhancement). | 3 | Delayed | Delay due to long permitting process | 1/ 1/ 2019 | 2019 | 1 |  | 1 | Rommelsbach (DE) | Herbertingen (DE) | Overhead Line | AC | 400 | 380 | 62 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2018 | 2019 | 1 | 5 | DEU | Rommelsbach | Herbertingen | 48.5315 | 9.2044 | 48.0601 | 9.4347
954 | 2014 | 2016 | [2014, 2015, 2016] | 986 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 198 | 986 | Area of Lake Constance | Point Wullenstetten – Point Niederwangen Between point Wullenstetten and point Niederwangen an upgrade of an existing 380-kV-line is necessary (grid enhancement). Thereby, a significantly higher transmission capacity is realized. The 380 kV substation station Dellmensingen is due to be extended (grid enhancement). | 2 | Investment on time | This project is a concretion of TYNDP 2012 project 44.A77. Due to the ongoing planning stage, this section was developed and an own investment item was created. | 2020 | 2020 | 1 | point Wullenstetten (DE) | point Niederwangen (DE) | 986 | Point Wullenstetten – Point Niederwangen Between point Wullenstetten and point Niederwangen an upgrade of an existing 380-kV-line is necessary (grid enhancement). Thereby, a significantly higher transmission capacity is realized. The 380 kV substation station Dellmensingen is due to be extended (grid enhancement). | 2 | Investment on time | Progressed as planned | 2020 | 2020 | 1 | point Wullenstette n (DE) | point Niederwange n (DE) | 198 | 986 | Area of Lake Constance | Wullenstetten - border area (DE-AT) | Between point Wullenstetten and point border area (DE-AT) an upgrade of an existing 380-kV-line is necessary (grid enhancement). Thereby, a significantly higher transmission capacity is realized. The 380 kV substation station Dellmensingen is due to be extended (grid enhancement). Between switching point Neuravensburg and Austrian National border (AT) a new line with a significantly higher transmission capacity will be constructed in an existing corridor (grid enhancement). | 2 | Investment on time |  | 1/ 1/ 2020 | 2020 | 1 |  | 1 | Wullenstetten (DE) | Austrian National border (AT) | Overhead Line | AC | 2000 | 380 | 94 | Upgrade |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2020 | 2020 | 0 | 6 | AUT;DEU | Wullenstetten | Austrian National Border | 48.3164 | 10.0689
955 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 987 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 153 | 987 | France-Alderney-Britain | France-Alderney-Britain (FAB) is a new 220km-long HVDC subsea interconnection between Exeter (UK) and Cotentin Nord (France) with VSC converter station at both ends. Expected rated capacity is 2*700 MW. | 2 | New Investment | Studies conducted after TYNDP2012 release have shown the economic viability of this interconnection and lead to develop this investment. Feasibility studies (marine surveys)are starting to find a suitable subsea route. | 2022 | 2022 | 1 | Cotentin Nord | Exeter | 987 | France-Alderney-Britain (FAB) is a new 220km-long HVDC subsea interconnection between Exeter (UK) and Cotentin Nord (France) with VSC converter station at both ends. Expected rated capacity is 2*700 MW. | 3 | Investment on time | The project application file was approved by theFrench Ministry in July 2014. Feasibility studies (marine surveys)are in progress to find a suitable subsea route. | 2022 | 2022 | 1 | Cotentin Nord | Exeter | 153 | 987 | France-Alderney-Britain | France-Alderney-Britain | France-Alderney-Britain (FAB) is a new 220km-long HVDC subsea interconnection between Exeter (UK) and Menuel (France) with VSC converter station at both ends. Expected rated capacity is 2*700 MW. | 3 | Investment on time | The notifications of the project were approved by the French and British authorities in July 2014. Feasibility studies have been finalised and a final route identified. Consent applications will be made in 2016. | 1/ 1/ 2022 | 2022 | 1 |  | 1 | Menuel (FR) | Exeter (GB) | Subsea Cable | DC | 1400 | 320 | 220 | New | 153 | 987 | France-Alderney-Britain | France-Alderney-Britain | 3 | Investment on time | possible risk of delay due to uncertainty of regulatory decisions | 1/ 1/ 2022 | 2022 | 1 | RTE,FAB Link Ltd | Menuel (FR) | Exeter (GB) | Subsea Cable | DC | 320 | 153 | 987 | France-Alderney-Britain | France-Alderney-Britain | France-Alderney-Britain (FAB) is a new 220km-long HVDC subsea interconnection between Exeter (UK) and Menuel (France) with VSC converter station at both ends. Expected rated capacity is 2*700 MW. | 3 | Delayed | Delayed due to uncertainty of regulatory decisions | 2025 | 2025 | 1 | FABLINK limited RTE Transmission Investment | 1.7.1 | 1 | 1 | Menuel (FR) | Exeter (GB) | OffshoreDCTransmissionCable | DC | 220 | New | 153 | 987 | France-Alderney-Britain | France-Alderney-Britain | France-Alderney-Britain (FAB) is a new 220km-long HVDC subsea interconnection between Exeter (UK) and Menuel (France) with VSC converter station at both ends. Expected rated capacity is 1250 MW. | 3 | Delayed | Delayed due to uncertainty of regulatory decisions | 12-2030 | 2030 | 1 | FABLINK Limited, Rte |  | 1 | 1 | Menuel (FR) | Exeter (GB) | OffshoreDCTransmissionCable | DC | 1250 | 320 | 220 | New | 153 | 987 | France-Alderney-Britain | France-Alderney-Britain | France-Alderney-Britain (FAB) is a new 220km-long HVDC subsea interconnection between Exeter (UK) and Menuel (France) with VSC converter station at both ends. Expected rated capacity is 1250 MW. | 3 | Delayed | Delayed due to uncertainty of regulatory decisions | 12-2031 | 2031 | 1 | FABLINK Limited, Rte |  | 1 | 1 | Menuel (FR) | Exeter (GB) | OffshoreDCTransmissionCable | DC | 1250 | 320 | 220 | New | 153 | 987 | France-Alderney-Britain | France-Alderney-Britain | France-Alderney-Britain (FAB) is a new 220km-long HVDC subsea interconnection between Exeter (UK) and Menuel (France) with VSC converter station at both ends. Expected rated capacity is 1250 MW. |  |  | 06-2033 | 2033 | 1 | FABLINK Limited | 1 | XX | XX | New | 2022 | 2033 | 11 | 19 | FRA;GBR | Menuel | Exeter | 49.4974 | -1.6142 | 48.1275 | -1.6565
956 | 2014 | 2015 | [2014, 2015] | 988 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 152 | 988 | France Germany Interconnection | Upgrade of the existing Vigy Ensdorf (Uchtelfangen) 400 kV double circuit OHL to increase its capacity. | 1 | New Investment | Commissioning date will result from the on-going technical feasibility under investigation. | 2030 | 2030 | 1 | Vigy | Ensdorf or further (tbd) | 988 | Upgrade of the existing 400 kV double circuit 400kV OHL from Vigy to Uchtelfangen or beyond to increase its capacity. | 2 | Investment on time | Commissioning date will result from the on-going technical feasibility under investigation. | 2030 | 2030 | 1 | Vigy | Uchtelfangen or further (tbd) | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | DEU;FRA | Vigy | Uchtelfangen Or Further | 49.2039 | 6.298
957 | 2014 | 2015 | [2014, 2015] | 989 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 152 | 989 | France Germany Interconnection | Operation at 400 kV of the second circuit of a 400kV double circuit OHL currently operated at 225 kV ; some restructuration of the existing grid may be necessary in the area. | 1 | New Investment | Studies in progress showed the feasibility of upgrading the existing asset in order to provide mutual support to Alsace and Baden and some exchange capacity increase between France and Germany. The detailed timeline of the investment is under definition. | 2026 | 2026 | 1 | Muhlbach | Eichstetten | 989 | Operation at 400 kV of the second circuit of a 400kV double circuit OHL currently operated at 225 kV ; some restructuration of the existing grid may be necessary in the area. | 2 | Rescheduled | The detailed timeline of the investment is under definition but it is expected works should be completed slightly before initially thought. | 2025 | 2025 | 1 | Muhlbach | Eichstetten | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2026 | 2025 | -1 | 11 | AUT;BEL;DEU;FRA | Muhlbach | Eichstetten |  |  | 48.0938 | 7.7314
958 | 2014 | 2018 | [2014, 2015, 2016, 2018] | 990 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 206 | 990 | Reinforcement Southern DE | AC-extension of the "C corridor" between two of its ending points in Southern Germany allowing the existing grid to deal with the additionnal flows from DC-link | 2 | New Investment | Standard processing | 2019 | 2019 | 1 | Grafenrheinfeld (DE) | Großgartach (DE) | 990 | AC-extension of the "C corridor" between two of its ending points in Southern Germany allowing the existing grid to deal with the additionnal flows from DC-link | 2 | Rescheduled | Standard processing | 2020 | 2020 | 1 | Grafenrheinf eld (DE) | Großgartach (DE) | 206 | 990 | Reinforcement Southern DE | Grafenrheinfeld - Großgartach | AC-extension of the "C corridor" between two of its ending points in Southern Germany allowing the existing grid to deal with the additionnal flows from DC-link. | 2 | Rescheduled | Standard processing | 1/ 1/ 2020 | 2020 | 1 |  | 0 | Grafenrheinfeld (DE) | Großgartach (DE) | Overhead Line | AC | 4310 | 380 | 158 | New | 206 | 990 | Reinforcement Southern DE | Grafenrheinfeld - Großgartach | 2 | Rescheduled |  | 2022 | 2022 | 1 |  | Grafenrheinfeld (DE) | Großgartach (DE) | Overhead Line | AC | 380 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2019 | 2022 | 3 | 8 | DEU | Grafenrheinfeld | Großgartach | 49.9907 | 10.2099 | 49.1425 | 9.1259
959 | 2014 | 2016 | [2014, 2015, 2016] | 992 | Commissioned | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 94 | 992 | GerPol Improvements | Installation of new PSTs in Vierraden | 2 | New Investment | Based on a common agreement between PSE and 50Hertz the investment was specified in more detail in close cooperation between PSE and 50Hertz. The common solution consists of PST in Vierraden (DE) and PST in Mikułowa (PL) Investment 799. | 2016 | 2016 | 1 | Vierraden |  | 992 | Installation of new PSTs in Vierraden | 3 | Rescheduled | The 380 kV commissioning will be possible after finalization of the new connecting OHL from Vierraden to Neuenhagen (near Berlin) to replace the current 220 kV network and form a new 380 kV grid. | 2017 | 2017 | 1 | Vierraden |  | 94 | 992 | GerPol Improvements | PST Vierraden | Installation of new PSTs in Vierraden | 3 | Delayed | The 380 kV commissioning will be possible after finalization of the new connecting OHL from Vierraden to Neuenhagen (near Berlin) to replace the current 220 kV network and form a new 380 kV grid. | 31/12/2018 | 2018 | 1 |  | 0 | Vierraden |  | Phase Shift Transformer |  | 1200 | 380 |  | New |  |  |  |  | 5 | Commissioned |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2016 | 2018 | 2 | 4 | DEU | Vierraden |  | 53.0978 | 14.2961
960 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 995 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 176 | 995 | Hansa PowerBridge | New DC cable interconnector between Sweden and Germany. | 1 | New Investment | RGBS common investigations for TYNDP 2014 | 2025 | 2025 | 1 | Station SE4 | Station DE | 995 | New DC cable interconnector between Sweden and Germany. | 1 | Investment on time | Progressed as planned | 2025 | 2025 | 1 | Station SE4 | Station DE | 176 | 995 | Hansa PowerBridge 1 | Hansa PowerBridge | New HVDC interconnector between Sweden (SE4) and Germany (50 Hertz) aiming to enhance the integration of the Nordic and the continental power market. Moreover the interconnector facilitates RES integration and increases the system adequacy in both systems. | 2 | Investment on time | RGBS common investigations for TYNDP 2014 | 2025 | 2025 | 1 |  | 1 | Station SE4 | Güstrow (DE) | Subsea Cable | DC | 700 | 300 | 250 | New | 176 | 995 | Hansa PowerBridge I | Hansa PowerBridge I | 3 | Investment on time |  | 2026 | 2026 | 1 | 50Hertz Transmission, Svenska Kraftnät (SvK) | Hurva (SE4) | Guestrow (DE) | Subsea Cable | DC | 300 | 176 | 995 | Hansa PowerBridge I | Hansa PowerBridge I | New HVDC interconnector between Sweden (SE4) and Germany (50 Hertz) aiming to enhance the integration of the Nordic and the continental power market. Moreover the interconnector facilitates RES integration and increases the system adequacy in both systems. | 3 | Investment on time |  | 2026 | 2026 | 1 | Svenska Kraftnät 50HERTZ |  | 1 | 1 | Hurva (SE4) | Guestrow (DE) | OffshoreDCTransmissionCable | DC | 300 | New | 176 | 995 | Hansa PowerBridge I | Hansa PowerBridge I | New HVDC interconnector between Sweden (SE4) and Germany (50 Hertz) aiming to enhance the integration of the Nordic and the continental power market. Moreover the interconnector facilitates RES integration and increases the system adequacy in both systems. | 3 | Investment on time |  | 12-2026 | 2026 | 1 | 50Hertz, Svenska kraftnät |  | 1 | 1 | Hurva (SE4) | Guestrow (DE) | OffshoreDCTransmissionCable | DC | 700 | 300 | 300 | New | 176 | 995 | Hansa PowerBridge I | Hansa PowerBridge I | New HVDC interconnector between Sweden (SE4) and Germany (50 Hertz) aiming to enhance the integration of the Nordic and the continental power market. Moreover the interconnector facilitates RES integration and increases the system adequacy in both systems. | 3 | Investment on time |  | 12-2029 | 2029 | 1 | 50Hertz, Svenska kraftnät |  | 1 | 1 | Hurva (SE4) | Guestrow (DE) | OffshoreDCTransmissionCable | DC | 700 | 300 | 300 | New | 176 | 995 | Interconnector DE – SWE I [HPB I] | Interconnector DE – SWE I [HPB I] | New HVDC interconnector between Sweden (SE4) and Germany (50 Hertz) aiming to enhance the integration of the Nordic and the continental power market. Moreover the interconnector facilitates RES integration and increases the system adequacy in both systems. | 1 |  | 12-2037 | 2037 | 1 | 50Hertz, Svenska kraftnät | 1 | XX | XX | New | 2025 | 2037 | 12 | 23 | DEU;SWE | Hurva | Guestrow | 55.796 | 13.4384 | 53.7936 | 12.1765
961 | 2015 | 2015 | [2015] | 996 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 | [11 empty] | 0 |  |  | 996 | A new HVDC link between LV-SE3, only as alternative of interconnector DE-SE4 | 2 | Investment on time | Progressed as planned | 2030 | 2030 | 1 | LV-Grobina | SE3 | [5 empty] | 6 | Cancelled |  |  |  | 0 | [19 empty] | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 15 | DEU | Lv-Grobina | Se
962 | 2014 | 2026 | [2014, 2015, 2016, 2018, 2020, 2022, 2024, 2026] | 997 | [6 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 187 | 997 | St. Peter - Pleinting | new 380-kV-line Pleinting (DE) - St. Peter (AT) on existing OHL corridor | 1 | New Investment | new investment | 2022 | 2022 | 1 | Pleinting (DE) | St. Peter (AT) | 997 | new 380-kV-line Pleinting (DE) - St. Peter (AT) on exting OHL corridor | 1 | Investment on time | Investment on time relative to TYNDP14 | 2022 | 2022 | 1 | Pleinting (DE) | St. Peter (AT) | 187 | 997 | St. Peter - Pleinting | 997 Pleinting - St. Peter | new 380-kV-line Pleinting (DE) - St. Peter (AT) on exting OHL corridor | 2 | Investment on time | Investment on time relative to TYNDP14 | 1/ 1/ 2022 | 2022 | 1 |  | 1 | Pleinting (DE) | St. Peter (AT) | Overhead Line | AC | 1500 | 380 | 60 | New | 187 | 997 | St. Peter (AT) - Pleinting (DE) | St. Peter (AT) - Pleinting (DE) | 3 | Investment on time |  | 2024 | 2024 | 1 | APG;TENNET-DE | Pleinting (DE) | St. Peter (AT) | Overhead Line | AC | 380 | 187 | 997 | St. Peter (AT) - Pleinting (DE) | 997 Pleinting - St. Peter | new 380-kV-line Pleinting (DE) - St. Peter (AT) on exting OHL corridor | 3 | Investment on time |  | 2028 | 2028 | 1 | Austrian Power Grid TenneT DE |  | 1 | 1 | Pleinting (DE) | St. Peter (AT) | ACTransmissionLine | AC | 60 | New | 187 | 997 | St. Peter (AT) - Pleinting (DE) | 997 Pleinting - St. Peter | new 380-kV-line Pleinting (DE) - St. Peter (AT) on exting OHL corridor | 3 | Investment on time |  | 12-2030 | 2030 | 1 | Austrian Power Grid, TenneT DE |  | 1 | 1 | Pleinting (DE) | St. Peter (AT) | ACTransmissionLine | AC | 0 | 380 | 60 | New | 187 | 997 | St. Peter (AT) - Pleinting (DE) | 997 Pleinting - St. Peter | new 380-kV-line Pleinting (DE) - St. Peter (AT) on exting OHL corridor | 3 | Investment on time |  | 12-2030 | 2030 | 1 | Austrian Power Grid, TenneT DE | 2.1.4 | 1 | 1 | Pleinting (DE) | St. Peter (AT) | ACTransmissionLine | AC | 0 | 380 | 60 | New | 187 | 997 | St. Peter (AT) - Pleinting (DE) | 997 Pleinting - St. Peter | new 380-kV-line Pleinting (DE) - St. Peter (AT) including new 380kV switchgears and branch Pirach |  |  | 12-2030 | 2030 | 1 | Austrian Power Grid, TenneT DE | 1 | XX | XX | New | 2022 | 2030 | 8 | 16 | AUT;DEU | Pleinting | St. Peter | 48.6605 | 13.1198 | 46.6202 | 14.335
963 | 2014 | 2020 | [2014, 2015, 2016, 2018, 2020] | 998 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 167 | 998 | Viking DKW-GB | 2x700 MW HVDC subsea link across the North Seas. | 1 | New Investment | New opportunity to integrate markets, new opportunity to exploit non correlated RES | 2030 | 2030 | 1 | Idomlund (DKW) | Stella West (GB) | 998 | 2x700 MW HVDC subsea link across the North Seas. New substations on both sides: GB: Bicker Fenn; DK: Revsing | 2 | Ahead of time | Project received connection offer from GB TSO at Bicker Fenn substation. Expected DK substation changed to Revsing. Project accepted for Cap-and-Floor regime by OFGEM' | 2020 | 2020 | 1 | Idomlund (DKW) | Stella West (GB) | 167 | 998 | Viking DKW-GB | DKW-GB link | 2x700 MW HVDC subsea link across the North Seas. New substations on both sides; GB; Bicker Fenn; DK- Revsing | 3 | Investment on time | Feasibility study finalized, UK cap and floor regulation awarded, public consultation ongoing, permit procedure ongoing, pre-application procedure started. supplier engagement ongoing, preparation of tender package for cables and converter ongoing. | 31/12/ 2022 | 2022 | 1 |  | 1 | Revsing (DKW) | Bicker Fen (GB) | Subsea Cable | DC | 1400 | 500 | 760 | New | 167 | 998 | Viking DKW-GB | Viking Link DKW-GB, TYNDP ID 167.998 | 3 | Investment on time |  | 31/12/ 2022 | 2022 | 1 | Energinet.dk, NGIHL | Revsing (DKW) | Bicker Fen (GB) | Subsea Cable | DC | 515 | 167 | 998 | Viking DKW-GB | Viking Link DKW-GB, TYNDP ID 167.998 | 2 x700 MW HVDC subsea link across the North Seas. New substations on both sides; Bicker Fen (GB); Revsing (DK) | 4 | Investment on time |  | 2023 | 2023 | 1 | Energinet.dk National Grid | 1.14 | 1 | 1 | Revsing (DKW) | Bicker Fen (GB) | OffshoreDCTransmissionCable | DC | 770 | New | [5 empty] | 6 | Cancelled |  |  |  | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2023 | -7 | 9 | DNK;GBR | Revsing | Bicker Fen | 55.5073 | 9.1751 | 52.937 | -0.22881
964 | 2014 | 2016 | [2014, 2015, 2016] | 999 | Cancelled | [5 empty] | 0 | [9 empty] | 0 | [9 empty] | 0 |  |  | 216 | 999 | Massif Central North | Erection of a new 400-kV double circuit line substituting an existing 400-kV single circuit line. | 1 | Investment on time | This long term investment is only needed for scenarios with high RES development in the area, especially wind and hydro; additional studies are needed for better investment definition. | 2030 | 2030 | 1 | Marmagne | Rueyres | 999 | Erection of a new 400-kV double circuit line substituting an existing 400-kV single circuit line. | 1 | Investment on time | This long term investment is only needed for scenarios with high RES development in the area, especially wind and hydro; additional studies are in progress for better investment definition. | 2030 | 2030 | 1 | Marmagne | Rueyres | 216 | 999 | Massif Central North | North Massif Central | Erection of a new 400-kV line substituting existing 400-kV or 225-kV lines. | 1 | Investment on time | This long term investment is needed for scenarios with high RES development in the area, especially wind and hydro and/or with high exchanges with Spain as in all 2030 visions (8GW); additional studies are in progress for better investment definition. | 1/ 1/ 2030 | 2030 | 1 |  | 0 | Marmagne or Eguzon | Rueyres | Overhead Line | AC | 2700 | 400 | 275 | New |  |  |  |  | 6 | Cancelled |  |  |  | 0 | [16 empty] | 0 | [20 empty] | 0 | [22 empty] | 0 | [21 empty] | 0 | [5 empty] | 2030 | 2030 | 0 | 16 | FRA | Marmagne Or Eguzon | Rueyres |  |  | 44.7481 | 1.8464