## Sheet1
| Sentence | KMeans
0 | The investment in planning phase. Expected problems with the routing cause adoption of commissioning date. | 6
1 | Feasibility study is expected to be launched. | 1
2 | Investment rescheduled due to, and in accordance with, delayed development of new power plant, as considered in the Master Plan 2020 in progress | 6
3 | Investment 60 is postponed in the new national transmission grid development plan. Construction of new NPP, which has impact to the necessity of this investment is unclear, so priority was taken to the other internal investments needed. | 6
4 | Investment depending on Visaginas NPP construction time. | 6
5 | Investment 61 is postponed in the new national transmission grid development plan. Construction of new NPPP is unclear, so priority was taken to the other internal investments needed. | 6
6 | Rescheduled following a review of priorities and dependencies for all grid reinforcements in Sweden. Thanks to postponement of this investment, other internal investments will be commissioned on time | 6
7 | In national plan route is replaced by different project, upgrading an existing route from Tjele to Idomlund (72.898). The known route (Endrup-Idomlund) from the TYNDP12 would additionally be necessary as soon as the interconnection to GB is built. | 6
8 | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by) | 7
9 | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by) | 7
10 | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by) | 7
11 | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by) | 7
12 | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by) | 7
13 | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by) | 7
14 | Investment rescheduled as the associated new wind power plants have been postponed | 6
15 | Investment rescheduled due to, and in accordance with, delayed development of new power plant, as considered in the Master Plan 2020 in progress | 6
16 | Investment rescheduled due to, and in accordance with, delayed development of new power plant, as considered in the Master Plan 2020 in progress | 6
17 | Investment was at conceptual stage in TYNDP2012; on-going feasibility studies lead to a more accurate commissioning date. | 6
18 | The need for this long-term investment was not confirmed by the regulatory authority within the national grid development plan 2012. Therefore further studies on this project are ongoing. | 6
19 | Delay due to missing confirmation by the regulator | 6
20 | Delay due to missing confirmation by the regulator | 6
21 | Delay due to missing confirmation by the regulator | 6
22 | Delay due to missing confirmation by the regulator | 6
23 | Change of the commissioning date as the investment is correlated with the investment 140. | 6
24 | Thanks to postponement, other internal investments will be commissioned on time. Congestions due to the delay will be handled by investing in a temporary system protection scheme. | 6
25 | Delayed due to anticipated changes in the local generation background. | 2
26 | Due to the expected delay on the connection of new RES in Portugal, the commissioning date of this project is delayed | 4
27 | Due to the expected delay on the connection of new RES in Portugal, the commissioning date of this project is delayed | 4
28 | Investment progresses as planned, rescheduled slightly since last TYNDP due to expected development on the drivers behind the investment. | 6
29 | The development of wind energy in Lower Austria was temporarily stopped by the federal state government to establish a concept for land use. Final concept was published in beginning of 2014 – project now continues with planned commissioning in 2021. | 6
30 | Investment rescheduled as a result of changes in planning data inputs. | 7
31 | Investment rescheduled as a result of changes in planning data inputs (demand reduction and projects of new thermal units are in stand by) | 7
32 | Investment rescheduled as the associated new wind power plants have been postponed | 6
33 | Investment was part of investment 43.A90 in TYNDP 2012. Now separately | 6
34 | In TYNDP 2012 this investment was part of investment 43.A90 | 6
35 | In TYNDP 2012 part of investment 43.A89 | 6
36 | The project have been moved forward because of prioritisation of the Synchronization project to which all those investments are related to | 0
37 | The project have been moved forward because of prioritisation of the Synchronization project to which all those investments are related to | 0
38 | The project have been moved forward because of prioritisation of the Synchronization project to which all those investments are related to | 0
39 | The project have been moved forward because of prioritisation of the Synchronization project to which all those investments are related to | 0
40 | In the previous TYNDP 2014 the investment was selected under the project Baltic corridor ID 163 and initially it was planed as 330 kV OHL between substations Salaspils RigasCHP2. During the CPS for TYNDP 2016 in the RGBS we explored that whole project B | 6
41 | Swissgrid has issued its new national strategic grid, and this investment is no longer in the (in the TYNDP 2016 jargon) mid-term category | 6
42 | The decision on the realization of the investment has been postponed. Alternative developments (internal reinforcements) will be realized to ensure the same cross border effect. | 6
43 | Planning ongoing minor delay due to coordination with project 183.1018 | 6
44 | No significant change | 5
45 | Due to the expected delay of the connection of new RES generation in North of Portugal, the commissioning date of this investment item was rescheduled | 4
46 | Feasibility study is expected to be launched. | 1
47 | additional investigation of feasibility | 6
48 | Changes on the generation side (in relation to other types of generation) | 2
49 | The investment progressed as previously planned. Intergovernmental agreements ask for speed up implementation of this project | 6
50 | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was rescheduled. | 4
51 | Changes in plans of thermal plants at Eemshaven offers the opportunity to phase the grid expansions. The a first phase consists of a new 380 kV connection between Eemshaven-Oudeschip and Vierverlaten and the upgrade the circuits form Diemen-Lelystad-Ens | 6
52 | Changes in the generation background | 2
53 | Based on current the generation connection dates the investment has been rescheduled. | 6
54 | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was rescheduled. | 4
55 | Due to the expected delay of the connection of new RES generation in Portugal, the commissioning date of this investment item was rescheduled | 4
56 | Due to the expected delay of the connection of new hydro power plant, the commissioning date of this investment item was rescheduled | 4
57 | Due to the expected delay of the connection of new hydro power plant, the commissioning date of this investment item was rescheduled | 4
58 | Changes due to correlation with Asturias Ring (investment 928) | 2
59 | Changes due to correlation with Asturias Ring (investment 928) | 2
60 | Planning has been actualized in accordance to achieved progress, with the evaluation of the final investment decision currently planned in 2018 | 6
61 | With the hypothesis of the nuclear phase out taking place as per the current legal framework in combination with the cancellation of plans to construct new production units in the area, the third phase of BRABO has been rescheduled. | 6
62 | The project is under consideration following to the changing scenario conditions. | 0
63 | Feasibility study is expected to be launched and it will be financed by EBRD. The Terms of Reference for the study will be finalized soon and will be followed by the process of procurement and contracting | 1
64 | Feasibility study is expected to be launched and it will be financed by EBRD. The Terms of Reference for the study will be finalized soon and will be followed by the process of procurement and contracting | 1
65 | Feasibility study is expected to be launched and it will be financed by EBRD. The Terms of Reference for the study will be finalized soon and will be followed by the process of procurement and contracting | 1
66 | Feasibility study is expected to be launched and it will be financed by EBRD. The Terms of Reference for the study will be finalized soon and will be followed by the process of procurement and contracting | 1
67 | Feasibility study is expected to be launched and it will be financed by EBRD. The Terms of Reference for the study will be finalized soon and will be followed by the process of procurement and contracting | 1
68 | Robustness of the envisioned solution towards the long- term perspective of the energy transition is subject of ongoing studies. | 6
69 | The commissioning date of the Investment has been rescheduled due to the postponing of the development of offshore windfarms in the North Sea. | 6
70 | The project is under consideration following to the changing scenario conditions. | 0
71 | Investment rescheduled as a result of changes in load forecast | 7
72 | Investment rescheduled as a result of changes in load forecast | 7
73 | Investment is dependent on the future operation of the SK-UA existing cross-border line, which has been prolonged till around 2030 based on the diagnostics. | 3
74 | The project is under consideration and will be realized if the decision on the construction of the third PL-DE line will be taken. | 6
75 | Due to change of plans of investments 58.140 and 58.726 this investment is also no longer associated with cross border development. However the same location for new substation is under consideration regarding the needs of local distribution operator. | 6
76 | Svenska kraftnät has changed estimated time for the permission process due to new information. | 6
77 | Postponed due to the build-up of generation schemes in the East Anglia area and demand increases in London. | 2
78 | Reschedules due to changes in generation background | 2
79 | Changes on the generation background | 2
80 | Rescheduled due to changes in the generation timescales. | 2
81 | Due to the expected delay of the connection of new hydro power plant, the commissioning date of this investment item was rescheduled | 4
82 | This new investment has been identified as a beneficial project in the NSCOGI study and is part of the national grid development plan | 6
83 | Rescheduled to be commissioned before than expected due to changes on the drivers on demand and generation in the area. It'll be part of new NDP and build as a DC. In a first step only 1 circuit will be installed. Costa Verde won’t be part of phase I | 2
84 | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was rescheduled | 4
85 | The detailed timeline of the investment is under definition but it is expected works should be completed slightly before initially thought. | 6
86 | Standard processing | 5
87 | The 380 kV commissioning will be possible after finalization of the new connecting OHL from Vierraden to Neuenhagen (near Berlin) to replace the current 220 kV network and form a new 380 kV grid. | 6
88 | Baltic States desinchronisation | 6
89 | - | 6
90 | - | 6
91 | - | 6
92 | In-depth feasibility studies are needed to find the most suitable solution taking into account socio-environmental conditions. The commissioning date is being reassessed accordingly. | 6
93 | - | 6
94 | Comissioning date changed from 2030 to 2025, to avoid splitting project 170."Baltic synchronisation" in two stages. | 0
95 | Comissioning date changed from 2030 to 2025, to avoid splitting project 170."Baltic synchronisation" in two stages. | 0
96 | The project has been rescheduled with an indicative date of 2025 related to its potential to security-of-supply (adequacy) contribution within a context of planned nuclear phase out. The evaluation of this potential as well as interaction with reinforcements on neighboring borders are subject of further studies. | 6
97 | The detailed timeline of the investment is under definition but it is expected works should be completed slightly before initially thought. | 6
98 | No significant change | 5
99 | Due to the expected delay of the connection of new RES generation in North of Portugal, the commissioning date of this investment item was rescheduled | 4
100 | Tests and gaining of experience for novel technical solution in progress. | 5
101 | Tests and gaining of experience for novel technical solution in progress | 5
102 | Feasibility study is expected to be launched. | 1
103 | additional investigation of feasibility | 6
104 | Changes on the generation side (in relation to other types of generation) | 2
105 | There is a common political will to speed up the project, but more detailed technical studies showed the need to reschedule the project till 2025 due to manufacturing and installation needs adjustment. Specifically there will be a partial operation of the link before 2025 as the first bipole will be in service in 2024. | 6
106 | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was rescheduled. | 4
107 | Changes in the generation background | 2
108 | Based on current the generation connection dates the investment has been rescheduled. | 6
109 | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was rescheduled. | 4
110 | Due to the expected delay of the connection of new RES generation in Portugal, the commissioning date of this investment item was rescheduled | 4
111 | Due to the expected delay of the connection of new hydro power plant, the commissioning date of this investment item was rescheduled | 4
112 | Due to the expected delay of the connection of new hydro power plant, the commissioning date of this investment item was rescheduled | 4
113 | Rescheduled due to changes in the Spanish Master Plan that consider a delay in the commissioning of the renewable generation link to this project | 2
114 | Feasibility studies showed the works are lighter and could be achieved earlier than initially thought. | 6
115 | Further studies performed after TYNDP2014 confirmed the feasibility of the project. The commisionning date follows the amount of generation installation in the area (Hydro, Solar and Wind). | 6
116 | Detailed feasibility studies showed the works could be achieved by 2022, earlier than initially planned, assuming acquisition of all necessary permits as planned. | 6
117 | BRABO III will be realized sequentially after BRABO II in anticipation of potential future integration of production unit / interconnectors in the Antwerp area, hereby safeguarding the long-term character of the increase of interconnection capacity of the North Border. | 6
118 | Feasibility study is expected to be launched. | 1
119 | Feasibility study is expected to be launched. | 1
120 | Feasibility study is expected to be launched. | 1
121 | Feasibility study is expected to be launched. | 1
122 | The commissioning date has been updated to be coherent with the new schedule of the activities also considering that the construction phase of the substation started in mid 2014 | 6
123 | Planning in progress coordinatedly between TERNA and APG | 6
124 | Feasibility study is expected to be launched. | 1
125 | Robustness of the envisioned reference solution towards the long-term perspective of the energy transition is subject of ongoing studies. | 6
126 | The commissioning date of the investment has been rescheduled due to the postponement of the development of offshore windfarms in the North Sea. | 6
127 | The need for this long-term investment was not confirmed by the regulatory authority within the national grid development plan 2014. Therefore the project has been rescheduled and further studies on this project are ongoing. | 6
128 | Standard processing | 5
129 | additional investigation of feasibility | 6
130 | Investment is dependant on the future operation of the SK-UA existing cross-border line, which has been prolongued till around 2030 based on the diagnostics. | 3
131 | Commissioning date is current estimation | 6
132 | 2019 refers to 1st step in modular construction of an offshore hub. Subject of ongoing alignment with wind farm developers and competent authorities. MOG is presented here into the extent that it would be considered as regulated infrastructure. | 6
133 | Investment on time | 6
134 | Rescheduled due to changes in the generation timescales. | 2
135 | The commissioning date was adjusted to optimize the planning and development of transmission system. | 6
136 | Due to the expected delay of the connection of new hydro power plant, the commissioning date of this investment item was rescheduled | 4
137 | The project is now starting the Initial Design and Pre-consultation Phase Feasibility Study resulted in minor commissioning postponement. | 6
138 | Rescheduled due to changes in the Spanish Master Plan that consider a delay in the commissioning of the renewable generation link to this project | 2
139 | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was rescheduled | 4
140 | due to new planning | 6
141 | Standard processing | 5
142 | under consideration, commissioning year 2035 | 6
143 | The National Regulatory Authorities of Greece and Cyprus approved the submitted Investment Request for the Project and agreed on the CBCA between them. The decision "Cross-Border Cost Allocation Between the Hellenic Regulatory Authority for Energy (RAE) and the Cyprus Energy Regulatory Authority (CERA)" provided on 10th of October 2017 concerned the implementation of PCIs 3.10.2 & 3.10.3. With the corresponding decision for PCI 3.10.1 not yet received, and to avoid delays in the implementation of the Project and to be in line with the obligations and commitments arising from the CBCA approval, the Project Promoter decided to amend the order of implementation of the three PCIs consisting PCI 3.10 as follows, with PCIs 3.10.2 & 3.10.3 implemented concurrently: PCI 3.10.3 Interconnection between Korakia, Crete and Attica region(EL) PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY) | 3
144 | The National Regulatory Authorities of Greece and Cyprus approved the submitted Investment Request for the Project and agreed on the CBCA between them. The decision "Cross-Border Cost Allocation Between the Hellenic Regulatory Authority for Energy (RAE) and the Cyprus Energy Regulatory Authority (CERA)" provided on 10th of October 2017 concerned the implementation of PCIs 3.10.2 & 3.10.3. With the corresponding decision for PCI 3.10.1 not yet received, and to avoid delays in the implementation of the Project and to be in line with the obligations and commitments arising from the CBCA approval, the Project Promoter decided to amend the order of implementation of the three PCIs consisting PCI 3.10 as follows, with PCIs 3.10.2 & 3.10.3 implemented concurrently: PCI 3.10.3 Interconnection between Korakia, Crete and Attica region(EL) PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY) | 3
145 | The National Regulatory Authorities of Greece and Cyprus approved the submitted Investment Request for the Project and agreed on the CBCA between them. The decision "Cross-Border Cost Allocation Between the Hellenic Regulatory Authority for Energy (RAE) and the Cyprus Energy Regulatory Authority (CERA)" provided on 10th of October 2017 concerned the implementation of PCIs 3.10.2 & 3.10.3. With the corresponding decision for PCI 3.10.1 not yet received, and to avoid delays in the implementation of the Project and to be in line with the obligations and commitments arising from the CBCA approval, the Project Promoter decided to amend the order of implementation of the three PCIs consisting PCI 3.10 as follows, with PCIs 3.10.2 & 3.10.3 implemented concurrently: PCI 3.10.3 Interconnection between Korakia, Crete and Attica region(EL) PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY) | 3
146 | posteponed | 5
147 | under consideration, commissioning year 2035 | 6
148 | LEG1 has been rescheduled to allow for 150 MW solar power plant (comprising energy storage) to be developped. GreenPower2020 feel this is necessary for 2 reasons: 1. to test and to qualify technologies in a given environment (hence not duplicating previous errors from others) and to identify the appropriate combination (PV + battery, CSP + steam, ...) before the utility-scale deployment of 2 x 1 GW. 2. To include energy generation as part of the project to enable LEG1's bi-lateral power exchange capability immediately. | 6
149 | Shifted to Long Term due to feasibility reasons - new Mid Term Project introduced. | 6
150 | Tests and gaining of experience for novel technical solution in progress. | 5
151 | increased construction complexity | 6
152 | Due to the expected delay of the connection of new RES generation, the commissioning date of this investment item was rescheduled | 4
153 | Tests and gaining of experience for novel technical solution in progress. | 5
154 | Having dificulities with acquiring the land | 8
155 | Having dificulities with acquiring the land | 8
156 | Having dificulities with acquiring the land | 8
157 | Due to the delay of the needed connection line Vitkov-Vernerov or Vitkov-Prestice, the timeschedule has to be aligned with the timeschedule of the line Vitkov-Prestice | 6
158 | The construction of phase one is completed. The second phase of construction (extention for the purpose of connection of new line) has to be aligned with the timeschedule of line Kocin-Mirovka | 6
159 | Due to the expected delay of the connection of new RES generation, the commissioning date of this investment item was rescheduled | 4
160 | A capacity review of committed generators and upcoming new connection policy rules will impact on renewable generation totals that drive the date of need for this investment. | 5
161 | Due to the expected delay of the connection of new RES generation, the commissioning date of this investment item was rescheduled | 4
162 | Project is expected 1 year earlier than TYNDP16 | 0
163 | Slight delay in the project development. | 6
164 | The commissioning date has been been updated to be consistent with the new plan of activities | 6
165 | An increase of transfer capacity across the BE-LU-DE corridor is envisioned towards the 2030-2040 time horizon. | 5
166 | Having dificulities with acquiring the land | 8
167 | A capacity review of committed generators and upcoming new connection policy rules will impact on renewable generation totals that drive the date of need for this investment. | 5
168 | A capacity review of committed generators and upcoming new connection policy rules will impact on renewable generation totals that drive the date of need for this investment. | 5
169 | Due to the expected delay of the connection of new RES generation, the commissioning date of this investment item was rescheduled | 4
170 | The remaining lifetime of Fenno-Skan 1 will be investigated before making final decisions on its renewal. In addition, a joint study showed that the substantial benefits of this project will be realized in case of significant increase of consumption, new RES generation or the decommissioning of the remaining Swedish Nuclear plants which is expected in the 2040s. | 6
171 | The National Regulatory Authorities of Greece and Cyprus approved the submitted Investment Request for the Project and agreed on the CBCA between them. The decision "Cross-Border Cost Allocation Between the Hellenic Regulatory Authority for Energy (RAE) and the Cyprus Energy Regulatory Authority (CERA)" provided on 10th of October 2017 concerned the implementation of PCIs 3.10.2 & 3.10.3. With the corresponding decision for PCI 3.10.1 not yet received, and to avoid delays in the implementation of the Project and to be in line with the obligations and commitments arising from the CBCA approval, the Project Promoter decided to amend the order of implementation of the three PCIs consisting PCI 3.10 as follows, with PCIs 3.10.2 & 3.10.3 implemented concurrently: PCI 3.10.3 Interconnection between Korakia, Crete and Attica region(EL) PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY) | 3
172 | The National Regulatory Authorities of Greece and Cyprus approved the submitted Investment Request for the Project and agreed on the CBCA between them. The decision "Cross-Border Cost Allocation Between the Hellenic Regulatory Authority for Energy (RAE) and the Cyprus Energy Regulatory Authority (CERA)" provided on 10th of October 2017 concerned the implementation of PCIs 3.10.2 & 3.10.3. With the corresponding decision for PCI 3.10.1 not yet received, and to avoid delays in the implementation of the Project and to be in line with the obligations and commitments arising from the CBCA approval, the Project Promoter decided to amend the order of implementation of the three PCIs consisting PCI 3.10 as follows, with PCIs 3.10.2 & 3.10.3 implemented concurrently: PCI 3.10.3 Interconnection between Korakia, Crete and Attica region(EL) PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY) | 3
173 | Awaiting PCI status | 3
174 | posteponed | 5
175 | LEG1 has been rescheduled to allow for 150 MW solar power plant (comprising energy storage) to be developped. GreenPower2020 feel this is necessary for 2 reasons: 1. to test and to qualify technologies in a given environment (hence not duplicating previous errors from others) and to identify the appropriate combination (PV + battery, CSP + steam, ...) before the utility-scale deployment of 2 x 1 GW. 2. To include energy generation as part of the project to enable LEG1's bi-lateral power exchange capability immediately. | 6
176 | Tests and gaining of experience for novel technical solution in progress. | 5
177 | Tests and gaining of experience for novel technical solution in progress. | 5
178 | Due to the expected delay of the connection of new RES generation, the commissioning date of this investment item was rescheduled | 4
179 | Having dificulities with acquiring the land | 8
180 | Having dificulities with acquiring the land | 8
181 | A capacity review of committed generators and upcoming new connection policy rules will impact on renewable generation totals that drive the date of need for this investment. | 5
182 | Rescheduled due to technical issue on HTLS cable | 6
183 | Delay in Permitting procedure | 6
184 | An increase of transfer capacity across the BE-LU-DE corridor is envisioned towards the 2030-2040 time horizon. | 5
185 | A capacity review of committed generators and upcoming new connection policy rules will impact on renewable generation totals that drive the date of need for this investment. | 5
186 | A capacity review of committed generators and upcoming new connection policy rules will impact on renewable generation totals that drive the date of need for this investment. | 5
187 | During the planning and design process since last TYNDP 2020 the exact construction and outage schedule was specified and coordinated and therefore the line reconstruction schedule was also changed. Planned commissioning in October-November 2025. Planned construction starts June 2023. | 6
188 | Adjustment of commissioning date to 2026 during the project planning process. | 6
189 | According to new studies, Fenno-Skan 1 lifetime can be continued until 2040 and this project will be commissioned after that. | 6
190 | additionnal works in Ensdorf to receive the PST need to be coordinated with previous works in the same substation (upgrade transformer) for internal reason | 6
191 | The PCI was rescheduled due 2 main reasons. 1) Regulatory processes in the Republic of Ireland has taken longer than anticipated. 2) Irish planning process has taken longer than planned. The project has now received approvals from regulators from both UK and Ireland and its planning permission. The project expects financial close in December 21 | 6
192 | Scope of the project changed due to technical reasons. Investment 1476 Wullenstetten – National Border DE-AT was previously under Project 322. | 6
193 | This investment item is postponed due to mutual agreement | 6
194 | The project has been rescheduled to be in line with the timing of other grid reinforcements to be compliant with the Clean Energy Package. | 6
195 | Revision of the grid expansion concept. Cascade effects due to project delays in projects ranked ahead. | 6
196 | Revision of the expansion concept. Cascade effects due to project delays in projects ranked ahead. | 6
197 | Due to increasing difficulties in the identification of feasible corridors with acceptable environmental and social impact, it was decided to reassess the project and its configuration considering the new network developments in the region and the update on the expected generation and demand evolution. | 6
198 | Adjustment of commissioning date to 2026 due to the long and complex approval process. | 6
199 | Adjustment of commissioning date to 2027 during the project planning process. | 6
200 | According to new studies, Fenno-Skan 1 lifetime can be continued until 2040 and this project will be commissioned after that. | 6
201 | This investment item is postponed due to mutual agreement | 6
202 | Reevaluation of the project's schedule | 0
203 | The end of construction of Darbėnai substation is expected to be delayed due to contractor’s delay to finalize technical design documentation of 330 kV Darbėnai switchyard. For this reason, the construction permit was received only on June 12th 2023 (initial plan was January 2023). Respectively, the preparation of detailed design and the construction works are being delayed. | 6
204 | The implementation timeline of GREGY Green Energy Interconnector has been updated by considering the ongoing execution of the final feasibility study. The final feasibility study will have been completed by May 2024. The project will be commissioned by December 2028 at the latest. This is a conservative plan, as the project promoter aims to exploit the possibility of reaching an agreement with the potential suppliers of cables and Electromechanical equipment (e.g., converters, etc.) to reduce the delivery time and hence reduce the overall time required to implement GREGY. | 6
205 | expansion of the project scope because of legislative change (empty tube/ cable tube) | 0
206 | expansion of the project scope because of legislative change (empty tube/ cable tube) | 0
207 | Revision of the grid expansion concept. Cascade effects due to project delays in projects ranked ahead. | 6
208 | Revision of the expansion concept. Cascade effects due to project delays in projects ranked ahead. | 6
209 | Revision of Danish Energy Island concept | 3
210 | Revision of Danish Energy Island concept | 3
211 | Reevaluation of the project's schedule | 0
212 | delay due to COVID crisis and to time required for the contractualisation of the 2 main EPC contracts | 6