## Sheet1
index | Inv_Status | year | Inv_index | Inv_Progress | Inv_Progress Driver | Cluster | Category
0 | 4 | 2014 | 1 | Delayed | Although the investment is already under construction some constraints regarding environmental issues led the commissioning date to delay | 13 | Delayed Cluster 13
31 | 2 | 2014 | 1039 | Delayed | The Volpago Substation was included in the TYNDP 2012 as part of the item 26.83 which had as commissioning date 2015. Permitting process delayed due to territorial constraint | 13 | Delayed Cluster 13
47 | 3 | 2014 | 1069 | Delayed | Delayed because National law RDL 13/2012 has frozen the permitting process until publication of the next NDP | 2 | Delayed Cluster 2
48 | 3 | 2014 | 1070 | Delayed | Delayed because National law RDL 13/2012 has frozen the permitting process until publication of the next NDP | 2 | Delayed Cluster 2
50 | 3 | 2014 | 1075 | Delayed | New axis for transits from East to the West, typically from Bulgaria to Bosnia and Montenegro, and further to the west. | 13 | Delayed Cluster 13
51 | 3 | 2014 | 1076 | Delayed | This upgrade is required for the construction of new 400 kV OHL Kragujevac - Kraljevo which will increase local security of supply and power transfer from Eastern to Western part of region. | 13 | Delayed Cluster 13
56 | 2 | 2014 | 1112 | Delayed | Delayed due to lack of funding | 14 | Delayed Cluster 14
65 | 3 | 2014 | 121 | Delayed | long permitting procedure (comprising several phases) | 6 | Delayed Cluster 6
74 | 3 | 2014 | 122 | Delayed | long permitting procedure (comprising several phases) | 6 | Delayed Cluster 6
128 | 3 | 2014 | 128 | Delayed | long permitting procedure (comprising several phases) | 6 | Delayed Cluster 6
138 | 3 | 2014 | 129 | Delayed | long permitting procedure (comprising several phases). In this case, Federal Court decision for partial cabling. | 6 | Delayed Cluster 6
144 | 3 | 2014 | 134 | Delayed | lines: long permitting procedure (comprising several phases)- Mühleberg substation: under construction | -1 | Outlier
217 | 2 | 2014 | 144 | Delayed | Planning ongoing - minor delay due to coordination with project 183.1018 | 14 | Delayed Cluster 14
228 | 3 | 2014 | 145 | Delayed | Permitting procedures take longer than expected | 0 | Delayed Cluster 0
237 | 3 | 2014 | 146 | Delayed | BE: Several months delay due to authorisation procedure in Belgium longer than expected (modification of "Plan de secteur" in Wallonia). DE: Delay due to unclear permitting framework (legal framework for planning approval is presently under development | 6 | Delayed Cluster 6
239 | 4 | 2014 | 147 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
246 | 3 | 2014 | 148 | Delayed | delay due to long permitting process | 0 | Delayed Cluster 0
252 | 3 | 2014 | 149 | Delayed | The investment is delayed because of changes in the investment driver | 10 | Delayed Cluster 10
269 | 3 | 2014 | 151 | Delayed | delay due to long permitting process | 0 | Delayed Cluster 0
290 | 3 | 2014 | 153 | Delayed | Delayed due to delayed of related investment 45.193 and unexpected long permitting process of the investment itself | 10 | Delayed Cluster 10
314 | 3 | 2014 | 156 | Delayed | The project is delayed due to delays in public-law and civil-law licensing procedures. | 14 | Delayed Cluster 14
323 | 3 | 2014 | 157 | Delayed | delay due to long permitting process | 0 | Delayed Cluster 0
332 | 4 | 2014 | 160 | Delayed | Delay due delay of windfarms | 0 | Delayed Cluster 0
358 | 4 | 2014 | 164 | Delayed |  | 7 | Delayed Cluster 7
366 | 4 | 2014 | 165 | Delayed |  | 7 | Delayed Cluster 7
382 | 4 | 2014 | 167 | Delayed |  | 7 | Delayed Cluster 7
487 | 4 | 2014 | 179 | Delayed | The section Rommerskrichen to Sechtem is delayed because the permitting procedures take longer than planned. The 36 km section from Sechtem to Weißenturm is already commissioned. | 6 | Delayed Cluster 6
497 | 3 | 2014 | 18 | Delayed | Delays in authorization process due to a change on the route and on the location of substations, induced by environmental concerns | 11 | Delayed Cluster 11
554 | 3 | 2014 | 193 | Delayed | Previously "mid term" is now updated to specific date. Partly under construction (section Vieselbach – Altenfeld). 3rd section (Altenfeld – Redwitz) in permitting process, long permitting process with strong public resistance. | -1 | Outlier
614 | 2 | 2014 | 2 | Delayed | Due to the expected delay of the connection of new RES generation in North of Portugal, the commissioning date of this investment item is delayed | -1 | Outlier
683 | 3 | 2014 | 212 | Delayed | delayed due to long permitting process | 0 | Delayed Cluster 0
684 | 2 | 2014 | 214 | Delayed | Expected commission date postponed on 2018 by reason of difficulties associated with finding the common national border crossing point. | -1 | Outlier
691 | 4 | 2014 | 235 | Delayed | slight delay, due to procedural reasons. In particular the previous tender has been cancelled and a new one was launched. Currently the project is under construction | -1 | Outlier
692 | 4 | 2014 | 236 | Delayed | land acquisition | 5 | Delayed Cluster 5
694 | 3 | 2014 | 239 | Delayed | additional investigation of feasibility | -1 | Outlier
695 | 3 | 2014 | 244 | Delayed | Delays in the expropriation and permission process. These issues have been resolved. | -1 | Outlier
696 | 3 | 2014 | 256 | Delayed | Delayed due to lack of funding. | 14 | Delayed Cluster 14
697 | 3 | 2014 | 257 | Delayed | Delayed due to difficulties with the acquisition of the land | 5 | Delayed Cluster 5
698 | 3 | 2014 | 258 | Delayed | Delayed due to difficulties with the acquisition of the land | 5 | Delayed Cluster 5
699 | 3 | 2014 | 262 | Delayed | Delayed due to difficulties with the acquisition of the land | 5 | Delayed Cluster 5
700 | 2 | 2014 | 265 | Delayed | Delayed due to lack of funding. | 14 | Delayed Cluster 14
701 | 3 | 2014 | 269 | Delayed | The investment was coordinated with investment 50.238. The main problems are right of land along the line path and permitting. | 10 | Delayed Cluster 10
703 | 3 | 2014 | 273 | Delayed | Longer than expected delay regarding clarification of legal framework for right of land acquirement and regarding environment permitting procedure. | 4 | Delayed Cluster 4
707 | 3 | 2014 | 302 | Delayed | Delayed due to permitting procedure difficulty | 0 | Delayed Cluster 0
708 | 3 | 2014 | 303 | Delayed | Delay caused by permitting process difficulty | 0 | Delayed Cluster 0
709 | 3 | 2014 | 304 | Delayed | Delayed due to permitting procedure difficulty | 0 | Delayed Cluster 0
710 | 3 | 2014 | 306 | Delayed | Complication of permitting procedure | 6 | Delayed Cluster 6
711 | 3 | 2014 | 307 | Delayed | Complication with permitting procedure. | 6 | Delayed Cluster 6
715 | 3 | 2014 | 311 | Delayed | Project commissioning date postponed due to rescheduling of transmission projects together with commission rescheduled on the generation investor's side | 13 | Delayed Cluster 13
716 | 3 | 2014 | 312 | Delayed | Project delayed due to rescheduling of transmission projects together with commission rescheduled on the generation investor's side | -1 | Outlier
717 | 3 | 2014 | 313 | Delayed | Project commissioning date postponed due to rescheduling of transmission projects together with commission rescheduled on the generation investor's side. Permitting procedure issues and wiring change. | 13 | Delayed Cluster 13
718 | 3 | 2014 | 314 | Delayed | Project delayed due to rescheduling of transmission projects together with commission rescheduled on the generation investor's side | -1 | Outlier
719 | 3 | 2014 | 315 | Delayed | Project commissioning date postponed due to rescheduling of transmission projects together with commission rescheduled on the generation investor's side. Wiring change to higher capacity. | 13 | Delayed Cluster 13
720 | 3 | 2014 | 316 | Delayed | Project is dependent on other investments which are delayed. | 10 | Delayed Cluster 10
724 | 4 | 2014 | 36 | Delayed | Answering all concerns expressed during the authorization process in Spain and environmental issues in France led to postponing the investment. Both issues are solved by now. | 10 | Delayed Cluster 10
734 | 3 | 2014 | 379 | Delayed | Several months delay due to difficulties with the acquisition of the land | 5 | Delayed Cluster 5
743 | 3 | 2014 | 4 | Delayed | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was delayed. | 13 | Delayed Cluster 13
745 | 3 | 2014 | 406 | Delayed | Revised progress due to less flexible system operations in a running system (voltage upgrade of existing lines). Commissioning date expected 2019-2021. | 13 | Delayed Cluster 13
747 | 3 | 2014 | 427 | Delayed | Rescheduled to develop a solid regional business case (including additional project partners); and to account for the time needed for the acceptance by the authorities of a preferred route. | 10 | Delayed Cluster 10
751 | 4 | 2014 | 440 | Delayed | Permitting procedures took longer than expected. The part from Maasvlakte to Bleiswijk has been commissioned. | 6 | Delayed Cluster 6
755 | 3 | 2014 | 444 | Delayed | Delay due to request of 3rd parties to examine more alternatives, and procedures launched , and due to appeals against the GRUP (land use act) by 3rd parties in States Council. Meanwile arrangements have been made, and the updated planning envisions end 2017/begin 2018 as new commissioning date. | -1 | Outlier
756 | 3 | 2014 | 445 | Delayed | Permitting procedure for adaptation of land use (GRUP) had to be reinitiated, in order to comply with the demand of investigating alternative solutions. | 11 | Delayed Cluster 11
764 | 3 | 2014 | 462 | Delayed | Further studies required before re-submission for planning consents | 6 | Delayed Cluster 6
766 | 3 | 2014 | 474 | Delayed | Due to the expected delay of the connection of new hydro power plants, the commissioning date of this investment item was delayed. | 13 | Delayed Cluster 13
767 | 3 | 2014 | 476 | Delayed | Due to the expected delay of the connection of new RES generation in Portugal, the commissioning date of this investment item is delayed | -1 | Outlier
770 | 3 | 2014 | 484 | Delayed | Due to the expected delay on the connection of new RES generation in the centre of Portugal, the commissioning date of this investment item is delayed | -1 | Outlier
771 | 3 | 2014 | 496 | Delayed | Delays in authorization process due to a change on the route and on the location of substations were induced by environmental concerns | 11 | Delayed Cluster 11
772 | 3 | 2014 | 497 | Delayed | Partial sections from the line found environmental problems in his original route. The problems are being solved with the identification of new routes, prompting a delay in the commissioning date. | 11 | Delayed Cluster 11
773 | 3 | 2014 | 498 | Delayed | Delays in the authorization process, due to a change of location of the substation. Timing correlated to investment 18 | 11 | Delayed Cluster 11
774 | 3 | 2014 | 499 | Delayed | Delays in the authorization process, due to a change of location of the substation. Timing correlated to investment 18 | 11 | Delayed Cluster 11
775 | 3 | 2014 | 500 | Delayed | Delays in the authorization process, due to a change of location of the substation. Timing correlated to investment 496. | -1 | Outlier
776 | 3 | 2014 | 501 | Delayed | Delays in the authorization process, due to a change of location of the substation. Timing correlated to investment 497. | 11 | Delayed Cluster 11
779 | 4 | 2014 | 505 | Delayed | Works completed in 2014; commercial operation expected after test period at the same time as the cable (investment 36). | -1 | Outlier
780 | 4 | 2014 | 506 | Delayed | Works completed in 2014; commercial operation expected after test period at the same time as the cable (investment 36). | -1 | Outlier
781 | 3 | 2014 | 508 | Delayed | Answering all concerns expressed during the authorization process led to postponing the investment. | 10 | Delayed Cluster 10
782 | 4 | 2014 | 509 | Delayed | Answering all concerns expressed during the authorization process led to postponing the investment. | 10 | Delayed Cluster 10
786 | 3 | 2014 | 537 | Delayed | Delayed because National law RDL 13/2012 has frozen the permitting process until publication of the next NDP | 2 | Delayed Cluster 2
787 | 3 | 2014 | 538 | Delayed | Delayed because National law RDL 13/2012 has frozen the permitting process until publication of the next NDP | 2 | Delayed Cluster 2
791 | 4 | 2014 | 55 | Delayed | After some delay in the works of the Frejus service gallery of the motorway, in which the cables will be installed, the project timeline has been updated. Works are already in progress. | -1 | Outlier
799 | 3 | 2014 | 604 | Delayed | Permitting procedure for adaptation of land use (GRUP) had to be reinitiated, in order to comply with the demand of investigating alternative solutions. | -1 | Outlier
800 | 3 | 2014 | 605 | Delayed | Permitting procedure for adaptation of land use (GRUP) had to be reinitiated, in order to comply with the demand of investigating alternative solutions. | -1 | Outlier
801 | 4 | 2014 | 606 | Delayed | Implementation of the project has been aligned with maintenance period of nuclear units ==> commissioning now foreseen in 2015 instead of end 2014 | 13 | Delayed Cluster 13
802 | 4 | 2014 | 607 | Delayed | Commissioning date of this inv. item aligned with implementation of inv. item 606 thus now 2015 instead of 2014 | 13 | Delayed Cluster 13
810 | 2 | 2014 | 619 | Delayed | Feasibility study is expected to be launched. | -1 | Outlier
813 | 4 | 2014 | 621 | Delayed | rescheduling of work due to further secondary permitting during land rights acquisition and construction phase | -1 | Outlier
814 | 4 | 2014 | 622 | Delayed | rescheduling of work due to further secondary permitting during land rights acquisition and construction phase | -1 | Outlier
818 | 3 | 2014 | 628 | Delayed | Feasibility study, ESIA and preliminary design finalized (financed by WBIF and supported by EC). Ongoing process of adoption to local legislation needs. | -1 | Outlier
821 | 3 | 2014 | 631 | Delayed | Feasibility study, ESIA and preliminary design finalized (financed by WBIF and supported by EC). Ongoing process of adoption to local legislation needs. | -1 | Outlier
825 | 3 | 2014 | 645 | Delayed | delay in the permitting process (EIA) | 3 | Delayed Cluster 3
840 | 2 | 2014 | 667 | Delayed | The old investment 43.A90 is now divided in several parts. | 10 | Delayed Cluster 10
855 | 2 | 2014 | 695 | Delayed | Expected commission date postponed on 2018 by reason of difficulties associated with finding the common national border crossing point. | -1 | Outlier
856 | 2 | 2014 | 696 | Delayed | Expected commission date postponed to 2018 as a result of negotiations between SEPS and MAVIR. | -1 | Outlier
857 | 2 | 2014 | 697 | Delayed | Expected commission date postponed to 2018 as a result of negotiations between SEPS and MAVIR. | -1 | Outlier
858 | 2 | 2014 | 698 | Delayed | Investment rescheduled as a result of changes in planning input data (need delayed) | 10 | Delayed Cluster 10
859 | 2 | 2014 | 699 | Delayed | Investment rescheduled as a result of changes in planning input data (need delayed) | 10 | Delayed Cluster 10
860 | 4 | 2014 | 70 | Delayed | rescheduling of work due to further secondary permitting during land rights acquisition and construction phase | -1 | Outlier
864 | 4 | 2014 | 708 | Delayed | Delays due to environmental licensing process | -1 | Outlier
865 | 2 | 2014 | 715 | Delayed | The investment was rescheduled in correlation with project 273. | 10 | Delayed Cluster 10
876 | 3 | 2014 | 742 | Delayed | Rescheduled due to timing of system changes that trigger the investment. End station name updated. | 10 | Delayed Cluster 10
878 | 4 | 2014 | 75 | Delayed | rescheduling of 6 months work due to technical issues during construction phase | -1 | Outlier
879 | 3 | 2014 | 752 | Delayed | 2018 is the earliest possible date: project is subject to outcome of ongoing design, legal, ownership & regulatory framework concertation with stakeholders. | 12 | Delayed Cluster 12
880 | 3 | 2014 | 753 | Delayed | Postponed due to the slow build up of generation in the East Anglia area and also in demand within London. | 13 | Delayed Cluster 13
881 | 3 | 2014 | 754 | Delayed | Postponed due to the build up of generation schemes in the East Anglia area and demand increases in London. | -1 | Outlier
893 | 3 | 2014 | 796 | Delayed | The commissioning time of the investment has been aligned with the schedule for the investment 139. | 10 | Delayed Cluster 10
894 | 3 | 2014 | 799 | Delayed | Investment postponed because of prolongation of the tendering process. Due to complexity of the technical solutions more time is needed for the tendering procedure. | 10 | Delayed Cluster 10
896 | 2 | 2014 | 800 | Delayed | Delayed due to lack of funding. | 14 | Delayed Cluster 14
904 | 3 | 2014 | 86 | Delayed | delay in the permitting process (EIA) concerning the part Foggia-Gissi still under authorization; the part Villanova Gissi is already authorized | 3 | Delayed Cluster 3
910 | 3 | 2014 | 9 | Delayed | Adjustments resulting from the new date of renewables projects. | 9 | Delayed Cluster 9
911 | 3 | 2014 | 90 | Delayed | delay in the permitting process (EIA) | 3 | Delayed Cluster 3
915 | 4 | 2014 | 92 | Delayed | permitting only recently completed (March 2013) and construction work had to be rescheduled accordingly. Note that the expected commissioning date for the project is December 2016 | 13 | Delayed Cluster 13
928 | 2 | 2014 | 939 | Delayed | In TYNDP 2012 part of investment 43.A89 | 10 | Delayed Cluster 10
946 | 3 | 2014 | 96 | Delayed | delay in the permitting process (EIA) | 3 | Delayed Cluster 3
5 | 3 | 2015 | 1005 | Delayed | Progressed as planned | 7 | Delayed Cluster 7
11 | 3 | 2015 | 1014 | Delayed | Progressed as planned | 7 | Delayed Cluster 7
14 | 2 | 2015 | 1020 | Delayed | Progressed as planned | 7 | Delayed Cluster 7
15 | 2 | 2015 | 1021 | Delayed | Progressed as planned | 7 | Delayed Cluster 7
25 | 3 | 2015 | 1033 | Delayed | Progressed as planned | 7 | Delayed Cluster 7
27 | 2 | 2015 | 1035 | Delayed | The investment is in the tendering procedure (design and build scheme). The investment is planned to be completed in Q1 2019. | 10 | Delayed Cluster 10
49 | 3 | 2015 | 1071 | Delayed | Progressed as planned | 7 | Delayed Cluster 7
51 | 3 | 2015 | 1076 | Delayed | “Realization of this project is delayed for one year because of problems with obtaining necessary permits on local level. Now, the problem is resolved and we are in the phase of closing financial structure for its realization.” | 9 | Delayed Cluster 9
55 | 1 | 2015 | 1111 | Delayed | Progressed as planned | 7 | Delayed Cluster 7
228 | 3 | 2015 | 145 | Delayed | Permitting procedures take longer than expected | 0 | Delayed Cluster 0
239 | 4 | 2015 | 147 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
246 | 4 | 2015 | 148 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
269 | 3 | 2015 | 151 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
290 | 3 | 2015 | 153 | Delayed | Delayed due to delay of related investment 45.193 and unexpected long permitting process of the investment itself | 10 | Delayed Cluster 10
366 | 4 | 2015 | 165 | Delayed | delay is due to long permitting process | 0 | Delayed Cluster 0
487 | 4 | 2015 | 179 | Delayed | The section Rommerskrichen to Sechtem is delayed because the permitting procedures take longer than planned. The 36 km section from Sechtem to Weißenturm is already commissioned. | 6 | Delayed Cluster 6
497 | 3 | 2015 | 18 | Delayed | The delay of this investment is affected by the explanation in the investment 496. Also, environmental problems lead to re-routing. | 10 | Delayed Cluster 10
541 | 3 | 2015 | 188 | Delayed | Delayed, due to public resistance and intricate construction planning. | 14 | Delayed Cluster 14
554 | 4 | 2015 | 193 | Delayed | 3rd section (Altenfeld – Redwitz) is under construction now, long permitting process with strong public resistance. | 6 | Delayed Cluster 6
682 | 1 | 2015 | 211 | Delayed | Delayed due to the long permitting process | 0 | Delayed Cluster 0
683 | 3 | 2015 | 212 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
685 | 3 | 2015 | 216 | Delayed | Significant delays in the authorisation process (EIA). | 3 | Delayed Cluster 3
688 | 3 | 2015 | 223 | Delayed | The investment is delayed due to environmental problems (including re-routing) and problems with cultural heritage authorities | 10 | Delayed Cluster 10
692 | 4 | 2015 | 236 | Delayed | land acquisition | 5 | Delayed Cluster 5
695 | 3 | 2015 | 244 | Delayed | Delays in the expropriation and permission process. These issues have been resolved. | -1 | Outlier
696 | 3 | 2015 | 256 | Delayed | Delayed due to lack of funding. | 14 | Delayed Cluster 14
697 | 3 | 2015 | 257 | Delayed | Delayed due to difficulties with the acquisition of the land | 5 | Delayed Cluster 5
698 | 3 | 2015 | 258 | Delayed | Delayed due to difficulties with the acquisition of the land | 5 | Delayed Cluster 5
699 | 3 | 2015 | 262 | Delayed | Delayed due to difficulties with the acquisition of the land | 5 | Delayed Cluster 5
712 | 3 | 2015 | 308 | Delayed | Based on CEPS request the competent authority is still in the process to change the status of the project to "public-interest project". | 9 | Delayed Cluster 9
721 | 3 | 2015 | 335 | Delayed | Delay due to lingering permit granting process (land acquisition, right of way-local municipalities zoning plans). | 4 | Delayed Cluster 4
750 | 3 | 2015 | 439 | Delayed | With a 380 kV substation at Rilland, the Zuid-West 380 kV project can be taken into service in two parts. The first part consists of the Borssele Rilland line including substation Rilland and the second part consist of the Rilland – Tilburg line. | 13 | Delayed Cluster 13
751 | 4 | 2015 | 440 | Delayed | Permitting procedures took longer than expected. The part from Maasvlakte to Bleiswijk has been commisssioned. | 6 | Delayed Cluster 6
756 | 3 | 2015 | 445 | Delayed | Progress made in permitting procedures brought clarification to preferential trajectory. Planning has been reviewed accordingly with 2019 based upon the hypothesis of acquiring all necessary permits as currently planned. | 6 | Delayed Cluster 6
760 | 4 | 2015 | 450 | Delayed | Delayed by one year due to interconnector progression. | -1 | Outlier
761 | 4 | 2015 | 452 | Delayed | Delay due to complexity in construction phase | 0 | Delayed Cluster 0
771 | 3 | 2015 | 496 | Delayed | Due to local opposition in the border area REN had to withdraw the Portuguese section of the interconnection of the ongoing EIA process to maintain the schedule of other investments included in the EIA needed for connecting new hydro in Cávado | 3 | Delayed Cluster 3
773 | 3 | 2015 | 498 | Delayed | The delay of this investment is affected by the explanation in the investment 496. Also, environmental problems lead to re-routing | 10 | Delayed Cluster 10
774 | 3 | 2015 | 499 | Delayed | The delay of this investment is affected by the explanation in the investment 496. Also, environmental problems lead to re-routing | 10 | Delayed Cluster 10
775 | 3 | 2015 | 500 | Delayed | Substation renamed to Ponte de Lima. See Investment 496. | -1 | Outlier
777 | 3 | 2015 | 503 | Delayed | Delays due to change of the definition of the project and national law RDL 13/2012 has frozen the permitting process until publication of the next NDP | 2 | Delayed Cluster 2
778 | 3 | 2015 | 504 | Delayed | National law RDL 13/2012 has frozen the permitting process until publication of the next NDP | 2 | Delayed Cluster 2
781 | 3 | 2015 | 508 | Delayed | Final phase of permitting. Investment pending of its publication in the BOE. | 6 | Delayed Cluster 6
796 | 3 | 2015 | 594 | Delayed | delays associated to the contract process and internal approval of budget including financing | 0 | Delayed Cluster 0
800 | 3 | 2015 | 605 | Delayed | Progress made in permitting procedures brought clarification to preferential trajectory. Planning has been reviewed accordingly with 2019 based upon the hypothesis of acquiring all necessary permits as currently planned. | 6 | Delayed Cluster 6
815 | 4 | 2015 | 624 | Delayed | The commissioning date has been updated to be coherent with the new schedule of the activities also considering that the construction phase of the substation started in mid-2014 | 13 | Delayed Cluster 13
817 | 3 | 2015 | 627 | Delayed | These projects are delayed because of delaying investment No 628 double OHL 400 kV B. Basta – Obrenovac and optimistic planning | 10 | Delayed Cluster 10
818 | 3 | 2015 | 628 | Delayed | The project is delayed because of need to accommodate Feasibility study (granted by WBIF and done according to WBIF needs) to national law needs.“ | -1 | Outlier
820 | 3 | 2015 | 630 | Delayed | Regional trilateral feasibility study (financed by WBIF and supported by EC) between three TSOs (EMS, NOS BiH and CGES), including ESIA and preliminary design is finished. | -1 | Outlier
821 | 3 | 2015 | 631 | Delayed | Feasibility study, ESIA and preliminary design finalized (financed by WBIF and supported by EC). Ongoing process of adoption to local legislation needs. | -1 | Outlier
825 | 3 | 2015 | 645 | Delayed | delay in the permitting process (EIA) | 3 | Delayed Cluster 3
829 | 4 | 2015 | 656 | Delayed | delay is due to long permitting process | 0 | Delayed Cluster 0
835 | 1 | 2015 | 662 | Delayed | The need for this long-term investment was not confirmed by the regulatory authority within the national grid development plan. Therefore further studies on this project are ongoing. | 10 | Delayed Cluster 10
864 | 4 | 2015 | 708 | Delayed | Delays due to environmental licensing process | -1 | Outlier
872 | 3 | 2015 | 733 | Delayed | Main reasons for delay are:- Permission for access to land corridor for the grids planned route from land owners more difficult than previous foreseen. -Svenska kraftnät has changed estimated time for the permission process due to new information. | 11 | Delayed Cluster 11
877 | 3 | 2015 | 747 | Delayed | Delay in project requirement due to generation going back. | 13 | Delayed Cluster 13
896 | 2 | 2015 | 800 | Delayed | Delayed due to lack of funding. | 14 | Delayed Cluster 14
911 | 3 | 2015 | 90 | Delayed | delay in the permitting process (EIA) | 3 | Delayed Cluster 3
931 | 1 | 2015 | 943 | Delayed | due to new planning | 7 | Delayed Cluster 7
934 | 1 | 2015 | 946 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
936 | 1 | 2015 | 948 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
938 | 1 | 2015 | 950 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
943 | 1 | 2015 | 955 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
946 | 3 | 2015 | 96 | Delayed | delay in the permitting process (EIA) | 3 | Delayed Cluster 3
27 | 3 | 2016 | 1035 | Delayed | The investment is in the tendering procedure (design and build scheme). The investment is planned to be completed in 2020. Change of commissioning date compared to previous reprting due to realization schedule of other investements (line Krajnik-Baczyna and Baczyna-Plewiska). | 10 | Delayed Cluster 10
32 | 2 | 2016 | 1041 | Delayed | Additional technical studies on-going. | 7 | Delayed Cluster 7
50 | 4 | 2016 | 1075 | Delayed | Due to insufficient financial support from EU this project is postponed. | 14 | Delayed Cluster 14
51 | 4 | 2016 | 1076 | Delayed | Due to insufficient financial support from EU this project is postponed. | 14 | Delayed Cluster 14
146 | 1 | 2016 | 136 | Delayed | Due to the changed market and grid situation in this area, there is a need for an update of the current study and its findings. | -1 | Outlier
147 | 1 | 2016 | 136 | Delayed | Due to the changed market and grid situation in this area, there is a need for an update of the current study and its findings. | -1 | Outlier
148 | 1 | 2016 | 136 | Delayed | Due to the changed market and grid situation in this area, there is a need for an update of the current study and its findings. | -1 | Outlier
149 | 1 | 2016 | 136 | Delayed | Due to the changed market and grid situation in this area, there is a need for an update of the current study and its findings. | -1 | Outlier
150 | 2 | 2016 | 1369 | Delayed | Awaiting international contracts for renewable energy | 1 | Delayed Cluster 1
158 | 3 | 2016 | 1385 | Delayed | A pure interconnector with Ofgem IPA approval. | -1 | Outlier
163 | 4 | 2016 | 139 | Delayed | Finalization of the investment in due date (2017) was not possible because of permit granting reasons (regarding building of the “Uckermark” line) on 50Hertz side. Therefore the schedule for switching off of the existing 220 kV line to 400 kV has been changed. The interconnector will be temporally disconnected until 2018 in order to perform necessary works in the substations Krajnik and Vierraden. In 2018 first two PST in Vierraden will be installed and the line will be connected on 400 kV through a 220/400 kV transformer. The project is planned to operate in final shape (4 PSTs in SS Vierraden and the 2x400 kV interconnector) by 2020, depending on the permit granting process for the “Uckermark” line. | 13 | Delayed Cluster 13
216 | 2 | 2016 | 1439 | Delayed | Awaiting international contracts for renewable energy | 1 | Delayed Cluster 1
218 | 2 | 2016 | 1440 | Delayed | Awaiting international contracts for renewable energy | 1 | Delayed Cluster 1
219 | 2 | 2016 | 1441 | Delayed | Awaiting international contracts for renewable energy | 1 | Delayed Cluster 1
220 | 2 | 2016 | 1442 | Delayed | Awaiting international contracts for renewable energy | 1 | Delayed Cluster 1
221 | 2 | 2016 | 1443 | Delayed | Awaiting international contracts for renewable energy | 1 | Delayed Cluster 1
222 | 2 | 2016 | 1444 | Delayed | Awaiting international contracts for renewable energy | 1 | Delayed Cluster 1
223 | 2 | 2016 | 1445 | Delayed | Awaiting international contracts for renewable energy | 1 | Delayed Cluster 1
224 | 2 | 2016 | 1446 | Delayed | Awaiting international contracts for renewable energy | 1 | Delayed Cluster 1
225 | 2 | 2016 | 1447 | Delayed | Awaiting international contracts for renewable energy | 1 | Delayed Cluster 1
226 | 2 | 2016 | 1448 | Delayed | Awaiting international contracts for renewable energy | 1 | Delayed Cluster 1
227 | 2 | 2016 | 1449 | Delayed | Awaiting international contracts for renewable energy | 1 | Delayed Cluster 1
229 | 2 | 2016 | 1450 | Delayed | Awaiting international contracts for renewable energy | 1 | Delayed Cluster 1
237 | 3 | 2016 | 146 | Delayed | The expected commissioning date of 2020 is based on the hypothesis of acquiring all necessary permits as planned. | 13 | Delayed Cluster 13
239 | 4 | 2016 | 147 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
246 | 4 | 2016 | 148 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
252 | 3 | 2016 | 149 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
259 | 3 | 2016 | 150 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
269 | 3 | 2016 | 151 | Delayed | Long permitting process and additional longer constructing phase due to requirement of underground cable in some parts of the line. | -1 | Outlier
314 | 3 | 2016 | 156 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
323 | 3 | 2016 | 157 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
487 | 4 | 2016 | 179 | Delayed | The section Rommerskrichen to Sechtem is delayed because the permitting procedures take longer than planned. The 36 km section from Sechtem to Weißenturm is already commissioned. | 6 | Delayed Cluster 6
497 | 3 | 2016 | 18 | Delayed | The delay of this investment is affected by the explanation in the investment 496. Also, environmental problems lead to re-routing. | 10 | Delayed Cluster 10
541 | 3 | 2016 | 188 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
554 | 4 | 2016 | 193 | Delayed | 3rd section (Altenfeld – Redwitz) is under construction now, long permitting process with strong public resistance. | -1 | Outlier
682 | 1 | 2016 | 211 | Delayed | delayed due to the project | 14 | Delayed Cluster 14
683 | 3 | 2016 | 212 | Delayed | Delayed due to long permitting process | 0 | Delayed Cluster 0
684 | 2 | 2016 | 214 | Delayed | The approval of the Contract of Construction for each PCI in the project between the two promoters has been in delay compared to the original schedule. The project promoters agreed jointly in November 2015 to set a new feasible commissioning date, which will also figure in the Contract. | 12 | Delayed Cluster 12
685 | 3 | 2016 | 216 | Delayed | Significant delays in the authorisation process (EIA). | 3 | Delayed Cluster 3
688 | 3 | 2016 | 223 | Delayed | ELES is currently in the process of gaining easment from the land owners. | 5 | Delayed Cluster 5
695 | 4 | 2016 | 244 | Delayed | Delayd due to dificulties with the acquisition of the land. This issue has been resolved. | 5 | Delayed Cluster 5
696 | 3 | 2016 | 256 | Delayed | Delayed due to lack of funding. | 14 | Delayed Cluster 14
697 | 3 | 2016 | 257 | Delayed | Delayed due to difficulties with the acquisition of the land | 5 | Delayed Cluster 5
698 | 3 | 2016 | 258 | Delayed | Delayed due to difficulties with the acquisition of the land | 5 | Delayed Cluster 5
699 | 3 | 2016 | 262 | Delayed | Delayed due to difficulties with the acquisition of the land | 5 | Delayed Cluster 5
701 | 4 | 2016 | 269 | Delayed | The investment was coordinated with investment no 238. The main problems are right of land along the line path and permitting. | 10 | Delayed Cluster 10
702 | 3 | 2016 | 270 | Delayed | Planned to start after investment 269 is finalized. | 10 | Delayed Cluster 10
703 | 3 | 2016 | 273 | Delayed | Longer than expected delay regarding clarification of legal framework for right of land acquirement and regarding environmental permitting procedure. | -1 | Outlier
705 | 3 | 2016 | 276 | Delayed | Longer than expected delay regarding clarification of legal framework for right of land acquirement and regarding environmental permitting procedure. | -1 | Outlier
706 | 4 | 2016 | 3 | Delayed | In the first stage the line will be conected between Pedralva and Vila Nova de Famalicão (previously Vila do Conde). New substation of Ponte de Lima (previously Viana do Castelo) will be commissioned in 2018 | -1 | Outlier
712 | 3 | 2016 | 308 | Delayed | Based onCEPS request the competent authority is still in the process to changethe status of the project to "public-interest project". | 9 | Delayed Cluster 9
721 | 3 | 2016 | 335 | Delayed | Delay due to lingering permit granting process and other formal aspects. | 4 | Delayed Cluster 4
733 | 2 | 2016 | 378 | Delayed | Project implementation depends on decisions about new nuclear power plant in Lithuania and project 170."Baltic synchronisation". | 9 | Delayed Cluster 9
736 | 1 | 2016 | 380 | Delayed | Investment implementation time depends from decisions about new Visaginas NPP and project 170. Baltic synchronization”. | 10 | Delayed Cluster 10
737 | 2 | 2016 | 382 | Delayed | Investment implementation time depends from decisions about new Visaginas NPP and project 170. Baltic synchronization” | 10 | Delayed Cluster 10
739 | 4 | 2016 | 385 | Delayed | The last part of reinforcement for Kurzemes ring project | -1 | Outlier
745 | 4 | 2016 | 406 | Delayed | Revised progress due to less flexible system operations in a running system (voltage upgrade of existing lines). Commissioning date expected 2019-2021. | 13 | Delayed Cluster 13
750 | 3 | 2016 | 439 | Delayed | With a 380 kV substation at Rilland, the Zuid-West 380 kV project can be taken into service in two parts. The first part consists of the Borssele - Rilland line including substation Rilland (2020) and the second part consist of the Rilland – Tilburg line (2025). | 13 | Delayed Cluster 13
756 | 3 | 2016 | 445 | Delayed | Progress made in permitting procedures brought clarification to preferential trajectory. Planning has been reviewed accordingly with 2020 based upon the hypothesis of acquiring all necessary permits as currently planned. | 6 | Delayed Cluster 6
760 | 4 | 2016 | 450 | Delayed | Delayed by one year due to interconnector progresion. | -1 | Outlier
761 | 4 | 2016 | 452 | Delayed | Delayed due to complexity in construction and issues with the | -1 | Outlier
764 |  | 2016 | 462 | Delayed | Further studies required before re-submission for planning consents | 6 | Delayed Cluster 6
771 | 3 | 2016 | 496 | Delayed | Due to local opposition in the border area REN had to withdraw the Portuguese section of the interconnection of the ongoing EIA process to maintain the schedule of other investments included in the EIA needed for connecting new hydro in Cávado | 3 | Delayed Cluster 3
773 | 3 | 2016 | 498 | Delayed | The delay of this investment is affected by the explanation in the investment 496. Also, environmental problems lead to re-routing | 10 | Delayed Cluster 10
774 | 3 | 2016 | 499 | Delayed | The delay of this investment is affected by the explanation in the investment 496. Also, environmental problems lead to re-routing | 10 | Delayed Cluster 10
775 | 3 | 2016 | 500 | Delayed | Substation renamed to Ponte de Lima. See Investment 496. | -1 | Outlier
796 | 3 | 2016 | 594 | Delayed | Delays because of closure on budget and financing | -1 | Outlier
800 | 3 | 2016 | 605 | Delayed | Progress made in permitting procedures brought clarification to preferential trajectory. Planning has been reviewed accordingly with 2019 based upon the hypothesis of acquiring all necessary permits as currently planned. | 6 | Delayed Cluster 6
805 | 3 | 2016 | 614 | Delayed | Common planning progress between Terna an APG ongoing. | 7 | Delayed Cluster 7
817 | 3 | 2016 | 627 | Delayed | Del_ Financing issues | -1 | Outlier
818 | 3 | 2016 | 628 | Delayed | Del_ Financing issues | -1 | Outlier
820 | 3 | 2016 | 630 | Delayed | Del_ Financing issues | -1 | Outlier
821 | 3 | 2016 | 631 | Delayed | Del_ Financing issues | -1 | Outlier
825 | 3 | 2016 | 645 | Delayed | delay in the permitting process (EIA) | 3 | Delayed Cluster 3
827 | 4 | 2016 | 654 | Delayed | due to the project | 7 | Delayed Cluster 7
829 | 4 | 2016 | 656 | Delayed | due to the project | 7 | Delayed Cluster 7
832 | 1 | 2016 | 659 | Delayed | due to the project | 7 | Delayed Cluster 7
833 | 3 | 2016 | 660 | Delayed | Delays due to permit granting reasons. | 14 | Delayed Cluster 14
837 | 2 | 2016 | 664 | Delayed | The commissioning date of the investment is delayed due to new preference of underground cable instead of overhead lines by german legal requirement. | 13 | Delayed Cluster 13
838 | 2 | 2016 | 665 | Delayed | The commissioning date of the investment is delayed due to new preference of underground cable instead of overhead lines by german legal requirement. | -1 | Outlier
843 | 3 | 2016 | 677 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
852 | 3 | 2016 | 687 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
855 | 2 | 2016 | 695 | Delayed | The approval of the Contract of Construction for each PCI in the project between the two promoters has been in delay compared to the original schedule. The project promoters agreed jointly in November 2015 to set a new feasible commissioning date, which will also figure in the Contract. | 12 | Delayed Cluster 12
856 | 2 | 2016 | 696 | Delayed | The approval of the Contract of Construction for each PCI in the project between the two promoters has been in delay compared to the original schedule. The project promoters agreed jointly in November 2015 to set a new feasible commissioning date, which will also figure in the Contract. | 12 | Delayed Cluster 12
857 | 2 | 2016 | 697 | Delayed | The approval of the Contract of Construction for each PCI in the project between the two promoters has been in delay compared to the original schedule. The project promoters agreed jointly in November 2015 to set a new feasible commissioning date, which will also figure in the Contract. | 12 | Delayed Cluster 12
861 | 3 | 2016 | 701 | Delayed | This investment is in correlation with investment no 269. | 10 | Delayed Cluster 10
862 | 3 | 2016 | 705 | Delayed | Investments 269 and 701 have to be finalized first. | 10 | Delayed Cluster 10
865 | 3 | 2016 | 715 | Delayed | This project is complementing with project 273. | 9 | Delayed Cluster 9
877 | 3 | 2016 | 747 | Delayed | Delay in project requirement due to generation going back. | -1 | Outlier
896 | 2 | 2016 | 800 | Delayed | Delayed due to lack of funding. | 14 | Delayed Cluster 14
904 | 3 | 2016 | 86 | Delayed | the part Foggia-Gissi still under authorization; the part Villanova Gissi has been commissioned in 2016. | 12 | Delayed Cluster 12
911 | 3 | 2016 | 90 | Delayed | delay in the permitting process (EIA) | 3 | Delayed Cluster 3
925 | 2 | 2016 | 935 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
928 | 3 | 2016 | 939 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
929 | 2 | 2016 | 940 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
941 | 1 | 2016 | 953 | Delayed | due to the project | 7 | Delayed Cluster 7
946 | 3 | 2016 | 96 | Delayed | delay in the permitting process (EIA) | 3 | Delayed Cluster 3
953 | 3 | 2016 | 985 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
959 | 3 | 2016 | 992 | Delayed | The 380 kV commissioning will be possible after finalization of the new connecting OHL from Vierraden to Neuenhagen (near Berlin) to replace the current 220 kV network and form a new 380 kV grid. | 13 | Delayed Cluster 13
11 | 3 | 2018 | 1014 | Delayed | A different location of the Converter Station in Switzerland is under evaluation due to local opposition. A rerouting of the final part of the Interconnector is under evaluation as well. | 13 | Delayed Cluster 13
83 | 4 | 2018 | 1228 | Delayed | Partially constructed. Delay due to the difficulty in finding a window for a planned outage necessary for the works. | 14 | Delayed Cluster 14
89 | 1 | 2018 | 1235 | Delayed | National Development Plan does not contain yet a solution for the second phase of projects 1011 and 1019, which compete with each other. | 9 | Delayed Cluster 9
100 | 3 | 2018 | 1251 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
110 | 3 | 2018 | 1261 | Delayed | permitting procedure | 6 | Delayed Cluster 6
133 | 2 | 2018 | 1285 | Delayed | reschedule | 10 | Delayed Cluster 10
136 | 3 | 2018 | 1288 | Delayed | preliminary clarifications | 7 | Delayed Cluster 7
139 | 2 | 2018 | 1290 | Delayed | reschedule | 10 | Delayed Cluster 10
145 | 1 | 2018 | 1356 | Delayed | Maali was listed and recommend for inclusion in the PCI list at the TEN-E regional groups meeting in Brussels 27th June 2017, however it was not supported by all member states in a closed meeting on 13th July due to a proposal to connect Shetland to Scotland with a 60MW distribution cable which would not have supported Maali. The 60MW connection was subsequently rejected by the GB Regulator Ofgem on 30th November 2018 opening the way for the planned >=600MW connection to Scotland and facilitating the connection of Maali. | 12 | Delayed Cluster 12
151 | 3 | 2018 | 1378 | Delayed | The Tunisian regulatory framework has been settled only recently and this delayed the overall permitting process | -1 | Outlier
153 | 3 | 2018 | 1380 | Delayed | PERMITTING - Delays due to environmental problems (including re-routing) | 3 | Delayed Cluster 3
154 | 3 | 2018 | 1381 | Delayed | The project programme was delayed comparing to the initial application for TYNDP 2016 due to two main factors. Firstly, the studies performed in conjunction with National Grid in order to determine a connection location in the UK, which commenced at the time of the application for TYNDP 2016, took longer time than expected. The studies were successfully completed in the late 2015. Secondly, two connection points were initially suggested in France - Le Havre and Barnabos. Further studies were required to determine the point of connection with the least impact on the national transmission system and greater feasibility of implementation. As an outcome, AQUIND accepted the PTF from RTE in respect of Barnabos substation. The project promoter commenced the studies with National Grid and RTE approximately at the same time as applying for TYNDP 2016 and at that stage such circumstances were not foreseeable. | -1 | Outlier
157 | 3 | 2018 | 1384 | Delayed | The permitting phase in Italy is ongoing since April 2014 but we are still facing some challenges regarding Environmental impact of the 380/132kV Substation Terna in Mese. Commissioning expected in 2021. | -1 | Outlier
158 | 2 | 2018 | 1385 | Delayed | The PCI was delayed due to regulatory processes in the Republic of Ireland which have now been remedied. The Commission for Regulation of Utilities (CRU), on 21 October 2017, directed EirGrid to progress grid applications from interconnectors with PCI status, including Greenlink; also the CRU issued an information paper on 21 March 2018 acknowledging Greenlink’s application and setting out the timeframe to develop, consult, and make an initial decision on, Greenlink’s application by 30 September 2018. | 12 | Delayed Cluster 12
207 | 3 | 2018 | 1430 | Delayed | The Tunisian regulatory framework has been settled only recently and this delayed the overall permitting process | -1 | Outlier
233 | 3 | 2018 | 1455 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
239 | 4 | 2018 | 147 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
240 | 3 | 2018 | 1472 | Delayed | Duration of permitting process. | 6 | Delayed Cluster 6
241 | 3 | 2018 | 1473 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
260 | 3 | 2018 | 1500 | Delayed | The approval of the Contract for Construction of PCI No 3.16.1. and PCI No 3.17 between the project promoters MAVIR and SEPS was delayed compared to the initial schedule. The approval and signing fo the Contract caused two years delay in the commissioning of the overhead lines. The Contract was signed on March 1st, 2017 and sets a new commissioning date of end 2020. MAVIR and SEPS do not foresee any additional delay in commissioning. | 12 | Delayed Cluster 12
261 | 3 | 2018 | 1501 | Delayed | The approval of the Contract for Construction of PCI No 3.16.1. and PCI No 3.17 between the project promoters MAVIR and SEPS was delayed compared to the initial schedule. The approval and signing fo the Contract caused two years delay in the commissioning of the overhead lines. The Contract was signed on March 1st, 2017 and sets a new commissioning date of end 2020. MAVIR and SEPS do not foresee any additional delay in commissioning. | 12 | Delayed Cluster 12
270 | 2 | 2018 | 1510 | Delayed | Delay due to complex multi-stage permitting process | 0 | Delayed Cluster 0
272 | 2 | 2018 | 1512 | Delayed | Delay due to complex multi-stage permitting process | 0 | Delayed Cluster 0
286 | 4 | 2018 | 1526 | Delayed | Due to the delay of B. Basta - Obrenovac and B. Basta - Pljevlja investments | 10 | Delayed Cluster 10
312 | 3 | 2018 | 1558 | Delayed | The main reasons for the delay are environmental problems in the permitting process (including problems with different authorities included in the process) and acquisition of or access to land. | 11 | Delayed Cluster 11
337 | 1 | 2018 | 1617 | Delayed | Project status was due to problems with permitting process (including problems with different authorities included in the process) changed from "in permitting" to "under consideration". | 11 | Delayed Cluster 11
497 | 3 | 2018 | 18 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 11 | Delayed Cluster 11
693 | 4 | 2018 | 238 | Delayed | National law changes affecting permitting, including complexities with the implementation of the new legislation implementing Regulation (EU) 347/2013 for permitting.Delays in construction works. | -1 | Outlier
701 | 4 | 2018 | 269 | Delayed | National law changes affecting permitting, including complexities with the implementation of the new legislation implementing Regulation (EU) 347/2013 for permitting.Delays related to acquisition of and access to land. | -1 | Outlier
702 | 3 | 2018 | 270 | Delayed | National law changes affecting permitting, including complexities with the implementation of the new legislation implementing Regulation (EU) 347/2013 for permitting.Delays due to correlation with other delayed infrastructure investment. | -1 | Outlier
703 | 3 | 2018 | 273 | Delayed | National law changes affecting permitting, including complexities with the implementation of the new legislation implementing Regulation (EU) 347/2013 for permitting.Delays related to acquisition of and access to land. | -1 | Outlier
704 | 3 | 2018 | 275 | Delayed | National law changes affecting permitting, including complexities with the implementation of the new legislation implementing Regulation (EU) 347/2013 for permitting.Delays related to acquisition of and access to land. | -1 | Outlier
712 | 3 | 2018 | 308 | Delayed | Delay due to the permit grant procedure and amendment of the respective legal framework | 4 | Delayed Cluster 4
713 | 3 | 2018 | 309 | Delayed | Delay due to the permit grant procedure and amendment of the respective legal framework | 4 | Delayed Cluster 4
717 | 3 | 2018 | 313 | Delayed | Delay due to the permit grant procedure and amendment of the respective legal framework | 4 | Delayed Cluster 4
718 | 3 | 2018 | 314 | Delayed | Delay due to the permit grant procedure and amendment of the respective legal framework | 4 | Delayed Cluster 4
764 | 3 | 2018 | 462 | Delayed | Investment delayed due to judicial reviews of planning consent in IE and delayed approval of planning consent in NI. | 6 | Delayed Cluster 6
771 | 3 | 2018 | 496 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 11 | Delayed Cluster 11
773 | 3 | 2018 | 498 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 11 | Delayed Cluster 11
774 | 3 | 2018 | 499 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 11 | Delayed Cluster 11
775 | 3 | 2018 | 500 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 11 | Delayed Cluster 11
787 | 3 | 2018 | 538 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
807 | 3 | 2018 | 616 | Delayed | permitting procedure | 6 | Delayed Cluster 6
817 | 3 | 2018 | 627 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 8 | Delayed Cluster 8
818 | 3 | 2018 | 628 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 8 | Delayed Cluster 8
820 | 3 | 2018 | 630 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 8 | Delayed Cluster 8
821 | 3 | 2018 | 631 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 8 | Delayed Cluster 8
840 | 3 | 2018 | 667 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
842 | 3 | 2018 | 676 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
853 | 2 | 2018 | 688 | Delayed | Delay due to long permitting | 0 | Delayed Cluster 0
854 | 2 | 2018 | 689 | Delayed | Scope of the project changed due to technical reasons. | 9 | Delayed Cluster 9
856 | 3 | 2018 | 696 | Delayed | The commissioning date was changed to 2020, as the ivestment is tied to the cross-border invetment (R. Sobota-Sajóivánka). | 13 | Delayed Cluster 13
857 | 3 | 2018 | 697 | Delayed | The commissioning date was changed to 2020, as the ivestment is tied to the cross-border invetment (R. Sobota-Sajóivánka). | 13 | Delayed Cluster 13
861 | 4 | 2018 | 701 | Delayed | The works contract regarding 400 kV Resita substation was canceled at the request of the legal administrator of the executor -in insolvency. Transelectrica analyzes different options to continue and complete the works. | 13 | Delayed Cluster 13
862 | 3 | 2018 | 705 | Delayed | Delays due to correlation with other delayed infrastructure investment. | -1 | Outlier
865 | 3 | 2018 | 715 | Delayed | National law changes affecting permitting, including complexities with the implementation of the new legislation implementing Regulation (EU) 347/2013 for permitting.Delays related to acquisition of and access to land. | -1 | Outlier
919 | 1 | 2018 | 927 | Delayed | The delay of this investment is affected by the explanation in the investment 538. | 10 | Delayed Cluster 10
929 | 2 | 2018 | 940 | Delayed | Delay due to long permitting process | 0 | Delayed Cluster 0
946 | 3 | 2018 | 96 | Delayed | permitting procedure | 6 | Delayed Cluster 6
11 | 3 | 2020 | 1014 | Delayed | A different location of the Converter Station in Switzerland has been evaluated due to local opposition. A rerouting of the final part of the Interconnector has been evaluated as well. | 13 | Delayed Cluster 13
54 | 1 | 2020 | 1107 | Delayed | The recently adopted Clean Energy Package will have a significant impact on the future market design. These developments are likely to have a major impact on the project of a second interconnector between Belgium and Germany. However, as a lot of these regulatory changes are still about to enter into force, the exact impact on this project cannot be established today. | 1 | Delayed Cluster 1
89 | 1 | 2020 | 1235 | Delayed | National Development Plan does not contain yet a solution for the second phase of projects 1011 and 1019, which compete with each other. | 9 | Delayed Cluster 9
96 | 2 | 2020 | 1245 | Delayed | Scope of the project changed due to technical reasons. | 9 | Delayed Cluster 9
107 | 3 | 2020 | 1259 | Delayed | Permitting procedure | 6 | Delayed Cluster 6
132 | 4 | 2020 | 1284 | Delayed | sundry reasons | 7 | Delayed Cluster 7
134 | 3 | 2020 | 1286 | Delayed | Permitting Procedure | 6 | Delayed Cluster 6
135 | 3 | 2020 | 1287 | Delayed | Permitting Procedure | 6 | Delayed Cluster 6
136 | 3 | 2020 | 1288 | Delayed | preliminary clarifications | 7 | Delayed Cluster 7
151 | 1 | 2020 | 1378 | Delayed | The Tunisian regulatory framework has been settled only recently and this delayed the overall permitting process. | -1 | Outlier
153 | 3 | 2020 | 1380 | Delayed | PERMITTING - Delays due to environmental problems (including re-routing) and delay of EIA assessment due to change of EIA Commission (2019) | 3 | Delayed Cluster 3
154 | 3 | 2020 | 1381 | Delayed | In 2018 UK Government, in accordance with the Planning Act 2008, designated AQUIND Interconnector as a Nationally Significant Infrastructure Project. This designation enables AQUIND Interconnector to apply for a Development Consent Order that would include all or nearly all permits and conditions necessary to start construction. Due to the "front-loading" approach and extremely robust evaluation and consultation requirements, which might have impact over more than one constituency, the DCO has been specifically designed to enable significant infrastructure developments. However, this process also takes longer than conventional planning application under the Town and Country Planning Act. Therefore commissioning of AQUIND was postponed by approximately a year from the date declared in the TYNDP 2018. The application for the DCO has been submitted on 14 November 2019. | 12 | Delayed Cluster 12
155 | 3 | 2020 | 1382 | Delayed | Permitting process in Norway | 6 | Delayed Cluster 6
157 | 3 | 2020 | 1384 | Delayed | The permitting phase in Italy is ongoing since April 2014 but we are still facing some challenges regarding Environmental impact of the 380/132kV Substation Terna in Mese. Commissioning expected in 2024. | -1 | Outlier
158 | 2 | 2020 | 1385 | Delayed | The PCI was delayed due to regulatory processes in the Republic of Ireland which have now been remedied. The Commission for Regulation of Utilities (CRU), on 21 October 2017, directed EirGrid to progress grid applications from interconnectors with PCI status, including Greenlink; also the CRU issued an information paper on 21 March 2018 acknowledging Greenlink’s application and setting out the timeframe to develop, consult, and make an initial decision on, Greenlink’s application by 30 September 2018. | 12 | Delayed Cluster 12
185 | 4 | 2020 | 141 | Delayed | Difficulties during construction | -1 | Outlier
207 | 1 | 2020 | 1430 | Delayed | The Tunisian regulatory framework has been settled only recently and this delayed the overall permitting process. | -1 | Outlier
240 | 4 | 2020 | 1472 | Delayed | Duration of permitting process. | 6 | Delayed Cluster 6
241 | 3 | 2020 | 1473 | Delayed | Delay due to complex and long permitting process | 0 | Delayed Cluster 0
243 | 3 | 2020 | 1476 | Delayed | Scope of the project changed due to technical reasons. | 9 | Delayed Cluster 9
245 | 3 | 2020 | 1478 | Delayed | The promoters asked to the respective NRA for the NTC recalculation not subject to conditions (EG. third party network reinforcements), which will be guaranteed for the exemption period and from the entry into the new commercial operation date (COD) of the interconnector. | 2 | Delayed Cluster 2
247 | 3 | 2020 | 1482 | Delayed | The promoter asked the respective NRA for the NTC recalculation not subject to conditions (eg third party network reinforcements), which will be guaranteed for the exemption period and from the entry into the new commercial operation date (COD) of the interconnector. | 2 | Delayed Cluster 2
255 | 4 | 2020 | 1493 | Delayed | Permitting is delayed | 0 | Delayed Cluster 0
269 | 4 | 2020 | 151 | Delayed | Due to complex and long permitting process | 0 | Delayed Cluster 0
286 | 4 | 2020 | 1526 | Delayed | Due to the delay of B. Basta - Obrenovac and B. Basta - Pljevlja investments | 10 | Delayed Cluster 10
314 | 4 | 2020 | 156 | Delayed | Due to complex and long permitting process | 0 | Delayed Cluster 0
391 | 4 | 2020 | 1685 | Delayed | Due to complex and long permisstin process | 0 | Delayed Cluster 0
400 | 1 | 2020 | 1694 | Delayed | Investment depends on plans to build offshore wind farms | 10 | Delayed Cluster 10
401 | 1 | 2020 | 1695 | Delayed | Investment depends on plans to build offshore wind farms | 10 | Delayed Cluster 10
423 | 2 | 2020 | 1721 | Delayed | reschedule | 10 | Delayed Cluster 10
433 | 3 | 2020 | 1733 | Delayed | Permitting procedure | 6 | Delayed Cluster 6
434 | 4 | 2020 | 1734 | Delayed | Permitting procedure | 6 | Delayed Cluster 6
497 | 3 | 2020 | 18 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 11 | Delayed Cluster 11
693 | 4 | 2020 | 238 | Delayed | Due to some delays related to investments 701 and 269 the line is not operated | 10 | Delayed Cluster 10
701 | 4 | 2020 | 269 | Delayed | Delays in issuing the normative acts necessary for the realization of the OHL which led to very long delays in the execution of works. The execution contract was suspended for a period of 6 months. | 14 | Delayed Cluster 14
703 | 4 | 2020 | 273 | Delayed | Delays related to land acquisition, obtaining approvals and modificatons to the public procurement legislation. | 5 | Delayed Cluster 5
704 | 3 | 2020 | 275 | Delayed | Delay in issuing the government decision for expropriation. | -1 | Outlier
717 | 3 | 2020 | 313 | Delayed | Delay due to the permit grant procedure and amendment of the respective legal framework | 4 | Delayed Cluster 4
764 | 3 | 2020 | 462 | Delayed | Investment delayed due to judicial reviews of planning consent in IE and delayed approval of planning consent in NI. | 6 | Delayed Cluster 6
771 | 3 | 2020 | 496 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 11 | Delayed Cluster 11
773 | 3 | 2020 | 498 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 11 | Delayed Cluster 11
774 | 3 | 2020 | 499 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 11 | Delayed Cluster 11
775 | 3 | 2020 | 500 | Delayed | Delays due to social and environmental problems (possibility of re-routing and/or siting or re-siting of facility(ies)). The permitting had to be reinitiated. | 11 | Delayed Cluster 11
807 | 3 | 2020 | 616 | Delayed | Project under consideration on SI side (permitting not started yet in Slovenia) | 9 | Delayed Cluster 9
817 | 3 | 2020 | 627 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 8 | Delayed Cluster 8
818 | 3 | 2020 | 628 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 8 | Delayed Cluster 8
820 | 3 | 2020 | 630 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 8 | Delayed Cluster 8
821 | 3 | 2020 | 631 | Delayed | Due to phasing of the project HVDC ME-IT cable and its infuluence on project Transbalkan corridor, there is a need for a new Study with economic and financial CBA analyses. | 8 | Delayed Cluster 8
837 | 3 | 2020 | 664 | Delayed | Due to complex and long approval process | 0 | Delayed Cluster 0
854 | 2 | 2020 | 689 | Delayed | Scope of the project changed due to technical reasons. | 9 | Delayed Cluster 9
861 | 4 | 2020 | 701 | Delayed | The contractor responsible for the execution of the investment has gone into insolvency and thus the auction must be resumed | -1 | Outlier
862 | 3 | 2020 | 705 | Delayed | Long duration of the procurement procedure, delays due to executor and the pandemic impact of COVID 19. | -1 | Outlier
865 | 4 | 2020 | 715 | Delayed | Delays due to the amendment of the public procurement legislation and resumption of auction due to non-compliant offers. | 14 | Delayed Cluster 14
872 | 3 | 2020 | 733 | Delayed | Permit denied. Appeal process ongoing | 4 | Delayed Cluster 4
928 | 4 | 2020 | 939 | Delayed | Due to complex and long permitting process | 0 | Delayed Cluster 0
955 | 3 | 2020 | 987 | Delayed | Delayed due to uncertainty of regulatory decisions | -1 | Outlier
11 | 3 | 2022 | 1014 | Delayed | Negotiations with the Swiss authorities are in progress and advancing | 1 | Delayed Cluster 1
27 | 4 | 2022 | 1035 | Delayed | The contract with the contractor was terminated in February 2020. The tender for a new contractor has already been concluded. | -1 | Outlier
111 | 1 | 2022 | 1262 | Delayed | Postponement of commissioning, currently the full focus is on HBPI | 13 | Delayed Cluster 13
151 | 1 | 2022 | 1378 | Delayed | The Tunisian regulatory framework has been settled only recently and this delayed the overall permitting process. | -1 | Outlier
153 | 3 | 2022 | 1380 | Delayed | PERMITTING - Delays due to environmental problems (including re-routing) and delay of EIA assessment due to change of EIA Commission (2019) | 3 | Delayed Cluster 3
154 | 3 | 2022 | 1381 | Delayed | Since TYNDP 2020, the situation with COVID and ongoing negotiations on Brexit and the Trade and Cooperation Agreement resulted in a delay with permitting and regulatory procedures in GB and France. Respectively commissioning of the project moved to 2026. | -1 | Outlier
155 | 1 | 2022 | 1382 | Delayed | Permitting process in Norway | 6 | Delayed Cluster 6
156 | 3 | 2022 | 1383 | Delayed | Brexit - investment request submitted but declared void on 24 December 2020 as there were no provisions in the FTA which would allow the French & UK regulators to continue to have competence to decide the investment request. A new investment request was submitted solely to CRE in March 2021. | 6 | Delayed Cluster 6
157 | 3 | 2022 | 1384 | Delayed | The permitting phase in Italy is ongoing since April 2014 but we are still facing some challenges regarding Environmental impact of the 380/132kV Substation Terna in Mese. Commissioning expected in 2025. | -1 | Outlier
182 | 3 | 2022 | 1407 | Delayed | The National Regulatory Authorities of Greece and Cyprus approved the submitted Investment Request for the Project and agreed on the CBCA between them. The decision "Cross-Border Cost Allocation Between the Hellenic Regulatory Authority for Energy (RAE) and the Cyprus Energy Regulatory Authority (CERA)" provided on 10th of October 2017 concerned the implementation of PCIs 3.10.2 & 3.10.3. With the corresponding decision for PCI 3.10.1 not yet received, and to avoid delays in the implementation of the Project and to be in line with the obligations and commitments arising from the CBCA approval, the Project Promoter decided to amend the order of implementation of the three PCIs consisting PCI 3.10 as follows, with PCIs 3.10.2 & 3.10.3 implemented concurrently: PCI 3.10.3 Interconnection between Korakia, Crete and Attica region(EL) PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY). The CBCA has been updated on 23.04.2021 | 12 | Delayed Cluster 12
184 | 3 | 2022 | 1409 | Delayed | The National Regulatory Authorities of Greece and Cyprus approved the submitted Investment Request for the Project and agreed on the CBCA between them. The decision "Cross-Border Cost Allocation Between the Hellenic Regulatory Authority for Energy (RAE) and the Cyprus Energy Regulatory Authority (CERA)" provided on 10th of October 2017 concerned the implementation of PCIs 3.10.2 & 3.10.3. With the corresponding decision for PCI 3.10.1 not yet received, and to avoid delays in the implementation of the Project and to be in line with the obligations and commitments arising from the CBCA approval, the Project Promoter decided to amend the order of implementation of the three PCIs consisting PCI 3.10 as follows, with PCIs 3.10.2 & 3.10.3 implemented concurrently: PCI 3.10.3 Interconnection between Korakia, Crete and Attica region(EL) PCI 3.10.2 Interconnection between Kofinou (CY) and Korakia, Crete (EL) PCI 3.10.1 Interconnection between Hadera (IL) and Kofinou (CY). The CBCA has been updated on 23.04.2021 | 12 | Delayed Cluster 12
207 | 1 | 2022 | 1430 | Delayed | The Tunisian regulatory framework has been settled only recently and this delayed the overall permitting process. | -1 | Outlier
236 | 3 | 2022 | 1458 | Delayed | Delayed due to permitting reasons. | 14 | Delayed Cluster 14
240 | 4 | 2022 | 1472 | Delayed | Duration of permitting process. | 6 | Delayed Cluster 6
241 | 3 | 2022 | 1473 | Delayed | Delay due to complex and long permitting process | 0 | Delayed Cluster 0
245 | 3 | 2022 | 1478 | Delayed | The promoters asked to the respective NRA for the NTC recalculation not subject to conditions (EG. third party network reinforcements), which will be guaranteed for the exemption period and from the entry into the new commercial operation date (COD) of the interconnector. The process is still ongoing. | 2 | Delayed Cluster 2
247 | 3 | 2022 | 1482 | Delayed | The promoter asked the respective NRA for the NTC recalculation not subject to conditions (eg third party network reinforcements), which will be guaranteed for the exemption period and from the entry into the new commercial operation date (COD) of the interconnector. The process is still ongoing. | 2 | Delayed Cluster 2
255 | 4 | 2022 | 1493 | Delayed | Due to a court case, an enforceable building permission for the Uckermark-line was delayed. As the court case was settled in July 2022 the upgrade of the Uckermark-line is proceeding. | 14 | Delayed Cluster 14
286 | 4 | 2022 | 1526 | Delayed | Adjusted to match the remainder of the project. | 9 | Delayed Cluster 9
287 | 4 | 2022 | 1527 | Delayed | Slightly delayed due to the long contractor choice process. | 14 | Delayed Cluster 14
288 | 4 | 2022 | 1528 | Delayed | Slightly delayed due to the long contractor choice process. | 14 | Delayed Cluster 14
305 | 3 | 2022 | 1544 | Delayed | Complicated permitting procedures | 6 | Delayed Cluster 6
345 | 3 | 2022 | 1628 | Delayed | The project connection date is delayed due events outwith of NeuConnect's direct control | -1 | Outlier
398 | 2 | 2022 | 1692 | Delayed | explanation missing | 7 | Delayed Cluster 7
481 | 4 | 2022 | 1783 | Delayed | Permit recieved. | 4 | Delayed Cluster 4
482 | 3 | 2022 | 1784 | Delayed | Permit denied. Appeal process ongoing | 4 | Delayed Cluster 4
497 | 3 | 2022 | 18 | Delayed | Delays in the Environmental Impact Assessment process | -1 | Outlier
693 | 5 | 2022 | 238 | Delayed | Due to some delays related to investments 701 and 269 the line is not operated | 10 | Delayed Cluster 10
717 | 3 | 2022 | 313 | Delayed | Delays due to other permit granting reasons | 4 | Delayed Cluster 4
764 | 3 | 2022 | 462 | Delayed | Investment delayed due to judicial reviews of planning consent in IE and delayed approval of planning consent in NI. | 6 | Delayed Cluster 6
771 | 3 | 2022 | 496 | Delayed | Delays in the Environmental Impact Assessment process. Section Vila Nova de Famalicão-Ponte de Lima was comissioned in 2021. | -1 | Outlier
773 | 3 | 2022 | 498 | Delayed | Delays in the Environmental Impact Assessment process | -1 | Outlier
774 | 3 | 2022 | 499 | Delayed | Delays in the Environmental Impact Assessment process | -1 | Outlier
775 | 3 | 2022 | 500 | Delayed | Delays due to correlation with other delayed infrastructure investments. | -1 | Outlier
807 | 1 | 2022 | 616 | Delayed | Project under consideration on SI side (permitting not started yet in Slovenia) | 9 | Delayed Cluster 9
818 | 3 | 2022 | 628 | Delayed | The investment suffered a one-year delay compared to the previous TYNDP due to the negotiations for closing the financial structure (grants, loans and own funds). | 10 | Delayed Cluster 10
821 | 3 | 2022 | 631 | Delayed | The investment suffered a one-year delay compared to the previous TYNDP due to the negotiations for closing the financial structure (grants, loans and own funds). | 10 | Delayed Cluster 10
825 | 3 | 2022 | 645 | Delayed | Delay due to permitting reasons. | 14 | Delayed Cluster 14
854 | 2 | 2022 | 689 | Delayed | Scope of the project changed due to technical reasons. | 9 | Delayed Cluster 9
862 | 4 | 2022 | 705 | Delayed | Long duration of the procurement procedure, delays due to executor and pandemic impact of COVID 19 | -1 | Outlier
865 | 4 | 2022 | 715 | Delayed | The contractor responsible for the construction has gone into insolvency | -1 | Outlier
911 | 4 | 2022 | 90 | Delayed | Delayed due to permitting reasons. | 14 | Delayed Cluster 14
955 | 3 | 2022 | 987 | Delayed | Delayed due to uncertainty of regulatory decisions | 14 | Delayed Cluster 14
11 | 3 | 2024 | 1014 | Delayed | Negotiations with the Swiss authorities are in progress and advancing | 1 | Delayed Cluster 1
26 | 2 | 2024 | 1034 | Delayed | The main reason of delay is due to unsuccessful converter stations and HDVC cable tenders as in both cases the prices offered significantly exceeded the contracting authorities’ budgets. As a result of it the replanning of the project activities has been started. | 8 | Delayed Cluster 8
111 | 1 | 2024 | 1262 | Delayed | Postponement of commissioning, currently the full focus is on HBPI. | 13 | Delayed Cluster 13
116 | 1 | 2024 | 1269 | Delayed | There is a slight delay due to the new circumstances and observations regarding the project. | 14 | Delayed Cluster 14
151 | 1 | 2024 | 1378 | Delayed | The project timeline has been delayed due to the evolution of the regulatory frameworks and supply chain constraints (specifically HVDC cable supply). | 8 | Delayed Cluster 8
153 | 3 | 2024 | 1380 | Delayed | PERMITTING - Due to the timing of the release of the exemption decision by the EC as preparatory to the start of the grid connection process in Austria. Furthermore, the commissioning of the line is linked to the construction of the new Wurmlach power station by the TSO and expected in 2029. | 13 | Delayed Cluster 13
154 | 3 | 2024 | 1381 | Delayed | Since TYNDP 2022, ongoing delay in implementation of energy chapter of the Trade and Cooperation Agreement together with the delay of the third Cap&Floor window by Ofgem resulted in a delay with permitting and regulatory procedures in GB and France. Respectively commissioning of the project moved to 2028. | -1 | Outlier
156 | 3 | 2024 | 1383 | Delayed | Brexit - investment request submitted but declared void on 24 December 2020 as there were no provisions in the FTA which would allow the French & UK regulators to continue to have competence to decide the investment request. A new investment request was submitted solely to CRE in March 2021. | 6 | Delayed Cluster 6
157 | 3 | 2024 | 1384 | Delayed | The permitting phase in Italy is ongoing since April 2014 but we are still facing some challenges regarding Environmental impact of the 380/132kV Substation Terna in Mese. Commissioning expected in 2025. | -1 | Outlier
182 | 4 | 2024 | 1407 | Delayed | We are currently in discussions to finalize the Cyprus-Israel link and move towards the construction phase, focusing on the investment requirements | 9 | Delayed Cluster 9
207 | 1 | 2024 | 1430 | Delayed | The project timeline has been delayed due to the evolution of the regulatory frameworks and supply chain constraints (specifically HVDC cable supply). | 8 | Delayed Cluster 8
240 | 4 | 2024 | 1472 | Delayed | Duration of permitting process. | 6 | Delayed Cluster 6
241 | 3 | 2024 | 1473 | Delayed | Delay due to complex and long permitting process | 0 | Delayed Cluster 0
245 | 3 | 2024 | 1478 | Delayed | The promoter asked the respective NRA for the NTC recalculation not subject to conditions (eg third party network reinforcements), which will be guaranteed for the exemption period and from the entry into the new commercial operation date (COD) of the interconnector. The process was concluded in July 2023. | 2 | Delayed Cluster 2
247 | 3 | 2024 | 1482 | Delayed | The promoter asked the respective NRA for the NTC recalculation not subject to conditions (eg third party network reinforcements), which will be guaranteed for the exemption period and from the entry into the new commercial operation date (COD) of the interconnector. The process was concluded in July 2023. | 2 | Delayed Cluster 2
255 | 4 | 2024 | 1493 | Delayed | Due to a court case, an enforceable building permission for the Uckermark-line was delayed. As the court case was settled in July 2022 the upgrade of the Uckermark-line is proceeding. | 14 | Delayed Cluster 14
279 | 3 | 2024 | 1519 | Delayed | Permitting procedure | 6 | Delayed Cluster 6
286 | 4 | 2024 | 1526 | Delayed | Adjusted to match the remainder of the project. Also, the project faced some issues regarding the land ownership. Those will not harm the construction. | 9 | Delayed Cluster 9
305 | 3 | 2024 | 1544 | Delayed | Complicated permitting procedures | 6 | Delayed Cluster 6
345 | 4 | 2024 | 1628 | Delayed | The project connection date is delayed due events outwith of NeuConnect's direct control | -1 | Outlier
383 | 3 | 2024 | 1670 | Delayed | Delays in permitting | 3 | Delayed Cluster 3
404 | 2 | 2024 | 1699 | Delayed | Updated consideration of the necessary investments and the scope of work. | 9 | Delayed Cluster 9
448 | 3 | 2024 | 1751 | Delayed | The permitting process is taking longer than anticipated. | 0 | Delayed Cluster 0
461 | 3 | 2024 | 1763 | Delayed | permitting procedure | 6 | Delayed Cluster 6
481 | 4 | 2024 | 1783 | Delayed | Permit recieved. | 4 | Delayed Cluster 4
482 | 3 | 2024 | 1784 | Delayed | Permit denied. Appeal process ongoing | 4 | Delayed Cluster 4
497 | 3 | 2024 | 18 | Delayed | Delays in the Environmental Impact Assessment process | -1 | Outlier
693 | 4 | 2024 | 238 | Delayed | Due to some delays related to investments 701 and 269 the line is not operated | 10 | Delayed Cluster 10
717 | 3 | 2024 | 313 | Delayed | Delays due to other permit granting reasons | 4 | Delayed Cluster 4
743 | 4 | 2024 | 4 | Delayed | Although the construction started on the section Feira-Ribeira de Pena, there is a public opposition to the project that is delaying the construction. Section V.Minho-Ribeira de Pena was comissioned in 2021. | -1 | Outlier
764 | 3 | 2024 | 462 | Delayed | Investment delayed due to judicial reviews of planning consent in IE and delayed approval of planning consent in NI. | 6 | Delayed Cluster 6
771 | 3 | 2024 | 496 | Delayed | Delays in the Environmental Impact Assessment process. Section Vila Nova de Famalicão-Ponte de Lima was comissioned in 2021. | -1 | Outlier
773 | 3 | 2024 | 498 | Delayed | Delays in the Environmental Impact Assessment process | -1 | Outlier
774 | 3 | 2024 | 499 | Delayed | Delays in the Environmental Impact Assessment process | -1 | Outlier
775 | 3 | 2024 | 500 | Delayed | Delays due to correlation with other delayed infrastructure investments. | -1 | Outlier
799 | 4 | 2024 | 604 | Delayed | Permitting process took longer than expected | 0 | Delayed Cluster 0
807 | 1 | 2024 | 616 | Delayed | Project under consideration on SI side (permitting not started yet in Slovenia) | 9 | Delayed Cluster 9
817 | 3 | 2024 | 627 | Delayed | Updated information regarding the scope of works and investments that will be necessary in order to complete this project. | 9 | Delayed Cluster 9
818 | 3 | 2024 | 628 | Delayed | Updated information regarding the scope of works and investments that will be necessary in order to complete this project. | 9 | Delayed Cluster 9
820 | 3 | 2024 | 630 | Delayed | Updated information regarding the scope of works and investments that will be necessary in order to complete this project. | 9 | Delayed Cluster 9
821 | 3 | 2024 | 631 | Delayed | Updated information regarding the scope of works and investments that will be necessary in order to complete this project. | 9 | Delayed Cluster 9
854 | 2 | 2024 | 689 | Delayed | Scope of the project changed due to technical reasons. | 9 | Delayed Cluster 9
862 | 4 | 2024 | 705 | Delayed | The execution contract is terminated | -1 | Outlier
865 | 4 | 2024 | 715 | Delayed | The contractor responsible for the construction has gone into insolvency | -1 | Outlier
885 | 4 | 2024 | 779 | Delayed | Delays in permitting and construction | -1 | Outlier
955 | 3 | 2024 | 987 | Delayed | Delayed due to uncertainty of regulatory decisions | 14 | Delayed Cluster 14